## Work List
Exported on: 2026-10-13 13:00:29
Filters applied:
Data source: VBGRAMG
District: NEEMUCH
Block: All
Panchayat: PIPLYAHADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1741003008/DP/22012034614512 — nirmal nir kup nirman | New | 0 | 0 | 2024-01-01
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1741003008/DP/22012034625922 — VRAKSHA ROPAN KARYA ( SHAMSHAN PARISAR) PIPLYHADI | Ongoing | 213933.68 | 3900 | 2024-09-07
MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1741003008/IF/22012035282687 — KAPILDHARA KOOP NIMAN( BHANWARSINGH JUJHARSINGH ) PIPLYAHADI | Ongoing | 405183.38 | 0 | 2025-01-06
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1741003008/IF/22012035448469 — DUG WELL RECHARGE PIT INDIVIDUAL ( SANJAY SHYAMLAL BANCHHADA ) HANMANTIYA | Approved | 0 | 0 | 2025-04-24
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1741003008/IF/22012035555245 — KAPIL DHARA KOOP NIRMAN ( RAMBABU BHERULAL ) PIPLYAHADI | Ongoing | 445836.67 | 5481 | 2025-06-06
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1741003008/IF/22012035567326 — KHET TALAB NIRMAN ( DHANNALAL FAKIRCHANDR ) PIPLYAHADI | Approved | 0 | 0 | 2025-06-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1741003008/IF/22012035572147 — KAPIL DHARA KOOP NIRMAN ( SHYAMLAL DEWILAL GAYRI ) PIPLYAHADI | Ongoing | 445836.67 | 0 | 2025-07-12
MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1741003008/IF/IAY/814333 — Construction of IAY House -IAY REG. NO. MP1733433 | Approved | 27000 | 0 | 2017-04-16
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003008/RC/22012034847177 — CC ROAD V NALI NIRMAN ( BHARAT KIR KE MAKAN SE BAPULAL KE BADHE KI OR ) PIPLYAHADI | Ongoing | 98415 | 0 | 2026-02-21
MANASA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003008/RC/22012034848166 — CC ROAD NIRMAN 5 VITT (ARNIYA ROAD SE DEVKANYA KE MAKAN KI OR ) PIPLYAHADI | Ongoing | 68000 | 0 | 2026-05-03
MANASA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003008/RC/22012034848167 — CC ROAD NIRMAN 5 VITT (AJAY KE MAKAN SE ROSHAN KE MAKAN KI OR DERA NO 2 ) PIPLYAHADI | Ongoing | 81000 | 64200 | 2026-07-21
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003008/RC/22012034849660 — CC ROAD NIRMAN 15 VITT (MALAHEDA ROD SE TEJSING CHANDRAWAT KE MAKAN KI OR ) PIPLYAHADI | Approved | 57000 | 0 | 2025-05-14
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1741003008/WC/22012035173345 — PERCOLATION TANK NIRMAN | New | 0 | 0 | 2024-04-01