## Work List
Exported on: 2026-10-09 19:52:50
Filters applied:
Data source: VBGRAMG
District: NEEMUCH
Block: All
Panchayat: ALHED
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1741003017/AV/22012034658123 — KHEL MAIDAN NIRMAN ( BAWDA ROAD KE PAAS ) ALHED | Ongoing | 476879.26 | 2400 | 2026-01-29
MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1741003017/AV/22012034661952 — KHEL MAIDAN NIRMAN ( BAWDA ROAD KE PAAS ) ALHED | New | 0 | 0 | 2024-10-02
MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1741003017/DP/22012034614368 — nirmal nir kup nirman | New | 0 | 0 | 2024-04-01
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1741003017/DP/22012034622751 — VRAKSHA ROPAN KARYA ( SHASKIY UPSWSTHAY PARISAR ) ALHED | Approved | 181705.15 | 0 | 2024-06-25
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1741003017/DP/22012034622755 — VRAKSHA ROPAN KARYA ( PURANI PAANI KI TANKI KE PAAS ) ALHED | Ongoing | 181705.15 | 0 | 2024-08-04
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1741003017/IF/22012035445722 — DUG WELL RECHARGE PIT INDIVIDUAL ( PAVAN BABULAL MALI ) ALHED | New | 0 | 0 | 2025-04-24
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1741003017/IF/22012035548025 — KAPIL DHARA KOOP NIRMAN ( DINESH RAMLAL SUTHAR ) ALHED | Approved | 0 | 0 | 2025-04-14
MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/4715219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130287747 | Ongoing | 27000 | 21900 | 2025-01-22
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5087710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128580465 | Ongoing | 27000 | 0 | 2025-08-02
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5902612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127981613 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5902662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128617732 | Ongoing | 27000 | 0 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5902842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127935439 | Physically Completed | 27000 | 17700 | 2026-06-03 | 2026-10-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5903208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136217294 | Ongoing | 27000 | 12000 | 2026-07-13
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5903254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129971943 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5903433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128051224 | Physically Completed | 27000 | 18300 | 2026-06-03 | 2026-10-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5903458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125782242 | Ongoing | 27000 | 7560 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5904157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131023245 | Physically Completed | 27000 | 2100 | 2026-05-10 | 2026-10-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5904779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127946887 | Ongoing | 27000 | 0 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5904940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124167031 | Ongoing | 27000 | 0 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5905313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128204627 | Ongoing | 27000 | 4200 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5905533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128102182 | Ongoing | 27000 | 20700 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5905539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127980662 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5906179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129216004 | Ongoing | 27000 | 2100 | 2026-07-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5907629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131022635 | Ongoing | 27000 | 5400 | 2026-04-12
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5907663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126434393 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5907861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127939752 | Ongoing | 27000 | 25200 | 2026-07-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5908046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128836307 | Ongoing | 27000 | 24000 | 2026-07-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5908135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130541597 | Ongoing | 27000 | 14000 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5908625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127970924 | Ongoing | 27000 | 4200 | 2026-04-20
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5908928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128124493 | Ongoing | 27000 | 4200 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5909162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128163699 | Physically Completed | 27000 | 10200 | 2026-05-10 | 2026-09-27
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5909188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129211862 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5909536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129217042 | Ongoing | 27000 | 7800 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5909967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131023045 | Ongoing | 27000 | 13305 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5910422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127926583 | Physically Completed | 27000 | 2100 | 2026-05-10 | 2026-10-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5910595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127527729 | Ongoing | 27000 | 2100 | 2026-07-13
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5910736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130285882 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5911213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128098007 | Ongoing | 27000 | 17700 | 2026-07-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5912044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128120054 | Ongoing | 27000 | 13305 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5912224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129216882 | Ongoing | 27000 | 21900 | 2026-07-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5912370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127518105 | Ongoing | 27000 | 15600 | 2026-07-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5913285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129216767 | Ongoing | 27000 | 6300 | 2026-04-12
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5913410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129215920 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5913958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128150921 | Ongoing | 27000 | 21600 | 2026-07-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5914091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130326894 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5914094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127980330 | Ongoing | 27000 | 0 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5914401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127494251 | Physically Completed | 27000 | 23100 | 2026-06-19 | 2026-09-27
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5915514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129211815 | Ongoing | 27000 | 10200 | 2026-05-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5915654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127931395 | Ongoing | 27000 | 4200 | 2026-07-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5916093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127509560 | Ongoing | 27000 | 0 | 2026-04-12
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5916756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127970291 | Ongoing | 27000 | 7800 | 2026-05-10
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5916814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128149801 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5917121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128136807 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5917218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128577949 | Ongoing | 27000 | 13305 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5917368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127923000 | Ongoing | 27000 | 4200 | 2026-07-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5917375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128561149 | Ongoing | 27000 | 0 | 2026-04-12
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5917637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127936965 | Ongoing | 27000 | 18300 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5918025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136218536 | Ongoing | 27000 | 7800 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5918252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128177188 | Ongoing | 27000 | 12300 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5918255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127979351 | Ongoing | 27000 | 0 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5918314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235582 | Ongoing | 27000 | 0 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5918836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128159569 | Ongoing | 27000 | 0 | 2026-04-12
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5919224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129218418 | Ongoing | 27000 | 0 | 2026-04-12
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5919355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130286554 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5919357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128904045 | Ongoing | 27000 | 18300 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5919759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125785711 | Physically Completed | 27000 | 7200 | 2026-05-03 | 2026-10-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5919774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128053126 | Physically Completed | 27000 | 5400 | 2026-04-12 | 2026-10-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5920394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138070158 | Ongoing | 27000 | 7800 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5921864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132068566 | Ongoing | 27000 | 5400 | 2026-04-12
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5921901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130291442 | Ongoing | 27000 | 18300 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5922383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131476584 | Ongoing | 27000 | 21300 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5922399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130328559 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5922776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129215015 | Ongoing | 27000 | 17100 | 2026-08-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5923321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128575026 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5923492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129213341 | Ongoing | 27000 | 700 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5924164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128177608 | Ongoing | 27000 | 4200 | 2026-07-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5924199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128172213 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5924496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131022455 | Physically Completed | 27000 | 0 | 2026-04-20 | 2026-10-04
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5924557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127938531 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5925536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126427990 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5925891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106903281 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5926054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128165145 | Ongoing | 27000 | 15900 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5926104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235809 | Ongoing | 27000 | 18300 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5926390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130150151 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5927477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128127303 | Ongoing | 27000 | 13305 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5927862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129215152 | Ongoing | 27000 | 2100 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5927951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235746 | Ongoing | 27000 | 11400 | 2026-08-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5928077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128137160 | Ongoing | 27000 | 12327 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5928118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128128025 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5929097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128141222 | Ongoing | 27000 | 21900 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5929130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129218141 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5929386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130531629 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5929447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128166635 | Ongoing | 27000 | 21000 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5929967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129210797 | Ongoing | 27000 | 2100 | 2026-05-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5930236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127987059 | Ongoing | 27000 | 16100 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5931646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136217366 | Ongoing | 27000 | 11200 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/5931694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131049845 | Ongoing | 27000 | 5700 | 2026-07-13
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6090943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128109026 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6090982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128151880 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6091008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128175128 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6091039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128197943 | Ongoing | 27000 | 1500 | 2026-08-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6091042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128200711 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6092769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130290716 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6092800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130316574 | Ongoing | 27000 | 21900 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6095030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136217912 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6095031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235184 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6125505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136218073 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6128327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127512569 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6129129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128643343 | Ongoing | 27000 | 4200 | 2026-07-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6129130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128644639 | Ongoing | 27000 | 10200 | 2026-06-19
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6129692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128155485 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6129940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128523896 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6131791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130315069 | Ongoing | 27000 | 4200 | 2026-07-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6132380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127502639 | Ongoing | 27000 | 16200 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6133486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127580359 | Ongoing | 27000 | 0 | 2026-06-04
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6134957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128129378 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6135202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128196102 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6136312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128916992 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6137071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131022374 | Ongoing | 27000 | 10200 | 2026-06-19
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6137673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131023573 | Ongoing | 27000 | 25500 | 2026-07-13
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6139575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128920421 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6141804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127500233 | Ongoing | 27000 | 24300 | 2026-07-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6144539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129212066 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6146927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130531656 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6149874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129211956 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6151937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235026 | Ongoing | 27000 | 11200 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6151938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235324 | Ongoing | 27000 | 0 | 2026-06-19
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6151939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136235485 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6152664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131049826 | Ongoing | 27000 | 6300 | 2026-07-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6152688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127506093 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6155150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130285478 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6156666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128630670 | Ongoing | 27000 | 18300 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6156949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128620208 | Ongoing | 27000 | 7800 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6157860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126430738 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6159506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128524914 | Ongoing | 27000 | 3600 | 2026-08-13
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6161520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128220904 | Ongoing | 27000 | 6300 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6166249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128176302 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6166342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127496595 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6171637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128640455 | Approved | 27000 | 0 | 2026-03-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6171821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128918151 | Ongoing | 27000 | 21000 | 2026-06-03
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6268097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127933156 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6268404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127521463 | Approved | 27000 | 0 | 2026-04-16
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6268568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128578713 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6292308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127498472 | Approved | 27000 | 0 | 2026-04-14
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6324304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128152403 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6324734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136217091 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741003017/IF/IAY/6385504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129218777 | Approved | 27000 | 0 | 2026-02-10
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003017/RC/22012034850601 — CC ROAD NIRMAN MLA (PAPULAL KE MAKAN SE SHAMSAN ROAD TAK ) ALHED | Ongoing | 68000 | 0 | 2025-12-16
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003017/RC/22012034850604 — CC ROAD NIRMAN MLA (JETRAM DHANGER KE MAKAN SE DHRMSHALA TAK ) ALHED | Ongoing | 106000 | 0 | 2025-12-11
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003017/RC/22012034850605 — CC ROAD NIRMAN MLA (SAMRATH PATIDAR KE BADE SE OMPRAKASH PATIDAR KE MAKAN TAK ) ALHED | Ongoing | 108000 | 0 | 2025-12-11
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003017/RC/22012034850687 — CC ROAD NIRMAN MLA (RAMESH DIDVANA KE MAKAN SE BALWANT KE MAKAN TAK) ALHED | Ongoing | 37000 | 0 | 2025-12-12
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741003017/RC/22012034850792 — CC ROAD NIRMAN 15 VITT (RAMESH GURJAR KE MAKAN SE NARENDRA TAVDWVHA KE BADE TAK) ALHED | Ongoing | 77000 | 0 | 2025-12-11
MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003017/WC/22012035129275 — STORM DRENAGE CHANEL BHAGVAN MALI KE MAKAN SE MAIN NALE TAK ALHED | Ongoing | 1168000 | 0 | 2024-07-03
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1741003017/WC/22012035173181 — PARCOLATION TANK NIRMAN | New | 0 | 0 | 2024-04-01
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1741003017/WC/22012035225887 — TALAB NIRMAN KARYA ( NAI AABADI ) ALHED | New | 0 | 0 | 2024-10-02
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1741003017/WC/22012035226170 — PARCOLATION TANK NIRMAN ( AKHEPUR ROAD PAR BHAG 01) ALHED | Approved | 199898.73 | 0 | 2024-10-02
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1741003017/WC/22012035226171 — PARCOLATION TANK NIRMAN ( AKHEPUR ROAD PAR BHAG 02) ALHED | Approved | 198081.19 | 0 | 2024-10-02
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1741003017/WH/22012034943805 — STOP DEM JIRNODHAR (RAMPRASAD KE KHET KE PASS) ALHED | Approved | 219651.14 | 0 | 2025-04-01
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1741003017/WH/22012034943806 — STOP DEM JIRNODHAR (GOPAL KACHHWA KE KHET KE PASS) ALHED | Approved | 0 | 0 | 2025-04-01
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1741003017/WH/22012034943807 — STOP DEM JIRNODHAR (PRABHULAL GURJER KE KHET KE PASS) ALHED | Approved | 0 | 0 | 2025-04-01