## Work List
Exported on: 2026-09-02 22:51:52
Filters applied:
Data source: VBGRAMG
District: NEEMUCH
Block: All
Panchayat: BARKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003088/DP/22012034614383 — nirmal nir kup nirman | New | 0 | 0 | 2024-04-01
MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003088/DP/22012034615977 — NIRMAL NIR KUP NIRMAN (DERA ME ) BARKHEDA | Physically Completed | 648891.55 | 0 | 2024-03-14 | 2026-08-08
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1741003088/DP/22012034621189 — VRAKSHA ROPAN KARYA ( SHAMSHAN GHAT PARISAR) BARKHEDA | Ongoing | 287591.67 | 0 | 2024-08-03
MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003088/IF/22012035273823 — KHET TALAB NIRMAN ( MANHORSINGH BHUWANISINGH BARKHEDI) BARKHEDA | Approved | 0 | 0 | 2024-11-06
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1741003088/IF/22012035586444 — EK BAGIYA MAA KE NAAM ( PUSPA KUWAR BAPUSINGH PANWAR ) BARKHEDA | Ongoing | 273791.93 | 0 | 2025-11-21
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1741003088/IF/22012035587869 — EK BAGIYA MAA KE NAAM (GATTU KUWAR BALWANT SINGH RAJPUT BARKHEDI ) BARKHEDA | Ongoing | 273791.93 | 3600 | 2025-11-18
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1741003088/IF/22012035587880 — EK BAGIYA MAA KE NAAM ( HANS KUNWAR DILIP SINGH RAJPUT BARKHEDI ) BARKHEDA | Ongoing | 272029.13 | 0 | 2025-09-02
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1741003088/IF/22012035587886 — EK BAGIYA MAA KE NAAM ( AANDA KUNWAR GATTU SINGN PANWAR BARKHEDI ) BARKHEDA | Ongoing | 274386.58 | 18600 | 2025-11-21
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1741003088/IF/22012035632592 — EK BAGIYA MAA KE NAAM ( MANJU KUNWAR VIJAY SINGH BARKHEDI ) BARKHEDA | Ongoing | 263511.37 | 0 | 2025-12-06
MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003088/IF/IAY/3956563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125148834 | Approved | 27000 | 0 | 2022-05-05
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003088/IF/IAY/4962304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125852889 | Ongoing | 27000 | 0 | 2026-04-22
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003088/IF/IAY/5019414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126094886 | Ongoing | 27000 | 0 | 2026-06-03
MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003088/IF/IAY/5272649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125851546 | Ongoing | 27000 | 0 | 2026-04-22
MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003088/IF/IAY/6151451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125758670 | Approved | 27000 | 0 | 2026-02-19
MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003088/RC/22012034635161 — SUDUR SADAK NIRMAN ( MOYA ROAD SE BARTHUN KI SEEMA TAK ) BARKHEDA | Physically Completed | 1496405.32 | 0 | 2023-05-26 | 2026-07-19
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003088/RC/22012034844621 — CC ROAD NIRMAN MLA (KARULAL KE MAKAN SE PREMCHAND KE MAKAN V RATANLAL KE MAKAN SE MAIN ROD)BARKHEDA | Ongoing | 208000 | 0 | 2025-07-16
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003088/RC/22012034847560 — CC ROAD NIRMAN 5 VITT (ANIL KE GHAR SE GOPI KE GHAR KI OR DERA BASTI ME) BARKHEDA | Approved | 131000 | 0 | 2025-04-14
MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003088/RC/22012034847561 — CC ROAD NIRMAN 15 VITT (KARULAL KE MAKAN SE HANSHRAJ KE MAKAN TAK DERA BASTI ME) BARKHEDA | Approved | 64000 | 0 | 2025-04-14
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003088/WC/22012035173227 — PARCOLATION TANK NIRMAN | New | 0 | 0 | 2024-04-01
MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003088/WC/22012035231022 — PARCOLATION TANK NIRMAN ( TALAB KE PASS BARKLHEDI) BARKHEDA | Approved | 0 | 0 | 2024-11-06
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741003088/WC/22012035291020 — DUG WELL RECHARGE PIT COMMUNITY ( SASKIY KOOP BACHDA BASTI ME) BARKHEDA | Approved | 25899.46 | 0 | 2025-04-14
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741003088/WC/22012035291021 — DUG WELL RECHARGE PIT COMMUNITY ( SASKIY KOOP GRAM BARKHEDI ME) BARKHEDA | Approved | 25899.46 | 0 | 2025-04-14
MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741003088/WC/22012035291022 — DUG WELL RECHARGE PIT COMMUNITY ( SASKIY KOOP GRAM BARKHEDA ME) BARKHEDA | Approved | 25899.46 | 0 | 2025-04-14