## Work List
Exported on: 2026-09-15 13:33:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NEEMUCH
Block: All
Panchayat: All
Status: Suspended
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JAWAD / KADWASA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741001013/DP/775 — वृक्षा रोपण- Singoli Bagu Raod Kinare aned choura raj sima tak (Kadwasa) DP/775 | Suspended | 488000 | 152352 | 2011-07-14
JAWAD / KADWASA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741001013/RC/120 — ग्रेवल मार्ग -अनेड से सिगोली मेनरोड ग्रेवल मार्ग (कदवासा)RC/ 120 | Suspended | 499000 | 207322 | 2010-04-04
JAWAD / KADWASA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741001013/RC/237 — ग्रेवल निर्माण- KADVASA SE MAHAPURAPURN BALAJI TAK (KADVASA) RC/237 | Suspended | 500000 | 142299 | 2011-02-07
JAWAD / KADWASA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741001013/RC/256 — खरंजा निर्माण - मेनरोड से बालाजी तक (कदवासा)/RC/256 | Suspended | 500000 | 37656 | 2011-06-02
JAWAD / KADWASA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741001013/RC/60 — ग्रेवल निर्माण- रस्‍तपुराबोर से धारडी अर्थवर्क (कदवासा) RC/60 | Suspended | 433000 | 298647 | 2009-11-16
JAWAD / KADWASA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741001013/RC/80 — खरंजा नि‍र्माण- (खरंजा निर्माण बडौलिया मोहल्‍ला से हरीजन मोहल्‍ला तक‍ (कदवासा)/RC/80 | Suspended | 500000 | 144195 | 2009-12-11
JAWAD / KADWASA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741001013/RC/81 — खरंजा नि‍र्माण- (खरंजा निर्माण दूरभाष केन्‍द्र से शाला भवन के गेट तक (कदवासा )/RC/81 | Suspended | 500000 | 4095 | 2009-12-11
JAWAD / KADWASA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741001013/RC/82 — खरंजा नि‍र्माण- (खरंजा निर्माण कन्‍हैयालाल के मकान से हरिजन मोहल्‍ला तक (कदवासा )/RC/82 | Suspended | 500000 | 6000 | 2009-12-11
NEEMUCH / DUNGALAWADA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002005/RC/22012034436242 — CC Road (Dhanshing patel ke makan se Nanda Ba ke makan tak Changera) Dunglawada | Suspended | 69700 | 6960 | 2019-03-10
NEEMUCH / DUNGALAWADA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1741002005/WH/19959618 — Watar Resectioning and Wastware Nala Gram Panchyat Dunglawada | Suspended | 53000 | 344 | 2017-05-17
NEEMUCH / DHANERIYAKAIAN | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1741002008/PG/9425895460 — KHEL MEDAN (GRAMIN KRIDANGAN 100*100) DHANERIYAKALA | Suspended | 353000 | 501 | 2017-03-19
NEEMUCH / KALIKOTHADI | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741002022/LD/22012034305388 — Shanthidham Kalikotkdi GP - Bhatkheda | Suspended | 180000 | 334 | 2017-03-16
NEEMUCH / JAMUNIYAKALAN | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1741002030/PG/9425895541 — PLAY GROUND GRAM JAMUNIYA KALA | Suspended | 341940 | 668 | 2017-03-29
NEEMUCH / AMLIKHEDA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1741002035/DP/22012034443989 — Nirmal Nir (Nirmal Nir Kup Nirman Umaheda) Amlikheda | Suspended | 535000 | 2088 | 2019-03-05
NEEMUCH / AMLIKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002035/IF/22012034346594 — Plantation (Sohandas Laxmandas Khel Medan Parisar) Amlikheda | Suspended | 335000 | 3096 | 2017-06-23
NEEMUCH / SIRKHEDA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1741002036/DP/22012034455405 — RFR_Borkhedi River Ringwal par Plantation Sirkheda | Suspended | 373989.79 | 0 | 2020-04-01
NEEMUCH / CHALDU | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002037/IF/22012034473838 — Kapildhara kup with recharg pit (chosarbai syamlal banjara jabcard-420) chaldu | Suspended | 210000 | 0 | 2019-01-08
NEEMUCH / ARNYA BORANA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002038/RC/22012034398716 — C.C. ROAD SAH NALI NIRMAN PWD SADAK SE PANCHAYAT BHAWAN ARNIYA BORANA | Suspended | 17280 | 176 | 2019-11-03
NEEMUCH / HARNAWADA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002043/IF/22012034474173 — Kapildhara with recharg pit Shambunath S/o Rodhanath Munnibai W/o Shambhu nath | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741002043/IF/22012034570168 — KHET TALAB (HIRALAL S/O BHAV SINGH) | Suspended | 108814.67 | 0 | 2021-03-01
NEEMUCH / HARNAWADA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741002043/RC/22012034369683 — Sudur Gram Sadak Kari se Karadiya | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741002043/RC/22012034369684 — Sudur Gram Sadak Harnawada se Lalpura Majra | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002043/RC/22012034504275 — c c road ambalal patidar ke makan se nai abadi tak | Suspended | 84800 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1741002043/WC/22012034437982 — Nala Nirman | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1741002043/WC/22012034444065 — Stopdam nirman Patel sahab ke khet ke pas Gram Harnawada | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1741002043/WC/22012034444067 — Stopdam nirman Lewda Khali ke pas Gram Harnawada | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002043/WC/22012034479833 — Parcolathion tank nirman Mataji ke magari GP:- Harnawada | Suspended | 376037.21 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1741002043/WC/22012034482536 — Sokhpit Nirmant Part 01 | Suspended | 13427.22 | 0 | 2020-10-30
NEEMUCH / HARNAWADA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002043/WC/22012034530068 — Parcolation Tank nirman School nirman Baludas ke khet ke pas | Suspended | 0 | 0 | 2020-10-30
NEEMUCH / CHEETAKHEDA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1741002047/LD/22012034359327 — Sukhe Patharo Ki surkha Diwar High Secondry School | Suspended | 0 | 0 | 2020-05-10
NEEMUCH / RABADIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741002049/IF/22012034575331 — Khet talab (Nathibai S/o Nathu Bhil) Niwasi Rabdiya | Suspended | 108814.67 | 190 | 2020-07-11
NEEMUCH / RABADIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741002049/IF/22012034575339 — Khet talab (Kawarlal S/o Kishanlal Maghwal) Rabdiya | Suspended | 108814.67 | 0 | 2020-08-07
NEEMUCH / RABADIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002049/RC/22012034449445 — CC ROAD NAI ABADI ROAD SIDE SE NARULAL BHIL K MAKAN TAK | Suspended | 68900 | 64560 | 2019-03-10
NEEMUCH / RABADIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002049/RC/22012034546294 — CC Road Gram Rabdiya (Lilabai Jatiya ke makan se Narulal Bhil ke makan tk) | Suspended | 27400 | 0 | 2021-08-11
NEEMUCH / RABADIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1741002049/WC/22012034482541 — Sokhpit Nirmant Part 01 | Suspended | 13427.22 | 0 | 2021-10-10
NEEMUCH / MAHUDIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1741002050/PG/9425895470 — KHEL MAIDAN (GRAMIN KRIDHANGAN ASHPURA) MAHUDIYA | Suspended | 353000 | 7014 | 2017-03-22
NEEMUCH / PHOPHALIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002053/IF/22012034346944 — Planthion Ramrao Shantidham Parisar | Suspended | 335000 | 2064 | 2017-06-22
NEEMUCH / PHOPHALIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002053/IF/22012034353533 — PLANTATION (JAGDISH MOTILAL SCHOOL PARISHAR UGRAN) PHOPLIYA | Suspended | 335000 | 2064 | 2017-06-23
NEEMUCH / TALKHDA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1741002060/DP/22012034435175 — NIRMAL NIR (KUP NIRMAN KHETAKHEDA DORIYA) TALKHEDA | Suspended | 535000 | 1044 | 2019-03-06
NEEMUCH / TALKHDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002060/IF/22012034462000 — Kapildhara Recharg Pith (Parkash Ambalal Baskheda) Talkheda | Suspended | 224416.79 | 364 | 2019-03-09
NEEMUCH / TALKHDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002060/IF/22012034465474 — Kapildhara kup with recharg pit Karulal Ganpatlal Mangilala | Suspended | 224416.79 | 348 | 2019-03-09
NEEMUCH / TALKHDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002060/IF/22012034472142 — Kapildhara (Mohanlal Hiralal Megwal Baskheda Jabcard-107) Talkheda | Suspended | 224416.79 | 348 | 2019-03-09
NEEMUCH / BAMANYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002063/IF/IAY/233652 — Construction of IAY House -IAY REG. NO. MP1377281 | Suspended | 17100 | 501 | 2017-02-02
NEEMUCH / LAKHMI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002065/RC/22012034472024 — CC Road (Premlal Ke Makan Se Jujar Bhill Ke Makan Ki Taraf) Lakhmi | Suspended | 27900 | 27808 | 2019-08-20
MANASA / TAMOTI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003005/DP/22012034444755 — NIRMAL NIR KUP NIRMAN ( SHIVPURIYA ) | Suspended | 535032.26 | 2088 | 2019-03-11
MANASA / SUWASARABUZURG | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003006/IF/22012034470286 — KAPIL DHARA KUP NIRMAN ( RAMPRASAD UDEY RAM MEGHWAL) SUWASRA BUJURG | Suspended | 224416.79 | 1044 | 2019-03-11
MANASA / SUWASARABUZURG | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003006/IF/IAY/1926942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4544481 | Suspended | 17100 | 0 | 2018-10-26
MANASA / PIPLYAHADI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003008/WC/22012034505650 — PARCOLATION TANK NIRMAN ( PIPLYAHADI ) | Suspended | 516045.41 | 0 | 2020-04-01
MANASA / PIPLON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003010/WC/22012034505684 — PARCOLATION TANK NIRMAN ( SHREE HANUMAN MANDIR KAI PAKSHIM KI AUR SHASHKIY BHUMI PAR ) POKHRDA | Suspended | 513469.95 | 4576 | 2019-11-29
MANASA / JALINER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1741003020/WC/22012034481260 — RFR BORKHEDI NADI APROCH CHANEL HELIPAID KE PASS SE TALAB KI OR KHETPALIYA JALINER | Suspended | 105527.91 | 1056 | 2019-12-24
MANASA / JALINER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1741003020/WC/22012034507577 — RFR BORKHEDI NADI SHAMSHAN WALA TALAB KI WEST WEAR NIRMAN 8 M JAINER | Suspended | 320981.95 | 4224 | 2019-12-12
MANASA / JALINER | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003020/WC/22012034508364 — RFE BORKHEDI NADI NALA TRENCHING GORILAL BANJARA SE RATAN LAL GIR K KHET TAK 100X1.25X1 JALINER | Suspended | 68191.66 | 4224 | 2019-12-12
MANASA / JALINER | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003020/WC/22012034509329 — RFE NALA TRENCHING GORILAL BANJARA SE RATAN LAL GIR K KHET TAK 150X2X1 PART -2 JALINER | Suspended | 112860.42 | 4224 | 2019-12-12
MANASA / JALINER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1741003020/WC/22012034511646 — RFR TALAI RESECTIONING -03 NONRAM RAWAT KE KHET K PASS 80 M KHETPALIYA JALINER | Suspended | 99221.73 | 1056 | 2020-01-01
MANASA / JALINER | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003020/WC/22012034512936 — RFR NALA WIDTHING BHAGIRATH GURJER KE KHET SE GUDU KE KHET TAK JALINER | Suspended | 97933.8 | 1056 | 2019-12-24
MANASA / JALINER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003020/WC/22012034518362 — RFR PERCOLATION TANK GOPAL DHANGER KE KHET K PASS JALINER | Suspended | 344893.58 | 1056 | 2020-02-19
MANASA / ARNYMALI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003021/DP/22012034443956 — RFR BORKHEDI NADI NIRMAL NIR KOOP NIRMAN ARNYAMALI | Suspended | 535032.26 | 348 | 2019-03-09
MANASA / DHAKANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003022/IF/22012034353488 — VRKSHA ROPAN PALESHWAR MANDIR ROAD AUR PARISAR DHAKNI | Suspended | 335000 | 25600 | 2017-06-23
MANASA / DHAKANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1741003022/LD/22012034554202 — NUTRISHIAN GARDEN SHG Community DHAKNI | Suspended | 799712.75 | 0 | 2021-05-20
MANASA / SHESHPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003023/FP/22012034362648 — NALA NIRMAN ( PANCHYAT PARISAR KAI PAAS ) SHESHPUR | Suspended | 644318.37 | 1044 | 2019-03-11
MANASA / NALKHEDA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003024/FP/22012034361569 — नाला निर्माण कार्य हाई स्‍कुल से प्राथमिक विधालय की तरफ टीएस 588 | Suspended | 1000000 | 3132 | 2018-12-01
MANASA / NALKHEDA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003024/FP/22012034361570 — नाला निर्माण कार्य हनुमान मंदिर से राजु मेहतर के मकान की तरफ टीएस 589 | Suspended | 1000000 | 3132 | 2018-12-01
MANASA / LODAKYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003026/RC/22012034535018 — CC ROAD NIRMAN ( MEN ROAD SY KAILASH CARPENTAR KAI MAKAN TAK ) LOADKYA | Suspended | 85900 | 0 | 2020-09-12
MANASA / AKLI | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003027/FP/22012034361159 — नाला निर्माण (ड्रैनेज) दशरथ बावरी के मकान से शमशान की ओर टीएस 314 | Suspended | 830000 | 174 | 2018-09-21
MANASA / AKLI | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003027/FP/22012034361237 — नाल निर्माण ड्रैनेज चैनल कार्य भगवान जाट के मकान से स्‍वास्‍थ केन्‍द्र की ओर टीएस 315 | Suspended | 830000 | 174 | 2018-10-03
MANASA / AKLI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003027/IF/22012034362265 — VRKSHA ROPAN KHEL MAIDAN TUMDA ANKLI BALWANT SINGH MOHAN SINGH | Suspended | 335000 | 5064 | 2017-07-26
MANASA / BADKUWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003030/WC/22012034446080 — SOCH PIT NIRMAN ( SHAMSHAN K PAS HANDPUMP K PAS ) BADKUWA | Suspended | 13304.93 | 1044 | 2019-03-13
MANASA / HANSPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003036/FP/22012034360727 — नाला निर्माण घनश्‍याम सुतार के मकान से गेदमल के मकान बरडिया मार्ग पर | Suspended | 1087694 | 6264 | 2018-06-16
MANASA / PIPLYAGHOTA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003038/IF/22012034353436 — VRKSHA ROPAN SHAMSHAN BHUMI OR NADI KAI KINARAY PIPLYA GHOTA | Suspended | 335000 | 3000 | 2017-06-24
MANASA / HANMANTIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003041/DP/22012034443490 — NIRMAL NIR KUP NIRMAN ( PULIYA KAI PAAS ) MAHESHPURIYA | Suspended | 535032.26 | 1044 | 2019-03-11
MANASA / HANMANTIYA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1741003041/WC/22012034330449 — तालाब निर्माण खैल मैदान के पास हनुमंत्‍या टीएस 21 | Suspended | 656000 | 2064 | 2017-07-06
MANASA / RAJPURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003048/IF/22012034363561 — VRKSHA ROPAN KALLA MAHRAJ RAJPURA SHIVKARAN BALMUKUND | Suspended | 335000 | 9880 | 2017-07-20
MANASA / CHIKLIBLOCK (GANESHPURA) | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Infra for Lqud Biomanure for Indviduals / Construction of Infrastructure for Liquid Biomanure for Individuals | Bio-Fertilizer | 1741003056/IF/22012034470423 — KAPIL DHARA KUP NIRMAN ( RAMCHANDR MANGI LAL MEGHWAL ) CHIKLIBLOCK | Suspended | 230400.79 | 0 | 2019-03-11
MANASA / DUDHLAI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1741003066/IF/22012034859035 — NIJI FALODHYAN ( MUNNA LAL MANGILAL ) DUDLAI | Suspended | 145000 | 0 | 2021-09-17
MANASA / CHACHOR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003071/DP/22012034443983 — NIRMAL NIR KOOP NIRMAN (sonawali koi se aage) | Suspended | 535032.26 | 2088 | 2019-03-09
MANASA / CHACHOR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003071/DP/22012034443984 — NIRMAL NIR (sHAMSHAN PARISAR PAR) | Suspended | 535032.26 | 1044 | 2019-03-14
MANASA / CHACHOR | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003071/FP/22012034360071 — पुलिया निर्माण कार्य सांगाखेडा रोड से नई आबादी सडक पर श्‍िावलाल के मकान के पास टीएस 776 चचौर | Suspended | 77000 | 5160 | 2017-10-25
MANASA / CHACHOR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003071/RC/22012034463976 — DPR CC ROAD ( KAILASH BAIRAGI KAI MAKAN SEY SHIVJI KAI BADEY KI AUR ) CHACHOR | Suspended | 47400 | 1044 | 2019-03-14
MANASA / CHACHOR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003071/RC/22012034469990 — DPR CC ROAD NIRMAN ( MEN ROAD SEY JAGDISH MANGILAL KAI BADEY TAK ) CHCHOR | Suspended | 25500 | 0 | 2021-08-21
MANASA / BANADA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1741003074/RC/22012034384707 — खरंजा निर्माण कार्य प्रभुलाल मेघवाल के बाडे से पानी की कुईया की ओर टीएस 1280 | Suspended | 303000 | 10320 | 2018-02-18
MANASA / KUNDAVASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003076/DP/22012034444003 — NIRMAL NIR KUP NIRMAN ( PULIYA KAI PAAS ) MERIYAKHEDI | Suspended | 535032.26 | 1044 | 2019-03-09
MANASA / CHANDRAPURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003079/IF/22012034359843 — VRKSHA ROPAN PRIMARY SCHOOL AUR PANCHAYAT BHAWAN PARISAR CHANDRPURA | Suspended | 335000 | 5160 | 2017-07-01
MANASA / ANARIYADAADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003081/IF/22012034351804 — VRKSHA ROPAN PRIMARY SCHOOL MAALKHEDA ARNYADHADHI | Suspended | 335000 | 9880 | 2017-06-26
MANASA / CHUKNI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003082/DP/22012034444800 — NIRMAL NIR KUP NIRMAN ( SHAMSHAN K PAAS ) CHUKNI KHEDA | Suspended | 535032.26 | 174 | 2019-03-09
MANASA / CHUKNI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003082/WC/22012034446496 — SOCH PIT NIRMAN ( RAJU BAPULAL K MAKAN K PAS HANPUMP K PAS 01 ) CHUKNIKHEDA | Suspended | 13304.93 | 174 | 2019-03-09
MANASA / CHUKNI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003082/WC/22012034446497 — SOCH PIT NIRMAN ( GOPAL PARTHA K MAKAN K PAS HANDPUPM K PAS 02 ) CHUKNIKHEDA | Suspended | 13304.93 | 174 | 2019-03-09
MANASA / DAANGDI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003083/IF/22012034351994 — VRKSHA ROPAN SHAMSHAN PARISAR DANGDI | Suspended | 335000 | 3000 | 2017-07-20
MANASA / PAAVATI | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003086/FP/22012034361363 — नाला निर्माण कार्य सीताराम गायरी के मकान से पुराने नाले की ओर टीएस 521 | Suspended | 466878 | 2088 | 2018-10-06
MANASA / PAAVATI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1741003086/WH/22012034388705 — तालाब जीर्णोद्वार कार्य शांतिधाम के पास सेमलीजागीर टीएस 39 | Suspended | 202000 | 2088 | 2018-06-30
MANASA / RAWATPURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003087/FP/22012034361613 — नाला निर्माण कार्य यात्री प्रतिक्षालय से पंचायत भवन की आेर टीएस 582 | Suspended | 1117000 | 2088 | 2019-02-23
MANASA / BARKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003088/IF/22012034353450 — VRKSHA ROPAN SHAMSHAN GHAT PARISAR BARKHEDA | Suspended | 335000 | 18032 | 2017-06-25
MANASA / BAARWADIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003092/IF/22012034417128 — कपिल धारा कूप निर्माण पप्‍पुलाल बाबरू भील बारवाडिया | Suspended | 210000 | 0 | 2018-06-09
MANASA / MOKAMPURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003094/IF/22012034356105 — VRKSHA ROPAN KARYPANCHYAT BHAWAN PARISAR MOKAMPURA | Suspended | 335000 | 3000 | 2017-07-20
MANASA / RAISINGHPURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003096/FP/22012034361240 — नाला निर्माण कार्य शमशान से मानसिंह गुर्जर के मकान की ओर टीएस 434 खेडी | Suspended | 972000 | 14616 | 2018-09-27
MANASA / RAISINGHPURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003096/FP/22012034361271 — नाला निर्माण कार्य शमशान से बंशीलाल गुर्जर के मकान की ओर टीएस 439 | Suspended | 810000 | 14616 | 2018-09-27
MANASA / RAISINGHPURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003096/FP/22012034361292 — नाला निर्माण कार्य दशरथ सेन के मकान से देवरा तक टीएस 495 | Suspended | 800000 | 4176 | 2018-09-29
MANASA / RAISINGHPURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1741003096/IF/22012034581809 — NIJI FALODHYAN ( BANSHILAL MANGILAL ) KHEDI | Suspended | 145000 | 0 | 2020-07-20
MANASA / RAISINGHPURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1741003096/IF/22012034581811 — NIJI FALODHYAN ( BASANTILAL MANGILAL ) KHEDI | Suspended | 145000 | 0 | 2020-07-20