## Work List
Exported on: 2026-09-14 07:54:47
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BARWANI
Block: All
Panchayat: BIJASAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001012/IF/22012034358536 — plantation work on private land Sankar chena bijasan | Physically Completed | 122250 | 28954 | 2018-03-12 | 2021-01-06
BARWANI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1742001014/DP/22012034424790 — plantesion niji ket ki med par group1 | Physically Completed | 187600 | 14932 | 2018-10-25 | 2021-09-29
BARWANI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1742001014/DP/22012034424794 — plantesion niji ket ki med par group2 | Physically Completed | 187600 | 17232 | 2018-10-25 | 2021-09-29
BARWANI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1742001014/DP/22012034424796 — plantesion niji ket ki med par group3 | Physically Completed | 187600 | 18910 | 2018-10-25 | 2021-09-29
BARWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1742001014/DP/22012034600282 — वसुधा वंदन - अमृत वाटिका (75) पंचायत के पीछे पहाड़ी पर | Closed | 55847.4 | 0 | 2023-09-22
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/ — Nadep mukesh bhikya | Closed | 0 | 0 | 2021-10-28
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034356837 — plantation work at panchayat ke piche pahad par bijasan | Deleted | 535000 | 0 | 2017-04-14
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034357276 — plantation work at panchayat ke piche bijasan | Completed | 535000 | 63297 | 2017-06-28 | 2018-10-10
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034357545 — plantation work on private land Karansingh Bajesingh | Physically Completed | 167388 | 32070 | 2018-03-14 | 2021-01-06
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034357554 — plantation work on private land sugri bhikya | Physically Completed | 377000 | 50218 | 2018-03-14 | 2021-01-06
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358481 — plantation work at mandir paresar bijasan | Completed | 535000 | 19444 | 2017-07-01 | 2018-03-15
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358691 — plantation work on private land Shri Ram Nageshwar | Closed | 290000 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358708 — Plantation Work on Private Land Abhimanyu Girvar | Closed | 135900 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358719 — Plantation Work on Private Land Govind Jogiya | Closed | 144000 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358726 — Plantation Work on Private Land | Closed | 135500 | 0 | 2017-05-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358735 — Plantation Work on Private Land Devendra Uttam | Closed | 141000 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358742 — Plantation Work on Private Land Vijay Ranchhod | Closed | 116000 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358747 — Plantation Work on Private Land Dongarsingh Dashriya | Closed | 135000 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358756 — Plantation Work on Private Land Mehtab Gokul | Closed | 135000 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358773 — plantation work on private land sakharam galya | Closed | 144800 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358776 — plantation work on private land shankar chaina | Closed | 135400 | 0 | 2017-06-07
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358780 — plantation work on private land radhesyam shankar | Completed | 378045 | 57918 | 2017-09-22 | 2020-05-23
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001014/IF/22012034358808 — Plantation Work on Private Land Sunil Nirbhaysingh | Closed | 523000 | 0 | 2017-06-07
BARWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742001014/IF/22012034549359 — kapildhara kup nirman santa bai kumesh bijasan | Completed | 242453.87 | 188088 | 2020-05-08 | 2022-11-20
BARWANI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012034592809 — नाडेप कम्पोस्ट निर्माण मंशाराम रुमाल | Closed | 12412.41 | 0 | 2020-07-18
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012034592814 — नाडेप कम्पोस्ट निर्माण जितेंद्र कन्हैया | Completed | 12412.41 | 12354.63 | 2021-10-22 | 2023-09-14
BARWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001014/IF/22012034618549 — SHG mamta sunil BIJASAN | Closed | 116279.95 | 0 | 2020-08-15
BARWANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1742001014/IF/22012034637856 — SHG bas kepodhe group1 | Completed | 142446.41 | 60153 | 2020-12-11 | 2023-08-30
BARWANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1742001014/IF/22012034637860 — SHG bas ke podhe group2 | Completed | 142446.41 | 62921 | 2020-12-16 | 2023-08-30
BARWANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1742001014/IF/22012034637863 — SHG bas ke podhe group 3 | Completed | 142446.41 | 59830 | 2020-12-11 | 2024-01-18
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012034896562 — Nadep(Santosh Suresh) | Completed | 14006.51 | 22 | 2021-11-20 | 2024-01-09
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012034896995 — jayram subhan Nadep | Closed | 14006.51 | 0 | 2021-10-29
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012034897000 — jitendra amarsingh nadep | Closed | 14006.51 | 0 | 2021-10-29
BARWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742001014/IF/22012034996149 — shokta gadda Bijasan | Closed | 0 | 0 | 2022-05-15
BARWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742001014/IF/22012034999452 — स्व्यक्तिगत सोखता गड्डा(नवल छितु, हीरालाल जलाल, देवराम जामसिंग) | Closed | 12270.42 | 0 | 2022-04-14
BARWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742001014/IF/22012034999761 — soak pit nirman kary,NAVAL, MUKESH ,HIRALAL,DEVRAM BIJASAN | Closed | 0 | 0 | 2022-04-28
BARWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012035173322 — Nadep Compost (Manak Ranjit) | Completed | 15106.37 | 12132 | 2023-10-06 | 2024-03-19
BARWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012035173331 — Nadep Compost(Govind Vishram) | Completed | 15106.37 | 14146 | 2023-10-07 | 2024-03-19
BARWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012035173340 — Nadep Compost(Gopal Chitu) | Completed | 15106.37 | 14041 | 2023-10-07 | 2024-03-19
BARWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742001014/IF/22012035173357 — Nadep Compost(Balram Sitaram) | Physically Completed | 15106.37 | 12948 | 2023-10-07 | 2026-02-22
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001014/IF/22012035231006 — Boundary Plantation Suresh Naththu | Deleted | 0 | 0 | 2024-04-14
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001014/IF/22012035231053 — Boundary Plantation Suresh Naththu | Ongoing | 145050.83 | 19327.36 | 2024-06-21
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001014/IF/22012035231326 — Boundary Plantation Punibai Kishor | Ongoing | 145050.83 | 19327.36 | 2024-06-21
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001014/IF/22012035231328 — Boundary Plantation Jitendra Kanheya | Ongoing | 145050.83 | 18368.32 | 2024-06-21
BARWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742001014/IF/22012035344668 — JGSA Well Recharge Structure Mukesh Bhikya | Physically Completed | 25899.46 | 24025.5 | 2025-04-23 | 2026-02-21
BARWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742001014/IF/22012035344683 — JGSA Well Recharge Structure Jagdish Karsan | Physically Completed | 25899.46 | 20616 | 2025-04-23 | 2026-02-21
BARWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742001014/IF/22012035344697 — JGSA Well Recharge Structure Abhimanyu Ambaram | Physically Completed | 25899.46 | 17500.5 | 2025-04-23 | 2026-02-21
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742001014/IF/22012035476784 — Farm Pond Balram Sitaram | Completed | 55865.38 | 28492.84 | 2025-05-24 | 2025-10-16
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742001014/IF/22012035543642 — Farm pond Suka Gala | Deleted | 147621.16 | 261 | 2025-05-24
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742001014/IF/22012035621925 — Pashushed Nirman Kary Chintamani Mukesh Amlali | Deleted | 0 | 0 | 2025-07-18
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/1188396 — Construction of IAY House -IAY REG. NO. MP1482323 | Completed | 15480 | 15480 | 2017-12-13 | 2018-02-21
BARWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/2515691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4544425 | Completed | 17100 | 14636 | 2020-05-29 | 2021-12-23
BARWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/2531617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4833479 | Completed | 17100 | 13244 | 2020-05-29 | 2021-09-28
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3873980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146926203 | Completed | 18360 | 18080 | 2022-06-09 | 2023-10-24
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3885975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375251 | Completed | 18360 | 16910 | 2022-06-09 | 2022-08-21
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3885976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375287 | Completed | 18360 | 17825 | 2022-06-16 | 2023-09-05
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3900020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010430 | Completed | 18360 | 16011 | 2022-06-09 | 2023-06-06
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3900021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010519 | Completed | 18360 | 18004 | 2023-06-16 | 2023-11-20
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3900022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012394 | Completed | 18360 | 17008 | 2022-06-09 | 2022-08-31
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3900024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012465 | Completed | 18360 | 18149 | 2022-07-27 | 2023-09-19
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3900025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012514 | Completed | 18360 | 17103 | 2022-10-12 | 2022-12-13
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/3900026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012556 | Completed | 18360 | 17348 | 2022-07-27 | 2022-10-23
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4108965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146918367 | Completed | 18360 | 17997 | 2023-06-16 | 2024-04-10
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4109703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010409 | Completed | 18360 | 16964 | 2022-07-23 | 2023-06-30
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4109705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010455 | Completed | 18360 | 16756 | 2022-12-11 | 2023-09-11
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4297740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146949811 | Completed | 18360 | 17199 | 2022-09-15 | 2023-06-30
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4297776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375105 | Completed | 18360 | 18306 | 2023-06-16 | 2023-09-05
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4312259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375119 | Completed | 18360 | 18284 | 2023-09-04 | 2024-02-28
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4349630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124601149 | Completed | 18360 | 18234 | 2022-09-15 | 2022-11-22
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4357860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375096 | Completed | 18360 | 18336 | 2022-09-22 | 2023-09-11
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4357999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012426 | Completed | 18360 | 17220 | 2022-09-15 | 2023-06-30
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4358543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146903482 | Completed | 18360 | 18029 | 2022-12-11 | 2023-07-07
BARWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4372114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375068 | Completed | 18360 | 17627 | 2022-12-11 | 2023-07-07
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4409950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012452 | Completed | 19890 | 19264 | 2023-08-08 | 2023-10-24
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4409951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012573 | Completed | 19890 | 18373 | 2023-09-04 | 2024-01-07
BARWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4409952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012578 | Completed | 19890 | 19389 | 2023-09-04 | 2023-12-12
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4654105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147374990 | Completed | 21870 | 20412 | 2024-10-16 | 2025-01-24
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4654107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375394 | Completed | 21870 | 20412 | 2024-10-23 | 2025-02-03
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4654108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375473 | Completed | 23490 | 19926 | 2024-10-16 | 2025-04-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4659402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010512 | Completed | 23490 | 22963 | 2025-04-17 | 2026-02-11
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4659406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012526 | Completed | 23490 | 21481 | 2025-01-21 | 2026-02-11
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4663440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148815624 | Completed | 23490 | 21870 | 2024-11-22 | 2025-04-22
BARWANI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/473281 — Construction of IAY House -IAY REG. NO. MP1876438 | Completed | 15030 | 15988 | 2017-01-30 | 2017-12-01
BARWANI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/478138 — Construction of IAY House -IAY REG. NO. MP1950302 | Completed | 15030 | 14208 | 2017-02-07 | 2018-01-02
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4833505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148815639 | Completed | 23490 | 22068 | 2024-11-29 | 2026-02-11
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4833506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148816193 | Completed | 21870 | 20412 | 2024-11-22 | 2025-01-19
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/4834201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148013032 | Completed | 23490 | 21978 | 2025-02-19 | 2026-02-11
BARWANI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/494132 — Construction of IAY House -IAY REG. NO. MP2181238 | Completed | 15030 | 13864 | 2017-01-30 | 2018-02-02
BARWANI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/527943 — Construction of IAY House -IAY REG. NO. MP2751649 | Completed | 15030 | 15868 | 2017-02-07 | 2017-12-01
BARWANI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/528366 — Construction of IAY House -IAY REG. NO. MP2759431 | Completed | 15030 | 14724 | 2017-02-07 | 2017-12-01
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375497 | Physically Completed | 27000 | 23490 | 2026-02-05 | 2026-09-07
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012403 | Ongoing | 27000 | 4176 | 2026-04-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012409 | Physically Completed | 27000 | 12528 | 2026-03-26 | 2026-09-13
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012417 | Physically Completed | 23490 | 22707 | 2025-08-27 | 2026-07-05
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012478 | Completed | 23490 | 23490 | 2025-09-09 | 2025-12-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012492 | Physically Completed | 23490 | 22707 | 2026-02-05 | 2026-04-19
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5457669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012502 | Physically Completed | 23490 | 22171 | 2025-07-11 | 2026-07-05
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5459412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148229737 | Completed | 23490 | 22432 | 2025-07-11 | 2026-02-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5461603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375343 | Completed | 23490 | 22446 | 2025-08-12 | 2026-02-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5463670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012522 | Ongoing | 27000 | 22171 | 2025-07-11
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5463671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012539 | Ongoing | 27000 | 7830 | 2026-04-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5464960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148815634 | Completed | 23490 | 23462 | 2025-07-11 | 2025-12-11
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5464963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148816196 | Physically Completed | 23490 | 14877 | 2026-04-03 | 2026-08-09
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5465617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010468 | Physically Completed | 23490 | 21910 | 2025-07-11 | 2026-04-12
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5465618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010489 | Physically Completed | 23490 | 22185 | 2025-09-23 | 2026-01-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5465619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010502 | Ongoing | 27000 | 261 | 2025-12-26
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147374902 | Completed | 23490 | 23462 | 2025-07-11 | 2026-01-26
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147374972 | Physically Completed | 23490 | 21402 | 2025-11-13 | 2026-05-03
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375007 | Ongoing | 27000 | 4176 | 2026-04-02
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375015 | Ongoing | 27000 | 7830 | 2026-04-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375131 | Physically Completed | 23490 | 22954 | 2026-03-13 | 2026-05-17
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375144 | Ongoing | 27000 | 20330 | 2025-07-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375154 | Completed | 23490 | 22968 | 2025-07-11 | 2026-02-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375177 | Completed | 23490 | 22379 | 2025-07-11 | 2026-02-11
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5466279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375217 | Physically Completed | 23490 | 7308 | 2026-02-05 | 2026-03-05
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5594360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375368 | Physically Completed | 23490 | 18009 | 2025-11-13 | 2026-03-05
BARWANI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/564357 — Construction of IAY House -IAY REG. NO. MP3821457 | Completed | 15030 | 15928 | 2017-01-30 | 2018-01-02
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5819959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148010532 | Ongoing | 27000 | 522 | 2026-04-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148816185 | Physically Completed | 23490 | 3654 | 2026-02-19 | 2026-03-29
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148815628 | Physically Completed | 23490 | 14616 | 2026-02-19 | 2026-07-05
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148012436 | Ongoing | 27000 | 3654 | 2026-04-02
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147374926 | Ongoing | 27000 | 522 | 2026-04-02
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147374997 | Ongoing | 27000 | 1827 | 2026-04-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375532 | Physically Completed | 23490 | 3393 | 2026-03-13 | 2026-03-29
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148815659 | Ongoing | 27000 | 7308 | 2025-03-10
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375192 | Physically Completed | 23490 | 10962 | 2026-02-19 | 2026-03-15
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5820877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375319 | Ongoing | 27000 | 1827 | 2026-04-02
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/584875 — Construction of IAY House -IAY REG. NO. MP1583358 | Completed | 15030 | 14496 | 2017-12-13 | 2018-05-10
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/5971623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147375418 | Approved | 27000 | 0 | 2025-03-26
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/816919 — Construction of IAY House -IAY REG. NO. MP1950605 | Completed | 15480 | 14568 | 2017-10-25 | 2018-10-30
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/818630 — Construction of IAY House -IAY REG. NO. MP2102805 | Completed | 15480 | 14104 | 2017-10-24 | 2018-03-15
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001014/IF/IAY/819530 — Construction of IAY House -IAY REG. NO. MP2179252 | Completed | 15480 | 16560 | 2017-10-24 | 2018-05-10
BARWANI | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1742001014/LD/22012034301171 — Shantidham Nirman Karya bijasan | Completed | 180000 | 179219.53 | 2017-03-01 | 2018-02-02
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1742001014/LD/22012034580809 — माँ की बगिया प्रा.वि. अमलाली | Closed | 0 | 0 | 2022-05-14
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1742001014/LD/22012034580810 — माँ की बगिया प्रा.वि. बिजासन | Closed | 0 | 0 | 2022-05-14
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1742001014/LD/22012034580811 — माँ की बगिया हाई स्कूल बिजासन | Closed | 0 | 0 | 2022-05-14
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1742001014/LD/22012034581064 — माँ की बगिया (आंगनवाडी केंद्र अमलाली) बिजासन | Completed | 10500.41 | 1230 | 2022-08-27 | 2023-07-08
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1742001014/LD/22012034581065 — माँ की बगिया (प्रा. वि. अमलाली) बिजासन | Completed | 10499.91 | 1140 | 2022-08-27 | 2023-07-08
BARWANI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1742001014/LD/3799388908 — नर्मदा परिक्रमा पथ अमलाली बिजासन | Completed | 407000 | 149643 | 2013-05-21 | 2015-12-10
BARWANI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/1193 — पुलिया निर्माण बिलनखोदरी मार्ग बिजासन | Completed | 471000 | 404850 | 2008-09-03 | 2008-09-17
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/22012034164688 — नर्मदा परिक्रमा पथ निर्माण | Deleted | 0 | 0 | 2012-04-14
BARWANI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/22012034164691 — नर्मदा परिक्रमा पथ निर्माण | Deleted | 0 | 0 | 2013-04-14
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/22012034164930 — Narmada Parikrama Path Nirman | Deleted | 0 | 0 | 2012-04-14
BARWANI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034171895 — PANCHPARMESVER CC ROED NIRMAN BIJASAN | Completed | 83000 | 22379 | 2013-06-18 | 2017-07-07
BARWANI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034311991 — cement cancrit road nirman kary naharsingh loniya ke khet se puranee sadak ki our gram bijasan | Completed | 178000 | 69316 | 2017-09-01 | 2018-03-15
BARWANI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034311994 — सीमेंट कांक्रीट रोड निर्माण कार्य नई सड़क से पुरानी सड़क की ओर ग्राम बिजासन | Deleted | 256000 | 0 | 2015-04-14
BARWANI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034323672 — C.C.road nirman kary bijasan | Completed | 1100000 | 83694 | 2017-01-30 | 2018-02-12
BARWANI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034370113 — cc road nirman m.s.se men road tak | Closed | 0 | 0 | 2017-04-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034377109 — CC ROAD NIRMAN AMARSINGH KE GHAR SE SYAMLAL KE GHAR TAK AMLALI | Completed | 21000 | 3112 | 2019-02-15 | 2020-01-22
BARWANI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034379155 — cc road nirman ramesh ke ghar se bansiya ke ghar tak | Completed | 86000 | 78354 | 2018-02-01 | 2019-03-13
BARWANI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034379158 — cc road nirman bansiya ke ghar se radhu ke dhar tak | Completed | 80000 | 80388 | 2018-03-13 | 2019-03-12
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034392443 — cc road nirman mohan ke ghar se devram ke ghar tak amlali bijasan | Closed | 96000 | 0 | 2018-04-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034392456 — cc road nirman mohan ke ghar se mehtab ke ghar tak amlali bijasan | Completed | 140000 | 94914 | 2019-02-23 | 2020-08-08
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034396173 — c.c.road nirman mehtab ke ghar se radhu ke ghar tak amlali bijasan | Completed | 80000 | 78210 | 2019-02-15 | 2020-03-22
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034435768 — c.c.road nirman bijasan | Closed | 0 | 0 | 2019-01-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034435769 — c.c.road nirman bijasan | Closed | 0 | 0 | 2019-01-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034435771 — c.c.road nirman bijasan | Closed | 0 | 0 | 2019-01-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034435772 — c.c.road nirman bijasan | Closed | 0 | 0 | 2019-01-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034435773 — c.c.road nirman amlali bijasan | Closed | 0 | 0 | 2019-01-01
BARWANI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034449488 — CC Raod Nirman Kary P V Bhavan Se Chensingh Ke Ghar Tak Amlali | Closed | 95900 | 0 | 2019-01-26
BARWANI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034468896 — c.c.road nirman work prathmik shala se chensingh ke ghar ki or amlali bijasan | Closed | 108000 | 0 | 2019-04-01
BARWANI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034469852 — CC Raod Nirman Kary Pramik School Se Chensingh Ke Ghar Tak Amlali | Physically Completed | 108000 | 15630 | 2020-02-18 | 2021-12-25
BARWANI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034476384 — c.c.road nirman men road se ratan chitar ke ghar ki or bijasan | Completed | 139000 | 45372 | 2019-11-13 | 2020-08-06
BARWANI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034538627 — c.c.road nirman ratan ke ghar se kailash ke ghar ki or bijasan | Completed | 36000 | 37758 | 2020-10-10 | 2020-12-28
BARWANI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034538628 — c.c.road nirman men road se mohan ke ke ghar ki or amlali | Closed | 26000 | 0 | 2020-05-19
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034579414 — CC Raod Nirman Kary Jagdish/Gopal Ke Ghar Se Modi Pura Ki Or Amlali Bijasan | Completed | 107000 | 100700 | 2021-08-13 | 2024-01-06
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034582680 — CC Raod Nirman Jwarsingh Ke Ghar Se Motimata Mandir Ki Our Bijasan | Closed | 56800 | 0 | 2021-08-15
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034601112 — CC Raod Nirman Kary Chensingh Ke Ghar Se Lalbai Ke Ghar Ki Or Bijasan | Completed | 67000 | 56512 | 2022-01-27 | 2022-06-20
BARWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034663146 — सीसी रोड(मथुरा के घर से मा.वि.) | Closed | 0 | 0 | 2023-04-14
BARWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034665659 — CC Raod Nirman Kary Mathura Ke Ghar Se Middel School Tak Bijasn | Deleted | 60000 | 202 | 2023-08-16
BARWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001014/RC/22012034824911 — Nali Nirman Kary Men Road Se purnvas Baswad Ki Our Bijasan | Physically Completed | 101000 | 52974 | 2025-02-07 | 2026-07-20
BARWANI | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/3003 — पाईप पुलिया निर्माण बसाहट स्‍थल बिजासन | Completed | 498000 | 333104.8 | 2009-09-27 | 2009-01-26
BARWANI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/3202 — अर्थकर्व मुरमीकरण एवं सडक निर्माण पुरानी से नई सडक तक बिजासन | Completed | 491000 | 452700 | 2010-05-18 | 2010-03-01
BARWANI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742001014/RC/3750 — घाट कटिंग कार्य निर्माण बिजासन | Completed | 244000 | 220110 | 2012-02-28 | 2015-08-15
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224066 — SOCHALAY NIRMAN SHANTILAL BILA BIJASAN | Completed | 4400 | 3996 | 2014-04-15 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224070 — SOCHALAY NIRMAN LAXMAN SAKHARAM BIJASAN | Completed | 4400 | 3996 | 2014-04-15 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224073 — SOCHALAY NIRMAN KAMAL KANHAYA BIJASAN | Completed | 4400 | 3996 | 2014-04-15 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224075 — SOCHALAY NIRMAN PABHU NATTU BIJASAN | Completed | 4400 | 3996 | 2014-04-15 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224078 — SOCHALAY NIRMAN MATHURALAL SAKHARAM BIJASAN | Completed | 4400 | 3996 | 2014-07-06 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224079 — SOCHALAY NIRMAN LILABAI SALKRAM BIJASAN | Deleted | 4400 | 0 | 2014-04-15
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224081 — SOCHALAY NIRMAN MAHENDRA BHADRA BIJASAN | Deleted | 4400 | 0 | 2012-04-26
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224083 — SOCHALAY NIRMAN KAMAL AMARSINGH BIJASAN | Deleted | 4400 | 0 | 2014-04-15
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224085 — SOCHALAY NIRMAN GOPICHAND BHADRA BIJASAN | Completed | 4400 | 3996 | 2014-04-15 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224088 — SOCHALAY NIRMAN ESAVAR BATTU BIJASAN | Deleted | 4400 | 0 | 2014-04-15
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224091 — SOCHALAY NIRMAN SONIBAI SAKHARAM BIJASAN | Completed | 4400 | 3996 | 2014-07-06 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034224097 — SOCHALAY NIRMAN GANGARAM BABU BIJASAN | Deleted | 4400 | 0 | 2014-04-15
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034226750 — sochalay nirman karyar mahesh ramesh bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034226755 — SOCHALAY NIRMAN MOHAN NANNU BIJASAN | Deleted | 4400 | 0 | 2012-04-15
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034226769 — sochalay nirman karya kishor chiman bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034226779 — sochalay nirman karya chindar naran bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034226784 — sochalay nirman karya jatan babu bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034226788 — sochalay nirman karya dasharth madan bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227319 — sochalay nirman karya ratan babu bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227324 — sochalay nirman karya shobharam shankar bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227327 — sochalay nirman karya mohan nannu bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227332 — sochalay nirman karya mahadev limchandra bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227335 — sochalay nirman karya ambaram dasharth bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227340 — sochalay nirman karya bau sardar bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227344 — sochalay nirman karya bholya gedalal bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227346 — sochalay nirman karya kalya mutariya bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227349 — sochalay nirman karya gokul gedalal bijasan | Completed | 4400 | 3996 | 2014-07-06 | 2015-04-22
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034227357 — sochalay nirman karya dinesh naharsing bijasan | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034237827 — sochalay nirman karya r radhesyam jalal | Deleted | 4400 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034238391 — shochalay nirman karya bhaggu kishan | Deleted | 0 | 0 | 2012-10-01
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034238726 — sochalay nirman karya shatilal magilal | Deleted | 0 | 0 | 2012-10-03
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034247280 — bau punja shochaly nirman karya | Deleted | 0 | 0 | 2012-10-03
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034247285 — bau punja shochaly nirman karya | Deleted | 0 | 0 | 2012-10-03
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034265221 — bhagwan kalu sochalya nirman karya | Deleted | 4400 | 0 | 2014-09-03
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034265226 — rajesh gokul sochalya nirman karya bijasan | Deleted | 4400 | 0 | 2014-09-03
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034265229 — bala taiba sochalya nirman karya bijasan | Deleted | 4400 | 0 | 2014-09-03
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034265235 — siva subhan sochalya nirman karya bijasan | Deleted | 0 | 0 | 2012-10-03
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034265241 — dewesing ranchhod sochalya nirman karya bijasan | Deleted | 4400 | 0 | 2014-09-03
BARWANI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034265255 — kishor shankar sochalya nirman karya | Deleted | 4400 | 0 | 2014-02-17
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034268989 — bhagwan kalu bijasan sochalya nirman karya | Deleted | 0 | 0 | 2014-09-17
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271609 — sochalya nirman karya mahendro bhadra bijasan | Completed | 4400 | 4006 | 2014-10-10 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271618 — sochalya nirnam karya bhaggu kisan bijasan | Deleted | 4400 | 2790 | 2014-10-10
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271619 — sochalya nirman karya radheshyam jalal sijasan | Completed | 4400 | 4006 | 2014-10-10 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271620 — sochalya nirman karya dinesh naharsing bijasa | Completed | 4400 | 3988 | 2014-10-10 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271621 — sochalya nirman karya gokul gendalal bijasan | Deleted | 4400 | 0 | 2014-10-10
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271622 — sochalya nirman karya bhagwan kalu bijasan | Completed | 4400 | 3988 | 2014-10-10 | 2015-04-22
BARWANI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271623 — sochalya nirman karya rajesh gokul bijasan | Deleted | 0 | 0 | 2012-10-03
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271624 — sochalya nirman karya rajesh gokul bijasan | Completed | 4400 | 4006 | 2014-10-10 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271625 — sochalya nirman karya bala taiba bijasan | Completed | 2640 | 2790 | 2014-10-10 | 2024-09-11
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271935 — sochalya nirman karya bau punja bijasan | Completed | 4400 | 2826 | 2014-10-10 | 2015-03-26
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271952 — sochalya nirman karya devising ranchhod bijasan | Completed | 4400 | 4006 | 2014-10-10 | 2015-04-22
BARWANI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034271954 — sochalya nirman karya kamal amarsingh sijasan | Completed | 4400 | 4006 | 2014-10-10 | 2015-04-22
BARWANI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742001014/RS/22012034280601 — mansharam sakharam soghalya nirman karya bijasan | Deleted | 4400 | 0 | 2014-02-17
BARWANI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1742001014/RS/22012034494801 — samudayak sochalay nirman bijasan | Completed | 43700 | 42840 | 2020-09-10 | 2020-10-25
BARWANI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742001014/WC/11 — बोल्‍डर चेक डेम बि‍जासन | Completed | 66000 | 150218.72 | 2006-04-02 | 2023-12-07
BARWANI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742001014/WC/1696 — हाईडोलिक स्‍टेक्‍चर निर्माण बिजासन | Completed | 440000 | 418757.4 | 2009-05-25 | 2009-06-20
BARWANI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1742001014/WC/22012034431785 — Talab nirman work bijasan | Closed | 0 | 0 | 2019-01-01
BARWANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742001014/WC/22012034564025 — sct work amlali bijasan | Completed | 649518.53 | 534516 | 2020-07-01 | 2021-12-31
BARWANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1742001014/WC/22012034602885 — terish formming bhijashn purane roud bhilt mandhir ke pash | Ongoing | 173010.11 | 90 | 2020-12-30
BARWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1742001014/WC/22012034693076 — ctr_gis_sct nirman panchayat bhawan ke piche pahadhi par | Completed | 645206.38 | 292730 | 2021-06-03 | 2022-11-10
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742001014/WC/22012035033926 — SCT_CPT Nimarn Kary Patelpura ke piche wala pahad gram amlali | Closed | 0 | 0 | 2022-10-02
BARWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742001014/WC/22012035033933 — SCT_CPT Nimarn Kary badpura ke pas wala pahad gram bijasan | Completed | 232999.7 | 191628.99 | 2023-06-16 | 2024-10-21
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742001014/WC/22012035033934 — SCT_CPT Nimarn Kary badpura ke pas wala pahad gram bijasan | Closed | 0 | 0 | 2022-10-02
BARWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742001014/WC/22012035239989 — RMS Check Dam Nirman Kary Amlali | Completed | 75000 | 72159.05 | 2025-02-07 | 2025-03-19
BARWANI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742001014/WC/3203 — हाइडोलिक स्‍टेक्‍चर निर्माण बिजासन | Completed | 491000 | 444297.12 | 2010-05-17 | 2010-08-01
BARWANI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742001014/WC/3741 — स्‍टाप डेम निर्माण कार्य सेमलीबैडी बिजासन | Completed | 491000 | 318739.2 | 2011-12-25 | 2012-08-25
BARWANI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742001014/WC/3833 — निस्‍तार तालाब निर्माण बिजासन | Completed | 413000 | 382686 | 2012-03-14 | 2014-08-30
BARWANI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742001014/WC/9993660991 — JAL SAWARDAN CCT BIJASAN | Completed | 414000 | 122033.9 | 2015-12-05 | 2017-11-09
BARWANI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742001014/WC/9993669942 — C.C.T.C.P.T BIJASAN | Deleted | 0 | 0 | 2015-04-14
BARWANI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1742001014/WH/1417 — हाईडोलिक स्‍टकचर बिजासन | Completed | 420000 | 9108 | 2008-01-01 | 2008-02-13
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001/IF/22012034375581 — Plantation Work Devisingh Fhata Bijasan | Physically Completed | 581250 | 76556 | 2018-03-12 | 2021-01-06
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001/IF/22012034375721 — Plantation Work Sriram Nageshwar, Govind Jogiya, or Vijay Ranchhod Amalali | Completed | 552420 | 90176 | 2017-09-22 | 2020-05-23
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001/IF/22012034375728 — Plantation Work Abhimanyu Abmaram, Naval Chhitu, Dogarsingh Dashriya, Or Mehtab Gokul Amlali | Completed | 550614 | 109678 | 2017-09-22 | 2020-05-23
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001/IF/22012034382763 — Plantation Work Bhavar Bajesingh Mukesh Bhikya Bijasan | Physically Completed | 623181 | 99684 | 2018-03-14 | 2021-01-06
BARWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742001/IF/22012034382769 — Plantation Work Naran Budha Bijasan | Physically Completed | 564746 | 84784 | 2018-03-12 | 2021-01-06