## Work List
Exported on: 2026-09-10 11:22:17
Filters applied:
Data source: VBGRAMG
District: BARWANI
Block: All
Panchayat: BOMYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1742001015/AV/22012034552434 — माँ अम्बे गौशाला निर्माण कार्य बोम्या | Ongoing | 3804727 | 80400 | 2021-05-18
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742001015/DP/22012034560713 — अमृत सरोवर वृक्षारोपण कार्य(किशोर गोमे के खेत के पास भाग -1) बोम्या | Ongoing | 713000 | 0 | 2022-08-11
BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742001015/DP/22012034560714 — अमृत सरोवर वृक्षारोपण कार्य(किशोर गोमे के खेत के पास भाग - 2)बोम्या | Ongoing | 713000 | 0 | 2022-08-11
BARWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742001015/IF/22012034469060 — kapil dhara kup nirman ladki bai dhulkiya bomya | Ongoing | 210000 | 0 | 2020-05-02
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001015/IF/22012035233593 — Boundary Plantation Bharsing Nuru | Ongoing | 145050.83 | 4200 | 2024-07-02
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001015/IF/22012035233597 — Boundary Plantation Ramesh motla | Ongoing | 145050.83 | 0 | 2024-07-02
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001015/IF/22012035233599 — Boundary Plantation Malsing Thavrya | New | 0 | 0 | 2024-04-14
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001015/IF/22012035233603 — Boundary Plantation Balsing Bhuru | Ongoing | 145050.83 | 0 | 2024-07-02
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742001015/IF/22012035233607 — Boundary Plantation Kailash rajan | Ongoing | 145050.83 | 6300 | 2024-07-02
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742001015/IF/22012035422893 — Farm pond Ramesh Motla | New | 0 | 0 | 2025-04-14
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/4823080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120823841 | Ongoing | 27000 | 0 | 2025-02-07
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/4823362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121627302 | Ongoing | 27000 | 0 | 2025-02-07
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/4823365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121629333 | Ongoing | 27000 | 0 | 2025-02-07
BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/4824699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122092612 | Ongoing | 27000 | 0 | 2025-02-07
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5460376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126302085 | Ongoing | 27000 | 0 | 2026-04-06
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5460832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122792891 | Ongoing | 27000 | 0 | 2026-04-06
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5464554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136337510 | Ongoing | 27000 | 0 | 2025-07-23
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5722668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126436020 | Physically Completed | 23490 | 0 | 2026-04-06 | 2026-07-19
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5735210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122025053 | Ongoing | 27000 | 0 | 2026-04-06
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5819896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123040990 | Ongoing | 27000 | 0 | 2025-12-05
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5820009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122066816 | Ongoing | 27000 | 0 | 2026-04-06
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5820897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123039203 | Ongoing | 27000 | 0 | 2026-04-06
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5820903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122795405 | Ongoing | 27000 | 0 | 2026-04-06
BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/5820923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124508818 | Physically Completed | 23490 | 0 | 2025-12-03 | 2026-07-19
BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742001015/IF/IAY/6133443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122794421 | Ongoing | 27000 | 0 | 2026-06-03
BARWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1742001015/LD/22012034949531 — चारागाह गौशाला के पास बोम्या | Approved | 964293.82 | 0 | 2025-01-26
BARWANI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001015/RC/22012034540735 — CC Road Nirman Kary Patel Falya Bomiya | Ongoing | 60000 | 0 | 2021-04-01
BARWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742001015/RC/22012034827915 — CC Road Nirman Kary Bhvyu Ke Ghar Se Choraha Tak Jamda Bedi | Approved | 96000 | 0 | 2024-04-14