## Work List
Exported on: 2026-09-15 18:36:19
Filters applied:
Data source: MGNREGA
District: BARWANI
Block: All
Panchayat: PALASIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1742003038/AV/22012034550483 — khel maidan palasiya | Completed | 215560.41 | 215307 | 2021-05-15 | 2023-07-31
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1742003038/AV/22012034569539 — shantidham nirman ramdevpura palasiya | Completed | 196981.11 | 193770 | 2021-10-28 | 2024-04-22
THIKRI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1742003038/AV/22012034628260 — आंगनवाड़ी भवन निर्माण=पलासिया | Completed | 312000 | 268664 | 2023-10-14 | 2025-02-19
THIKRI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1742003038/AV/22012034628262 — आंगनवाड़ी भवन निर्माण=झोलपीपरी | Completed | 312000 | 265753 | 2023-06-14 | 2025-02-19
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/DP/22012034521062 — waterpond | Completed | 332962.02 | 139646 | 2021-03-06 | 2021-12-14
THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1742003038/DP/22012034601535 — vasudha vandan hanuman mandir ke pass | Closed | 55847.4 | 0 | 2023-10-14
THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1742003038/DP/22012034609185 — Plantation work hanu man mandir pass palasiya | Ongoing | 872152.77 | 26932 | 2024-07-22
THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1742003038/DP/22012034609186 — Plantation work hanu man mandir pass palasiya | Closed | 0 | 0 | 2023-04-14
THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742003038/DP/22012034617235 — Plantation hanuman mandir wali pahadi palasiya | Ongoing | 506952.08 | 79608.47 | 2024-10-23
THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1742003038/DP/22012034624757 — वृक्षारोपण निर्माण कार्य हनुमान मंदिर के पास पलासिया पहाड़ी पर | New | 0 | 0 | 2024-07-05
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742003038/DP/77 — व्रक्षारोपण एवं जलसंवर्धन कार्य (4.93 नकटीमाता) पल | Completed | 493000 | 171164 | 2011-11-01 | 2012-05-16
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742003038/IF/22012034339764 — कपिल धारा कूप सह खेत निर्माण दयासिंग रणछोड | Completed | 230000 | 148216 | 2017-05-16 | 2020-01-24
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351866 — plantation work palasiya pahadi 1 | Completed | 535000 | 325864 | 2017-06-23 | 2020-12-28
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351874 — plantation work palasiya pahadi par 2 | Completed | 535000 | 56299.95 | 2017-06-28 | 2024-04-26
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351882 — plantation work Palasiya pahadi par 03 | Completed | 535000 | 31600 | 2017-06-28 | 2020-12-28
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351890 — plantation work sajway pahadi Bhag-1 | Completed | 535000 | 433133 | 2017-06-17 | 2023-12-06
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351897 — plantation work sajway pahadi Bhag-2 | Completed | 535000 | 83548 | 2017-06-28 | 2024-04-26
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351908 — plantation work jholpipri pahadi | Completed | 535000 | 38142 | 2017-07-02 | 2020-12-28
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351918 — plantation work sajway school | Completed | 252000 | 54508 | 2017-06-23 | 2020-12-28
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351928 — plantation work sajway pmgsy road Bhag-1 | Completed | 335000 | 22306 | 2017-07-02 | 2020-12-28
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351933 — plantation work sajway pmgsy road Bhag-2 | Completed | 335000 | 19064 | 2017-07-04 | 2020-12-28
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003038/IF/22012034351941 — plantation work panchayat pariser | Completed | 168000 | 8500 | 2017-08-08 | 2019-10-21
THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742003038/IF/22012034439712 — व्‍यक्तिगत शौचालय निर्माण उंकार नारायण सजवाय | Closed | 1200000000 | 0 | 2018-08-15
THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1742003038/IF/22012034439713 — व्‍यक्तिगत शौचालय निर्माण गुडडू जसवन सजवाय | Closed | 1200000000 | 0 | 2018-08-15
THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1742003038/IF/22012034439714 — व्‍यक्तिगत शौचालय निर्माण नानुराम सीताराम सजवाय | Closed | 1200000000 | 0 | 2018-08-15
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742003038/IF/22012034475203 — Kapil Dhara Koop Nirman Kary Hit. Motilal Yadav | Completed | 200000 | 188704 | 2019-06-01 | 2021-06-25
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742003038/IF/22012034492885 — kapildhara 2.00 jaysingh shersingh palasiya | Closed | 0 | 0 | 2019-06-26
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003038/IF/22012034597735 — PASHU SHED DHANKUVARBAI | Closed | 0 | 0 | 2020-04-08
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612013 — बाँस वृक्षारोपण सीमा नानुराम पलासिया | Completed | 68904.57 | 27553.63 | 2021-01-28 | 2025-04-11
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612015 — बाँस वृक्षारोपणगिरधारी दित्या पलासिया | Completed | 62566.11 | 25203.56 | 2020-12-10 | 2025-04-18
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612016 — बाँस वृक्षारोपण लक्ष्मी दित्या पलासिया | Completed | 59996.57 | 29084.82 | 2020-12-10 | 2025-04-11
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612018 — बाँस वृक्षारोपण सारिका श्यामू पलासिया | Completed | 116265.03 | 41488.98 | 2020-12-10 | 2025-04-27
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612019 — बाँस वृक्षारोपण लक्ष्मी भारत पलासिया | Closed | 0 | 0 | 2020-08-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612021 — बाँस वृक्षारोपण धनु मोहन पलासिया | Closed | 0 | 0 | 2020-08-15
THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612022 — बाँस वृक्षारोपण सीमा कैलाश पलासिया | Ongoing | 64015.81 | 27520.73 | 2024-09-25
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1742003038/IF/22012034612023 — बाँस वृक्षारोपण रामकोर उदयराम पलासिया | Completed | 62203.68 | 19190 | 2020-12-10 | 2024-06-19
THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1742003038/IF/22012035232117 — Plantataion med pr shyamu udayram palasiya | Ongoing | 145050.83 | 17018 | 2024-07-26
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003038/IF/22012035468151 — JGSA 2025 Khet Talab Nirman Sukan Asharam palasiya | Deleted | 0 | 0 | 2025-04-14
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003038/IF/22012035468295 — JGSA 2025 Khet Talab Nirman Sukan Asharam palasiya | Physically Completed | 55865.38 | 53253.83 | 2025-05-06 | 2026-03-31
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003038/IF/22012035468371 — JGSA 2025 Khet Talab Nirman badri Narayan palasiya | Deleted | 55865.38 | 105.03 | 2025-05-06
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003038/IF/22012035477093 — JGSA 2025 Khet Talab Nirman Sitaram Narayan palasiya | Approved | 55865.38 | 0 | 2025-04-14
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003038/IF/22012035477105 — JGSA 2025 Khet Talab Nirman Hari Narayan palasiya | Approved | 55865.38 | 0 | 2025-04-14
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742003038/IF/22012035534620 — JGSA 2025 Khet Talab nirman Budiya Narayan palasiya | Physically Completed | 55865.38 | 39288.6 | 2025-05-27 | 2026-03-17
THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742003038/IF/22012035566815 — JGSA2025 Khet talab dwarkibai shivji jholpipri | Approved | 55865.38 | 0 | 2025-04-15
THIKRI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003038/IF/313 — मेढ बंधान (.23900 पुनिया मंगल्‍या सजवाय) पलासिया | Completed | 23100 | 6040 | 2011-02-08 | 2011-02-08
THIKRI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003038/IF/314 — मेढ बंधान (.23900 सीताराम धना सजवाय) पलासिया | Completed | 23100 | 11764 | 2011-02-08 | 2011-04-03
THIKRI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003038/IF/315 — मेढ बंधान ( .23900 गुलाब पीरीया सजवाय) पलासिया | Completed | 23100 | 5430 | 2011-02-08 | 2011-02-08
THIKRI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003038/IF/9926731644 — पशुशेड निर्माण (सीताराम-गोपाल झोलपीपरी) | Completed | 80000 | 79945.58 | 2014-08-13 | 2015-07-24
THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1742003038/IF/9926731645 — बकरी शेड निर्माण (घनश्याम -हीरा सजवाय) | Deleted | 45000 | 0 | 2013-08-15
THIKRI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742003038/IF/9926734757 — कपिलधारा कूप निर्माण (लक्ष्मण-धन्नालाल सजवाय ) | Completed | 183000 | 178297.1 | 2014-06-11 | 2015-11-18
THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003038/IF/9993654955 — पशुशेडनिर्माण (नानुराम -गणेश सजवाय ) | Deleted | 80000 | 0 | 2014-01-15
THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003038/IF/9993720759 — मेढ़ बंधान | Deleted | 0 | 0 | 2016-01-02
THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/1029734 — Construction of IAY House -IAY REG. NO. MP2335882 | Completed | 15480 | 17052 | 2018-11-01 | 2019-01-07
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2170277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1491636 | Completed | 15840 | 15720 | 2019-09-04 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2282920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1714016 | Completed | 15840 | 15600 | 2019-08-06 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2327522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151414 | Completed | 17100 | 15880 | 2019-11-21 | 2021-04-12
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2327523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151285 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2327524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151168 | Completed | 15840 | 15840 | 2019-11-21 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2327525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151141 | Completed | 15840 | 15664 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2327526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151076 | Completed | 15840 | 15840 | 2019-12-26 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4165189 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4165452 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199072 | Completed | 15840 | 15840 | 2019-11-21 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199062 | Completed | 17100 | 13728 | 2019-11-21 | 2020-10-10
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4184329 | Completed | 15840 | 14784 | 2019-11-21 | 2020-05-15
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4183375 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4177148 | Completed | 15840 | 15840 | 2019-11-21 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4176201 | Completed | 15840 | 14784 | 2020-02-04 | 2020-05-15
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4172862 | Completed | 15840 | 15840 | 2019-11-21 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4168033 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4159850 | Completed | 15840 | 15840 | 2019-11-21 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2328589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4158829 | Completed | 17100 | 15456 | 2019-11-21 | 2021-12-08
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4141447 | Completed | 15840 | 15840 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4791249 | Completed | 15840 | 14784 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4791279 | Completed | 17100 | 13728 | 2019-11-21 | 2020-10-15
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4791940 | Completed | 15840 | 15664 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4791950 | Completed | 17100 | 13728 | 2019-12-12 | 2020-10-15
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4800692 | Completed | 17100 | 13728 | 2019-11-21 | 2020-10-15
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4801683 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4812361 | Completed | 15840 | 15840 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4822816 | Completed | 15840 | 15840 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4838627 | Completed | 15840 | 15840 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4886204 | Completed | 15840 | 15840 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2330658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5598065 | Completed | 15840 | 15840 | 2019-12-12 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2332089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4175777 | Completed | 15840 | 15664 | 2020-01-07 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2332093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4177250 | Completed | 15840 | 15664 | 2019-11-21 | 2020-05-17
THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2332096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4183364 | Completed | 15840 | 15488 | 2019-11-21 | 2020-05-17
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2482688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4100794 | Completed | 17100 | 15580 | 2020-05-21 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2484160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4137274 | Completed | 17100 | 16910 | 2020-05-21 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2484900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4148161 | Completed | 17100 | 16910 | 2020-05-21 | 2021-03-18
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2485132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4151160 | Completed | 17100 | 16720 | 2020-05-21 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2486013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4161107 | Completed | 17100 | 16530 | 2020-05-21 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2486290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4164025 | Completed | 17100 | 14250 | 2020-05-21 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2486621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4167552 | Completed | 17100 | 17100 | 2020-05-21 | 2020-12-27
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2486672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4167988 | Completed | 17100 | 16150 | 2020-05-21 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2486866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4170419 | Completed | 17100 | 15200 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2486993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4171669 | Completed | 17100 | 17100 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2487339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4175852 | Completed | 17100 | 16720 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2487566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4178711 | Completed | 17100 | 16910 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2487908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4183355 | Completed | 17100 | 15960 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2487981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4184452 | Completed | 17100 | 16720 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2488024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4184805 | Completed | 17100 | 17100 | 2020-05-21 | 2021-01-27
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2488116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4185937 | Completed | 17100 | 15960 | 2020-05-21 | 2021-01-27
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2488118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4185943 | Completed | 17100 | 16720 | 2020-05-21 | 2021-04-12
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2489006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199035 | Completed | 17100 | 13870 | 2020-05-21 | 2021-04-12
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2489008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199046 | Completed | 17100 | 16720 | 2020-05-21 | 2021-04-12
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2489011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199050 | Completed | 17100 | 17100 | 2020-05-21 | 2021-04-12
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2489018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199102 | Completed | 17100 | 16910 | 2020-05-21 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2489035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199174 | Completed | 17100 | 16910 | 2020-05-21 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2515154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4538343 | Completed | 17100 | 16910 | 2020-05-17 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2515575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4543105 | Completed | 17100 | 16340 | 2020-05-17 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2515830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4545853 | Completed | 17100 | 16530 | 2020-05-23 | 2021-03-05
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2517225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4560601 | Completed | 17100 | 17100 | 2020-05-21 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2517459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4563667 | Completed | 17100 | 16910 | 2020-05-17 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2517720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4567080 | Completed | 17100 | 15580 | 2020-05-17 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2517866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4568583 | Completed | 17100 | 16910 | 2020-05-21 | 2021-03-18
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2517896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4568918 | Completed | 17100 | 15580 | 2020-05-17 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2518407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4575847 | Completed | 17100 | 17100 | 2020-05-17 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2518411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4575871 | Completed | 17100 | 15580 | 2020-05-17 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2518436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4576074 | Completed | 17100 | 16530 | 2020-05-21 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2519095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4584510 | Completed | 17100 | 16530 | 2020-05-21 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2519521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4589132 | Completed | 17100 | 16340 | 2020-05-21 | 2021-01-04
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2529665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4789945 | Completed | 17100 | 15580 | 2020-05-21 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2529697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4791271 | Completed | 17100 | 15580 | 2020-05-23 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2529761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4793074 | Completed | 17100 | 17100 | 2020-05-21 | 2020-12-28
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2530041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4800232 | Completed | 17100 | 16720 | 2020-05-23 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2530744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4815943 | Completed | 17100 | 16340 | 2020-05-23 | 2021-01-19
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2531642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4833952 | Completed | 17100 | 17100 | 2020-05-23 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2531745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4836001 | Completed | 17100 | 17100 | 2020-05-24 | 2020-10-15
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2732995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4784939 | Completed | 17100 | 17280 | 2021-03-14 | 2021-12-07
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2733295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4588960 | Completed | 17100 | 17280 | 2021-03-14 | 2021-12-07
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/2737760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4566997 | Completed | 17100 | 15368 | 2021-03-14 | 2022-04-16
THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/3696783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114750329 | Completed | 23490 | 23478 | 2022-06-09 | 2025-07-08
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/433601 — Construction of IAY House -IAY REG. NO. MP1419879 | Completed | 15030 | 13582 | 2017-02-03 | 2018-02-15
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/445433 — Construction of IAY House -IAY REG. NO. MP1509251 | Completed | 15030 | 14854 | 2017-02-03 | 2019-02-02
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/448784 — Construction of IAY House -IAY REG. NO. MP1547187 | Completed | 15030 | 15124 | 2017-02-03 | 2017-11-10
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/449787 — Construction of IAY House -IAY REG. NO. MP1560258 | Completed | 15030 | 11720 | 2017-02-03 | 2018-06-30
THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/4555772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114760871 | Completed | 23490 | 22986 | 2025-02-07 | 2026-02-07
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/455778 — Construction of IAY House -IAY REG. NO. MP1637217 | Completed | 15030 | 13145 | 2017-02-03 | 2017-11-10
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/456259 — Construction of IAY House -IAY REG. NO. MP1642358 | Completed | 15030 | 13139 | 2017-02-03 | 2018-06-12
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/459987 — Construction of IAY House -IAY REG. NO. MP1690168 | Completed | 15030 | 15522 | 2017-02-03 | 2017-11-10
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/460168 — Construction of IAY House -IAY REG. NO. MP1693125 | Completed | 15030 | 13694 | 2017-03-02 | 2017-11-10
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/589415 — Construction of IAY House -IAY REG. NO. MP1584247 | Completed | 15030 | 13866 | 2017-02-03 | 2018-02-15
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/590575 — Construction of IAY House -IAY REG. NO. MP3292120 | Completed | 15030 | 14814 | 2017-02-03 | 2019-02-02
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/79027 — Construction of IAY House -IAY REG. NO. MP-42-003-038-001/09 | Completed | 14310 | 13356 | 2016-09-18 | 2016-12-23
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/79028 — Construction of IAY House -IAY REG. NO. MP-42-003-038-001/007 | Completed | 14310 | 14310 | 2016-09-18 | 2016-12-23
THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/79029 — Construction of IAY House -IAY REG. NO. MP-42-003-038-002/43 | Completed | 14310 | 2280 | 2020-05-24 | 2021-01-19
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/79030 — Construction of IAY House -IAY REG. NO. MP-42-003-038-002/57 | Completed | 14310 | 14310 | 2016-09-18 | 2017-03-26
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/79031 — Construction of IAY House -IAY REG. NO. MP-42-003-038-003/015 | Completed | 14310 | 14310 | 2016-09-18 | 2016-12-23
THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/800917 — Construction of IAY House -IAY REG. NO. MP2751377 | Completed | 15480 | 16008 | 2018-11-01 | 2019-01-07
THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/801671 — Construction of IAY House -IAY REG. NO. MP2846205 | Completed | 15480 | 15890.4 | 2018-01-05 | 2019-01-07
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/85103 — Construction of IAY House -IAY REG. NO. MP-42-003-038-003/0043 | Completed | 14310 | 14310 | 2016-09-18 | 2017-02-12
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/85105 — Construction of IAY House -IAY REG. NO. MP-42-003-038-003/018 | Completed | 14310 | 14310 | 2016-09-18 | 2016-12-23
THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003038/IF/IAY/85107 — Construction of IAY House -IAY REG. NO. MP-42-003-038-003/24 | Completed | 14310 | 14310 | 2016-09-18 | 2016-12-23
THIKRI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1742003038/LD/22012034299070 — Shantidham | Deleted | 0 | 0 | 2016-08-16
THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1742003038/LD/22012034299202 — शांतिधाम सजवाय (1.80) पलासिया | Completed | 180000 | 174929.46 | 2017-01-27 | 2018-05-15
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1742003038/LD/22012034507574 — sct work ramdev phadhi palasiya | Completed | 453710.33 | 423130 | 2020-06-19 | 2021-03-15
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1742003038/LD/22012034510678 — Talab gahrikran sajvay | Completed | 149109 | 152000 | 2020-06-13 | 2021-03-15
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1742003038/LD/22012034518350 — plantesion samudayik sarsavati pahadhi palasiya | Closed | 0 | 0 | 2020-05-20
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1742003038/LD/22012034529657 — terece forming palasiya | Completed | 107641.39 | 94491 | 2021-02-04 | 2023-07-20
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1742003038/LD/22012034538757 — maidan samatalikaran panchayat bhawan ke pass palasiya | Deleted | 0 | 0 | 2020-10-02
THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1742003038/LD/22012034596544 — Poshan vatika hanuman mandir ke pass palasiya | Closed | 1461210.87 | 0 | 2023-04-14
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1742003038/LD/85 — शांतिधाम निर्माण्‍ा (4.42 झोलपिपरी) पलासिया | Completed | 442000 | 246802 | 2012-02-07 | 2012-06-19
THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034186471 — पंचपरमेश्‍वर सीसी रोड सजवाय पलासिया | Completed | 171000 | 128705 | 2013-10-02 | 2014-02-17
THIKRI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034198434 — c.c. road sajway hanuman mandir se malu ke ghar ta | Deleted | 156000 | 0 | 2012-01-16
THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034201386 — c.c.road (raju dayaram ke ghar se ghanshyam hira k | Completed | 170000 | 127512 | 2014-02-05 | 2014-04-16
THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1742003038/RC/22012034212438 — SUDOOR GRAM KHET SADAK YOJNA PALASIYA [14.31] | Completed | 1431000 | 87530 | 2014-03-05 | 2017-03-07
THIKRI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034267786 — c.c.rode palasiya(samudayek bhsvan se suresh ke makan tk ) sajway | Completed | 80000 | 71123 | 2015-09-08 | 2015-12-11
THIKRI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034289418 — NALI NIRMAN PALASIYA (PANCH PARMESHWAR+NREGA) | Completed | 162000 | 145915 | 2015-11-30 | 2017-04-01
THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034321966 — cc road with pkki nali | Deleted | 0 | 0 | 2017-01-26
THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034321973 — cc road with pkki nali | Deleted | 0 | 0 | 2017-01-26
THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034322149 — सीसीरोड राजु दयाराम के घर से कन्‍हैया दितिया के घर तक | Completed | 300000 | 26808 | 2017-01-28 | 2018-06-30
THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034369050 — Ccroad Niraman | Deleted | 0 | 0 | 2018-04-01
THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034433016 — C C RODE NIRMAN(NANDU RAMA KE MAKAN SE SANJU DAGDU RAMDEVPURA 5.10) PALASIYA | Completed | 77000 | 114840 | 2019-01-01 | 2019-10-02
THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034440658 — cc road nirman | Deleted | 0 | 0 | 2018-12-28
THIKRI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034482528 — CC road nirman nathu ke ghar mahesh ke ghar tak | Closed | 54000 | 0 | 2019-04-26
THIKRI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034482530 — Nali nirman kishore ke ghar birju ke ghar tak | Closed | 68000 | 0 | 2019-04-26
THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034531727 — CC road (ramdevpura -)palasiya धनसिंह के मकान से प्रकास के मकान तक | Deleted | 0 | 0 | 2020-06-20
THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034532824 — CC ROAD NIRMAN-DHANSINGH SOMA KE MAKAN SE PRAKASH KASHIRAM KE MAKAN TAK | Completed | 49000 | 64980 | 2020-08-07 | 2021-03-18
THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034539303 — सी.सी.रोड़ निर्माण-अनिल रमेश के बाड़ से नये पंचायत भवरामदेवपुरा पलासिया | Deleted | 0 | 0 | 2020-08-15
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034562238 — सी.सी.रोड़ निर्माण-अनिल रमेश के बाड़े से नये पंचायत भवन तक रामदेवपूरा पलासिया | Completed | 76000 | 78358 | 2021-04-05 | 2021-10-14
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034571545 — CC ROAD NIRMAN-ANIL RAMESH KE GHAR SE MIDLE SCHOOL TAK PART-2 PALASIYA (RAMDEVPURA) | Deleted | 0 | 0 | 2021-04-14
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034571547 — CC ROAD NIRMAN-ANIL RAMESH KE GHAR SE MIDLE SCHOOL TAK PART-2 PALASIYA (RAMDEVPURA) | Completed | 58000 | 55970 | 2021-05-27 | 2021-10-14
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034607427 — CC ROAD NIRMAN-MIDDLE SCHOOL SE MAIN ROAD TAK PART-1 SAJWAY | Completed | 189150 | 188868 | 2022-02-22 | 2023-03-08
THIKRI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034615325 — सी.सी.रोड़ निर्माण कार्य मिडिल स्कूल से नाले तक झोलपिपरी | Completed | 120000 | 103904 | 2022-12-28 | 2023-12-25
THIKRI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034621719 — सी.सी.रोड़ निर्माण कार्य हनुमान मंदिर से पुराने सामुदायिक भवन तक झोलपिपरी | Deleted | 0 | 0 | 2022-08-16
THIKRI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/22012034621721 — सी.सी.रोड़ निर्माण कार्य हनुमान मंदिर से पुराने सामुदायिक भवन तक झोलपिपरी | Deleted | 130000 | 0 | 2022-08-16
THIKRI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1742003038/RC/29 — घाट कटिंग पलासिया 4.56 लाख पलासिया | Completed | 339580 | 326390 | 2008-07-01 | 2010-09-20
THIKRI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003038/RC/311 — जीएसबी मार्ग (फुटला तालाब से ढाकरिया 4.94 लाख) पलासिया | Completed | 494000 | 361958 | 2011-03-01 | 2011-06-19
THIKRI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1742003038/RC/385 — आंतरिक मार्ग (5.00 सातमात्रा से ख्‍वाजा पहाडीतक) प | Completed | 500000 | 126720 | 2012-06-12 | 2012-06-26
THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1742003038/RS/22012034496089 — नवीन सामुदायिक स्वच्छता परिसर पलासिया | Deleted | 43700 | 0 | 2020-09-01
THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1742003038/RS/22012034510764 — samudayik shouchalay nirman hanuman mandir parisar palasiya | Completed | 43700 | 41734 | 2021-03-10 | 2021-06-26
THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1742003038/RS/22012034641107 — सार्वजनिक शौचालय निर्माण- पलासिया | Completed | 43000 | 44268 | 2022-02-11 | 2023-03-08
THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1742003038/SK/9993648592 — Bharat Nirman Rajeev Gandhi Sewa Kendra,PALASIYA | Completed | 1279000 | 1064932.23 | 2016-06-13 | 2021-04-14
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/01 — निस्‍तार तालाब (सजवाय) पलासिया 4.89 | Completed | 488900 | 0 | 2006-04-28 | 2007-01-03
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/02 — रपट निर्माण पलासिया 4.85 | Completed | 445390 | 217600 | 2006-09-05 | 2006-08-15
THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1742003038/WC/05 — निस्‍तार तालाब भाग 2 पलासिया 5.00 लाख | Completed | 500000 | 223224.96 | 2008-05-13 | 2015-05-04
THIKRI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/1 — सीसीटी जलसंवर्धन (झोलपिपरी) पलासिया | Completed | 258266 | 249159 | 2008-01-16 | 2008-09-01
THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/10 — आर एम एस (भाग-1) झोलपीपरी (पलासिया 4.97) | Completed | 493407 | 493403.74 | 2008-05-13 | 2017-09-30
THIKRI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/175 — सीसीटी सैलपर्ण (4.96 जलसंवर्धन) पलासिया | Completed | 496000 | 461733 | 2009-06-30 | 2010-09-25
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/2 — खेत तालाब गुलाब पिदीया (सजवाय) पलासिंया | Completed | 1360 | 0 | 2006-07-25 | 2006-07-30
THIKRI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/22012034319948 — CCT Work Jholpipri Palsiya | Completed | 500000 | 466802 | 2017-02-23 | 2017-06-14
THIKRI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/22012034324837 — Palasiya talab jirdodhar | Deleted | 22000 | 0 | 2017-05-16
THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1742003038/WC/22012034429043 — S CT (SAJVAY)4.13 PALASIYA | Completed | 413000 | 440568 | 2018-12-31 | 2019-07-11
THIKRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1742003038/WC/22012034429045 — SCT ( RAMDEVPURA BEDI 4.13) PALASIYA | Completed | 413000 | 146268 | 2022-07-22 | 2024-04-22
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1742003038/WC/22012034579649 — sct ramdevpura phadhi 2 palasiya | Completed | 483356.81 | 425980 | 2020-10-06 | 2021-03-12
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742003038/WC/22012034616689 — water pond palasiya | Closed | 0 | 0 | 2021-01-26
THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/22012034622356 — Water pond nirman- hanuman mandir ke pass pahadi par palasiya | Completed | 109055.32 | 115559 | 2021-03-14 | 2021-08-08
THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1742003038/WC/22012034653977 — CTR_GIS_gully plug LBCT RAMDEVPURA PHADI PR RAMDEVPURA PHAADI PER | Completed | 55816.2 | 47864 | 2021-06-08 | 2021-10-14
THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742003038/WC/22012034762640 — CTR_GIS Water pond satmatra pahadi par ramdevpura palasia | Completed | 338902.57 | 269428 | 2021-06-24 | 2022-04-14
THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1742003038/WC/22012034762651 — CTR_GIS cct nirman satmatra pahadi par ramdevpura palasia | Completed | 164218.1 | 154014 | 2021-08-10 | 2022-04-14
THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1742003038/WC/22012034762657 — CTR_GIS gully plug satmatra pahadi par ramdevpura palasia | Completed | 174896.12 | 112392 | 2021-07-05 | 2023-07-20
THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742003038/WC/22012034788199 — CTR_GIS_cct work satmatra pahadi par ramdevpura palasiya | Closed | 0 | 0 | 2021-04-14
THIKRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1742003038/WC/22012034955423 — स्टॉपडेम रिनोवेशन कार्य झोलपिपरी पलासिया | Completed | 72426.5 | 71495 | 2022-05-09 | 2024-06-26
THIKRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1742003038/WC/22012034986021 — SCT nirman Ramdev pura pahadi pr part 3 palasiya | Completed | 183893.52 | 158304 | 2022-10-09 | 2024-06-20
THIKRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742003038/WC/22012034986031 — Samudayik water pond pahadi pr palasiya | Closed | 446979.48 | 0 | 2022-04-14
THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742003038/WC/22012035094780 — SCT NIRMAN HANUMAN MANDIR KE PASS PALASIYA PAHADI PAR 4.13 | Completed | 409269 | 356968 | 2023-10-07 | 2025-05-03
THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1742003038/WC/22012035175394 — sct work palasiya | New | 0 | 0 | 2024-01-26
THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/22012035205036 — Sct work hanuman mandir ke samne 2 palasiya | Physically Completed | 354219.57 | 136408 | 2024-07-09 | 2026-06-20
THIKRI | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003038/WC/257 — वाटर पौण्‍ड (4.48) पलासिया | Completed | 448000 | 257982 | 2009-09-29 | 2007-08-15
THIKRI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/265 — स्‍टापडेम निर्माण (4.99 झोलपीपरी) पलासिया | Completed | 499000 | 479446 | 2009-10-15 | 2010-09-29
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/3 — खेत तालाब पुन्‍या मंगल्‍या (सजवाय) पलासिंया | Completed | 1360 | 0 | 2006-07-25 | 2006-07-30
THIKRI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/341 — निस्‍तार तालाब (4.85) पलासिया | Completed | 485000 | 453740 | 2010-03-27 | 2010-11-10
THIKRI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/342 — वाटर पौण्‍ड (4.99 झोल पीपरी) पलासिया | Completed | 499000 | 478140 | 2010-05-18 | 2010-11-14
THIKRI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/343 — स्‍टापडेम (4.99 क्र. 2 ) पलासिया | Completed | 499000 | 412900 | 2010-01-26 | 2010-09-25
THIKRI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/344 — स्‍टापडेम (4.99 क्र. 3) पलासिया | Completed | 499000 | 422000 | 2010-01-26 | 2010-09-13
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/4 — खेत तालाब द्वितीय कालू (सजवाय) पलासिंया | Completed | 1360 | 0 | 2006-07-25 | 2006-07-30
THIKRI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1742003038/WC/459 — परकोलेंशन टैंक(4.81) पलासिया | Completed | 481000 | 402140 | 2010-11-09 | 2011-02-19
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/5 — खेत तालाब सीताराम धना (सजवाय) पलासिंया | Completed | 1360 | 0 | 2006-07-25 | 2006-07-30
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/521 — वाटर पौण्‍ड (4.77 कवाजा पहाडी के पास) पलासिया | Completed | 456000 | 297260 | 2011-05-31 | 2011-06-13
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/522 — वाटर पौण्‍ड (4.77 हनुमान मन्दिर चिकली बैडी) पलासिया | Completed | 456000 | 354730 | 2011-05-31 | 2011-06-13
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/588 — तालाब नवीनीकरण (0.34) पलासिया | Completed | 32000 | 30012 | 2011-06-21 | 2011-08-26
THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/6 — कुप कपिल धारा सीताराम ध्‍ाना (सजवाय) पलासिया | Completed | 65000 | 28560 | 2008-05-13 | 2008-09-01
THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/688 — स्‍टाप डेम नवीनीकरण (0.84 झोलपीपरी) पलासिया | Completed | 84000 | 35640 | 2012-09-18 | 2012-09-23
THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/690 — तालाब नवीनीकरण (0.92 झोलपीपरी) पलासिया | Completed | 92000 | 86064 | 2012-07-17 | 2012-09-09
THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/691 — स्‍टाप डेम नवीनीकरण (0.99 झोलपीपरी) पलासिया | Completed | 99000 | 21384 | 2012-09-11 | 2012-09-16
THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/692 — वाटर पौण्‍ड (4.44 श्‍यामु पटेल के खेत पास) पलासिया | Completed | 444000 | 207900 | 2012-09-11 | 2012-09-26
THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/693 — वाटर पौण्‍ड (4.44 श्‍यामु पटेल के खेत पास) पलासिया | Completed | 498000 | 154440 | 2012-06-19 | 2015-05-04
THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/694 — स्‍टाप डेम नवीनीकरण (0.78 झोलपीपरी) पलासिया | Deleted | 75000 | 0 | 2012-04-10
THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/7 — कुप कपिल धारा छगन कालू (सजवाय) पलासिया | Completed | 65000 | 35288 | 2008-05-13 | 2008-09-01
THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/8 — कुप कपिल धारा फूलसिंग पून्‍या (झोलपीपरी) पलासिया | Completed | 65000 | 63525 | 2008-04-15 | 2008-09-01
THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/9 — तलाई निर्माण (4.48) पलासिया | Completed | 431430 | 310560 | 2008-06-03 | 2008-09-01
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003038/WC/9993623282 — निस्‍तार तलाई (2.00) पलासिया | Completed | 200000 | 185400 | 2011-05-11 | 2015-05-04
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003038/WC/9993623298 — बोल्‍डर वाल (1.50) पलासिया | Completed | 150000 | 144488 | 2011-04-19 | 2017-09-30
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1742003038/WC/9993623441 — संकन पौण्‍ड (1.00) पलासिया | Completed | 100000 | 71300 | 2011-06-15 | 2017-09-30
THIKRI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742003038/WC/9993649427 — cct palasiya 1[2.34] | Completed | 234000 | 128830 | 2014-03-05 | 2016-04-22
THIKRI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742003038/WC/9993649436 — CCT PALASIYA 2[2.60] | Completed | 260000 | 229685 | 2014-03-05 | 2016-01-22
THIKRI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1742003038/WC/9993670765 — सी.सी.टी | Deleted | 0 | 0 | 2016-04-01
THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1742003038/WH/2 — जल संवर्धन सीसीटी पलासिया | Completed | 414962 | 0 | 2006-08-08 | 2008-01-24
THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742/WC/9993623734 — RGM निस्‍तार तलाई (4.57) पलासिया | Completed | 457000 | 422164 | 2011-07-01 | 2011-11-25