## Work List
Exported on: 2026-09-08 00:17:11
Filters applied:
Data source: VBGRAMG
District: BARWANI
Block: All
Panchayat: JULWANIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742004023/IF/22012035270954 — KAPILDHARA KUP NIRMAN KRYA LILABAI DAYRAM | Ongoing | 267533.14 | 0 | 2025-05-25
RAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/205062 — Construction of IAY House -IAY REG. NO. MP-42-004-023-001/733 | Approved | 27000 | 0 | 2016-03-18
RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/4604021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124038268 | Ongoing | 27000 | 0 | 2024-11-04
RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/4833834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145220241 | Ongoing | 27000 | 0 | 2025-01-12
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/4833838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145222894 | Ongoing | 27000 | 0 | 2026-02-13
RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/4854846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124043755 | Ongoing | 27000 | 0 | 2025-02-08
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145219474 | Ongoing | 27000 | 0 | 2025-06-17
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145219563 | Ongoing | 27000 | 0 | 2025-05-01
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145221298 | Ongoing | 27000 | 0 | 2025-05-06
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145221675 | Ongoing | 27000 | 0 | 2025-05-06
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145221794 | Physically Completed | 23490 | 0 | 2025-05-06 | 2026-07-19
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145221878 | Ongoing | 27000 | 0 | 2025-05-11
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145222486 | Ongoing | 27000 | 0 | 2025-05-06
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5112313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145223568 | Ongoing | 27000 | 0 | 2025-05-06
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5113783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124038501 | Ongoing | 27000 | 0 | 2025-06-24
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5113784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124041668 | Physically Completed | 23490 | 3900 | 2025-05-10 | 2026-08-09
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5121081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124039770 | Ongoing | 27000 | 0 | 2025-05-11
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5125045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145223184 | Ongoing | 27000 | 0 | 2025-05-06
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5132153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124035168 | Ongoing | 27000 | 0 | 2025-05-11
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5573851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150266333 | Ongoing | 27000 | 0 | 2025-06-24
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5574530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145221031 | Ongoing | 27000 | 0 | 2025-06-17
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5574886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145222788 | Ongoing | 27000 | 0 | 2025-06-18
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5575596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264842 | Ongoing | 27000 | 8400 | 2025-06-24
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5589245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145333379 | Physically Completed | 23490 | 0 | 2025-07-02 | 2026-07-19
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5589464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124037097 | Ongoing | 27000 | 0 | 2025-07-22
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5589532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124036226 | Physically Completed | 23490 | 0 | 2025-05-12 | 2026-07-12
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5590380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132238503 | Ongoing | 27000 | 0 | 2025-06-24
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5590381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132238675 | Ongoing | 27000 | 0 | 2025-07-08
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5813340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145219272 | Ongoing | 27000 | 0 | 2026-02-26
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5813454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124049754 | Ongoing | 27000 | 0 | 2025-10-12
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5813716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124036064 | Physically Completed | 23490 | 0 | 2026-02-13 | 2026-07-12
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5813798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145333482 | Ongoing | 27000 | 0 | 2026-02-20
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5813846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123522369 | Ongoing | 27000 | 0 | 2026-02-20
RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/5813854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124036733 | Physically Completed | 23490 | 0 | 2026-02-20 | 2026-07-12
RAJPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/6060281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145223291 | Ongoing | 27000 | 0 | 2026-05-13
RAJPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/6060282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145223969 | Ongoing | 27000 | 0 | 2026-05-14
RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/6198317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123038036 | Approved | 27000 | 0 | 2025-02-27
RAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/76811 — Construction of IAY House -IAY REG. NO. MP-42-004-023-001/407 | Approved | 27000 | 0 | 2016-01-01
RAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/76824 — Construction of IAY House -IAY REG. NO. MP-42-004-023-001/103 | Approved | 27000 | 0 | 2016-01-01
RAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004023/IF/IAY/79709 — Construction of IAY House -IAY REG. NO. MP-42-004-023-001/467 | Approved | 27000 | 0 | 2016-01-05
RAJPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004023/RC/22012034578775 — Pipe culwert Nirman Dargah k Piche Nale Pr | Physically Completed | 921477.9 | 0 | 2021-12-03 | 2026-07-13
RAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004023/RC/22012034822956 — Cc Road Nirman Karya police thane k pas se bhaya sursing k ghar ki or | Approved | 47000 | 0 | 2024-06-11
RAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004023/RC/22012034823046 — Cc Road Nirman Karya Heera K Makan Se Irshad K Makan K Pass Tk | Physically Completed | 41000 | 0 | 2025-03-04 | 2026-07-13
RAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004023/RC/22012034823051 — Cc Road Nirman Karya Juwansing k Ghar Se Chunnilal K Ghar Tk286 | Approved | 46000 | 0 | 2024-06-11
RAJPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1742004023/WC/22012035142698 — Nalla nirman kary (5.31) puliya se purna nala tak julwaniya | Ongoing | 425000 | 0 | 2023-10-07