## Work List
Exported on: 2026-09-09 22:38:03
Filters applied:
Data source: VBGRAMG
District: BARWANI
Block: All
Panchayat: BORLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NEWALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742006005/IF/22012035079484 — Kapildhara kup nirman borli pandya arya | Ongoing | 235656.75 | 0 | 2023-10-07
NEWALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742006005/IF/22012035079486 — Kapildhara kup nirman borli gopal arya | Ongoing | 235656.75 | 70991 | 2023-10-07
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742006005/IF/22012035252395 — पशु शेड निर्माण संजय आर्य बोरली | Ongoing | 129285.24 | 0 | 2024-11-08
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006005/IF/22012035546456 — JGSA खेत तालाब निर्माण लताबाई रामदास सेकेडमोहली बोरली | New | 0 | 0 | 2025-05-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006005/IF/22012035567177 — JGSA खेत तालाब निर्माण मोतिरम कनोजे सेकेडमोहली बोरली | New | 0 | 0 | 2025-06-10
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006005/IF/22012035569199 — JGSA खेत तालाब निर्माण कुवरसिंघ गुलाब सेकेडमोहली बोरली | New | 0 | 0 | 2025-06-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006005/IF/22012035569203 — JGSA खेत तालाब निर्माण मोतिरम रामा सेकेडमोहली बोरली | Ongoing | 67356.02 | 0 | 2025-10-14
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/205383 — Construction of IAY House -IAY REG. NO. MP-42-006-005-002/50 | Ongoing | 27000 | 0 | 2024-08-30
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/4825361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122790468 | Physically Completed | 23490 | 0 | 2024-11-15 | 2026-07-24
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/4826629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125818154 | Ongoing | 27000 | 0 | 2024-12-01
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/4888756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122244852 | Ongoing | 27000 | 0 | 2025-03-13
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5490910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122792490 | Ongoing | 27000 | 0 | 2025-04-28
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5492372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121995823 | Physically Completed | 27000 | 0 | 2025-05-15 | 2026-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5494292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125710319 | Ongoing | 27000 | 0 | 2025-05-15
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5653146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125540029 | Ongoing | 27000 | 0 | 2025-11-27
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5653385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126046371 | Physically Completed | 23490 | 0 | 2025-08-21 | 2026-07-19
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5654102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118860622 | Ongoing | 27000 | 900 | 2025-06-09
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5654104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118864129 | Physically Completed | 27000 | 2420 | 2025-08-21 | 2026-09-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5654105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118865407 | Ongoing | 27000 | 1200 | 2025-06-09
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5655533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122266218 | Ongoing | 27000 | 900 | 2025-06-09
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5655607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117390713 | Completed | 23490 | 0 | 2025-06-09 | 2026-07-29
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5655620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120807974 | Ongoing | 27000 | 0 | 2025-06-25
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5655744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122755413 | Physically Completed | 27000 | 0 | 2025-06-09 | 2026-09-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5691502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123241410 | Ongoing | 27000 | 1200 | 2025-09-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5691506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122244330 | Physically Completed | 23490 | 0 | 2025-09-03 | 2026-07-24
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5691593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123240620 | Ongoing | 27000 | 0 | 2025-08-21
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5715958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117010675 | Physically Completed | 23490 | 0 | 2025-08-02 | 2026-07-24
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5715960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117010780 | Physically Completed | 23490 | 0 | 2025-08-21 | 2026-07-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5716023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118865869 | Completed | 23490 | 0 | 2025-08-02 | 2026-07-24
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5716291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125314149 | Physically Completed | 23490 | 0 | 2025-08-29 | 2026-07-24
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5721775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125697898 | Ongoing | 27000 | 6300 | 2026-05-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5724139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117390716 | Physically Completed | 23490 | 0 | 2025-09-25 | 2026-08-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5734298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125712966 | Physically Completed | 23490 | 0 | 2025-09-03 | 2026-07-19
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5734299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125854186 | Ongoing | 27000 | 0 | 2026-04-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5734355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117010775 | Physically Completed | 23490 | 0 | 2025-09-03 | 2026-07-26
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5734382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125694151 | Physically Completed | 27000 | 0 | 2025-09-02 | 2026-09-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5817671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127108901 | Ongoing | 27000 | 3750 | 2025-12-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5817769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118862594 | Ongoing | 27000 | 0 | 2025-09-27
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5817833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117390787 | Ongoing | 27000 | 1700 | 2026-05-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5817892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122245580 | Physically Completed | 27000 | 0 | 2025-09-27 | 2026-09-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5817919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122266681 | Physically Completed | 23490 | 0 | 2025-09-27 | 2026-07-19
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5818130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126129611 | Ongoing | 27000 | 4200 | 2025-12-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5818141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117010698 | Physically Completed | 27000 | 150 | 2025-10-06 | 2026-09-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5818181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126130033 | Ongoing | 27000 | 3150 | 2025-10-06
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5818501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125818846 | Physically Completed | 27000 | 0 | 2026-03-06 | 2026-09-02
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5859831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120808052 | Physically Completed | 23490 | 0 | 2026-03-18 | 2026-07-12
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5873303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127075326 | Ongoing | 27000 | 2100 | 2026-04-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5873310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125731747 | Physically Completed | 27000 | 0 | 2026-03-06 | 2026-09-02
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5873312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122758088 | Physically Completed | 27000 | 1050 | 2026-04-11 | 2026-09-02
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5873361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127058001 | Ongoing | 27000 | 5550 | 2026-05-09
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/5873364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128025181 | Ongoing | 27000 | 2100 | 2026-04-12
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/6082696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122755977 | Ongoing | 27000 | 6300 | 2026-05-13
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006005/IF/IAY/6086634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125715119 | Ongoing | 27000 | 6300 | 2026-05-11
NEWALI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742006005/WC/22012034600663 — सामुदायिक खेत तालाब बोरली | Ongoing | 109055.32 | 600 | 2021-01-27