## Work List
Exported on: 2026-09-06 11:12:12
Filters applied:
Data source: VBGRAMG
District: BARWANI
Block: All
Panchayat: KANPURI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NEWALI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1742006019/DP/22012034587337 — वसुधा वंदन - अमृत वाटिका (75) मानव केंद्र आश्रम कानपुरी | Ongoing | 55847.4 | 0 | 2023-08-28
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742006019/IF/22012034449525 — कपिल धारा कुप निर्माण जगन रूपचंद कानपुरी | Ongoing | 200000 | 0 | 2024-04-18
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742006019/IF/22012034584483 — पशु शेड निर्माण शाबाबाई वैचाण कानपुरी | Ongoing | 101273.16 | 0 | 2024-04-30
NEWALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742006019/IF/22012034719172 — कपिल धारा कूप निर्माण लक्ष्मण सरदार वरल्यापानी | Ongoing | 247839.67 | 0 | 2022-04-15
NEWALI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006019/IF/22012034781432 — खेत तालाब निर्माण रामेश्वर डेगरिया वरल्यपानी | Ongoing | 111248.93 | 0 | 2022-03-05
NEWALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006019/IF/22012034939524 — Kapildhara kup Nirman Jagdish D/O Rupchand | Ongoing | 250732.62 | 0 | 2022-06-21
NEWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742006019/IF/22012035409996 — JGSA 2025 Recharge Structure Kapil dhara kup jagan rupchand kanpuri | New | 0 | 0 | 2025-04-14
NEWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742006019/IF/22012035410253 — JGSA 2025 Recharge Structure Kapil dhara kup shantiram banshi kanpuri | New | 0 | 0 | 2025-04-14
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742006019/IF/22012035491198 — JGSA Khet talab nirman Sardar bhangya warlyapani kanpuri | New | 0 | 0 | 2025-04-14
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035589194 — Ek Bagiya maa ke naam Ekari bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Bio-gas plant for individual | Bio-gas plant | 1742006019/IF/22012035591584 — Biogas Nirman Munni Bai ke ghar ke pass Kanpuri | Approved | 0 | 0 | 2025-06-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592232 — Ek Bagiya Maa ke name MUNNI BAI MP-42-006-019-003/313 KANPURI | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592236 — Ek Bagiya Maa ke name MUNNI BAI MP-42-006-019-003/313 KANPURI | Ongoing | 264307.49 | 0 | 2025-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592251 — Ek Bagiya Maa ke name JHAMI BAI MP-42-006-019-003/49 KANPURI | Ongoing | 263510.03 | 0 | 2025-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592269 — Ek Bagiya Maa ke name REKHA BAI MP-42-006-019-003/199 KANPURI | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592284 — Ek Bagiya Maa ke name BATIBAI MP-42-006-019-003/731 KANPURI | Ongoing | 263510.03 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592291 — Ek Bagiya Maa ke name LAKDI BAI MP-42-006-019-003/193 KANPURI | Ongoing | 263510.03 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035592302 — Ek Bagiya Maa ke name RESHMA BAI MP-42-006-019-003/260 KANPURI | Ongoing | 263510.03 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593293 — Ek Bagiya maa ke naam Jhami bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593315 — Ek Bagiya maa ke naam Lakdi bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593321 — Ek Bagiya maa ke naam jhami bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593326 — Ek Bagiya maa ke naam Reshma bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593332 — Ek Bagiya maa ke naam Mangli bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593337 — Ek Bagiya maa ke naam Mangla bai kanpuri | Ongoing | 263510.03 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593367 — Ek Bagiya maa ke naam Sugariya bai kanpuri | Ongoing | 263510.03 | 0 | 2025-09-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593373 — Ek Bagiya maa ke naam Jila bai kanpuri | Ongoing | 263510.03 | 0 | 2025-09-28
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593386 — Ek Bagiya maa ke naam Chevanti bai kanpuri | New | 0 | 0 | 2025-08-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593389 — Ek Bagiya maa ke naam Chevati bai kanpuri | Ongoing | 263510.03 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035593392 — Ek Bagiya maa ke naam vepari bai kanpuri | Ongoing | 263510.03 | 0 | 2025-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035603232 — Ek Bagiya Maa Ke Naam Rekha Bai Kanpuri | New | 0 | 0 | 2025-08-27
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035603496 — Ek Bagiya Maa Ke Naam Rekhabai Kanpuri | Ongoing | 263510.03 | 0 | 2025-10-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607640 — Ek Bagiya Ma Ke Naam Rekha Bai Kanpuri | New | 0 | 0 | 2025-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607649 — Ek Bagiya Ma Ke Naam Reshma Bai Kanpuri | New | 0 | 0 | 2025-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607659 — Ek Bagiya Ma Ke Naam Rekha Bai Kanpuri | New | 0 | 0 | 2025-08-30
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607867 — Ek Bagiya Maa Ke Naam Bhagadibai Warlyapani | Ongoing | 270536.27 | 0 | 2025-09-28
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607876 — Ek Bagiya Ma Ke Naam Rekha Bai Kanpuri | Approved | 263510.03 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607884 — Ek Bagiya Ma Ke Naam Reshma Bai Kanpuri | New | 0 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607911 — Ek Bagiya Ma Ke Naam Gurli Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035607918 — Ek Bagiya Ma Ke Naam Siyani Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035608451 — Ek Bagiya Ma Ke Naam Duhriya Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035608461 — Ek Bagiya Ma Ke Naam Ikari Bai Kanpuri | New | 0 | 0 | 2025-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035608493 — Ek Bagiya Ma Ke Naam Ikari Bai Khote Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035610772 — Ek Bagiya Ma Ke Naam Sawi Bai Khote Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035610778 — Ek Bagiya Ma Ke Naam Sangeeta Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035610786 — Ek Bagiya Ma Ke Naam Sawatri Bai Kanpuri | New | 0 | 0 | 2025-09-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035610796 — Ek Bagiya Ma Ke Naam Sargli Bai Kanpuri | New | 0 | 0 | 2025-09-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035612069 — Ek Bagiya Ma Ke Naam Sawatri Bai Kanpuri | New | 0 | 0 | 2025-09-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035612138 — Ek Bagiya Ma Ke Naam Sawatri Bai Kanpuri | New | 0 | 0 | 2025-09-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035612860 — Ek Bagiya Ma Ke Naam Sawatri Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035612870 — Ek Bagiya Ma Ke Naam Sargli Bai Kanpuri | Approved | 0 | 0 | 2025-09-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035612878 — Ek Bagiya Ma Ke Naam Mamanta Bai Kanpuri | New | 0 | 0 | 2025-09-04
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035613284 — Ek Bagiya Ma Ke Naam Shardabai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035613371 — Ek Bagiya Ma Ke Naam Durga Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035613411 — Ek Bagiya Ma Ke Naam Kusma Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-13
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035613429 — Ek Bagiya Ma Ke Naam Jam Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035613444 — Ek Bagiya Ma Ke Naam Gita Bai Solanki Walryapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035613453 — Ek Bagiya Ma Ke Naam Imala Bai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035614979 — Ek Bagiya Ma Ke Naam Saba Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-13
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035614987 — Ek Bagiya Ma Ke Naam Imala Bai Warlyapani Kanpuri | New | 0 | 0 | 2025-09-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035617401 — Ek Bagiya Maa Ke Naam Munni Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-20
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035617411 — Ek Bagiya Maa Ke Naam Sunita Bai Kanpuri | New | 0 | 0 | 2025-09-09
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035617412 — Ek Bagiya Maa Ke Naam Sunita Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-13
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035618623 — Ek Bagiya Maa Ke Naam Sarita Bai Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-13
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035618627 — Ek Bagiya Maa Ke Naam Banu Bai Arya Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-13
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035619670 — Ek Bagiya Ma Ke Naam Anjali Bai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-16
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035619672 — Ek Bagiya Ma Ke Naam Rasa Bai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-16
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035619674 — Ek Bagiya Ma Ke Naam Nanu Bai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-15
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035619677 — Ek Bagiya Ma Ke Naam Rehndi Bai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-16
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035621131 — Ek Bagiya Ma Ke Naam Milubai Bai Warlyapani Kanpuri | Ongoing | 263510.03 | 0 | 2025-09-20
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035628224 — Ek Bagiya Maa Ke Naam Mamta Bai Kanpuri | New | 0 | 0 | 2025-10-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035628225 — Ek Bagiya Maa Ke Naam Ajma Bai Kanpuri | Ongoing | 174149.14 | 0 | 2025-10-05
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035628226 — Ek Bagiya Maa Ke Naam Chivati Bai Kanpuri | New | 0 | 0 | 2025-10-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742006019/IF/22012035628227 — Ek Bagiya Maa Ke Naam Mevadi Bai Kanpuri | New | 0 | 0 | 2025-10-03
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4719163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133899260 | Physically Completed | 27000 | 0 | 2024-10-14 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4821377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755169 | Physically Completed | 27000 | 0 | 2024-11-20 | 2026-08-31
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4821383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757367 | Ongoing | 27000 | 0 | 2026-04-23
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4822400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757408 | Physically Completed | 27000 | 0 | 2024-12-02 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4823392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121654378 | Physically Completed | 27000 | 0 | 2024-12-02 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4824081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122678602 | Ongoing | 27000 | 0 | 2024-12-14
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4824082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122679811 | Physically Completed | 27000 | 0 | 2024-12-14 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4824087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122685871 | Physically Completed | 27000 | 0 | 2025-02-19 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4831628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133898719 | Physically Completed | 27000 | 0 | 2024-12-14 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/4867384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133893816 | Physically Completed | 27000 | 0 | 2025-02-19 | 2026-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5554124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116330972 | Physically Completed | 27000 | 0 | 2025-05-17 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5557343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125353405 | Approved | 27000 | 0 | 2025-03-08
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5558158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755447 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5558161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755889 | Physically Completed | 27000 | 0 | 2025-05-16 | 2026-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5558346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133898814 | Physically Completed | 23490 | 0 | 2026-01-03 | 2026-07-26
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5561870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122660468 | Physically Completed | 23490 | 0 | 2025-08-20 | 2026-07-12
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5562945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133894469 | Approved | 27000 | 0 | 2025-03-17
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5563509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122686804 | Physically Completed | 27000 | 0 | 2025-05-16 | 2026-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5563820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117754820 | Ongoing | 27000 | 0 | 2025-08-20
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5564266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117756314 | Physically Completed | 23490 | 0 | 2025-08-20 | 2026-07-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5564267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117756507 | Ongoing | 27000 | 0 | 2025-08-20
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5564511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133900243 | Physically Completed | 23490 | 0 | 2026-02-21 | 2026-07-26
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5565437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122601296 | Ongoing | 27000 | 0 | 2025-08-20
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5565438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122603237 | Ongoing | 27000 | 0 | 2025-08-20
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5565447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122677713 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5671008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122601080 | Ongoing | 27000 | 0 | 2026-03-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5671303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122660378 | Physically Completed | 23490 | 0 | 2025-08-20 | 2026-07-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5691970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122557782 | Ongoing | 27000 | 0 | 2025-08-20
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5692053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125351441 | Physically Completed | 23490 | 0 | 2026-03-11 | 2026-07-26
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5707146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133901420 | Ongoing | 27000 | 0 | 2025-12-19
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5707209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122679047 | Ongoing | 27000 | 0 | 2025-08-21
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5707538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133895793 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5707956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133899168 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757424 | Ongoing | 27000 | 0 | 2026-04-10
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757493 | Approved | 27000 | 0 | 2025-03-07
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114156618 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755159 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125321709 | Physically Completed | 23490 | 0 | 2026-03-11 | 2026-07-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133898909 | Physically Completed | 27000 | 0 | 2026-01-03 | 2026-08-31
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122668582 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122668698 | Ongoing | 27000 | 0 | 2026-04-10
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125518417 | Ongoing | 27000 | 0 | 2026-04-23
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117756578 | Ongoing | 27000 | 0 | 2026-04-10
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125316996 | Ongoing | 27000 | 0 | 2026-04-10
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133899629 | Ongoing | 27000 | 0 | 2026-01-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133899869 | Ongoing | 27000 | 0 | 2026-01-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133901342 | Physically Completed | 27000 | 0 | 2025-12-19 | 2026-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133902146 | Ongoing | 27000 | 0 | 2025-12-19
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133902229 | Physically Completed | 27000 | 0 | 2025-12-19 | 2026-08-31
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113485480 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122600256 | Approved | 27000 | 0 | 2024-10-07
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122680344 | Physically Completed | 23490 | 0 | 2026-03-11 | 2026-07-26
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122679653 | Ongoing | 27000 | 0 | 2026-04-10
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117754946 | Ongoing | 27000 | 0 | 2026-04-10
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755479 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755495 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117756946 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757137 | Physically Completed | 23490 | 0 | 2025-03-01 | 2026-07-26
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123793700 | Ongoing | 27000 | 0 | 2026-04-23
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133828783 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133894540 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133895105 | Ongoing | 27000 | 0 | 2026-03-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106101406 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106101560 | Ongoing | 27000 | 0 | 2026-04-23
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116329818 | Physically Completed | 23490 | 0 | 2025-03-08 | 2026-07-12
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122688927 | Ongoing | 27000 | 0 | 2026-03-12
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125319607 | Approved | 27000 | 0 | 2025-03-01
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5846352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125350425 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117754760 | Approved | 27000 | 0 | 2025-03-24
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133897037 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122680507 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115124068 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122666710 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122681361 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755107 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122005497 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5866459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133897772 | Ongoing | 27000 | 0 | 2026-04-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/5883080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122670370 | Ongoing | 27000 | 0 | 2026-03-11
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6076512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117756371 | Approved | 27000 | 0 | 2026-01-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6076513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117756400 | Approved | 27000 | 0 | 2026-01-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6076515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757768 | Approved | 27000 | 0 | 2026-02-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6076516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757823 | Approved | 27000 | 0 | 2026-02-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6082523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122671670 | Approved | 27000 | 0 | 2026-01-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6082524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122673601 | Approved | 27000 | 0 | 2026-01-25
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6082542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122689222 | Approved | 27000 | 0 | 2026-01-03
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6088419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126614817 | Approved | 27000 | 0 | 2026-01-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6091328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128521277 | Approved | 27000 | 0 | 2026-01-23
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6185317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117755829 | Approved | 27000 | 0 | 2026-02-09
NEWALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742006019/IF/IAY/6195300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757868 | Approved | 27000 | 0 | 2026-02-28
NEWALI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1742006019/LD/22012034533546 — गौचर भूमि निर्माण कानपुरी | Ongoing | 792213.45 | 0 | 2021-01-18
NEWALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742006019/WC/22012034985301 — Samudayek khat talab Nirman Makna ke khat ke pass warliyapani | Ongoing | 356340.1 | 0 | 2024-08-08
NEWALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742006019/WC/22012035136770 — सी.सी.टी.एवं एस.सी.टी. निर्माण वरल्यपानी | Ongoing | 237751.5 | 0 | 2024-04-08
NEWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1742006019/WC/22012035140022 — Stop dam nirman school falya kanpuri | Ongoing | 939842.51 | 0 | 2026-03-16
NEWALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1742006019/WC/22012035202930 — STOP DAM NIRMAN Ramlal ke khet ke pass Kanpuri | New | 0 | 0 | 2024-06-10
NEWALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742006019/WC/22012035319334 — Samudayek khet Talab kanpuri School Faliya | Approved | 30000 | 0 | 2025-06-04