## Work List
Exported on: 2026-09-14 10:59:00
Filters applied:
Data source: VBGRAMG
District: BARWANI
Block: All
Panchayat: MENDLYAPANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SENDHAWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007007/IF/IAY/202422 — Construction of IAY House -IAY REG. NO. MP-42-007-007-001/30 | Approved | 27000 | 0 | 2016-03-11
SENDHAWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007007/IF/IAY/202423 — Construction of IAY House -IAY REG. NO. MP-42-007-007-001/34 | Approved | 27000 | 0 | 2016-03-11
SENDHAWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007007/IF/IAY/205471 — Construction of IAY House -IAY REG. NO. MP-42-007-007-001/123 | Approved | 27000 | 0 | 2016-03-11
SENDHAWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012034559557 — कपिलधारा कूप निर्माण ( 2.00 कलरसिंग गुटिया ) मेंदल्यापानी | Ongoing | 246126.86 | 0 | 2021-03-10
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035220704 — कपिल धारा कूप निर्माण ( रमेश माया ) मेंदल्यापानी | Ongoing | 232656.75 | 0 | 2024-04-21
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035220855 — कपिल धारा कूप निर्माण ( चिनका राणा ) मेंदल्यापानी | Ongoing | 232656.75 | 0 | 2024-04-21
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035220859 — कपिल धारा कूप निर्माण ( दुर्गाबाई चिंदा ) मेंदल्यापानी | Ongoing | 232656.75 | 0 | 2024-04-21
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Bio-gas plant for individual | Bio-gas plant | 1742007093/IF/22012035250835 — वृक्षा रोपण कार्य ( गुच्छा नहारसिंह ) ग्राम मेंदल्यापानी | Approved | 0 | 0 | 2024-07-10
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Bio-gas plant for individual | Bio-gas plant | 1742007093/IF/22012035250838 — वृक्षा रोपण कार्य ( अकलसिंह रायसिंह ) ग्राम मेंदल्यापानी | Approved | 0 | 0 | 2024-07-10
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1742007093/IF/22012035254450 — वृक्षा रोपण कार्य ( अकलसिंह रायसिंह ) ग्राम मेंदल्यापानी | Ongoing | 173308.58 | 0 | 2025-04-01
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1742007093/IF/22012035254451 — वृक्षा रोपण कार्य ( गुच्छा नहारसिंह ) ग्राम मेंदल्यापानी | Ongoing | 206200.49 | 0 | 2025-04-01
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1742007093/IF/22012035254452 — वृक्षा रोपण कार्य ( चिन्दा ढेमा ) ग्राम मेंदल्यापानी | Ongoing | 173308.58 | 0 | 2025-08-19
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742007093/IF/22012035330044 — Khet talab | New | 0 | 0 | 2025-04-10
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035330286 — कपिल धारा कूप (भीका जमसिंग) | New | 0 | 0 | 2025-04-10
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035330288 — कपिल धारा कूप (भीका जमसिंग) | New | 0 | 0 | 2025-04-10
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742007093/IF/22012035332291 — KHET TALAB /BHAGWAN MANGU | New | 0 | 0 | 2025-04-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742007093/IF/22012035332639 — खेत तालाब (भगवान मंगू) | Approved | 347409.68 | 0 | 2025-04-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035332751 — कपिल धारा कूप (रावजी जंगलसिंग) | Approved | 0 | 0 | 2025-04-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035333788 — खेत तालाब (नरमसिंह गोपाल ) | New | 0 | 0 | 2025-04-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035333814 — खेत तालाब (नरमसिंह गोपाल ) | Approved | 0 | 0 | 2025-04-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035357101 — कपिल धारा कूप (भीका जमसिंग) | Ongoing | 267533.14 | 0 | 2025-05-21
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035357184 — कपिल धारा कूप (रावजी जंगलसिंग) | Ongoing | 267533.14 | 0 | 2025-05-21
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035360260 — कपिल धारा कूप (नरमसिह गोपाल) | Approved | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742007093/IF/22012035377525 — रिचार्ज गड्ढा (रेमसिंग जमसिंह) | Approved | 25899.46 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1742007093/IF/22012035379210 — रिचार्ज गड्ढा (रमेश भार सिंह) | Approved | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742007093/IF/22012035379332 — रिचार्ज गड्ढा (सुभाष रूमसिंग) | New | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742007093/IF/22012035379380 — रिचार्ज गड्ढा (शांताराम फूलसिंग) | New | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742007093/IF/22012035379484 — रिचार्ज गड्ढा (गुच्छा जमरा) | Approved | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742007093/IF/22012035379655 — रिचार्ज गड्ढा (कालिया पावा) | New | 0 | 0 | 2025-04-14
SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035397472 — कपिल धारा कूप (मना रायसिंग) | Ongoing | 267533.14 | 0 | 2026-06-03
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035477540 — कपिल धारा कूप (भीका जमसिंग) | New | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035477841 — कपिल धारा कूप (भीका जमसिंग) | New | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035477847 — कपिल धारा कूप (भीका जमसिंग) | New | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035480461 — KAPILDHRA KUP bhika jamsing | Approved | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/22012035480548 — Kapildhara kup Mana Raysing | Approved | 0 | 0 | 2025-04-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035590088 — EK BAGIYA MAA KE NAAM Gani bai Jai Shri samuh mendliyapani | Ongoing | 283754.05 | 0 | 2025-09-13
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035590281 — EK BAGIYA MAA KE NAAM Baka bai shivshankar samuh mendliyapani | Ongoing | 283754.05 | 0 | 2025-09-17
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035591059 — EK BAGIYA MAA KE NAAM Jhingali bai Vir Khaja Naik samuh mendliyapani | Ongoing | 283754.05 | 0 | 2025-09-26
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035596670 — EK BAGIYA MAA KE NAAM Usha bai Santoshi samuh mendliyapani | New | 0 | 0 | 2025-08-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035596671 — EK BAGIYA MAA KE NAAM Usha bai Santoshi samuh mendliyapani | New | 0 | 0 | 2025-08-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035596733 — EK BAGIYA MAA KE NAAM Usha bai Durga mahila kisan SHG samuh mendliyapani | Approved | 283754.05 | 0 | 2025-08-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035596768 — EK BAGIYA MAA KE NAAM Runa Bai Jai Shri samuh mendliyapani | Ongoing | 283754.05 | 0 | 2025-09-17
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035597459 — EK BAGIYA MAA KE NAAM Subi bai santishi samuh mendliyapani | Approved | 283754.05 | 0 | 2025-08-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035598870 — EK BAGIYA MAA KE NAAM SARBAI SHG VIR KHAJYA NAIK SAMUH MENDLIYAPANI | New | 0 | 0 | 2025-08-22
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035598875 — EK BAGIYA MAA KE NAAM SARBAI SHG VIR KHAJYA NAIK SAMUH MENDLIYAPANI | Ongoing | 283754.05 | 0 | 2025-09-13
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035598882 — EK BAGIYA MAA KE NAAM NANLI BAI SHG VIR KHAJYA NAIK SAMUH MENDLIYAPANI | Approved | 0 | 0 | 2025-08-22
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035602923 — EK BAGIYA MAA KE NAAM Nanli Bai Vir Khajya Naik samuh mendliyapani | Approved | 283754.05 | 0 | 2025-08-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035602990 — EK BAGIYA MAA KE NAAM Ira bai Jai shri samuh mendliyapani | Ongoing | 283754.05 | 0 | 2025-09-13
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035620636 — EK BAGIYA MAA KE NAAM sukli bai Sheetal SHG samuh mendliyapani | New | 0 | 0 | 2025-09-13
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007093/IF/22012035620639 — EK BAGIYA MAA KE NAAM Sukli bai Sheetal SHG samuh mendliyapani | Ongoing | 283754.05 | 0 | 2025-09-21
SENDHAWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742007093/IF/9993708708 — Kapildhara kup nirman(2.02 Hama Dhema)Mendlyapani | Ongoing | 202000 | 0 | 2016-01-30
SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/3757398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120265430 | Approved | 27000 | 0 | 2022-04-27
SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4263764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119959575 | Ongoing | 27000 | 0 | 2022-09-23
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4576174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118426544 | Ongoing | 27000 | 0 | 2025-08-27
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4584660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120014957 | Ongoing | 27000 | 0 | 2025-03-28
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4585688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119673382 | Physically Completed | 27000 | 0 | 2025-03-28 | 2026-09-09
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4595056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121732957 | Ongoing | 27000 | 0 | 2025-03-28
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4595704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122406034 | Physically Completed | 27000 | 0 | 2025-04-01 | 2026-09-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4595776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122416111 | Physically Completed | 27000 | 0 | 2025-04-01 | 2026-09-09
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4595787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122417291 | Physically Completed | 27000 | 0 | 2025-03-28 | 2026-09-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4595953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122119915 | Ongoing | 27000 | 0 | 2025-04-01
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4595964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122121495 | Ongoing | 27000 | 0 | 2025-04-01
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4596238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121975346 | Ongoing | 27000 | 0 | 2025-03-28
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4601398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123904806 | Physically Completed | 27000 | 0 | 2025-03-28 | 2026-09-09
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4619034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125841765 | Physically Completed | 27000 | 0 | 2025-03-28 | 2026-09-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4822451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118426521 | Ongoing | 27000 | 0 | 2025-05-14
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/4889034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124168570 | Physically Completed | 27000 | 0 | 2025-04-01 | 2026-09-11
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5112827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123886888 | Ongoing | 27000 | 0 | 2025-09-19
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5114223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103549691 | Physically Completed | 27000 | 0 | 2025-09-19 | 2026-09-11
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5117471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122402004 | Ongoing | 27000 | 0 | 2025-09-19
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5119335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103546144 | Ongoing | 27000 | 0 | 2025-09-19
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5123146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103549450 | Physically Completed | 23490 | 0 | 2025-07-17 | 2026-08-16
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5129999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122405745 | Ongoing | 27000 | 0 | 2025-07-17
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5130423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121732442 | Physically Completed | 23490 | 0 | 2025-09-19 | 2026-07-12
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5130442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122118879 | Ongoing | 27000 | 0 | 2025-09-19
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5131305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122179099 | Physically Completed | 23490 | 0 | 2025-09-19 | 2026-08-09
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5131374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123884000 | Physically Completed | 23490 | 0 | 2025-09-12 | 2026-08-16
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5133224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122793012 | Ongoing | 27000 | 0 | 2025-10-11
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5508580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126442948 | Approved | 27000 | 0 | 2025-03-04
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5509124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126070790 | Physically Completed | 27000 | 0 | 2025-09-19 | 2026-09-11
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5511152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103551131 | Approved | 27000 | 0 | 2025-03-04
SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5511153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103552944 | Physically Completed | 27000 | 0 | 2025-11-09 | 2026-08-30
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5511224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124752311 | Approved | 27000 | 0 | 2025-03-04
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5849019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122412133 | Physically Completed | 23490 | 0 | 2025-02-19 | 2026-08-09
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5849139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123809926 | Approved | 27000 | 0 | 2025-02-18
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5849326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103546426 | Approved | 27000 | 0 | 2025-02-18
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5849383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124152868 | Physically Completed | 23490 | 0 | 2025-03-04 | 2026-08-16
SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742007093/IF/IAY/5997303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122415105 | Approved | 27000 | 0 | 2025-02-19
SENDHAWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1742007093/RS/22012034544939 — सामुदायिक शोक पिट ( पटेल फल्या,जमरा फल्या,नवाड फल्या,रावताल्या फल्या,निंगवाल फल्या ) मेंदल्यापानी | Ongoing | 91916.92 | 0 | 2021-08-24
SENDHAWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1742007093/WC/22012034891370 — REPAIRE OF STOP DAM BHURLA HARDAS KE KHET KE PAS MENDLYAPANI | Ongoing | 90634.79 | 0 | 2022-05-26