## Work List
Exported on: 2026-09-09 22:40:25
Filters applied:
Data source: VBGRAMG
District: KATNI
Block: All
Panchayat: NIMKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAHORIBAND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1744005048/AV/22012034400788 — aganwadi bhawan nirman karya purane panchayat bhawan me | Ongoing | 180000 | 0 | 2019-02-21
BAHORIBAND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1744005048/FR/22012034323207 — samudayak khet talab nirman sehighur ke pass neemkheda | New | 0 | 0 | 2024-04-01
BAHORIBAND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1744005048/FR/22012034323208 — samudayak khet talab nirman sahu ke pass neemkheda | New | 0 | 0 | 2024-04-01
BAHORIBAND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1744005048/FR/22012034323209 — samudayak khet talab nirman salhai ki bhatiya ke pass neemkheda | New | 0 | 0 | 2024-04-01
BAHORIBAND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744005048/IF/22012035298556 — कपिलधारा कूप निर्माण कार्य महेद्र/गिरानी रजक | Approved | 0 | 0 | 2024-10-02
BAHORIBAND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1744005048/IF/22012035516597 — Dugwell recharga for individual Ummed/Bisram Rajak | Approved | 0 | 0 | 2025-04-14
BAHORIBAND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Wasteland Block Plantation of Horticulture Trees for Individuals | Plantation | 1744005048/IF/22012035601073 — EA BAGIYA MAA KE NAAM SUNITA GADARI | Ongoing | 278974.26 | 0 | 2025-09-10
BAHORIBAND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744005048/IF/22012035640720 — Ek Bagiya Maa Ke Naam GAYTRI BAI LUHAR | Ongoing | 270537.6 | 0 | 2025-11-08
BAHORIBAND | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744005048/IF/22012035640898 — Pashu Shed Nirman Kary Radha Bai / Kishan Lal Vishkarma | Ongoing | 75735.14 | 4590 | 2026-04-02
BAHORIBAND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744005048/IF/22012035644010 — Ek Bagiya Maa Ke Naam Anita Bai Sahu | Ongoing | 158009.92 | 0 | 2025-11-22
BAHORIBAND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744005048/IF/22012035644014 — Ek Bagiya Maa Ke Naam Suhadra Bai | Ongoing | 158290.57 | 0 | 2025-11-22
BAHORIBAND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744005048/IF/IAY/3061777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2802812 | Ongoing | 27000 | 0 | 2021-04-17
BAHORIBAND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744005048/IF/IAY/4612034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125508045 | Ongoing | 27000 | 0 | 2024-09-28
BAHORIBAND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744005048/IF/IAY/858121 — Construction of IAY House -IAY REG. NO. MP1589460 | Approved | 27000 | 0 | 2020-07-14
BAHORIBAND | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005048/WC/22012035205757 — Contour Trench Nirman Kary Lamhari ki Bhatiya khasra no 1145 me | Ongoing | 1006307.67 | 0 | 2024-08-14
BAHORIBAND | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005048/WC/22012035218751 — Contour Trench Nirman Kary Sehidhur Ki Bhatiya Khasara No 1084 | Approved | 0 | 0 | 2024-04-01
BAHORIBAND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744005048/WC/22012035304924 — Dugwell recharga pit nahar ke pass | New | 0 | 0 | 2025-04-14
BAHORIBAND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744005048/WC/22012035305448 — Dugwell recharga madhaymik school ke pass | Approved | 25899.46 | 0 | 2025-04-14
BAHORIBAND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744005048/WC/22012035305449 — Dugwell recharga koshilya barman ke ghar ke pass | Approved | 25899.46 | 0 | 2025-04-14
BAHORIBAND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1744005048/WC/22012035328636 — Kantoor trench nirman khasra no 1220 | Ongoing | 1242811.47 | 33750 | 2026-03-08
BAHORIBAND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1744005048/WC/VB/22012035329559 — kantoor trench neemkheda bara wali bhatiya par bhag 2 | Ongoing | 199534.49 | 165120 | 2026-08-04
BAHORIBAND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005048/WC/VB/22012035329855 — kantor trench nirman karay Muktidham ke pass khsra no 346 me | Ongoing | 199534.49 | 0 | 2026-09-01
BAHORIBAND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005048/WC/VB/22012035330032 — कंटूर ट्रेंच निर्माण कार्य खसरा न 1220 पार्ट 3 नीमखेडा | Approved | 199534.49 | 0 | 2026-07-01
BAHORIBAND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005048/WC/VB/22012035330034 — कंटूर ट्रेंच निर्माण कार्य सेहिधुर की भटिया पार्ट 4 में | Ongoing | 199534.49 | 91750 | 2026-08-05
BAHORIBAND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005048/WC/VB/22012035330039 — कंटूर ट्रेंच निर्माण कार्य खसरा न.1145में पार्ट 2 | Ongoing | 199534.49 | 0 | 2026-09-02