## Work List
Exported on: 2026-10-25 00:46:54
Filters applied:
Data source: VBGRAMG
District: KATNI
Block: All
Panchayat: PALI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHIMERKHEDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1744006011/AV/22012034653504 — सामुदायिक भवन निर्माण कार्य - पाली | Physically Completed | 200000 | 0 | 2024-03-17 | 2026-08-20
DHIMERKHEDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen Shed for Government School for Community | Constr of Kitchen Shed | 1744006011/AV/22012034655866 — किचिन शेड निर्माण कार्य मारसिहुडी | Ongoing | 387000 | 0 | 2024-03-16
DHIMERKHEDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1744006011/DP/22012034580269 — VRUKSHAROPAN NIRMAN KARY-PANI TANKI KE PASS AVM HANUMAN MANDIR KE PASS GRAM PALI | Ongoing | 756333.55 | 0 | 2023-07-16
DHIMERKHEDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1744006011/DP/22012034628376 — कंटूर तेंच निर्माण कार्य साथिया के पास ग्राम मारसिहुडी | Approved | 70000 | 0 | 2024-08-18
DHIMERKHEDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1744006011/DP/22012034628377 — कंटूर तेंच निर्माण कार्य साथिया के पास ग्राम मारसिहुडी | Approved | 0 | 0 | 2024-08-18
DHIMERKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of Major Distributary Canal for Community | Construction of Canal | 1744006011/IC/22012034892896 — CPT Nirman Kary talab ke pass pali | Approved | 1197390.21 | 0 | 2025-10-02
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744006011/IF/22012035644041 — ek bagiya ma ke naam anita bai jharpani | New | 0 | 0 | 2025-08-01
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744006011/IF/22012035644055 — ek bagiya ma ke naam anita bai jharpani | Ongoing | 164101.38 | 7001.12 | 2026-02-18
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744006011/IF/22012035645776 — Ek Bagiya Maa Ke Naam ranu bai mehra pali | New | 0 | 0 | 2025-08-01
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744006011/IF/22012035645779 — Ek Bagiya Maa Ke Naam ranu bai mehra pali | Ongoing | 164793.52 | 14101.6 | 2025-12-07
DHIMERKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/4651672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146111353 | Ongoing | 27000 | 0 | 2024-10-15
DHIMERKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/4662090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148313419 | Completed | 27000 | 7830 | 2024-10-15 | 2026-10-23
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5648388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151603286 | Ongoing | 27000 | 0 | 2025-09-22
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145364381 | Ongoing | 27000 | 0 | 2025-10-05
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121702282 | Completed | 27000 | 7830 | 2025-10-05 | 2026-09-11
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146398226 | Ongoing | 27000 | 0 | 2025-10-05
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146466246 | Ongoing | 27000 | 7830 | 2025-09-11
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146466277 | Ongoing | 27000 | 7830 | 2025-09-11
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146485580 | Ongoing | 27000 | 7830 | 2025-08-04
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5649976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146896918 | Ongoing | 27000 | 3654 | 2025-08-04
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5650241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145259629 | Ongoing | 27000 | 7830 | 2025-07-20
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5650242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151454035 | Ongoing | 27000 | 7830 | 2025-10-05
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5651752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143442027 | Completed | 27000 | 16830 | 2025-07-05 | 2026-10-23
DHIMERKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/5651753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143442066 | Completed | 27000 | 16830 | 2025-07-05 | 2026-10-23
DHIMERKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744006011/IF/IAY/6097818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146857872 | Ongoing | 27000 | 0 | 2026-05-14
DHIMERKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744006011/WC/22012035317873 — कंटूर टेंच निर्माण कार्य साथिया भाटिया के पास साथिया भाटिया के पास मारसिहुडी | Approved | 85000 | 0 | 2025-04-11
DHIMERKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744006011/WC/22012035317874 — कंटूर टेंच निर्माण कार्य साथिया भाटिया के पास साथिया भाटिया के पास मारसिहुडी | Deleted | 1400000 | 0 | 2025-04-11
DHIMERKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1744006011/WC/22012035325559 — SCT Nirman Kary talab ke pass gram pali | Approved | 1108999.69 | 0 | 2025-12-26
DHIMERKHEDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744006011/WC/VB/22012035331274 — कन्टूर टेंच निर्माण कार्य - सिद्ध वाली भाटिया में पाली | Ongoing | 198979.28 | 160480 | 2026-09-20
DHIMERKHEDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744006011/WC/VB/22012035331278 — कन्टूर टेंच निर्माण कार्य - तालाब के ऊपर वाली भाटिया में पाली | Ongoing | 198979.28 | 170811.52 | 2026-08-07
DHIMERKHEDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744006011/WC/VB/22012035331280 — कन्टूर टेंच निर्माण कार्य - बिलोहा भाटिया में ग्राम झारपानी | Ongoing | 198979.28 | 99661.67 | 2026-08-07