## Work List
Exported on: 2026-09-14 22:44:59
Filters applied:
Data source: MGNREGA + VBGRAMG
District: KATNI
Block: All
Panchayat: All
Status: Suspended
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RITHI / RITHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001001/IF/22012034347462 — व़क्षारांपण कार्य मुक्तिधाम परसिर | Suspended | 335000 | 21692 | 2017-06-06
RITHI / RITHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001001/IF/22012034353415 — राजीव गांधी महाविद्वालय एवं रा0अ0 लोधी0 हा0से0 स्‍कूल परिसर रीठी | Suspended | 535000 | 16400 | 2017-06-20
RITHI / RITHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001001/IF/22012034365535 — वक्षा रोपण कार्य पुलिस थाना परिसर रीठी | Suspended | 335000 | 18336 | 2017-07-15
RITHI / RITHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1744001001/WC/22012034445079 — NAWEEN TALAB NIRMAN KARYA VRACHHAROPAN KE BAJU MAI RITHI | Suspended | 1296000 | 100 | 2019-03-06
RITHI / DHANIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1744001003/AV/22012034467195 — GOUSHALA NIRMAN KARYA GHANIYA | Suspended | 2762000 | 0 | 2019-08-24
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034343895 — वक्षारोपण कार्य रोड के दाेनो तरफ घनियां पहुंच मार्ग में | Suspended | 335000 | 25228 | 2017-06-07
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034343898 — वक्षारोपण कार्य मुक्तिधाम परिसर ग्राम धनिया में | Suspended | 335000 | 7050 | 2017-06-07
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034343899 — वक्षारोपण कार्य मुक्तिधाम परिसर कैथाटोला | Suspended | 335000 | 16408 | 2017-06-07
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034343902 — वक्षारोपण कार्य मुक्तिधाम परिसर ग्राम कछारखेडा में | Suspended | 335000 | 15092 | 2017-06-07
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034344078 — वक्षारोपण कार्य परिसर कैथाटोला | Suspended | 535000 | 14850 | 2017-06-07
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034344087 — व़क्षारोपण कार्य मॉडल स्‍कूल रोड बायपास के दोनो तरफ | Suspended | 335000 | 20190 | 2017-06-07
RITHI / DHANIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001003/IF/22012034344097 — व़क्षारोपण कार्य ईजीएस परिसर अहिरगवां में | Suspended | 335000 | 16350 | 2017-06-07
RITHI / MOHAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744001004/RC/22012034449595 — सी सी रोड सह नाली निर्माण कार्य (खेर माता से गोतम के घर तक) | Suspended | 66000 | 900 | 2019-03-09
RITHI / PATEHARA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744001005/RS/22012034407175 — manrega toilet work barelal/ dashrath | Suspended | 12000 | 11440 | 2018-04-09
RITHI / BHARTPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001009/IF/22012034343137 — व़क्षारोपण कार्य भरतपुर से बडगांव मार्ग में | Suspended | 335000 | 19330 | 2017-06-03
RITHI / BHARTPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001009/IF/22012034343140 — व़क्षारोपण कार्य मा0 शाला परिसर में | Suspended | 335000 | 15130 | 2017-06-03
RITHI / RUDMUD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001010/IF/22012034345647 — व़क्षारांपण कार्य मुक्तिधाम के पास | Suspended | 335000 | 26886 | 2017-06-03
RITHI / DEWGOW | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744001011/RS/22012034313100 — टूटे फूटे शौचालय निर्माण कार्य देवगांव 10 हितग्राही तक0 283 दिनांक 06/12/2016 | Suspended | 98000 | 58800 | 2016-12-15
RITHI / DEWGOW | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744001011/RS/22012034338105 — INDIVISUAL TOILET NIRMAN KARYA 256 DATE 06/11/2016 | Suspended | 98000 | 19600 | 2017-04-24
RITHI / HARDUA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001016/IF/22012034343208 — व़क्षारोपण कार्य सामुदायिक परिसर शा0 हाई स्‍कूल | Suspended | 535000 | 26284 | 2017-06-05
RITHI / HARDUA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001016/IF/22012034343218 — व़क्षारोपण कार्य शा0 हायर सेकेण्‍डरी स्‍कूल परिसर खिरवा टोला | Suspended | 535000 | 35356 | 2017-06-05
RITHI / BADGAW | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1744001017/AV/22012034467274 — gaoshala nirman kary badgaw | Suspended | 2762000 | 0 | 2019-08-24
RITHI / PATOHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001019/IF/22012034330540 — कपिलधारा कूप निर्माण कार्य पूजा बाई / चरण सिंह | Suspended | 204000 | 8250 | 2017-04-01
RITHI / PATOHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001019/IF/22012034343186 — व़क्षारोपण कार्य बरहा से लेकर नयाटोला तलैया तक | Suspended | 335000 | 26582 | 2017-05-27
RITHI / JAMUNIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1744001020/AV/22012034371560 — मुक्तिधाम निर्माण कार्य मढ़ा देवरी | Suspended | 180000 | 660 | 2018-08-10
RITHI / SEEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001021/IF/22012034330919 — कपिलधारा कूप निर्माण कार्य राममिलन / सिपाही भुमिया | Suspended | 204000 | 80 | 2017-04-06
RITHI / SEEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001021/IF/22012034344130 — व़क्षारोपण कार्य मढिया से सैदा मार्ग के दोनो तरफ | Suspended | 335000 | 30620 | 2017-06-29
RITHI / SEEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001021/IF/22012034344137 — व़क्षारोपण कार्य SAIDA KI BHATIYA WRAKSHAROPAN KARY MUNDHI BHATIYA ME | Suspended | 335000 | 29060 | 2017-06-22
RITHI / GODANA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1744001025/WC/22012034447110 — parkulasan tank nirman karya (chourahai ke pass) | Suspended | 683000 | 900 | 2019-03-10
RITHI / KHMRIYA-1 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001028/IF/22012034330504 — कपिलधारा कूप निर्माण कार्य रामकुमार / अनंता | Suspended | 204000 | 160 | 2017-04-01
RITHI / KHMRIYA-1 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001028/IF/22012034330508 — कपिलधारा कूप निर्माण कार्य रामविशाल /मरजदी | Suspended | 204000 | 160 | 2017-04-01
RITHI / KHMRIYA-1 | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001028/IF/22012034343204 — व़क्षारोपण कार्य सडक किनारे शिव घाट से पीपटी घाट तक | Suspended | 335000 | 18450 | 2017-05-31
RITHI / BARGI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001034/IF/22012034339403 — कपिलधारा कूप निर्माण कार्य कन्‍हैया / डरूवा | Suspended | 200000 | 50 | 2017-06-08
RITHI / BARGI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001034/IF/22012034339410 — कपिलधारा कूप निर्माण कार्य बारो बाई / सुकरतिया | Suspended | 200000 | 150 | 2017-06-08
RITHI / GURAGIKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001036/IF/22012034330569 — कपिलधारा कूप निर्माण कार्य कमलाप्रसाद / मोतीलाल | Suspended | 200000 | 64060 | 2017-04-03
RITHI / LALPURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001037/DP/22012034240355 — नवीन सामुदायिक परिसर में वृक्षारोपण - प्राथमिक शाला परिसर | Suspended | 335000 | 20419 | 2017-05-10
RITHI / LALPURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744001037/DP/2444 — punah sthapana rf-139 lalpura | Suspended | 37000 | 45271 | 2010-02-20
RITHI / LALPURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744001037/DP/2448 — pun sthapana kary RDF RF 141 | Suspended | 0 | 1200 | 2010-02-23
RITHI / BAKLEHATA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744001038/RS/22012034381648 — tute phute sochalay krya bakhleta 1 | Suspended | 98000 | 0 | 2018-07-10
RITHI / UMARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001041/IF/22012034346749 — व़क्षारांपण कार्य रेल्‍वे फाटक से कुपिया मार्ग में | Suspended | 335000 | 29758 | 2017-06-15
RITHI / KUMRWARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744001042/IF/22012034496907 — RFR_KATNI RIVER_KHET TALAB BHOLA MAESHA | Suspended | 39327.06 | 100 | 2020-05-05
RITHI / KUMRWARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744001042/IF/22012034497175 — RFR_KATNI RIVER_KHET TALAB RAJENDRA SINGH | Suspended | 0 | 0 | 2021-09-08
RITHI / SIMARAKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001044/IF/22012034330809 — कपिलधारा कूप निर्माण कार्य राजाराम / सेवा | Suspended | 204000 | 100 | 2017-04-25
RITHI / SIMARAKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744001044/IF/22012034330913 — कपिलधारा कूप निर्माण कार्य इन्‍द्रपाल सिंह / महिपाल सिंह | Suspended | 200000 | 600 | 2017-10-25
RITHI / SIMARAKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001044/IF/22012034343715 — व़क्षारोपण कार्य खम्‍हरिया से इमलिया मार्ग में | Suspended | 335000 | 38140 | 2017-06-06
RITHI / SIMARAKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001044/IF/22012034344153 — व़क्षारोपण कार्य मुक्तिधाम परिसर ग्राम इमलिया | Suspended | 335000 | 35140 | 2017-05-30
RITHI / SIMARAKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001044/IF/22012034344155 — व़क्षारोपण कार्य बद्वी ीी जमुन के पास भटिया तक | Suspended | 335000 | 33424 | 2017-05-30
RITHI / SIMARAKALA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1744001044/IF/22012034347465 — व़क्षारांपण कार्य मुक्तिधाम परसिर | Suspended | 335000 | 32631 | 2017-06-05
RITHI / BADGAW-1 | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1744001048/RC/22012034306782 — सी सी रोड एवं नाली निर्माण कार्य | Suspended | 42375 | 400 | 2019-03-08
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588752 — pashu shed nirman karya rohini prasad/ gaya prasad | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1744002001/IF/22012034588755 — Goat shed nirman karya sheetal / babulal | Suspended | 46636.05 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588756 — Pashu shed nirman karya ramvishal/sukh lal | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1744002001/IF/22012034588758 — Goat shed nirman karya veeran / jhutta | Suspended | 46636.05 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1744002001/IF/22012034588759 — goat shed nirman karya kisan lal piprodh | Suspended | 46636.05 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588760 — pashu shed nirman karya ram milan / dayali | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588764 — pashu shed nirman karya mahesh /sewa lal | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588765 — pashu shed nirman kmarya lallu / dhanu | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588767 — padhu shed nirman karya chunnu/ kalicharan | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588768 — pashu shed nirman karya kailash / badri prasad | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / PIPRODH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002001/IF/22012034588773 — pashu shed nirman karya nimma kushwaha piprodh | Suspended | 101273.16 | 0 | 2020-09-03
KATNI / LAKHAPATERI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002002/IF/22012034587397 — Bakri shed Nirmanya Mohan lal /summa Adiwasi | Suspended | 0 | 0 | 2020-07-28
KATNI / BADA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1744002003/RS/22012034590392 — SLWM -SOAKPIT NIRMAN KARYA AANGANWADI KE PASS | Suspended | 1200 | 0 | 2021-10-15
KATNI / BADA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1744002003/RS/22012034590402 — SLWM -SOAKPIT NIRMAN KARYA PDS KE PASS | Suspended | 1200 | 0 | 2021-10-15
KATNI / JARWAHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1744002005/DP/22012034491147 — वृक्षा रोपण कार्य मुक्तिधाम में | Suspended | 563986.66 | 0 | 2021-05-15
KATNI / DEWRITOLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1744002007/IF/22012034546637 — med bandhan kary (rohini choubey) | Suspended | 33809.45 | 0 | 2021-05-05
KATNI / DEWRITOLA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1744002007/RS/22012034480415 — Nadef | Suspended | 0 | 0 | 2020-05-02
KATNI / DEWRITOLA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1744002007/WH/22012034390308 — narsari talab jirnodhar | Suspended | 0 | 0 | 2020-05-02
KATNI / GULWARA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744002010/RC/22012034390704 — C C ROAD AVAM NALI NIRMAN HORIDAI SE MIDDLE SCHOOL TAK | Suspended | 111000 | 0 | 2020-12-11
KATNI / GULWARA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1744002010/RS/22012034480178 — Nadep nirman kary asmani mata ke pass ward no 4 | Suspended | 0 | 0 | 2021-11-18
KATNI / GULWARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1744002010/WC/22012034470551 — RFR शोक पिट सोहन के घर पास | Suspended | 15000.33 | 0 | 2021-11-18
KATNI / GULWARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002010/WC/22012034485814 — RFR Ward no 4 me Vishali sahu ke ghar pass | Suspended | 0 | 0 | 2021-11-18
KATNI / GULWARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002010/WC/22012034485817 — RFR Sok Pit Sallu Viswkarma ke ghar ke pas | Suspended | 0 | 0 | 2021-11-17
KATNI / GULWARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002010/WC/22012034485821 — RFR Sok Pit Deshraj ke ghar pas | Suspended | 0 | 0 | 2021-11-18
KATNI / BICHUWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1744002018/WH/22012034390426 — Talab renovation karya | Suspended | 0 | 0 | 2020-12-31
KATNI / PADRIYA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1744002029/AV/22012034572489 — SLWM-SEGREGATION SHED-PADARIYA | Suspended | 1916000 | 0 | 2021-09-10
KATNI / PADRIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744002029/IF/22012034496791 — RFR-FARM POND-MUKESH /BASANTA KOL KE KHET ME | Suspended | 331656.11 | 3840 | 2020-05-05
KATNI / PADRIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1744002029/IF/22012034821029 — SLWM-KITCHEN GAURDEN-DUKHILAL CHAUDHRY EVAM ANYA 10 HITGRAHI | Suspended | 20002.72 | 0 | 2021-07-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485114 — RFR - सोकपटि निर्माण श्‍मसान घाट के पास | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485622 — RFR-SOKPIT NIRMAD KARYA KHER MAI MANDIR KE PASS HAND PUMP ME | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485625 — RFR-SOKPIT AWAS MOHALLA MEN ANGANBADI KE PASS HAND PUMP ME | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485628 — RFR-SOKPIT GRMA PANCHAYAT KE PASS HAND PUMP ME | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485630 — RFR-SOKPIT-RAJJU GADARI KE GHAR KE PASS HAND PUMP ME | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485632 — RFR- SOKPIT- HANDPUMP ME SHUKLAJI KE GHAR KE PASS | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485633 — RFR-SOKPIT-HANDPUMP ME-KAILASHIYA GADARI KE GHAR KE PASS | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485634 — RFR-SOKPIT-HANDPUMP ME-SHIKSHA GAURANTEE SCHOOL KE PASS | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485635 — RFR-SOKPIT-HANDPUMP ME-PRIMARY SCHOOL KE PASS | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485636 — RFR-SOKPIT-HANDPUMP ME- MITHAILAL CHAUDHARY KE GHAR KE PASS | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485637 — RFR-SOKPIT-HANDPUMP ME-PANI KI TANKI KE PASS | Suspended | 15062.64 | 0 | 2021-04-12
KATNI / PADRIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1744002029/WC/22012034485638 — RFR-SOKPIT-HANDPUMP ME- GANESH MANDIR KE PASS | Suspended | 15009.04 | 0 | 2021-04-12
KATNI / JUHALI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744002031/RC/22012034554297 — c c road avam nali nirmaan munnilal chaudhary ke ghar se tekchand chaudhary ke ghar tak | Suspended | 21510 | 0 | 2021-10-02
KATNI / MATWARPADARIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002047/IF/22012034585300 — cattal sade rajkumari/asharam | Suspended | 101273.16 | 310 | 2020-07-24
KATNI / KHMTRA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1744002048/IF/22012034546463 — ,,KALLU/DEVIPRASAD MED BANDHAN | Suspended | 0 | 0 | 2020-07-21
KATNI / KHMTRA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1744002048/IF/22012034565413 — RAMKHILAVAN/SEWALAL MED BANDHAN | Suspended | 38139.67 | 0 | 2020-07-21
KATNI / KACHARGOW JOWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1744002050/IF/22012034564510 — med badhan-kamlesh patel | Suspended | 0 | 0 | 2021-04-12
KATNI / BISTRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744002053/IF/22012034585848 — पशु शेड सरला बाई बिस्तरा | Suspended | 101273.16 | 6460 | 2020-08-09
BADWARA / BUJBUJA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1744003033/WC/22012034379519 — खेत तालाब निर्माण कार्य बुजबुजा ग्राम गढौैहा | Suspended | 380000 | 0 | 2018-06-08
BADWARA / SAKARIGADH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1744003064/WC/22012034379743 — खेत तालाब 144 निर्माण करुआकाप | Suspended | 368018.81 | 0 | 2018-07-31
BADWARA / SAKARIGADH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744003064/WC/22012034381314 — लूज बोल्डर चेक निर्माण खसरा क्रमांक 39/B करुआकाप | Suspended | 42900 | 0 | 2018-07-31
BADWARA / SAKARIGADH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744003064/WC/22012034381316 — लूज बोल्डर चेक निर्माण खसरा क्रमांक154/A करुआकाप | Suspended | 34320 | 0 | 2018-07-31
BADWARA / SAKARIGADH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744003064/WC/22012034381318 — लूज बोल्डर चेक निर्माण खसरा क्रमांक154/B करुआकाप | Suspended | 38610 | 0 | 2018-07-31
BADWARA / SAKARIGADH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744003064/WC/22012034381332 — लूज बोल्डर चेक निर्माण खसरा क्रमांक162/A करुआकाप | Suspended | 34320 | 0 | 2018-07-31
BADWARA / SAKARIGADH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Loose Boulder Structure / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744003064/WC/22012034381336 — लूज बोल्डर चेक निर्माण खसरा क्रमांक 39/A करुआकाप | Suspended | 34320 | 0 | 2018-07-31
BADWARA / SAKARIGADH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1744003064/WC/22012034381338 — खेत तालाब निर्माण करुआकाप 164 | Suspended | 368019 | 0 | 2018-07-31
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1744004001/DP/22012034524654 — medbadhan nirmad karya achhelal barman | Suspended | 40001.45 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004001/IF/22012034406394 — KAPILDHARA KOOP MORMAN VIDYA BAI RAMKUMAR | Suspended | 200000 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004001/IF/22012034406395 — KAPIL DHARA KOOP NIRMAN SHEKH RAJJABH | Suspended | 200000 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1744004001/IF/22012034511005 — RFR KATNI REVER MED BANDHAN MADHAV BARMAN | Suspended | 40620.55 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1744004001/IF/22012034511275 — RFR KATNI REVER MED BANDHAAN LAAL MUHAMMAD | Suspended | 50028.28 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1744004001/IF/22012034555952 — MED BADHAN SUNDAR LAL BURMAN | Suspended | 38863.04 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1744004001/IF/22012034556002 — medbadhan kary Rameswar prasad | Suspended | 37683.64 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1744004001/IF/22012034556047 — medbandhan kary sharad yadav | Suspended | 37683.64 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1744004001/IF/22012034605502 — नंदनफलोद्यान रामविशाल यादव के खेत में | Suspended | 118000 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MOHASH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1744004001/IF/22012034668630 — medbadhan nirmad karya parshotam yadav/jagesur | Suspended | 40001.45 | 0 | 2021-05-30
VIJAYRAGHAVGADH / MUDEHARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744004002/WC/22012034447608 — RFR-katni River-कंटूर ट्रेंच निर्माण बंशीलाल के खेत के उपर-मुडेहरा | Suspended | 218000 | 20250 | 2019-03-09
VIJAYRAGHAVGADH / MUDEHARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744004002/WC/22012034447613 — RFR-katni River-कंटूर ट्रेंच निर्माण राकस खोल मेन रोड के जंगल में-मुडेहरा | Suspended | 218000 | 200 | 2019-03-09
VIJAYRAGHAVGADH / KANTI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004004/IF/22012034386394 — kapildhara kup nirman athaiya/dhanuva | Suspended | 230000 | 0 | 2018-01-01
VIJAYRAGHAVGADH / KANTI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004004/IF/22012034386398 — kapildhara kup nirman chandrabhan/sipahi | Suspended | 230000 | 0 | 2018-01-01
VIJAYRAGHAVGADH / SURMA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1744004021/RS/22012034489891 — samudayeek swakchaata Parisar Bus Stand ke pass Surma | Suspended | 50000 | 0 | 2020-08-13
VIJAYRAGHAVGADH / DEWRIKALA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1744004025/RS/22012034489888 — samudayeek swakachhata parisar Kanya Salal Bazar haat Ke pass | Suspended | 100000 | 0 | 2020-06-01
VIJAYRAGHAVGADH / ROHARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004030/IF/22012034330703 — khet talav sah koop nirman deenbandhu lodhi rohaniya | Suspended | 230000 | 196238 | 2017-04-04
VIJAYRAGHAVGADH / ROHARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004030/IF/22012034330725 — kapildhara koop nirman kishan singh rathor / bhandhari | Suspended | 100000 | 75456 | 2018-02-06
VIJAYRAGHAVGADH / SINGODI | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1744004037/AV/22012034573688 — SLWM कचरा से‍ग्रीगेशन शेड निर्माण सिनगौडी | Suspended | 1916000 | 0 | 2021-10-04
VIJAYRAGHAVGADH / SINGODI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744004037/LD/22012034569825 — MA KI BAGIYA GPS SINGOUDI | Suspended | 6200 | 0 | 2021-09-13
VIJAYRAGHAVGADH / CHORI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744004058/RC/22012034462955 — CC ROAD NIRAMN SHUKHADEO KEWAT KE GHAR SE FULIYA KE GHAR TAK | Suspended | 57375 | 0 | 2019-06-08
VIJAYRAGHAVGADH / CHORI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744004058/RC/22012034462968 — CC ROAD NIRAMN RAJJU KE GHAR SE GREBAL ROAD TAK | Suspended | 95625 | 0 | 2019-06-08
VIJAYRAGHAVGADH / GOHWAL | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1744004059/AV/22012034391905 — anganbadi work 2 | Suspended | 180000 | 0 | 2020-10-27
VIJAYRAGHAVGADH / GOHWAL | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1744004059/RS/22012034491514 — सामुदायिक स्वच्छता परिसर ,नयी बस्ती , गोहावल | Suspended | 50000 | 0 | 2020-10-27
VIJAYRAGHAVGADH / DIDHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1744004060/IF/22012034668103 — medbadhan sahkhanti kisanlal/ jhalla kewat | Suspended | 42629.05 | 3480 | 2021-04-26
VIJAYRAGHAVGADH / DIDHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1744004060/IF/22012034668112 — medbadhan sahkhanti harkesh/deenbandhu kewat | Suspended | 41362.48 | 2045 | 2021-05-01
VIJAYRAGHAVGADH / KUNDREHE | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1744004063/IF/22012034556173 — med bandhan surypal singh | Suspended | 56218.64 | 0 | 2021-11-02
VIJAYRAGHAVGADH / KUNDREHE | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1744004063/IF/22012034585301 — NRLM Balari shed Maya Bai | Suspended | 46636.05 | 290 | 2020-08-14
VIJAYRAGHAVGADH / KUNDREHE | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1744004063/IF/22012034585304 — NRLM Bakari Shed Suraj Deen | Suspended | 46636.05 | 0 | 2021-11-11
VIJAYRAGHAVGADH / KUNDREHE | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744004063/IF/22012034596721 — NRLM pasu sed nirman ramkali kol/babulal kol | Suspended | 63531.21 | 290 | 2020-08-14
VIJAYRAGHAVGADH / KUNDREHE | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744004063/IF/22012034596725 — Pasu sed nirman dulari bai kol | Suspended | 63531.21 | 0 | 2021-11-11
VIJAYRAGHAVGADH / DOKARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1744004064/AV/22012034541132 — boundary wall niriman prathamik shala | Suspended | 88000 | 380 | 2020-10-23
VIJAYRAGHAVGADH / DOKARIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1744004064/IF/22012034622330 — BARMI COMPOST PIT NIRMAN HEMRAJ MISHRA | Suspended | 15051.87 | 0 | 2021-09-13
VIJAYRAGHAVGADH / DOKARIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1744004064/IF/22012034622341 — VARMI COMPOST PIT NIRMAN VINAY LOHAR | Suspended | 15045.32 | 0 | 2021-09-13
VIJAYRAGHAVGADH / DOKARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744004064/RC/22012034541081 — cc road nirman kelas ke ghar se | Suspended | 70000 | 208 | 2020-11-12
VIJAYRAGHAVGADH / ETORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004067/IF/22012034473593 — KAPIL DHARA KOOP NIRMAN DASRATH/BALAPRASAD | Suspended | 200000 | 0 | 2020-01-17
VIJAYRAGHAVGADH / KUTESHWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744004068/LD/22012034508908 — MEDBADHAN NARESH SAHU | Suspended | 50063.66 | 0 | 2021-04-21
BAHORIBAND / SIHUDI BAKAL | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1744005006/AV/22012034391094 — Aaganwadi Bhavan Nirman Karya Sihundi 2 | Suspended | 180000 | 135996 | 2019-03-07
BAHORIBAND / KIVLARHA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1744005007/AV/22012034373456 — Khad godam nirman karya kivlarha | Suspended | 964000 | 1044 | 2018-10-06
BAHORIBAND / MAJHGWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Rpair & maint of brick/stone Kharanja Roads - Comm / Repair and maintenance of Kharanja (brick/stone) Roads for Community | Repair & Maint of Community infrastructure | 1744005013/AV/22012034587557 — बाउन्‍डीबाल निर्माण कार्य आगनवाडी भवन ग्राम पंचायत मझगंवा | Suspended | 51000 | 0 | 2021-08-15
BAHORIBAND / MAJHGWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744005013/IF/22012034395174 — Kapil dhara koop nirman karya -Leela bai/ Heera lal | Suspended | 200000 | 660 | 2018-02-05
BAHORIBAND / MAJHGWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744005013/RC/22012034579808 — सी सी रोड नाली निर्माण कार्य शा0प्रा0 शाला परिसर ग्राम पंचायत मझगंवा | Suspended | 680000 | 0 | 2021-08-17
BAHORIBAND / PATIRAJA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744005016/IF/22012034399135 — koop nirman kary laxmi lodhi | Suspended | 200000 | 3695 | 2018-03-06
BAHORIBAND / PATIRAJA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744005016/IF/22012034480949 — khet talab sah koop nirman shri ram / battilal | Suspended | 230000 | 35280 | 2019-06-24
BAHORIBAND / BASHAN | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1744005018/IF/22012034417285 — worksha ropan kary endra singh sukhchain | Suspended | 188000 | 55202 | 2018-06-24
BAHORIBAND / AMADI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744005019/IF/22012034624786 — Pashu shaid Nirman karya Rajbhan/Bhagurath amadi | Suspended | 0 | 0 | 2021-01-18
BAHORIBAND / AMADI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1744005019/IF/22012034625572 — Pashu shaid Nirman karya Janka/Doulat yadav amadi | Suspended | 0 | 0 | 2021-01-18
BAHORIBAND / SUPELI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744005023/IF/22012034483232 — KhetTalab Nirman Dhaniram/Pooran | Suspended | 123129.28 | 0 | 2021-01-01
BAHORIBAND / SUPELI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744005023/IF/22012034567358 — Med badhan karya kadam/pusau | Suspended | 0 | 0 | 2021-01-01
BAHORIBAND / SUPELI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744005023/LD/22012034543729 — Med bandhan ompratap/dharamdas | Suspended | 53131.99 | 0 | 2021-01-22
BAHORIBAND / SUPELI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1744005023/WC/22012034487343 — SOKPIT NIRMAN KARYA NANNHUSINGH KE GHAR PASS | Suspended | 27783.14 | 0 | 2021-01-01
BAHORIBAND / SUPELI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1744005023/WC/22012034487344 — SOKPIT NIRMAN KRYA KHER MATA NAL KE HANDPUMP PASS | Suspended | 26525.49 | 0 | 2021-01-01
BAHORIBAND / SUPELI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1744005023/WC/22012034487348 — SOKPIT NIRMAN KARYA DIPCHAND KI BARI ME | Suspended | 26706.25 | 0 | 2021-01-01
BAHORIBAND / TIGWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1744005027/AV/22012034514374 — बाउंड्रीवाल निर्माण कार्य माध्यमिक शाला परिसर तिगवा | Suspended | 48000 | 4160 | 2020-08-06
BAHORIBAND / TIGWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744005027/IF/9993720988 — koop nirman kary jagat /babulal | Suspended | 200000 | 240 | 2019-03-10
BAHORIBAND / TIGWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744005027/RC/22012034466919 — cc road nirman | Suspended | 0 | 0 | 2019-11-08
BAHORIBAND / AMGAWA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1744005028/WC/22012034504957 — nveen talab patharkhadiya amgwa | Suspended | 1155731.35 | 64910 | 2020-03-06
BAHORIBAND / PATHRADI(PIP) | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1744005029/DP/22012034433419 — braksharopan kary khasra n. 8 plat path pipriya | Suspended | 544000 | 0 | 2021-11-20
BAHORIBAND / PATHRADI(PIP) | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005029/DP/22012034433533 — brakshharopan kary kha.n.8/3 pipariya | Suspended | 544000 | 0 | 2021-11-20
BAHORIBAND / PATHRADI(PIP) | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005029/DP/22012034433537 — brakshhropan kary kha.n.8/5pipariya | Suspended | 544000 | 0 | 2021-11-20
BAHORIBAND / PATHRADI(PIP) | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005029/DP/22012034433538 — brakshharopan kary kha.n.8/6pipariya | Suspended | 544000 | 0 | 2021-11-20
BAHORIBAND / PATHRADI(PIP) | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005029/DP/22012034433539 — brakshharopan kha. n. 8/6 pipariya | Suspended | 544000 | 0 | 2021-11-20
BAHORIBAND / PATHRADI(PIP) | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1744005029/IF/22012034472949 — Khet Talab Nirman Karya Ramprasad /Mayaram | Suspended | 91000 | 200 | 2019-03-10
BAHORIBAND / PATHRADI(PIP) | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1744005029/IF/22012034565625 — Medh bandhan karya ramshay fulchand | Suspended | 51107.92 | 0 | 2021-11-20
BAHORIBAND / JUJHARI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1744005031/IF/22012034351171 — खेत तालाब एवं कूप निर्माण कार्य भूरा यादव ग्राम पं0 जुझारी | Suspended | 230000 | 0 | 2017-06-19
BAHORIBAND / JUJHARI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744005031/IF/22012034399364 — कपिल धारा कूप निर्माण कार्य भैयासिन्ह /मिठाईलाल् | Suspended | 200000 | 10100 | 2018-03-21
BAHORIBAND / PAHARUA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744005035/IF/22012034484701 — RFR_KATNI RIVER_KHET TALAB_(PRAMODD S/O SABDAL/556 /PALI) | Suspended | 310385.56 | 5220 | 2019-07-16
BAHORIBAND / NIMKHEDA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005048/DP/22012034243428 — planteion kary muktidham me talab ke pass | Suspended | 33500000000 | 0 | 2017-06-02
BAHORIBAND / NIMKHEDA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005048/DP/22012034243882 — Palantesion karay sehidhur ke part no.3 me | Suspended | 53500000000 | 0 | 2017-06-08
BAHORIBAND / NIMKHEDA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005048/DP/22012034243966 — VRAKSHA ROPAN KARY BARA BALI BHATIYA ME | Suspended | 53500000000 | 0 | 2017-06-09
BAHORIBAND / KUDAN | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1744005055/WC/4435 — नहर सुधार कार्य बाई तरफ कूडन | Suspended | 145000 | 338270 | 2008-09-11
BAHORIBAND / MOHANIYA NEEM | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1744005057/AV/22012034514187 — बाउंड्रीवाल निर्माण कार्य शासकीय प्राथमिक आदिवासी उन्नयन शाला | Suspended | 0 | 0 | 2020-05-02
BAHORIBAND / BANDHIDURI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble contour bund for individuals / Construction of Pebble contour Bund for Individuals | Construction of Bund | 1744005060/IF/22012034687663 — CTR MED BHANDHAN KARYA SURENDRA/DAYARAM | Suspended | 61911.69 | 504 | 2021-04-30
BAHORIBAND / BANDHIDURI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1744005060/WC/22012034544204 — RFR_KATNI_RIVER_TALAB GAHRIKARAN MEDE KI TALIYA | Suspended | 716339.48 | 1278 | 2020-11-12
BAHORIBAND / BANDHIDURI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1744005060/WC/22012034606881 — CPT NIRMAN KARYA CHADARI BHATIYA KE PAS | Suspended | 438919.39 | 332755 | 2021-01-24
BAHORIBAND / DURI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005061/WC/22012034565309 — RFR_KATNI_RIVER _KANTINYU KANTUR TRANCH KHANDIYA KI BHATIYA PART 1 | Suspended | 674593.71 | 601168 | 2020-10-02
BAHORIBAND / KHIRAHANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1744005062/WC/22012034544202 — RFR_KATNI_RIVER TALAB GAHARIKARAN BADA NALA KE PAS | Suspended | 713034.97 | 50380 | 2020-05-14
BAHORIBAND / SALAYA PIYASHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1744005065/WC/22012034505668 — RFR-KATNI RIVER-NAVEEN TALAB NIRMAN UTTAMPUR KHASRA NO-610 | Suspended | 1474146.77 | 180 | 2020-11-11
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034260433 — RFR-KATNI RIVER-खेतसमतलीकरण-बिहारी/रामदेव | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034261462 — RFR-KATNI RIVER-खेतसमतलीकरण-हरी सिंह /झुम्मु | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034261465 — RFR-KATNI RIVER-खेतसमतलीकरण-किशोरी /सुघराम | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034261470 — RFR-KATNI RIVER-खेतसमतलीकरण-ईतिया /प्रेमलाल चौधरी | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034261476 — RFR-KATNI RIVER-खेतसमतलीकरण-मुराली /कतउ चौधरी | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034261477 — RFR-KATNI RIVER-खेतसमतलीकरण-सुंदर /भद्दी कोल | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1744005066/LD/22012034261478 — RFR-KATNI RIVER-खेतसमतलीकरण-रामसुजान/रामदेव दाहिया | Suspended | 0 | 0 | 2020-06-15
BAHORIBAND / TEWRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744005066/RC/22012034450151 — सीसी रोड निर्माण विनोदजैन के घर से ईस्वरी बसोर के घर के तक | Suspended | 41000 | 0 | 2021-01-01
BAHORIBAND / TEWRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744005066/RC/22012034585754 — सी.सी रोड नालीनिर्माण सुनीताकोल के घर से विनोदजैन की ओर | Suspended | 100000 | 0 | 2021-08-14
BAHORIBAND / TEWRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1744005066/WC/22012034566418 — RFR-KATNI RIVER कंटुर टॆंच निर्माण खसरा-381 भाग/2 | Suspended | 578902.69 | 0 | 2021-01-03
BAHORIBAND / BICHUWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1744005067/AV/22012034373328 — खाद गोदाम निर्माण बिचुआ | Suspended | 964000 | 0 | 2020-05-18
BAHORIBAND / LAKHANWARA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1744005068/LD/22012034260845 — shantidham nirmaan karya ligri | Suspended | 180000 | 1080 | 2017-08-31
BAHORIBAND / LAKHANWARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744005068/WC/22012034443017 — RFR_KATNI RIVER_लूज बोल्डर चेक लखनवारा नाला भाग एक | Suspended | 24451 | 510 | 2019-03-07
BAHORIBAND / LAKHANWARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1744005068/WC/22012034443043 — RFR_KATNI RIVER_लूज बोल्डर चेक डुडिया नाला भाग एक | Suspended | 24451 | 510 | 2019-03-05
BAHORIBAND / SANSHARPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1744005070/RC/22012034366651 — खेत सड्क रमघडा़ से डुगरिया मार्ग | Suspended | 1196000 | 326673.07 | 2017-11-24
BAHORIBAND / MATWARA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1744005074/DP/22012034240731 — व्रछारोपन कार्य सन्ति धाम के पास खुड़ावल 02 | Suspended | 52500000000 | 0 | 2017-05-12
BAHORIBAND / CHANDANKHEDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744005078/IF/22012034687467 — CTR khet talab nirman asha rani | Suspended | 110516.06 | 0 | 2021-04-28
DHIMERKHEDA / NEGI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744006005/IF/IAY/1182021 — Construction of IAY House -IAY REG. NO. MP2295953 | Suspended | 17100 | 0 | 2017-10-24
DHIMERKHEDA / NEGI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744006005/IF/IAY/1708099 — Construction of IAY House -IAY REG. NO. MP2356328 | Suspended | 17100 | 0 | 2018-06-13
DHIMERKHEDA / KACHNARI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1744006010/IF/22012034584443 — GKRA Kattle Shed Nirman Kary Vijay Singh/Pratap Singh Dhanwahi | Suspended | 101273.16 | 100 | 2020-08-05
DHIMERKHEDA / SAGONA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744006017/IF/22012034316512 — kup nirman & khet talab nirman kary lakhan /jhunnisingh | Suspended | 230000 | 29637 | 2017-03-09
DHIMERKHEDA / SAGONA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744006017/IF/22012034325943 — kapildhara koop avam khet talab jagpate/mahlal | Suspended | 230000 | 36616 | 2017-04-01
DHIMERKHEDA / DHANA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1744006026/IF/22012034554593 — Med Bandhan- Hitgrahi Kailash Chand Mehra/Ganesh Prasad- Ghana | Suspended | 39937.52 | 0 | 2020-10-11
DHIMERKHEDA / ANTRWED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744006028/RC/22012034519373 — सी सी रोड निर्माण कार्य मुख्य मार्ग से करन पटेल के घर की ओर अमगवा | Suspended | 19000 | 0 | 2021-11-13
DHIMERKHEDA / ANTRWED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744006028/RC/22012034519377 — सी सी रोड निर्माण कार्य मुख्य मार्ग से जवाहर बर्मन के घर की ओर बिजौरा | Suspended | 15000 | 0 | 2021-11-13
DHIMERKHEDA / ANTRWED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1744006028/RS/22012034496662 — GKRA सामुदायिक स्वच्छता परिसर बस स्टेण्ड पुरानी पंचायत भवन के पास | Suspended | 0 | 0 | 2020-09-26
DHIMERKHEDA / ANTRWED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1744006028/WH/22012034390255 — तालाब विस्‍तारीकरण, टिकरिया | Suspended | 0 | 0 | 2021-11-13
DHIMERKHEDA / KHAMHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1744006029/AV/22012034572076 — मुक्तिधाम सैड निर्माण कार्य-गिदोहा (खाम्हा) | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / KHAMHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1744006029/AV/22012034572079 — मुक्तिधाम सैड निर्माण कार्य-चंदी दाई के पास खाम्हा | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / KHAMHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744006029/RC/22012034375978 — सी सी रोड निर्माण कार्य | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / KHAMHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1744006029/RC/22012034440219 — सुदूर सडु़क निर्माण करही से खिरहनी की ओर | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / KHAMHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1744006029/RC/22012034440225 — सी0 सी0 रोड निर्माण कार्य मेन रोड से देवीदास लोधी के घर की ओर | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / KHAMHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1744006029/WC/22012034803997 — tranch line patbaba padadi -01 | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / KHAMHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1744006029/WC/22012034803998 — tranch line patbaba padadi -02 | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1744006031/IF/22012034682184 — मेड़ बंधान निर्माण कार्य- रामजी/काशीराम कलार | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1744006031/IF/22012034683631 — मेड़ बंधान निर्माण कार्य- जवाहर लाल/ अधिया कोल | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1744006031/IF/22012034683634 — मेड़ बंधान निर्माण कार्य- रूपलाल/बाबू लाल | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1744006031/IF/22012034683653 — मेड़ बंधान निर्माण कार्य- विनोद कुमार/ तुलसी राम कोल | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1744006031/IF/22012034683656 — मेड़ बंधान निर्माण कार्य- श्याम लाल/खूबबी लाल कोल | Suspended | 0 | 0 | 2021-10-20
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1744006031/RS/22012034523241 — Slwm वर्मी कम्पोस्ट - अहरी खेल मैदान परसेल में | Suspended | 0 | 0 | 2021-11-10
DHIMERKHEDA / PARSEL | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maintenance of Earthen Spur for Community / Repair and Maintenance of Earthen Spur for Community | Repair & maint of Water Harvesting Structures | 1744006031/WC/22012034493397 — sokpit nirman kary radha krashan mandir ke pass | Suspended | 19230.96 | 0 | 2021-11-10
DHIMERKHEDA / GHUGHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744006034/RS/22012034322827 — shouchalay marammat bala prasad | Suspended | 8800 | 800 | 2017-03-02
DHIMERKHEDA / GHUGHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744006034/RS/22012034322838 — shouchalay marammat bhagchand/sitaram | Suspended | 8800 | 808 | 2017-03-02
DHIMERKHEDA / GHUGHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744006034/RS/22012034323538 — shouchalay marammat rani bai/mohan | Suspended | 8800 | 800 | 2017-03-02
DHIMERKHEDA / GHUGHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744006034/RS/22012034323551 — shouchalay marammat santo/sonelal | Suspended | 8800 | 800 | 2017-03-02
DHIMERKHEDA / GHUGHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744006034/RS/22012034323562 — shouchalay marammat harprasad/ramkumar | Suspended | 8800 | 808 | 2017-03-02
DHIMERKHEDA / GHUGHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1744006034/RS/22012034323565 — shochalay marammat sombati/dasrath | Suspended | 8800 | 800 | 2017-03-02
DHIMERKHEDA / DEWRIMUGELI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1744006045/WC/22012034438028 — तालाब विस्‍तारीकरण, पड़रिया | Suspended | 0 | 0 | 2020-07-20
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1744006056/LD/22012034467419 — RFR_KATNI RIVER मेड बंधान जिया लाल /ब्रजलाल | Suspended | 50235.1 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1744006056/LD/22012034467420 — RFR_KATNI RIVER मेड बंधान लखन /ब्रजलाल | Suspended | 50235.1 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1744006056/LD/22012034467422 — RFR_KATNI RIVER मेड बंधान सरदार सिह /राम सिंह | Suspended | 50235.1 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1744006056/LD/22012034467424 — RFR_KATNI RIVER_मेड बंधान छोटे /गनेशा | Suspended | 50235.1 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1744006056/LD/22012034467426 — RFR_KATNI RIVER_मेड बंधान राजेन्द्र सिह /वीरेन्द सिह | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467764 — RFR_KATNI RIVER मेड बंधान दिलराज /छोटे | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467765 — RFR_KATNI RIVER मेड बंधान नरेश /रतन | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467766 — RFR_KATNI RIVER मेड बंधान महपाल /कुंजी | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467768 — RFR_KATNI RIVER मेड बंधान नंदी /सुकरू | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467769 — RFR_KATNI RIVER मेड बंधान जगदीश /जौहर | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467770 — RFR_KATNI RIVER मेड बंधान निरपत /सुकरू | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467771 — RFR_KATNI RIVER मेड बंधान हुकुम /सुकरू | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467773 — RFR_KATNI RIVER मेड बंधान समनू /नन्हू | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / BHULA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744006056/LD/22012034467776 — RFR_KATNI RIVER मेड बंधान इन्दो बाई /कोदू | Suspended | 52233.84 | 0 | 2020-08-21
DHIMERKHEDA / SALARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1744006058/WC/22012034486179 — Khet Talab Nirman Dhani Singh S/o Nandu Singh | Suspended | 0 | 0 | 2020-06-29
DHIMERKHEDA / SALARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1744006058/WC/22012034486180 — Khet Talab Nirman Milan Singh S/o Surendra Singh | Suspended | 0 | 0 | 2020-06-29
DHIMERKHEDA / ATRIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744006066/IF/22012034323987 — कपिलधारा एवं खेत तलाव - रावेन्‍द्र सिंह/जहांन सिंह | Suspended | 230000 | 165220 | 2017-03-18
DHIMERKHEDA / JHIRRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744006073/IF/22012034314079 — KAPIL DHARA KOOP AWAM KHET TALAB NIRMAN KUSUM BAI/PARSADI | Suspended | 230000 | 0 | 2017-03-08
RITHI / BASHUDHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1744/RC/22012034177382 — बासुध से चिरुहला रोड निमार्ण कार्य | Suspended | 4045000 | 1084281.4 | 2012-12-04