## Work List
Exported on: 2026-09-05 12:54:57
Filters applied:
Data source: VBGRAMG
District: DINDORI
Block: All
Panchayat: BILGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAHPURA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1745001023/AV/22012034534011 — बाउण्ड्रीवाल निर्माण कार्य प्राथ‍मिक शाला ग्राम पंचायत बिलगाँव | Physically Completed | 1080228.57 | 0 | 2021-02-03 | 2026-08-06
SHAHPURA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1745001023/AV/22012034573817 — बाउण्‍ड्रीवाल निर्माण कार्य ग्राम पंचायत बिलगॉंव | Physically Completed | 1376692.52 | 0 | 2021-09-03 | 2026-08-06
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1745001023/IF/22012035303720 — Pashu Shed Nirman Karya Hit Dropat Lal Sahu / Dwarka Sahu GP Bilgaon | Approved | 0 | 0 | 2025-02-03
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1745001023/IF/22012035303727 — Pashu Shed Nirman Karya Hit MihiLal Sahu / Tannu Sahu GP Bilgaon | Approved | 0 | 0 | 2025-02-03
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745001023/IF/22012035390250 — JGSA Kapildhara Koop Nirman Hit Umashankar / Babulal G P Bilgaon | Approved | 0 | 0 | 2025-04-22
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1745001023/IF/22012035550087 — Pashu Shed Nirman Hit. Kamla Prasad / Kandhi Sahu G.P. Bilgaon | Approved | 0 | 0 | 2025-04-22
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745001023/IF/22012035568675 — Kapil Dhara Koop Nirman Hit. Umashankar / Babulal G.P. Bilgaon | Approved | 0 | 0 | 2025-04-22
SHAHPURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745001023/IF/IAY/2982932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2585241 | Approved | 28500 | 0 | 2021-01-25
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745001023/IF/IAY/3254586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2436691 | Approved | 28500 | 0 | 2021-10-22
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745001023/IF/IAY/3319056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3982445 | Ongoing | 28500 | 0 | 2022-02-08
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745001023/IF/IAY/5504418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147951010 | Approved | 28500 | 0 | 2025-03-05
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1745001023/WC/22012035311693 — JGSA Rechage Pit Nirman PS School GP Bilgaon | Approved | 0 | 0 | 2025-04-22
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1745001023/WC/22012035311697 — JGSA Rechage Pit Nirman HS School GP Bilgaon | Approved | 0 | 0 | 2025-04-22
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001023/WC/VB/22012035329863 — Construction of Boulder Check Ramkishor ke khet pass G.P. Bilgaon | Ongoing | 299990.64 | 9500 | 2026-08-05
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001023/WC/VB/22012035329958 — Construction Of Boulder check For Ramkishor ke khet pass Part 02 G P Bilgaon | Ongoing | 299990.64 | 0 | 2026-08-14
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001023/WC/VB/22012035330246 — Construction Of Boulder Check Barapni Nala G.P. Bilgaon | Approved | 282662.69 | 0 | 2026-06-05
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001023/WC/VB/22012035330291 — Construction Of Boulder Check Narayan Ke Khet Pass G P Bilgaon | Approved | 396446.51 | 0 | 2026-06-05
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001023/WC/VB/22012035330300 — Construction Of Boulder Check Dropat Lal Ke Khet Pass G P Bilgaon | Approved | 177544.93 | 0 | 2026-06-05
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001023/WC/VB/22012035330303 — Contour Trench Khasra No 87 G P Bilgaon | Approved | 281714.41 | 0 | 2026-06-05
SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001023/WC/VB/22012035330311 — Contour Trench Ramkishor ke khet pass G P Bilgaon | Approved | 562688.5 | 0 | 2026-06-05