## Work List
Exported on: 2026-09-10 14:41:22
Filters applied:
Data source: VBGRAMG
District: DINDORI
Block: All
Panchayat: DARRIMOHGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DINDORI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1745002062/DP/22012034592365 — Vasudha-Vandan- Amrit Vatika- Darri Mohgaon | Ongoing | 55847.4 | 0 | 2023-08-22
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745002062/DP/22012034629508 — रोड किनारे प्लानटेशन निर्माण कार्यबल्ही से छिंदगांव सरहद तक | Approved | 0 | 0 | 2025-04-16
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745002062/DP/22012034629509 — दर्री से बल्ही ग्रेवल रोड किनारे प्लानटेशन निर्माण कार्य | Approved | 0 | 0 | 2025-04-16
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745002062/DP/22012034629510 — ददराटोला से प्राथमिक शाला भवन तक रोड किनारे प्लान्टेशन निर्माण कार्य | Approved | 0 | 0 | 2025-04-17
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745002062/DP/22012034629765 — JGSA road said plantation balhi se chandgaon medo tak | Approved | 0 | 0 | 2025-04-16
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745002062/IF/22012035446485 — JGSA khet talab nirman kary Amratiya / Dholi gram Drrimohgaon | Approved | 25899.46 | 0 | 2025-04-14
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745002062/IF/22012035491770 — Kapildhara Koop nirman kary Lamiyabai/Mohanlal Gram Balhi Mal | Ongoing | 405511.37 | 0 | 2025-05-11
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745002062/IF/22012035546870 — JGSA Khet talab nirman kary hit -kulesh/Mangal Singh balhi gp Darrimohgaon | Approved | 0 | 0 | 2025-04-16
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745002062/IF/22012035550804 — JGSA khet talab nirman kary hit amratiya /dholi gp darrimohgaon | Approved | 0 | 0 | 2025-04-15
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745002062/IF/22012035550813 — JGSA khet talab nirman kary hit muliya bai /hannu gusiya ryt gp darrimohgaon | Approved | 0 | 0 | 2025-04-15
DINDORI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/3770515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127403697 | Ongoing | 28500 | 3654 | 2022-09-18
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5991518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123780198 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5991639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125541013 | Ongoing | 28500 | 0 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5991640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125541177 | Physically Completed | 24795 | 0 | 2026-03-09 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5991671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125073420 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118313863 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127407953 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127410148 | Ongoing | 28500 | 0 | 2026-03-09
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127413439 | Ongoing | 28500 | 0 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127426025 | Physically Completed | 24795 | 0 | 2026-03-09 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125677642 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125295075 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125316069 | Ongoing | 28500 | 0 | 2026-03-09
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127826303 | Ongoing | 28500 | 3654 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127847390 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127819641 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5992999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127821437 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-08-04
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127822178 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127824073 | Physically Completed | 28500 | 4959 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127824430 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127825389 | Physically Completed | 28500 | 4959 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127843296 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127857961 | Physically Completed | 24795 | 0 | 2026-03-22 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127858862 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123436497 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123437799 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127849358 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127851460 | Physically Completed | 28500 | 4959 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125684347 | Physically Completed | 28500 | 4959 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125698704 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127137488 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127416243 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5993970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125312314 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125074709 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121676387 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127425607 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118303339 | Ongoing | 28500 | 0 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124726835 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126293641 | Physically Completed | 28500 | 1305 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123198534 | Physically Completed | 28500 | 4959 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125883710 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5994999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125688672 | Ongoing | 28500 | 4200 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5995454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125866813 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5995604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123450276 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5995722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121669484 | Physically Completed | 28500 | 1305 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5995745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127412417 | Physically Completed | 28500 | 1305 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126378395 | Physically Completed | 28500 | 1305 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126296555 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-08-04
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125313581 | Ongoing | 28500 | 1305 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125313129 | Physically Completed | 28500 | 4959 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127857158 | Physically Completed | 28500 | 0 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127854747 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-08-04
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123199935 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127130605 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125874041 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123449663 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123437110 | Ongoing | 28500 | 0 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127410512 | Ongoing | 28500 | 0 | 2026-03-22
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5996845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125071926 | Physically Completed | 28500 | 5481 | 2026-03-09 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124729933 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127845893 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125702764 | Physically Completed | 24795 | 0 | 2026-03-09 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117500102 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127833243 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125311928 | Ongoing | 28500 | 4200 | 2026-03-22
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121722942 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118076482 | Physically Completed | 28500 | 3654 | 2026-03-08 | 2026-08-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127127858 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5997953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127826768 | Ongoing | 28500 | 8400 | 2026-03-08
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5998269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125348601 | Physically Completed | 28500 | 0 | 2026-03-08 | 2026-09-02
DINDORI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/5998291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125336792 | Physically Completed | 24795 | 0 | 2026-03-08 | 2026-07-31
DINDORI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/6080024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120238553 | Ongoing | 28500 | 4200 | 2026-07-15
DINDORI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/6089486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127119709 | Ongoing | 28500 | 8400 | 2026-07-15
DINDORI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745002062/IF/IAY/6090596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127870693 | Ongoing | 28500 | 0 | 2026-07-20
DINDORI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1745002062/WC/22012034594083 — Pey jal koop nirman kary- kachhar me Darri Mohgoan | Ongoing | 470874.11 | 0 | 2020-11-19
DINDORI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745002062/WC/22012035245648 — Naveen talab nirman karya-Darri Mohgaon | Approved | 0 | 0 | 2024-10-04
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1745002062/WC/22012035291261 — koop Richarj nirman kary chota das ke ghar ke pass balhi me | New | 0 | 0 | 2025-04-16
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745002062/WC/22012035293330 — JGSA roof water harvesting nirman kary panchayat bhavan Darrimohgaon | Approved | 0 | 0 | 2025-04-15
DINDORI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745002062/WC/22012035293362 — JGSA roof water harvesting nirman kary p/s Darrimohgaon | Approved | 0 | 0 | 2025-04-15
DINDORI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745002062/WC/VB/22012035332048 — boulder check nirman karya gdarrimohgaon mal gp darrimohgaon | Ongoing | 70698.95 | 0 | 2026-08-20
DINDORI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745002062/WC/VB/22012035332049 — boulder check nirman karya g ghusiya ryt gp darrimohgaon | Ongoing | 70698.95 | 26428.48 | 2026-08-19
DINDORI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745002062/WC/VB/22012035332050 — boulder check nirman karya gdarrimohgaon ryt gp darrimohgaon | Ongoing | 262508.4 | 2574 | 2026-08-20
DINDORI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745002062/WC/VB/22012035332051 — boulder check nirman karya gdarrimohgaon ryt gp darrimohgaon | Ongoing | 70698.95 | 0 | 2026-08-20
DINDORI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745002062/WC/VB/22012035332052 — boulder check nirman karya g balhi mal gp darrimohgaon | Ongoing | 134635.43 | 955.52 | 2026-08-20
DINDORI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1745/RC/22012034660542 — Gravel Road Nirman karya Darrimohgaon To Balhi Tak | Ongoing | 6605000 | 0 | 2024-02-14