## Work List
Exported on: 2026-09-15 15:56:47
Filters applied:
Data source: VBGRAMG
District: DINDORI
Block: All
Panchayat: DEORI MAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AMARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1745003019/DP/22012034621434 — vraksha ropan karya kharmer nadi kinare deori mal | Ongoing | 343775.14 | 16500 | 2024-07-24
AMARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1745003019/DP/22012034621438 — Dudhariya Talab kinare vraksharopan karya deori mal | Ongoing | 343775.14 | 0 | 2024-07-12
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1745003019/DP/22012034629511 — JGSA Road side plantation Amarpur marg se samnapur marga tak devri | Ongoing | 475330.71 | 12825 | 2025-05-07
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003019/DP/22012034629512 — JGSA Road side plantation gopi ke ghr se krashkumar ke khet tak devri | Ongoing | 475330.71 | 440 | 2025-05-07
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003019/DP/22012034629514 — JGSA Road side plantation dudhariya talab se ganesh ke khet tak devri | Ongoing | 475330.71 | 440 | 2025-05-07
AMARPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745003019/IF/22012034472374 — kapil dhara gayan singh deori | Ongoing | 230000 | 0 | 2019-03-10
AMARPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745003019/IF/22012034482822 — kapil dhara sah khet talab sanju/rammilan | Ongoing | 251081.24 | 0 | 2020-02-03
AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745003019/IF/22012034646358 — kup nirman kary santu/sonu gp dewari | Ongoing | 230000 | 0 | 2021-04-11
AMARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1745003019/IF/22012034732607 — Kup nirman ramkumar/nandau gp dewari | Ongoing | 230000 | 0 | 2021-05-20
AMARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1745003019/IF/22012035086978 — pashu shed nirman karya santu /sonu deveri | Completed | 122000 | 0 | 2023-09-06 | 2026-08-24
AMARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1745003019/IF/22012035086979 — pashu shed nirman karya kalyan / nanhu devri | Completed | 122000 | 0 | 2023-09-06 | 2026-08-24
AMARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003019/IF/IAY/2665673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4560053 | Approved | 28500 | 0 | 2020-10-01
AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003019/IF/IAY/3347607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5188486 | Approved | 28500 | 0 | 2021-11-13
AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003019/IF/IAY/3351472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5525752 | Approved | 28500 | 0 | 2021-11-13
AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003019/IF/IAY/3351538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5529708 | Approved | 28500 | 0 | 2021-11-13
AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003019/IF/IAY/3351622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5534708 | Approved | 28500 | 0 | 2021-11-13
AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003019/IF/IAY/3351760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5546490 | Approved | 28500 | 0 | 2021-11-13
AMARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1745003019/RC/22012034837769 — Sudoor Sampark Marg Nirmaan Devisingh ke Ghar Se Bhader Singh ke khet Tak GP Deori | Approved | 0 | 0 | 2024-10-03
AMARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1745003019/WC/22012035133917 — construction of check dam kandhwa nala Deori Gp Deori | Ongoing | 648493.67 | 0 | 2023-10-08
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1745003019/WC/22012035313405 — Percolation Tank Nirmaan Mudiyaa Ke Pas GP Deori Mal | Approved | 199466.8 | 0 | 2025-04-15
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1745003019/WC/22012035313407 — Percolation Tank Nirmaan Beda Ke Pas GP Devri Mal | Approved | 199466.8 | 0 | 2025-04-14
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003019/WC/VB/22012035330264 — Staggered Contour Trainch Nirman Karya Konha Pahadi Part 01 Gram Devri mal Panchayat Devri Mal | Ongoing | 201335.8 | 0 | 2026-08-05
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003019/WC/VB/22012035330266 — Staggered Contour Trainch Nirman KaryaMurli Toriya Pahadi GramDevri Mal Gram PanchayatDevri Mal | Approved | 0 | 0 | 2026-04-14
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003019/WC/VB/22012035330268 — Staggered Contour Trainch Nirman Karya Pipraha Pahadi Gram Devri Mal Gram Panchayat Devri Mal | Ongoing | 299688.6 | 76581.6 | 2026-08-09