## Work List
Exported on: 2026-09-11 08:36:23
Filters applied:
Data source: VBGRAMG
District: DINDORI
Block: All
Panchayat: SAKKA MAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AMARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1745003032/DP/22012034621495 — plantation work kharmer nadi kinare sakka | Ongoing | 499951.46 | 3250 | 2024-07-11
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003032/DP/22012034629458 — JGSA Road side Plantation Mandla Dindori Road to Khairda Sakarahi Nalla | Approved | 0 | 0 | 2025-04-10
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003032/DP/22012034629459 — JGSA Road side Plantation Mandla Dindori Road to Kachnari Road | Approved | 0 | 0 | 2025-04-10
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003032/DP/22012034629460 — JGSA Road side Plantation Mandla Dindori Road Kharmer Nadi to Sakka mal | Approved | 0 | 0 | 2025-04-10
AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745003032/IF/22012035630485 — Ek Bagiya Ma Ke Name Dropati / Bhagvat MP45003032001/10 Sakka Mal | Approved | 0 | 0 | 2025-10-02
AMARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003032/IF/IAY/110441 — Construction of IAY House -IAY REG. NO. MP-45-003-032-001/1168 | Approved | 28500 | 0 | 2015-10-26
AMARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003032/IF/IAY/110442 — Construction of IAY House -IAY REG. NO. MP-45-003-032-001/769 | Approved | 28500 | 0 | 2015-10-26
AMARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003032/IF/IAY/110443 — Construction of IAY House -IAY REG. NO. MP-45-003-032-001/792 | Approved | 28500 | 0 | 2015-10-26
AMARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003032/IF/IAY/110444 — Construction of IAY House -IAY REG. NO. MP-45-003-032-001/799 | Approved | 28500 | 0 | 2015-10-26
AMARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003032/IF/IAY/110445 — Construction of IAY House -IAY REG. NO. MP-45-003-032-001/869 | Approved | 28500 | 0 | 2015-10-26
AMARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745003032/WC/22012035182129 — TEDHIYA NALA KACHNARI ME CHEK DAME NIRMAN KARY KACHNARI | Ongoing | 1151058.14 | 0 | 2024-03-13
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745003032/WC/22012035280069 — JGSA Construction of Naveen Talab Badhni kunha Kachnari | Ongoing | 1751901.16 | 0 | 2025-06-12
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745003032/WC/22012035291557 — JGSA ROOF TOP RAIN WATERHARVESTING RAJIV GANDHI SEVA KENDRA SAKKA | Completed | 27853.08 | 0 | 2025-05-06 | 2026-08-23
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745003032/WC/22012035294348 — JGSA Roof Water Harvesting Panchayat Bhawan Sakka mal | Completed | 27853.08 | 0 | 2025-05-06 | 2026-08-23
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745003032/WC/22012035294349 — JGSA Roof Water Harvesting CSC Bhawan Sakka | Completed | 27853.08 | 0 | 2025-05-06 | 2026-08-23
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745003032/WC/22012035295383 — JGSA ROOF TOP RAIN WATERHARVESTING CSC BUILDING SAKKA | Approved | 0 | 0 | 2025-04-19
AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1745003032/WC/22012035296770 — CONSTRECTION OF PERCOLETION TANK NIRMAN BACHHAI NALA SAKKA | Approved | 0 | 0 | 2025-04-19
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003032/WC/VB/22012035330338 — Staggered Countur Trainch Nirman Karya Pani Tanki Pass Gram Kachnari Gram Panchayat Sakka Mall | Ongoing | 85203.3 | 44574.58 | 2026-08-13
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003032/WC/VB/22012035330341 — Staggered Countur Trainch Nirman KaryaSamshan Ke Paa Gram Sakka Mall Gram Panchayat Sakka Mall | Approved | 0 | 0 | 2026-04-14
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003032/WC/VB/22012035330344 — Staggered Countur Trainch Nirman Karya Umarghati Barela Gram Sakka Gram Panchayat Sakka Mall | Ongoing | 114709.14 | 50111.96 | 2026-08-13
AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745003032/WC/VB/22012035330347 — Staggered Countur Trainch Nirman Karya Amrat Sarovar Barela Gram Sakka Gram Panchayat Sakka Mall | Ongoing | 114709.14 | 58463.67 | 2026-08-13