## Work List
Exported on: 2026-09-04 22:47:12
Filters applied:
Data source: VBGRAMG
District: DINDORI
Block: All
Panchayat: KAROPANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BAJAG | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1745004015/AV/22012034573121 — बाउंड्रीवॉल निर्माण प्राथमिक शाला बुधगंव माल | Ongoing | 1265153.53 | 0 | 2021-07-08
BAJAG | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1745004015/DP/22012034556461 — वक्षा रोपड कार्य प्रधान मंत्री सडक अमरकटक मार्ग से बुधगांव की ओर | Ongoing | 407718.19 | 0 | 2022-05-24
BAJAG | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1745004015/DP/22012034556641 — कार्य का नाम वक्षा रोपड मुख्य मार्ग से प्रधान मंत्री सडक बांसाटोला की और कारोपानी | Ongoing | 407718.19 | 0 | 2022-05-27
BAJAG | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1745004015/DP/22012034614891 — samudayik poshan vatika karaya karopani | Ongoing | 990539.1 | 0 | 2024-06-02
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1745004015/DP/22012034629745 — vvraksha ropan karya karopani khasra number 103 | Ongoing | 342109.82 | 0 | 2025-05-25
BAJAG | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1745004015/IF/22012034816888 — व़़क्षा रोपड कार्य संगम घाट से चरखुटिया की और कारोपानी भाग 01 | Ongoing | 394489.84 | 0 | 2021-07-01
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745004015/IF/22012035476097 — Talab Nirman karya sumeri pita sonsaya karopani | New | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745004015/IF/22012035476119 — Talab Nirman karya sumeri pita sonsaya karopani | New | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1745004015/IF/22012035514891 — khet talab nirman karay sarju maravi/ramparsad karopani | Approved | 268553.45 | 0 | 2025-04-14
BAJAG | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/3998216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114717314 | Approved | 28500 | 0 | 2022-05-06
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/4672357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116648915 | Physically Completed | 24795 | 0 | 2024-09-15 | 2026-08-09
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/4672366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116654301 | Ongoing | 28500 | 0 | 2024-11-08
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/4820194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114052388 | Completed | 24795 | 0 | 2025-05-08 | 2026-08-24
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/4885026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116544960 | Approved | 28500 | 0 | 2024-10-09
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5109979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151979142 | Ongoing | 28500 | 0 | 2025-10-25
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5109985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151979861 | Completed | 24795 | 0 | 2025-10-25 | 2026-08-24
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5263026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144817791 | Completed | 24795 | 0 | 2025-10-25 | 2026-08-24
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5278783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124083832 | Approved | 28500 | 0 | 2025-03-02
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5439809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127963017 | Approved | 28500 | 0 | 2025-03-02
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5439828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127966924 | Approved | 28500 | 0 | 2025-03-05
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5440181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144821963 | Ongoing | 28500 | 0 | 2025-10-26
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5440183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144822316 | Ongoing | 28500 | 0 | 2025-10-26
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5440184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144822388 | Ongoing | 28500 | 0 | 2025-10-26
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5440574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123830370 | Approved | 28500 | 0 | 2025-03-03
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5441741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125500878 | Physically Completed | 28500 | 0 | 2025-10-23 | 2026-08-30
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5441948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116453707 | Completed | 24795 | 0 | 2025-10-26 | 2026-08-24
BAJAG | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5442022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115949014 | Ongoing | 28500 | 0 | 2026-06-06
BAJAG | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5442023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115949852 | Ongoing | 28500 | 0 | 2026-07-31
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5442733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118765886 | Approved | 28500 | 0 | 2025-02-27
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5443978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121579622 | Physically Completed | 24795 | 0 | 2025-03-02 | 2026-08-09
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5447469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114729534 | Approved | 28500 | 0 | 2025-03-03
BAJAG | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5449991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118738686 | Approved | 28500 | 0 | 2025-02-27
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5580737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127961007 | Approved | 28500 | 0 | 2025-04-16
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5691234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114739360 | Completed | 24795 | 0 | 2025-10-26 | 2026-08-24
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5722133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144821371 | Ongoing | 28500 | 0 | 2025-10-26
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5728009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116546161 | Physically Completed | 24795 | 0 | 2025-10-26 | 2026-08-24
BAJAG | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745004015/IF/IAY/5904075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151786949 | Physically Completed | 24795 | 0 | 2025-10-23 | 2026-07-26
BAJAG | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1745004015/RC/22012034842677 — GRAVEL ROAD NIRMAN KARY BANSA TOLA SE THIGRA TOLA TAK | Approved | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1745004015/RS/22012035137682 — Sarojini kop recharge fit sumarbahi budhgaon karopani | New | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1745004015/RS/22012035137683 — Sarvjanik koop recharge fit sumarbahi budhgaon karopani | Approved | 0 | 0 | 2025-04-14
BAJAG | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745004015/WC/22012035235631 — contour trench Nirman karya tiranga Tola karopani | New | 0 | 0 | 2024-11-13
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1745004015/WC/22012035298499 — Sarvjanik koop recharge fit began tola ka karopani | New | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1745004015/WC/22012035309387 — RECHARGE FIT KAROPANI BHARAT KE GHAR PASS | Approved | 0 | 0 | 2025-05-14
BAJAG | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745004015/WC/VB/22012035332058 — contour trench nirmad karya charkhutiya karopani | Approved | 517694.33 | 0 | 2026-07-20
BAJAG | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745004015/WC/VB/22012035332063 — contour trench nirmad karya budhgoan mal karopani | Approved | 575786.01 | 0 | 2026-07-20
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1745004015/WH/22012034944249 — jal Ganga samvardhan abhiyan ke tahat talab dirn udhar char kutiya kaurav Pani khasra number 147 | Approved | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1745004015/WH/22012034944325 — jal Ganga samvardhan abhiyan ke tahat talab dirunadhar karya Tinga Tola karopani | Approved | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1745004015/WH/22012034944326 — jal Ganga samvardhan abhiyan ki tahat talab girne udhar kaya Began tola karopani | Approved | 0 | 0 | 2025-04-14
BAJAG | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1745004015/WH/22012034944327 — jal Ganga samvardhan abhiyan ke tahat talab jhunu dhaar Karay Budhgaon karopani | Approved | 0 | 0 | 2025-04-14