## Work List
Exported on: 2026-09-14 19:38:47
Filters applied:
Data source: VBGRAMG
District: DINDORI
Block: All
Panchayat: SARAS DOLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MEHANDWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1745007014/DP/22012034616668 — VERCHA ROPAN KARAY JADHA BAND KE PAS PHADHI ME SARASDOLI | Ongoing | 823790.43 | 0 | 2024-06-12
MEHANDWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745007014/DP/22012034629347 — J G S A Vircharopan Karya Pitrol Pamp Se Rajghadhi Ghat Tak Sarasdoli | Ongoing | 475330.71 | 21521 | 2025-05-04
MEHANDWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745007014/DP/22012034629371 — J G S A Vircharopan Karya Koor Tola Terha Se Payali Sharhad Tak Sarasdoli | Approved | 0 | 0 | 2025-04-14
MEHANDWANI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745007014/IF/22012034403109 — KHEAT TALAB SA KUP NIRMAN KARY SAMBHUPRASAD/REWA | Ongoing | 230000 | 0 | 2019-01-13
MEHANDWANI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745007014/IF/22012034452156 — KAPIL DHARA KUP NIRMANHITGRAHI HARCHAT BAI/VISBNATH | Ongoing | 230000 | 0 | 2019-02-05
MEHANDWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1745007014/IF/22012035272398 — Pashu Sead Nerman Kary Ramsaroop Sahu/ Dadulal Sahu Sarasdoli | Approved | 0 | 0 | 2024-10-03
MEHANDWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745007014/IF/22012035628976 — EK BAGIYA MAA KE NAM HIT MEENA GRAM SARSDOLI | Ongoing | 194111.67 | 7639.92 | 2025-10-12
MEHANDWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745007014/IF/22012035629183 — EK BAGIYA MAA KE NAAM HIT YMUNA BAI SAHU GRAM SARASDOLI | Ongoing | 194111.67 | 7339.95 | 2025-10-12
MEHANDWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745007014/IF/22012035629602 — EK BAGIYA MAA KE NAM NARBADIYA BAI/THAGGU PRASHAD SAHU GRAM SARSDOLI | Ongoing | 194111.67 | 10860.12 | 2025-10-15
MEHANDWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745007014/IF/22012035629713 — EK BAGIYA MAA KE NAM ANUSUIYA BAI/JEHAR GRAM SARSDOLI | Ongoing | 194111.67 | 1044 | 2025-10-16
MEHANDWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745007014/IF/22012035633751 — Eak bagiaya maa ke nam hit sangeeta bai gram sarasdoli | Ongoing | 194112.99 | 7298 | 2025-10-24
MEHANDWANI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745007014/IF/IAY/124042 — Construction of IAY House -IAY REG. NO. MP-45-007-014-001/7206 | Approved | 28500 | 0 | 2016-01-28
MEHANDWANI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745007014/IF/IAY/1984964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2588561 | Approved | 28500 | 0 | 2019-06-14
MEHANDWANI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745007014/IF/IAY/2091195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3976979 | Approved | 28500 | 0 | 2019-06-14
MEHANDWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745007014/IF/IAY/2622952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5437191 | Completed | 24795 | 0 | 2021-01-28 | 2026-08-11
MEHANDWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745007014/IF/IAY/5826123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781874 | Approved | 28500 | 0 | 2025-02-25
MEHANDWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745007014/IF/IAY/784808 — Construction of IAY House -IAY REG. NO. MP1462410 | Approved | 28500 | 0 | 2017-04-07
MEHANDWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1745007014/RC/22012034838546 — Gravel Road Nirman Karya Koor Tola Se Bahra Talab Tak Sarasdoli | Approved | 0 | 0 | 2025-01-27
MEHANDWANI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745007014/WC/22012034572380 — CHEK DEAM NERMAN KARYA MARGHTAN NALA DARIVETOOLA ME | Ongoing | 1382563.33 | 0 | 2020-08-27
MEHANDWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1745007014/WC/22012035090820 — NALA VESATARIKARAN KARAY SHUNHA PTAPAR NALA SARASDOLI ME | Ongoing | 636511.64 | 0 | 2023-08-07
MEHANDWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1745007014/WC/22012035097511 — VERKCHA ROOPAN KARYA VASHUDHA VANDAN KE THAT PANCHAYAT BHAVAN KE PAS TALAB SARASDOLI ME | Ongoing | 84852 | 0 | 2023-08-14
MEHANDWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745007014/WC/22012035296509 — J G S A Rain Water Harvesting Kary Panchayat Bhavan Sarasdoli me | Approved | 0 | 0 | 2025-04-14
MEHANDWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745007014/WC/VB/22012035329912 — stregard trench rajgadi pahadi sarasdoli | Ongoing | 924619.49 | 77403.58 | 2026-08-03
MEHANDWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745007014/WC/VB/22012035330767 — Contour trench jalda pahadi sarasdoli | Ongoing | 997652.49 | 70590.57 | 2026-08-05
MEHANDWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745007014/WC/VB/22012035332059 — Staggered trench nirman karya koor tola pahadi part 01 | Ongoing | 997652.49 | 58690.76 | 2026-08-07
MEHANDWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745007014/WC/VB/22012035332254 — stregard trench rajgadi pahadi bhag 2 sarasdoli | Ongoing | 997652.49 | 53624.79 | 2026-08-10