## Work List
Exported on: 2026-10-16 20:19:42
Filters applied:
Data source: VBGRAMG
District: ANUPPUR
Block: All
Panchayat: BELIYA BADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ANUPPUR | 2022-2023 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of Workshed for SHG for Community | Construction of building/workshed for SHG | 1746002008/AV/22012034575061 — सेग्रिगेसन सेड निर्माण बेलियाबाड़ी( SLWM) | Ongoing | 597931.81 | 0 | 2022-05-02
ANUPPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1746002008/AV/22012034663857 — khel maidan EGS school jarhatola beliyabadi ke pass | Approved | 656237.3 | 0 | 2025-01-26
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034617821 — kaIttal sed nirman ramakant pandey /puran ram pandey | Ongoing | 101804.91 | 0 | 2021-04-14
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034617863 — kaittal sed nirman kusum jogi / ramsajeevan | Ongoing | 101804.91 | 0 | 2021-04-16
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034617864 — kaittal sed nirman sukhani /magal kol | Ongoing | 101804.91 | 0 | 2021-03-12
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034617872 — kaittal sed lalji raidas / chhohaiya | Ongoing | 101804.91 | 0 | 2021-03-12
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034617887 — kaittal sed nirman beena pandey /balram prsad | Ongoing | 101804.91 | 0 | 2021-12-06
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034635866 — cattle sheltee nirman kunilal/gallu goji | Ongoing | 101804.91 | 0 | 2021-09-13
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034635871 — cattle sheltee nirman bablu kol/dindayal | Ongoing | 101804.91 | 0 | 2021-03-12
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034635884 — cattle sheltee nirman ramnivas kushwava | Ongoing | 101804.91 | 0 | 2021-03-12
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034635887 — cattle sheltee nirman chitrwati ramesh kewat | Ongoing | 101804.91 | 0 | 2021-06-03
ANUPPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034636305 — cattle sheltee nirman hetlal late dadu sahu | Ongoing | 102033.26 | 0 | 2022-05-27
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034638052 — cattle sheltee nirman ramnathkol/sampat kol | Ongoing | 101804.91 | 0 | 2021-03-12
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034647808 — cattle sheltee nirman dhiraj kumar/krishna avatar | Ongoing | 101804.91 | 0 | 2021-03-20
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034647813 — cattle sheltee nirman om prakash/dadnram | Ongoing | 101804.91 | 0 | 2021-03-13
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034664324 — cattle sheltee nirman shiv prasad/gangu kol | Ongoing | 101804.91 | 0 | 2021-09-13
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034666799 — cattle sheltee nirman mira devi/krishna ambika | Ongoing | 102033.26 | 0 | 2021-08-12
ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746002008/IF/22012034666801 — cattle sheltee nirman sanjay/ramsakha mishra | Ongoing | 101804.91 | 0 | 2021-04-18
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035268032 — khet talab nirman kar | New | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035268038 — Khet talab nirman lashmi kant mishra /beni prasad | New | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035274284 — khet talab nirman kar govind shing/ chotelal | Approved | 384434.93 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035274291 — khet talab nirman kar loknath shing/ ram singh | New | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035275825 — khet talab nirman kar Ramkishor mishra/ mahavali | New | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035275826 — khet talab nirman kar Ramkishor mishra/ mahavali | Approved | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035292716 — khet talab nirman kar jitendra kumar mishra/ hanuman mishra | Approved | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035293154 — khet talab nirman kar devendra mishra/ hanuman | Approved | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035293559 — khet talab nirman kar susheel kumar pandey/ chandrabhushan | New | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035293565 — khet talab nirman kar susheel kumar pandey/ chandrabhushan | Approved | 0 | 0 | 2024-10-02
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035293579 — khet talab nirman kar somvati mishra/ ramcharan | Approved | 0 | 0 | 2024-10-02
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035320202 — khet talab nirman kar sushila bai/ ramshin | New | 0 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035320453 — khet talab nirman kar devendra mishra/hanuman | New | 0 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1746002008/IF/22012035404457 — kapildhara koop nirman kary shiv prasad prajapati/ amardeen | Approved | 0 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1746002008/IF/22012035404665 — kapildhara koop nirman kary jalebiya yadav / bheemsen yadav | Approved | 0 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746002008/IF/22012035461676 — khet talab nirman kar debendra mishra/ hanuman | Approved | 188102.07 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1746002008/IF/22012035477884 — kapildhara koop nirman kary yadbendra prajapati/ jailal | Approved | 0 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1746002008/IF/22012035477922 — kapildhara koop nirman kary babbu kol / bhookhan kol | Approved | 0 | 0 | 2025-04-01
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1746002008/IF/22012035557914 — kapildhara koop nirman kary manoj kumar yadav / bheemsen yadav | Approved | 0 | 0 | 2025-04-14
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1746002008/IF/22012035617390 — EK BAGIYA MAA KE NAAM HITGRAHI GUDIYA KOL / BABBU KOL | Ongoing | 193536.55 | 5950 | 2025-09-17
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/2354409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4085504 | Ongoing | 28500 | 0 | 2020-06-17
ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/3190340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4084327 | Approved | 28500 | 0 | 2020-12-10
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/4563122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116251810 | Ongoing | 28500 | 0 | 2025-04-22
ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/4997855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116251756 | Physically Completed | 28500 | 0 | 2025-04-22 | 2026-09-25
ANUPPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/5874070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151933322 | Ongoing | 28500 | 0 | 2026-05-16
ANUPPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/5876917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116251795 | Approved | 28500 | 0 | 2025-02-27
ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/80047 — Construction of IAY House -IAY REG. NO. MP-46-002-008-001/36 | Approved | 28500 | 0 | 2016-01-07
ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/80048 — Construction of IAY House -IAY REG. NO. MP-46-002-008-001/42 | Approved | 28500 | 0 | 2016-01-07
ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/80049 — Construction of IAY House -IAY REG. NO. MP-46-002-008-001/55 | Approved | 28500 | 0 | 2016-01-07
ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/80050 — Construction of IAY House -IAY REG. NO. MP-46-002-008-001/57 | Approved | 28500 | 0 | 2016-01-07
ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/80051 — Construction of IAY House -IAY REG. NO. MP-46-002-008-001/8 | Approved | 28500 | 0 | 2016-01-07
ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1746002008/IF/IAY/80052 — Construction of IAY House -IAY REG. NO. MP-46-002-008-001/81 | Approved | 28500 | 0 | 2016-01-07
ANUPPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1746002008/WC/22012034687407 — check dam nirman mundamada nalame ramsingh ke khet ke pas | Ongoing | 1469813.52 | 0 | 2021-09-13