## Work List
Exported on: 2026-10-27 07:51:27
Filters applied:
Data source: VBGRAMG
District: BURHANPUR
Block: All
Panchayat: AMULLAKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHAKNAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1747008003/IF/22012035086780 — हितेषी कपिल धारा( राजकुमार नारायण केखेत में)GP AMULLAKALA | Ongoing | 282417.57 | 0 | 2023-06-04
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035291568 — खेत तालाब निर्माण कार्य बिलु बाई ओंकार के खेत में | Approved | 223614.18 | 0 | 2025-01-01
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035293867 — खेत तालाब बुला नानू के खेत में ग्राम पंचायत अमुल्लाकला | Approved | 130779.94 | 0 | 2024-10-02
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035293870 — खेत तालाब रामसिह मोती के खेत में ग्राम पंचायत अमुल्लाकला | Approved | 130779.94 | 0 | 2024-10-02
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035350059 — FROM POND RADELAL KE KHET ME | Approved | 149088.48 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035350061 — FROM POND SONAY BAI KE KHET ME | Approved | 149088.48 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035408633 — FROM POND BULAI BAI KE KHET ME | Approved | 149088.48 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035415418 — FROM POND BILU BAI KE KHET ME | New | 0 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035470181 — Farm Pond Nanakram ke khet me GP Amullakala | Approved | 149088.48 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008003/IF/22012035470266 — JAL GANGA SANRAKSHAN ABHIYAN ANTARGAT KUP RICHARGE PIT SHANTI BAI KE KHET ME | Approved | 25899.46 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008003/IF/22012035470312 — Farm Pond Nandlal ke khet me GP Amullakala | Approved | 149088.48 | 0 | 2025-04-15
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008003/IF/22012035535475 — JAL GANGA SANRAKSHAN ABHIYAN ANTARGAT KUP RICHARGE PIT RAMSINGH MOTIRAM KE KHET ME | Approved | 25899.46 | 0 | 2025-04-16
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008003/IF/22012035547217 — JGSA richarge 2025 structure Sabulal gangaram k khet me | Approved | 0 | 0 | 2025-04-16
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008003/IF/22012035547319 — JAL GANGA SAMVARDHA DAGWELL RICHARCH RADELAL NANU KE KHET ME | Approved | 0 | 0 | 2025-04-16
KHAKNAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/111370 — Construction of IAY House -IAY REG. NO. MP-47-008-003-001/107 | Approved | 27000 | 0 | 2015-10-21
KHAKNAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/111371 — Construction of IAY House -IAY REG. NO. MP-47-008-003-001/110 | Approved | 27000 | 0 | 2015-10-21
KHAKNAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/111372 — Construction of IAY House -IAY REG. NO. MP-47-008-003-001/148 | Approved | 27000 | 0 | 2015-10-21
KHAKNAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/111373 — Construction of IAY House -IAY REG. NO. MP-47-008-003-001/167 | Approved | 27000 | 0 | 2015-10-21
KHAKNAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/3799747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102434722 | Ongoing | 27000 | 0 | 2022-08-27
KHAKNAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/3800933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100917911 | Approved | 27000 | 0 | 2022-05-02
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/4934635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102402232 | Ongoing | 27000 | 0 | 2025-08-29
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/4934691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102433628 | Physically Completed | 27000 | 1800 | 2025-05-02 | 2026-09-29
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/4936900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100916993 | Physically Completed | 27000 | 4500 | 2025-04-16 | 2026-09-09
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/4936912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100918165 | Physically Completed | 27000 | 9000 | 2026-01-30 | 2026-09-29
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/4936914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100918263 | Approved | 27000 | 0 | 2025-02-09
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/4936918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100918622 | Approved | 27000 | 0 | 2025-02-09
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5246448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102196300 | Physically Completed | 27000 | 0 | 2025-04-16 | 2026-10-04
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5305723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100917829 | Approved | 27000 | 0 | 2025-03-06
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5521403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102401811 | Ongoing | 27000 | 1800 | 2025-05-02
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5647376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102166467 | Approved | 27000 | 0 | 2025-02-09
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5647727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100694781 | Ongoing | 27000 | 9000 | 2026-07-02
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5682535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100698228 | Ongoing | 27000 | 0 | 2026-09-24
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008003/IF/IAY/5873383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100917835 | Approved | 27000 | 0 | 2025-02-09
KHAKNAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1747008003/RC/VB/22012034854442 — CC rods munni bai bhuriya ke ghar se sabula gangaram ghar takl ke ghar tak | New | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1747008003/RC/VB/22012034854443 — CC rods munni bai bhuriya ke ghar se sabula gangaram ghar takl ke ghar tak | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1747008003/WC/22012034522954 — CONTOUR TRECH(ASHOK NAVLSING KE KHET ME)GP AMULLAKALA | Ongoing | 169124.84 | 0 | 2020-06-22
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1747008003/WC/VB/22012035330742 — शासकीय भूमि पर हैण्डपम्प पम्प हनुमान मोहल्ला सोक पिट | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1747008003/WC/VB/22012035330751 — शासकीय भूमि पर हैण्डपम्प पम्प सोक पिट मुठवा बाबा गली | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1747008003/WC/VB/22012035330754 — शासकीय भूमि पर ट्यूवबेल सोक पिट सामुदायिक भवन के पास | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1747008003/WC/VB/22012035330756 — शासकीय भूमि पर हैण्डपम्प पम्प सोक पिट मुख्य गली | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1747008003/WC/VB/22012035331541 — Fram ponds sarkari bhumi par no .1 | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1747008003/WC/VB/22012035331543 — From pond sarkari bhumi par no.2 | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1747008003/WC/VB/22012035331546 — From pond sarkari bhumi par no.3 | Approved | 0 | 0 | 2026-04-14
KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1747008003/WC/VB/22012035331547 — From pond sarkari bhumi par no.4 | Approved | 0 | 0 | 2026-04-14