## Work List
Exported on: 2026-10-17 06:16:04
Filters applied:
Data source: VBGRAMG
District: BURHANPUR
Block: All
Panchayat: DABALI KALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHAKNAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1747008015/DP/22012034595668 — MERI MATI MERA DESH SCHOOL PARISAR KE PASS G. P. DAWALIKALA | Ongoing | 55847.4 | 0 | 2024-10-23
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008015/IF/22012035501495 — JGSA 2025 RECHARGE STRUCTURE KAPILDHARA KUP NASRIYA HARSING | Ongoing | 23999.46 | 0 | 2025-05-14
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008015/IF/22012035501569 — KHET TALAB NIRMAN NASRIYA KE KHET PAS | Ongoing | 199833.35 | 0 | 2025-05-14
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008015/IF/22012035501586 — KHET TALAB NIRMAN NAVALSING KE KHET PAS | Ongoing | 199059.17 | 0 | 2025-05-14
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1747008015/IF/22012035523438 — KHET TALAB NIRMAN RUPSING KE KHET PAS | Ongoing | 199811.22 | 0 | 2025-05-23
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008015/IF/22012035523466 — JGSA 2025 RECHARGE STRUCTURE KAPILDHARA KUP LAXMIBAI | Ongoing | 23999.46 | 0 | 2025-05-23
KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1747008015/IF/22012035557836 — JGSA 2025 RECHARGE STRUCTURE KAPILDHARA KUP THUSYA | Approved | 0 | 0 | 2025-05-29
KHAKNAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/3252030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1152299 | Approved | 27000 | 0 | 2021-07-23
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/354393 — Construction of IAY House -IAY REG. NO. MP1138978 | Approved | 27000 | 0 | 2017-01-12
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/355440 — Construction of IAY House -IAY REG. NO. MP1140984 | Approved | 27000 | 0 | 2016-12-27
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/355744 — Construction of IAY House -IAY REG. NO. MP1141429 | Approved | 27000 | 0 | 2016-12-27
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/357186 — Construction of IAY House -IAY REG. NO. MP1143889 | Approved | 27000 | 0 | 2016-12-27
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/357207 — Construction of IAY House -IAY REG. NO. MP1143941 | Approved | 27000 | 0 | 2017-01-10
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/359605 — Construction of IAY House -IAY REG. NO. MP1148119 | Approved | 27000 | 0 | 2016-12-27
KHAKNAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4262794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100878365 | Approved | 27000 | 0 | 2022-06-11
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4531578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100623320 | Physically Completed | 23490 | 0 | 2024-11-23 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4533389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100867649 | Physically Completed | 23490 | 0 | 2024-12-25 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4533407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100870644 | Physically Completed | 23490 | 0 | 2024-11-04 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4533409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871013 | Physically Completed | 23490 | 0 | 2025-01-02 | 2026-08-12
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4549005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106418721 | Ongoing | 27000 | 3600 | 2026-07-07
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4684385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100867883 | Physically Completed | 23490 | 0 | 2024-11-23 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4684578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622396 | Physically Completed | 23490 | 0 | 2024-11-23 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4686712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105834441 | Physically Completed | 23490 | 0 | 2024-11-04 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4689629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106420066 | Approved | 27000 | 0 | 2024-09-18
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4700686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105834264 | Physically Completed | 23490 | 0 | 2025-05-29 | 2026-08-09
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4817422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622598 | Physically Completed | 23490 | 0 | 2024-11-16 | 2026-08-12
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4817424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622909 | Physically Completed | 23490 | 0 | 2025-06-26 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4817425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622970 | Physically Completed | 23490 | 0 | 2025-02-01 | 2026-08-12
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4934241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871759 | Physically Completed | 23490 | 0 | 2025-06-26 | 2026-08-12
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4938074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106419137 | Approved | 27000 | 0 | 2025-02-22
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4986890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100621819 | Physically Completed | 23490 | 0 | 2025-05-09 | 2026-08-12
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4986891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622157 | Ongoing | 27000 | 0 | 2025-05-09
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4989446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106421875 | Ongoing | 27000 | 0 | 2025-05-09
KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/4989448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106423515 | Approved | 27000 | 0 | 2025-02-21
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5599605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106668892 | Ongoing | 27000 | 0 | 2025-05-09
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5599614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871236 | Physically Completed | 23490 | 0 | 2025-05-09 | 2026-08-12
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5599632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622198 | Ongoing | 27000 | 0 | 2025-05-09
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5599750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100621503 | Ongoing | 27000 | 5400 | 2025-05-09
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5599886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105349821 | Ongoing | 27000 | 0 | 2025-09-08
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5656455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106424700 | Ongoing | 27000 | 8100 | 2026-08-04
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5656458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100621643 | Approved | 27000 | 0 | 2025-05-01
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5656459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100622029 | Ongoing | 27000 | 900 | 2026-04-18
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5656694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106424845 | Ongoing | 27000 | 300 | 2026-08-04
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5670930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871331 | Approved | 27000 | 0 | 2025-05-24
KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/5873413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106471218 | Physically Completed | 27000 | 300 | 2026-02-27 | 2026-08-30
KHAKNAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/615237 — Construction of IAY House -IAY REG. NO. MP2107481 | Approved | 27000 | 0 | 2017-02-05
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6339219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106421050 | Ongoing | 27000 | 0 | 2026-08-22
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6339317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106423363 | Approved | 27000 | 0 | 2026-06-18
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6339362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106466793 | Approved | 27000 | 0 | 2026-06-18
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6339688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106420662 | Approved | 27000 | 0 | 2026-06-19
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6339899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106421500 | Approved | 27000 | 0 | 2026-06-19
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6339955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113675651 | Approved | 27000 | 0 | 2026-06-18
KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/6340000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100621319 | Ongoing | 27000 | 0 | 2026-09-05
KHAKNAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1747008015/IF/IAY/900298 — Construction of IAY House -IAY REG. NO. MP2141046 | Approved | 27000 | 0 | 2017-04-04
KHAKNAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1747008015/LD/22012034942760 — warchha ropan karay aaganwadi panchayat parisar dawali kala | Approved | 196215.59 | 0 | 2024-06-14
KHAKNAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Medicinal Trees for Community | Plantation | 1747008015/WC/22012035109661 — faram ponad nirman nirman g.p.dawali kala | Ongoing | 385261.22 | 0 | 2024-03-16