## Work List
Exported on: 2026-10-12 10:02:46
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: HAIDAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748001082/IF/22012035492284 — koop nirman vandana/rakesh haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748001082/IF/22012035521910 — khet talab nirman piragbai ke khet me haider | New | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748001082/IF/22012035662290 — Keith Talab Nirman Dileep Ke Khet Ke paas | New | 0 | 0 | 2025-12-26
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/1530039 — Construction of IAY House -IAY REG. NO. MP1214099 | Ongoing | 27000 | 7200 | 2025-12-18
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4096769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129568291 | Ongoing | 27000 | 0 | 2024-12-28
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4539399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103591289 | Ongoing | 27000 | 0 | 2025-01-10
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4539428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103600228 | Ongoing | 27000 | 3600 | 2025-02-01
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4539433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103600468 | Ongoing | 27000 | 0 | 2025-01-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4539669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235156 | Ongoing | 27000 | 0 | 2025-08-28
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4539670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235499 | Ongoing | 27000 | 0 | 2025-02-15
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4550247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113461476 | Ongoing | 27000 | 3600 | 2025-01-10
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4638669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131486797 | Ongoing | 27000 | 0 | 2024-12-28
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4651530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146064424 | Ongoing | 27000 | 7200 | 2025-03-10
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4658957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146950009 | Ongoing | 27000 | 0 | 2024-11-19
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4666315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150640355 | Ongoing | 27000 | 0 | 2024-12-29
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4668186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149131788 | Ongoing | 27000 | 0 | 2024-12-29
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4817306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235031 | Ongoing | 27000 | 0 | 2024-12-28
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4817307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235603 | Ongoing | 27000 | 3600 | 2025-01-10
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4817588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103600720 | Ongoing | 27000 | 0 | 2025-02-19
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4818831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113691255 | Ongoing | 27000 | 14400 | 2024-12-28
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4818843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113700793 | Ongoing | 27000 | 0 | 2025-02-19
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/4832899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147155616 | Ongoing | 27000 | 0 | 2025-02-19
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5456026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131875620 | Ongoing | 27000 | 3600 | 2025-04-29
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5456385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103601738 | Completed | 23490 | 0 | 2025-04-29 | 2026-09-02
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5516468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149260972 | Ongoing | 27000 | 0 | 2025-04-29
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5664244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152072370 | Ongoing | 27000 | 18600 | 2025-08-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5664245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152072371 | Ongoing | 27000 | 0 | 2025-08-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103591623 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113508711 | Ongoing | 27000 | 0 | 2025-12-27
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235756 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103588936 | Physically Completed | 23490 | 0 | 2025-12-28 | 2026-08-09
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113525120 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113458618 | Ongoing | 27000 | 10800 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235438 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103588672 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235075 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146596943 | Ongoing | 27000 | 0 | 2025-12-27
ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147148779 | Ongoing | 27000 | 0 | 2026-05-05
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5867990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113484790 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103592946 | Completed | 23490 | 0 | 2025-12-28 | 2026-09-02
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113514645 | Ongoing | 27000 | 16200 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149744072 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495824 | Completed | 23490 | 0 | 2025-12-27 | 2026-09-02
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146839189 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103602858 | Physically Completed | 23490 | 0 | 2025-12-27 | 2026-08-16
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103588421 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131156572 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146628675 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103599305 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113450055 | Ongoing | 27000 | 18000 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103598695 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113521562 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103583160 | Completed | 23490 | 0 | 2025-12-27 | 2026-09-02
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149738199 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144673732 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130454262 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107186933 | Ongoing | 27000 | 0 | 2025-12-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235369 | Ongoing | 27000 | 0 | 2025-12-31
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/5868645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103602375 | Completed | 23490 | 0 | 2025-12-27 | 2026-09-02
ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6192867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103595071 | Ongoing | 27000 | 0 | 2026-05-05
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6325696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146632379 | Approved | 27000 | 0 | 2026-03-23
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6325830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113903071 | Approved | 27000 | 0 | 2026-03-24
ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6325836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103592639 | Approved | 27000 | 0 | 2026-04-28
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6325893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103591980 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113774684 | Approved | 27000 | 0 | 2026-03-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149260350 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103601437 | Approved | 27000 | 0 | 2026-03-23
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103593412 | Approved | 27000 | 0 | 2026-03-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113840790 | Approved | 27000 | 0 | 2026-03-23
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113635474 | Approved | 27000 | 0 | 2026-03-23
ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130428123 | Approved | 27000 | 0 | 2026-04-16
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6326542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105414510 | Approved | 27000 | 0 | 2026-03-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103600422 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148578836 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145440395 | Approved | 27000 | 0 | 2025-03-03
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149228870 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146860743 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149146821 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103595365 | Approved | 27000 | 0 | 2025-02-16
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149732466 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146863928 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103582178 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132338477 | Approved | 27000 | 0 | 2025-03-03
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131486873 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131486773 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103600022 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129944980 | Approved | 27000 | 0 | 2025-03-03
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147147185 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148993776 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129941184 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103419317 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147143183 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148962454 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129888454 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130442828 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113663952 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149129102 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131159078 | Approved | 27000 | 0 | 2025-03-03
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113545865 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146866633 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103582547 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146103731 | Approved | 27000 | 0 | 2025-02-16
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129566979 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146073020 | Approved | 27000 | 0 | 2025-03-01
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147161900 | Approved | 27000 | 0 | 2025-03-01
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146945842 | Approved | 27000 | 0 | 2025-03-17
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103599151 | Approved | 27000 | 0 | 2025-05-13
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113709179 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113500019 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131486789 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103599361 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129590541 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146078896 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147376591 | Approved | 27000 | 0 | 2025-02-20
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105235409 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146832605 | Approved | 27000 | 0 | 2025-02-20
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113708182 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146613688 | Approved | 27000 | 0 | 2025-03-01
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146640842 | Approved | 27000 | 0 | 2025-03-03
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148959975 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148517409 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113654670 | Approved | 27000 | 0 | 2025-02-24
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131486782 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6341525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113668395 | Approved | 27000 | 0 | 2025-02-21
ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6368244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147363318 | Approved | 27000 | 0 | 2026-06-26
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6374689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113845927 | Approved | 27000 | 0 | 2026-03-24
ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001082/IF/IAY/6374752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129566861 | Approved | 27000 | 0 | 2026-03-21
ISAGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748001082/RC/22012034848587 — CC sadak Main Road se Sheel kumar ke ghar ki or gram Haider | Approved | 74000 | 0 | 2025-04-14
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035211999 — Community Khet talab Nirman pathar par goushala ke pas | Approved | 0 | 0 | 2024-04-01
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1748001082/WC/22012035212003 — Samudayik koop nirman banjarya | Approved | 0 | 0 | 2024-04-01
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035212818 — community khet talab Nirman Pathar Par | New | 0 | 0 | 2024-06-10
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035228505 — samudayik khet talab nirman pathar par 3 | Approved | 0 | 0 | 2024-10-02
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035228518 — samudayik khet talab nirman parwati ke khet ke pass | Approved | 0 | 0 | 2024-10-02
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035247600 — samudayik khet talab nirman barkhwan ke khet ke pass | Approved | 0 | 0 | 2025-01-26
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035247602 — samudayik khet talab nirman pathar par amarsingh ke khet ke pass | Approved | 0 | 0 | 2025-01-26
ISAGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035254748 — Percolation tank pathar pr goti ke khere ke paas Haider | Approved | 0 | 0 | 2025-01-24
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035281954 — Percolation tank pathar per 1 Haider | New | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035285735 — Community Ponds Nirman Pathar per 3 Haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035285745 — Community Ponds Nirman Pathar per number 4 Haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035285759 — Percolation tank pathar pr numbr 3 Haidar | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035306435 — Community Ponds Nirman Pathar per Arvind ke khere ke paas Haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035306440 — Community Ponds Nirman Pathar per purani taliya ke khere ke paas Haider | New | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035306442 — Community Ponds Nirman Pathar per purani taliya ke khere ke paas Haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035306443 — Community Ponds Nirman Pathar per purani taliya ke paas Haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748001082/WC/22012035306446 — Community Ponds Nirman Pathar per purani taliya ke khere ke paas Haider | Approved | 0 | 0 | 2025-04-14
ISAGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1748001082/WC/22012035319865 — Check Dam Nirman Nale par gram Haider | Approved | 95000 | 0 | 2025-04-14