## Work List
Exported on: 2026-10-07 12:44:15
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: SIRSOD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHANDERI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1748002047/DP/22012034434291 — Brakchhropan nirman kary soodur sadk ke kinare gram sirsod | Ongoing | 342000 | 0 | 2018-12-23
CHANDERI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/2606172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1665490 | Ongoing | 27000 | 0 | 2021-05-06
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/3232374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1163833 | Ongoing | 27000 | 0 | 2025-02-21
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/3238276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1170307 | Ongoing | 27000 | 0 | 2025-02-13
CHANDERI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/3673127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102197442 | Ongoing | 27000 | 0 | 2022-07-19
CHANDERI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/3708239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100931283 | Ongoing | 27000 | 0 | 2022-09-15
CHANDERI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4336924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103435217 | Ongoing | 27000 | 0 | 2023-12-27
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4542450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105872675 | Ongoing | 27000 | 0 | 2025-01-29
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4988333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105579531 | Ongoing | 27000 | 0 | 2025-05-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4988337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105581610 | Ongoing | 27000 | 0 | 2025-05-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4988338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105581647 | Ongoing | 27000 | 0 | 2025-05-20
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4988342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105583082 | Ongoing | 27000 | 3600 | 2025-04-07
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4990544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105872625 | Ongoing | 27000 | 0 | 2025-05-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4990558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105877031 | Ongoing | 27000 | 7200 | 2025-04-07
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4990561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105878322 | Ongoing | 27000 | 7200 | 2025-04-07
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4995143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105689215 | Ongoing | 27000 | 0 | 2025-05-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/4995144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105691415 | Ongoing | 27000 | 0 | 2025-05-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5110783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020539 | Ongoing | 27000 | 0 | 2025-05-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5606373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105876918 | Ongoing | 27000 | 0 | 2025-05-20
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010496 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023512 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152004460 | Ongoing | 27000 | 7200 | 2025-06-24
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152004461 | Physically Completed | 27000 | 7200 | 2025-08-31 | 2026-09-06
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020533 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020541 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152021556 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152011047 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010828 | Ongoing | 27000 | 3600 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5666196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117759584 | Ongoing | 27000 | 0 | 2025-08-31
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5674898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152027313 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5674965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023148 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023112 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023180 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023508 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023510 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023516 | Physically Completed | 23490 | 0 | 2025-10-30 | 2026-07-05
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020525 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5675279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020529 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5687847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152027326 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5687926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152027375 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5719390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152004463 | Ongoing | 27000 | 14400 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026332 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013246 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013255 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152016122 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152016123 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152016129 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026313 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013229 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013236 | Ongoing | 27000 | 10800 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026361 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5776733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026372 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023511 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152021557 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152021560 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152027440 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152016124 | Ongoing | 27000 | 10800 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152027247 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023209 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/5803418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152027420 | Ongoing | 27000 | 0 | 2025-10-30
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6176500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105883672 | Approved | 27000 | 0 | 2026-03-22
CHANDERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6177203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105872231 | Ongoing | 27000 | 0 | 2026-09-25
CHANDERI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6178591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105691436 | Ongoing | 27000 | 7200 | 2026-07-13
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6246234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103438514 | Approved | 27000 | 0 | 2026-03-23
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6247211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105691391 | Approved | 27000 | 0 | 2025-02-19
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6247782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105880296 | Approved | 27000 | 0 | 2026-03-23
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6302237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105888179 | Approved | 27000 | 0 | 2024-09-12
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6303933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105890515 | Approved | 27000 | 0 | 2026-03-23
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6306050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105891319 | Approved | 27000 | 0 | 2026-03-23
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6317541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152016132 | Approved | 27000 | 0 | 2025-01-20
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6317981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023514 | Approved | 27000 | 0 | 2025-01-29
CHANDERI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6387048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105886166 | Approved | 27000 | 0 | 2026-03-22
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6394843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105582282 | Approved | 27000 | 0 | 2025-02-04
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6395047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105582890 | Approved | 27000 | 0 | 2025-02-04
CHANDERI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748002047/IF/IAY/6395633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117759649 | Approved | 27000 | 0 | 2025-02-04
CHANDERI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748002047/RC/22012034543326 — CC road nirman kary dehro hendpamp se gangaram yadav ke makan tak gram sirsod | Ongoing | 124313 | 0 | 2021-06-08
CHANDERI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748002047/RC/22012034843104 — CC road nirman kary Hanuman ji mandir se Sujan singh ke ghar tak Gp sirsod | Ongoing | 42799 | 0 | 2026-03-19
CHANDERI | 2016-2017 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1748002047/SK/9993648380 — Bharat Nirman Rajeev Gandhi Sewa Kendra,SIRSOD | Ongoing | 1285000 | 0 | 2016-11-03