## Work List
Exported on: 2026-10-11 07:41:33
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: GARROLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOKNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005033/AV/22012034666859 — Shantidham nirman karya gram Nandnai | Ongoing | 237790.04 | 0 | 2026-01-13
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005033/IF/22012035438587 — Kapildhara Kup Danveer Singh Yadav S/o Bharat Singh | Ongoing | 322434.5 | 0 | 2025-05-23
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005033/IF/22012035540462 — Khet Talab Ramkrishan Yadav s/o Kalyan Singh Gram Garroli | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005033/IF/22012035556080 — Koop nirman karya Parvat singh / Majboot singh | Ongoing | 322434.5 | 0 | 2025-06-20
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/119470 — Construction of IAY House -IAY REG. NO. MP-48-005-033-001/12 | Approved | 27000 | 0 | 2016-01-22
ASHOKNAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/2168748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5747556 | Approved | 27000 | 0 | 2019-06-12
ASHOKNAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/2168749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5747615 | Approved | 27000 | 0 | 2019-06-12
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/3711870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114844632 | Ongoing | 27000 | 0 | 2022-08-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/4560721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114853063 | Ongoing | 27000 | 8400 | 2024-10-03
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/4693654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114847567 | Ongoing | 27000 | 0 | 2024-10-15
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/4693697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114867432 | Ongoing | 27000 | 0 | 2024-10-15
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/4993743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114728784 | Ongoing | 27000 | 0 | 2025-03-22
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/4995789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114841747 | Ongoing | 27000 | 0 | 2025-03-22
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/4998610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114845710 | Ongoing | 27000 | 0 | 2025-03-22
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/5000113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117588147 | Ongoing | 27000 | 0 | 2025-03-22
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6176462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116530704 | Ongoing | 27000 | 22800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6176609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114845454 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6176644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114729096 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6176796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106478510 | Ongoing | 27000 | 12000 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6177516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114861447 | Physically Completed | 23490 | 13500 | 2026-04-21 | 2026-08-09
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6180059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107017408 | Ongoing | 27000 | 13800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6181095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107017908 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6181597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114727319 | Physically Completed | 23490 | 13800 | 2026-04-21 | 2026-08-23
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6181671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114845175 | Ongoing | 27000 | 0 | 2026-05-05
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6181963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117638636 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6182025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114729568 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6182103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116045298 | Physically Completed | 23490 | 4500 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6187062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114849197 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6187375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114868089 | Ongoing | 27000 | 22800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6187907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114704691 | Physically Completed | 23490 | 3600 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6188144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117637183 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6188450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117635528 | Physically Completed | 27000 | 16200 | 2026-05-05 | 2026-09-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6189853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116214698 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6189974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114851611 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6190415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114844317 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6191008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114848407 | Physically Completed | 23490 | 7200 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6191961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114867594 | Physically Completed | 23490 | 13800 | 2026-04-21 | 2026-08-23
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6192097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116842704 | Physically Completed | 23490 | 5400 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6192408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114847994 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6192762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114865222 | Ongoing | 27000 | 22800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6193765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114867102 | Physically Completed | 27000 | 21300 | 2026-04-21 | 2026-09-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6194248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114866881 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6194736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107016539 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6195047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114866028 | Physically Completed | 27000 | 0 | 2026-04-21 | 2026-09-07
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6195049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114849307 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6195405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117588230 | Ongoing | 27000 | 16200 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6196283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114727715 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6196930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114851361 | Completed | 27000 | 22800 | 2026-04-21 | 2026-09-28
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6197314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114705019 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6197646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114844427 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6197992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114844154 | Physically Completed | 23490 | 10500 | 2026-04-21 | 2026-08-23
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6198505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114865858 | Ongoing | 27000 | 7200 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6198716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114728341 | Physically Completed | 27000 | 10500 | 2026-04-21 | 2026-09-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6198851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114862894 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6199199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117636841 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6199962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113457154 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6200139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114861775 | Ongoing | 27000 | 22800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6200198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120550865 | Ongoing | 27000 | 0 | 2026-04-22
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6201475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114867050 | Ongoing | 27000 | 3600 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6202428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107016832 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6204840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117588188 | Ongoing | 27000 | 16500 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6205471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114843987 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6206472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114727561 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6206721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116522659 | Physically Completed | 23490 | 1200 | 2026-04-21 | 2026-07-19
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6206844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116214726 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6206977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114857185 | Ongoing | 27000 | 22800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6207034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117636731 | Ongoing | 27000 | 14400 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6207189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114728949 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6207229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107017066 | Ongoing | 27000 | 14400 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6207632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114845581 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6207833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117589645 | Ongoing | 27000 | 9000 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6209068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113952512 | Ongoing | 27000 | 19800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6210652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116843322 | Completed | 27000 | 21300 | 2026-04-21 | 2026-09-28
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6211051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126757138 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6211730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116522380 | Physically Completed | 23490 | 9900 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6212198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117588569 | Ongoing | 27000 | 0 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6212640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114863599 | Ongoing | 27000 | 13800 | 2026-04-21
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6213029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114704809 | Approved | 27000 | 0 | 2026-02-13
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6213160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114837358 | Ongoing | 27000 | 13500 | 2026-05-05
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6213367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114843113 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6213653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116522816 | Physically Completed | 23490 | 7200 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6214883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114848845 | Physically Completed | 23490 | 6000 | 2026-04-21 | 2026-07-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6215390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114861701 | Physically Completed | 27000 | 10500 | 2026-04-21 | 2026-09-13
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6215710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114864022 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6215845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144592217 | Ongoing | 27000 | 21300 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6216703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117636590 | Physically Completed | 23490 | 9000 | 2026-04-21 | 2026-08-09
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6216787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114863407 | Physically Completed | 23490 | 7200 | 2026-04-21 | 2026-08-02
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6217452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114843344 | Ongoing | 27000 | 1800 | 2026-04-21
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6308685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114730864 | Ongoing | 27000 | 0 | 2026-10-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6308688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114846935 | Ongoing | 27000 | 0 | 2026-10-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005033/IF/IAY/6310061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114843694 | Ongoing | 27000 | 0 | 2026-10-08
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1748005033/WC/22012035327470 — Pecolation Tank Tanke ke Pas Garroli | Approved | 0 | 0 | 2026-01-26