## Work List
Exported on: 2026-10-21 14:20:33
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: RIJODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOKNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005034/AV/22012034657623 — Shantidham nirman gram rijoda | New | 0 | 0 | 2024-06-11
ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1748005034/IF/22012035225081 — Khet talab Shriram/ gangaram | Ongoing | 282445.46 | 0 | 2024-12-26
ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1748005034/IF/22012035251761 — Braksharopan Nirman Karya Mohan Singh / Diman Singh | Approved | 0 | 0 | 2024-06-12
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005034/IF/22012035295254 — Hitesi Koop Nirman karya Lallu/Harnam Singh | Ongoing | 312155.12 | 0 | 2025-05-25
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005034/IF/22012035296150 — Koop Nirman karya Rajendra/lalsahab | Ongoing | 312155.12 | 0 | 2025-07-05
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005034/IF/22012035296151 — Koop Nirman karya Amarjeet/raghuraj singh | Ongoing | 312155.12 | 0 | 2025-05-04
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035296157 — Khet Talab Nirman karya veersingh/sultan singh | Approved | 281159.94 | 0 | 2025-01-24
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035473878 — Khet talab nirman karya Varsha ke khet mein | Ongoing | 199718.64 | 0 | 2026-03-19
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035565414 — Khet talab nirman karya indar singh / daloop singh | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035565416 — Khet talab nirman karya Gajram / hartum singh | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035565421 — Khet talab Nirman karya Jitendra kumar / Ramsingh | Ongoing | 199718.64 | 0 | 2026-03-22
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035565427 — Khet talab nirman karya sisupal singh / Nathan singh | Ongoing | 199718.64 | 0 | 2026-03-19
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035565430 — Khet talab nirman karya gajendra singh / sultan singh | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035651367 — Khet talab niraman karya khuman singh / sardar singh | Ongoing | 199718.64 | 0 | 2026-03-22
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005034/IF/22012035651368 — Khet Talab Nirman Karya Dayaram / Dalveer | Ongoing | 199718.64 | 0 | 2026-02-26
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748005034/IF/22012035652834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.121984456 | Ongoing | 23490 | 0 | 2026-06-09
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748005034/IF/22012035660046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982550 | Ongoing | 23490 | 0 | 2026-05-22
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748005034/IF/22012035660050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121987915 | Ongoing | 23490 | 0 | 2026-05-22
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/122387 — Construction of IAY House -IAY REG. NO. MP-48-005-034-001/17 | Approved | 27000 | 0 | 2016-01-27
ASHOKNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/1916258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4166420 | Approved | 27000 | 0 | 2018-07-25
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/199147 — Construction of IAY House -IAY REG. NO. MP-48-005-034-001/8 | Approved | 27000 | 0 | 2016-03-17
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/2612796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5559693 | Ongoing | 27000 | 18000 | 2026-05-22
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4077095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121978984 | Ongoing | 27000 | 0 | 2025-03-12
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4086635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125900452 | Approved | 27000 | 0 | 2022-05-17
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4137520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125896506 | Approved | 27000 | 0 | 2022-05-20
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4265039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121986457 | Ongoing | 27000 | 0 | 2025-03-12
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4823857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121986200 | Ongoing | 27000 | 0 | 2025-02-21
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4888985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121417540 | Ongoing | 27000 | 0 | 2025-02-21
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/4990355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011036 | Ongoing | 27000 | 0 | 2025-03-22
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/5001997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982575 | Physically Completed | 23490 | 0 | 2025-03-22 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/5011047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121425713 | Ongoing | 27000 | 0 | 2025-03-22
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/5690084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125056384 | Ongoing | 27000 | 0 | 2025-08-27
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6176219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116007817 | Ongoing | 27000 | 12600 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6177547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125062204 | Ongoing | 27000 | 8400 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6180797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982644 | Ongoing | 27000 | 12600 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6181932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117983318 | Ongoing | 27000 | 10500 | 2026-06-13
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6185235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117983383 | Ongoing | 27000 | 12600 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6188937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982794 | Ongoing | 27000 | 21600 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6190170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982764 | Ongoing | 27000 | 0 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6192255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982851 | Ongoing | 27000 | 8400 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6192498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121978541 | Ongoing | 27000 | 10500 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6193377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117983194 | Ongoing | 27000 | 12600 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6193716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121987159 | Physically Completed | 27000 | 24600 | 2026-05-04 | 2026-10-18
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6194520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982861 | Ongoing | 27000 | 14100 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6195287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121980227 | Ongoing | 27000 | 17700 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6195774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121827249 | Ongoing | 27000 | 24600 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6205704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117983214 | Ongoing | 27000 | 12600 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6207629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121977269 | Ongoing | 27000 | 23700 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6215795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982820 | Ongoing | 27000 | 19500 | 2026-05-04
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6255107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117983349 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6258687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121981098 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6258690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121982322 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6258694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121983901 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6259220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121979981 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6259222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121980893 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6259223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121982116 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6281476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121979489 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6287871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982803 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6367731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117982503 | Approved | 27000 | 0 | 2026-04-06
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005034/IF/IAY/6368039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121979727 | Approved | 27000 | 0 | 2026-03-16
ASHOKNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1748005034/WC/22012034715378 — khet talab nirmayn kary vijaykumar /mulaym singh | Ongoing | 292486.2 | 0 | 2021-09-23
ASHOKNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1748005034/WC/22012034766211 — kheat talab nirmayn kary ushabai /mahendra | Ongoing | 293546.14 | 0 | 2021-09-20
ASHOKNAGAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748005034/WC/22012034975878 — Khet talab sheelkumar/ramsingh | Ongoing | 282203.89 | 0 | 2022-05-26
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1748005034/WC/22012035317751 — check dem nirman karya Mahendra singh ke khet ke pas (Convergence) | Ongoing | 102000 | 0 | 2026-02-26