## Work List
Exported on: 2026-10-24 02:34:00
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: BISORE
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOKNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005077/AV/22012034668077 — Shantidham Nirman Karya Kushwah Mohalla ke pas | New | 0 | 0 | 2025-10-02
ASHOKNAGAR | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005077/AV/22012034668078 — Shantidham Nirman Karya pathar ke pas | Ongoing | 329804.8 | 0 | 2026-04-09
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1748005077/IC/22012034889606 — Samudayik koop nirman karya Baag mein | New | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1748005077/IC/22012034892993 — Sarvajanik Koop nirman karya Surai ke pas Gram Bisore | Ongoing | 605674.69 | 300 | 2026-04-09
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005077/IF/22012035315959 — Hitesi koop nirman ravindra singh ke khet mein | Approved | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005077/IF/22012035315965 — Hiteshi Koop nirman karya Pransingh/phoolsingh | Approved | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005077/IF/22012035585776 — Ek bagiya Maa ke naam GEETA BAI BALMIK | Ongoing | 178945.27 | 0 | 2025-09-02
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005077/IF/22012035585778 — Ek bagiya Maa ke naam ASHOKI BAI/KALYAN | Ongoing | 272878.63 | 0 | 2025-09-07
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005077/IF/22012035596183 — Ek Bagiya Maa Ke naam Arti Bai/Sitaram | Ongoing | 269386.03 | 0 | 2025-09-07
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005077/IF/22012035632749 — Khet talab nirman karya Pappu sapera ke khet mein | Approved | 0 | 0 | 2025-10-02
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005077/IF/22012035632782 — Khet talab nirman karya Santo Bai ke khet mein | New | 0 | 0 | 2025-10-02
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005077/IF/22012035632783 — Khet talab nirman karya Santo Bai ke khet mein | Approved | 0 | 0 | 2025-10-02
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005077/IF/22012035654635 — Khet talab nirman karya Balveer ke khet mein | Ongoing | 199164.42 | 0 | 2026-02-05
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/200918 — Construction of IAY House -IAY REG. NO. MP-48-005-077-001/15 | Approved | 27000 | 0 | 2016-03-21
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4198678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123568433 | Ongoing | 27000 | 0 | 2022-08-16
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4318846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125284053 | Ongoing | 27000 | 0 | 2022-09-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4546685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106356886 | Ongoing | 27000 | 0 | 2025-02-11
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4560761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114858289 | Ongoing | 27000 | 0 | 2024-10-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4560819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114867628 | Physically Completed | 23490 | 7200 | 2024-10-24 | 2026-08-16
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4582322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118826499 | Ongoing | 27000 | 0 | 2024-10-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4602486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123924756 | Ongoing | 27000 | 0 | 2025-02-11
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4602503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123927850 | Ongoing | 27000 | 0 | 2025-02-11
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4941246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106356904 | Ongoing | 27000 | 11100 | 2025-03-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4989855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106356863 | Physically Completed | 27000 | 0 | 2025-03-24 | 2026-09-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4989856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106356933 | Physically Completed | 23490 | 1800 | 2025-03-24 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/4989857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106356964 | Ongoing | 27000 | 5400 | 2025-03-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5005383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119939511 | Physically Completed | 23490 | 0 | 2025-03-24 | 2026-07-05
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5012846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123437071 | Physically Completed | 23490 | 0 | 2025-03-24 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5012864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123442103 | Physically Completed | 23490 | 0 | 2025-03-24 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5016933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123925556 | Ongoing | 27000 | 0 | 2025-03-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5016934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123926695 | Physically Completed | 23490 | 0 | 2025-03-24 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5016944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123934988 | Ongoing | 27000 | 9600 | 2025-03-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5018152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125532744 | Physically Completed | 23490 | 1800 | 2025-03-24 | 2026-08-02
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5114107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147727677 | Ongoing | 27000 | 12600 | 2025-03-24
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5473268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115374334 | Ongoing | 27000 | 16200 | 2025-05-04
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5473269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115374355 | Physically Completed | 23490 | 1800 | 2025-05-04 | 2026-08-10
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5475321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106937560 | Physically Completed | 23490 | 1800 | 2025-07-31 | 2026-08-02
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5475322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106937665 | Ongoing | 27000 | 0 | 2025-05-04
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005077/IF/IAY/5476365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118835804 | Ongoing | 27000 | 0 | 2025-05-04
ASHOKNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1748005077/WC/22012034558932 — Khet talab Ashok /khumna Kori | Ongoing | 332572.21 | 0 | 2020-06-11
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748005077/WC/22012035267806 — Community Khet talab nirman karya Shailendra ke khet ke pas | Approved | 292763.62 | 0 | 2025-04-01
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1748005077/WC/22012035321498 — Percolation Tank nirman kraya MAhendra sapera ke khet ke pas | Approved | 198606.9 | 0 | 2025-10-02
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1748005077/WC/22012035325727 — Percolation tank nirman karya Fardai pahadi par survey no 169 | Approved | 0 | 0 | 2025-10-02
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1748005077/WH/22012034945476 — Talab Jirnoddhar karya Patarya talab Gram Bisore | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1748005077/WH/22012034945477 — Talab Jirnoddhar karya Bhujariya talab Gram Bisore | New | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1748005077/WH/22012034945478 — Talab Jirnoddhar karya Bhujariya talab Gram Bisore | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1748005077/WH/22012034945485 — Talab jirnoddhar karya Patariya Talab Bisore | New | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1748005077/WH/22012034945486 — Talab jirnoddhar karya Patariya Talab Bisore | Ongoing | 903560.61 | 300 | 2026-03-25