## Work List
Exported on: 2026-10-05 21:57:37
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: PILI GHATA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOKNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005084/AV/22012034668447 — Shantidham nirman karya Sindh nadi ke pas pilighata | Ongoing | 295881.94 | 0 | 2026-02-05
ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1748005084/DP/22012034624343 — Braksharopan Karya Deher Pilighata | Approved | 0 | 0 | 2024-06-12
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035299734 — Khet talab nirman karya Nathan singh/kastoora | Approved | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035299735 — Khet talab nirman karya Laliya/jugta | Approved | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035299740 — Khet talab nirman karya anant singh/Prabhulal | Approved | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035299742 — Khet talab nirman karya pradeep/ramveer singh | Approved | 0 | 0 | 2025-01-24
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035454971 — Khet Talab Nirman karye Amar Singh Banjara | Approved | 351377.54 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035455144 — Khet Talab Nirman karye Kamlu prajapati | Approved | 0 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035489231 — Khet Talab Nirman Nathan Jatav ke khet par | Approved | 351377.54 | 0 | 2025-04-14
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005084/IF/22012035489419 — Khet Talab Nirman Revaram Jatav | Approved | 351665.86 | 0 | 2025-04-14
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/122424 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/14 | Physically Completed | 23490 | 0 | 2026-04-14 | 2026-08-09
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/122425 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/85 | Approved | 27000 | 0 | 2016-01-27
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/122426 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/88 | Approved | 27000 | 0 | 2016-01-27
ASHOKNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/1929153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4464257 | Ongoing | 27000 | 0 | 2018-09-28
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/200920 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/101 | Approved | 27000 | 0 | 2016-03-21
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/200921 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/43 | Approved | 27000 | 0 | 2016-03-21
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/200922 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/48 | Approved | 27000 | 0 | 2016-03-21
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/200923 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/58 | Approved | 27000 | 0 | 2016-03-21
ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/200924 — Construction of IAY House -IAY REG. NO. MP-48-005-084-002/74 | Approved | 27000 | 0 | 2016-03-21
ASHOKNAGAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/2102291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4186344 | Approved | 27000 | 0 | 2019-06-17
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4002566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846654 | Ongoing | 27000 | 0 | 2022-10-08
ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4037275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106515823 | Ongoing | 27000 | 0 | 2022-07-21
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4546983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106515764 | Ongoing | 27000 | 0 | 2025-02-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4582453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846673 | Ongoing | 27000 | 0 | 2025-02-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4608314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114680797 | Ongoing | 27000 | 0 | 2024-10-19
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4620748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126757375 | Ongoing | 27000 | 0 | 2024-10-19
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4817646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102159692 | Ongoing | 27000 | 0 | 2025-01-06
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4836619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150587724 | Physically Completed | 23490 | 0 | 2024-11-17 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4840156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018570 | Ongoing | 27000 | 0 | 2024-12-08
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4840525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020005 | Ongoing | 27000 | 0 | 2024-12-08
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4840527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020010 | Physically Completed | 23490 | 0 | 2024-12-08 | 2026-07-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4841520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152034160 | Ongoing | 27000 | 0 | 2025-02-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4888883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114680827 | Physically Completed | 27000 | 2700 | 2025-02-13 | 2026-09-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4897091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018566 | Ongoing | 27000 | 0 | 2025-02-13
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4900832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018466 | Ongoing | 27000 | 0 | 2025-02-13
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4942172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114680913 | Ongoing | 27000 | 0 | 2025-05-03
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/4989538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106515878 | Ongoing | 27000 | 0 | 2025-03-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5003618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846681 | Ongoing | 27000 | 0 | 2025-03-26
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5021647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126812088 | Physically Completed | 27000 | 3600 | 2025-03-26 | 2026-10-01
ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5083720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126837707 | Physically Completed | 27000 | 3600 | 2025-03-26 | 2026-10-01
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5391886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117727701 | Ongoing | 27000 | 0 | 2025-04-15
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5392310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126755139 | Physically Completed | 23490 | 0 | 2025-04-15 | 2026-08-02
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5402084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150706609 | Ongoing | 27000 | 0 | 2025-04-28
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5472702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114680967 | Physically Completed | 27000 | 3600 | 2025-04-28 | 2026-10-01
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5472931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102259281 | Physically Completed | 27000 | 2700 | 2025-05-03 | 2026-08-30
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5473659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148955177 | Ongoing | 27000 | 9000 | 2025-04-28
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5473926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125996790 | Ongoing | 27000 | 0 | 2025-05-03
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5475319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106933727 | Ongoing | 27000 | 0 | 2025-04-28
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5476910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126753794 | Physically Completed | 27000 | 3600 | 2025-04-28 | 2026-10-01
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5476912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126759048 | Physically Completed | 27000 | 3600 | 2025-04-28 | 2026-10-01
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5476972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126815267 | Physically Completed | 27000 | 0 | 2025-05-03 | 2026-10-01
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5478938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846664 | Ongoing | 27000 | 0 | 2025-05-03
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5482372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127474452 | Ongoing | 27000 | 3600 | 2025-04-28
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5626276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018562 | Ongoing | 27000 | 0 | 2025-07-28
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5626433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020002 | Ongoing | 27000 | 0 | 2025-06-07
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5626434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020008 | Ongoing | 27000 | 7200 | 2025-10-31
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5626435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020009 | Ongoing | 27000 | 7200 | 2025-10-31
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5627139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020011 | Physically Completed | 27000 | 10800 | 2025-06-07 | 2026-09-20
ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/5689733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106933723 | Ongoing | 27000 | 0 | 2025-08-28
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6067956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105187456 | Physically Completed | 27000 | 3600 | 2026-04-14 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6069961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113494558 | Physically Completed | 27000 | 18300 | 2026-05-11 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6072257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115121523 | Physically Completed | 27000 | 10800 | 2026-04-14 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6074719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116598283 | Ongoing | 27000 | 16200 | 2026-05-11
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6176594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103410374 | Physically Completed | 27000 | 16200 | 2026-05-02 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6176873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878930 | Ongoing | 27000 | 10800 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6182440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149147885 | Physically Completed | 27000 | 16200 | 2026-05-02 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6185869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105187429 | Physically Completed | 27000 | 18000 | 2026-05-11 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6190848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125997401 | Physically Completed | 27000 | 19800 | 2026-05-02 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6192830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117841763 | Ongoing | 27000 | 10800 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6193521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117526464 | Ongoing | 27000 | 14400 | 2026-05-02
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6197363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106933745 | Ongoing | 27000 | 3600 | 2026-05-02
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6197915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103410116 | Physically Completed | 27000 | 16200 | 2026-05-02 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6200112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117872982 | Ongoing | 27000 | 14400 | 2026-05-02
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6209886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117318545 | Ongoing | 27000 | 18000 | 2026-05-02
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6213121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144626694 | Physically Completed | 27000 | 19800 | 2026-05-02 | 2026-10-01
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6216100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106878900 | Ongoing | 27000 | 10800 | 2026-05-08
ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005084/IF/IAY/6217380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106822566 | Physically Completed | 27000 | 16200 | 2026-05-02 | 2026-10-01
ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1748005084/WH/22012034945484 — तालाब जीर्णोद्धार कार्य राधेश्याम के खेत के पास ग्राम पीलीघटा | Ongoing | 906559.17 | 489308.74 | 2026-02-23