## Work List
Exported on: 2026-10-22 00:10:15
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: BARRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MUNGAOLI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748007015/IF/22012034802838 — Kapildhara kup Nirman Ramraja Yadav | Ongoing | 247839.67 | 0 | 2022-01-31
MUNGAOLI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748007015/IF/22012034810724 — HIteshi kapil dahra kup nirman bhagban singh / mathurala | Ongoing | 250732.62 | 0 | 2022-02-23
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007015/IF/22012035235552 — Khet talab nirman kary Genda lal/Puran singh yadav | Approved | 379996.13 | 0 | 2024-06-07
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007015/IF/22012035235557 — Khet talab nirman kary Jagarnath singh/Pran singh | Approved | 379996.13 | 0 | 2024-06-07
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007015/IF/22012035235563 — Khet talab nirman kary Kala bai w/o Than singh Adiwasi | Ongoing | 379996.13 | 0 | 2026-02-07
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007015/IF/22012035267045 — Khettalab nirman kary ram singh lodhi | Approved | 0 | 0 | 2024-10-02
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007015/IF/22012035348675 — Khettalab nirman kary ashok sen | New | 0 | 0 | 2025-04-14
MUNGAOLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/192436 — Construction of IAY House -IAY REG. NO. MP-48-007-015-001/59 | Ongoing | 27000 | 0 | 2018-06-07
MUNGAOLI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/192437 — Construction of IAY House -IAY REG. NO. MP-48-007-015-002/5 | Approved | 27000 | 0 | 2016-02-19
MUNGAOLI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/2099549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4125255 | Ongoing | 27000 | 0 | 2019-08-03
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/2430228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5166899 | Ongoing | 27000 | 0 | 2025-02-15
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/3243000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4235966 | Ongoing | 27000 | 0 | 2025-02-15
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/3253515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1922646 | Ongoing | 27000 | 0 | 2025-02-15
MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/3672759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104975382 | Ongoing | 27000 | 0 | 2023-09-01
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/3672762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104975657 | Ongoing | 27000 | 0 | 2022-07-14
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/4574603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117690345 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/4823813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121017856 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/4862803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106705911 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/4869998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113819194 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/4900071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151972887 | Ongoing | 27000 | 0 | 2025-04-30
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5361255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106705792 | Ongoing | 27000 | 10800 | 2025-05-03
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5361533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102231387 | Ongoing | 27000 | 7200 | 2025-05-03
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5518988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152002968 | Ongoing | 27000 | 0 | 2025-05-03
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5520963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009452 | Ongoing | 27000 | 23400 | 2025-05-03
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5524205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010076 | Ongoing | 27000 | 12600 | 2025-05-03
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5528274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152002228 | Ongoing | 27000 | 7200 | 2025-05-03
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5532287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151996415 | Ongoing | 27000 | 18000 | 2025-05-03
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5683688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009483 | Approved | 27000 | 0 | 2024-11-19
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5842753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152003173 | Ongoing | 27000 | 14400 | 2025-11-13
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5842782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010983 | Ongoing | 27000 | 0 | 2025-11-13
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5842858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151969421 | Ongoing | 27000 | 0 | 2025-11-13
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5843225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995611 | Physically Completed | 23490 | 4800 | 2025-11-13 | 2026-08-02
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5843226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151996816 | Physically Completed | 27000 | 0 | 2025-11-13 | 2026-09-06
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/5868180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115265303 | Ongoing | 27000 | 0 | 2026-01-22
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6179494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117690193 | Ongoing | 27000 | 7200 | 2026-04-27
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6183370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116142028 | Physically Completed | 27000 | 12300 | 2026-04-27 | 2026-10-04
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6191411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115423418 | Ongoing | 27000 | 17400 | 2026-04-27
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6208596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104975895 | Ongoing | 27000 | 10800 | 2026-04-27
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6250442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113819197 | Ongoing | 27000 | 1800 | 2026-10-09
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6250909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115295192 | Ongoing | 27000 | 3600 | 2026-10-09
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6252594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116314816 | Deleted | 27000 | 0 | 2026-04-10
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6253117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116255369 | Ongoing | 27000 | 1800 | 2026-10-09
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6269072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128533956 | Deleted | 27000 | 0 | 2026-04-13
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6280902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106705208 | Ongoing | 27000 | 1800 | 2026-10-09
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6304181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117690210 | Ongoing | 27000 | 1800 | 2026-10-09
MUNGAOLI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/630930 — Construction of IAY House -IAY REG. NO. MP1002199 | Ongoing | 27000 | 0 | 2017-03-22
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6316497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128534756 | Approved | 27000 | 0 | 2026-06-09
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6377645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117702380 | Ongoing | 27000 | 1800 | 2026-10-09
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007015/IF/IAY/6405602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116141744 | Approved | 27000 | 0 | 2026-02-09
MUNGAOLI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1748007015/RC/22012034573047 — sudur sadak nirman kary barra pipriya se prathmik school ki or | Ongoing | 1212217.77 | 0 | 2021-08-28
MUNGAOLI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007015/RC/22012034818621 — CC Road Nirman Kary Mudrakhurd se Primary School prangan me | Ongoing | 100000 | 0 | 2024-06-23
MUNGAOLI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007015/RC/22012034821349 — CC Road Nirman kary Ram babu lodhi k makan se Main road tak | Approved | 35000 | 0 | 2024-06-15
MUNGAOLI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007015/RC/22012034821353 — CC Road Nirman Kary Gudda Adiwasi k Ghar se Ram babu Prajapati k ghar ki or | Approved | 39000 | 0 | 2024-06-07
MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1748007015/RC/22012034849353 — CC Road Nirman kary Mandir parisar Barra | Approved | 60000 | 0 | 2025-08-15
MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007015/RC/22012034849354 — CC Road Nirman Kary Midile school parisar Barra | Approved | 22000 | 0 | 2025-08-15
MUNGAOLI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1748007015/RS/22012035128913 — Nali nirman kary Kallu sen k makan se nale ki or | Approved | 44000 | 0 | 2024-06-07
MUNGAOLI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1748007015/WC/22012034554989 — khet talab shri ram /jugtilal lodhi | Ongoing | 332572.21 | 0 | 2022-02-22
MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035257474 — Talab nirman kary shree ram ke khet ke pas | Approved | 0 | 0 | 2025-01-26
MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035257476 — Talab nirman kary harnarayan lodhi ke khet ke pas | Approved | 0 | 0 | 2025-01-26
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035259055 — Talab nirman kary shreeram ke khet ke pas | Ongoing | 1498913.62 | 0 | 2025-04-15
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035259056 — Talab nirman kary harnarayan ke khet ke pas | Ongoing | 1498841.27 | 0 | 2026-03-25
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1748007015/WC/22012035297563 — Dugwell Recharge pit shantidham ke pas wale koop | Approved | 25899.46 | 0 | 2025-04-14
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035329220 — Jirnodhar nirman kary rood me nale par gram barra | Approved | 0 | 0 | 2025-10-02
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035329221 — Jirnodhar nirman kary sardar ke khet ke pas gram barra | Approved | 0 | 0 | 2025-10-02
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035329222 — Jirnodhar nirman kary shishupal ke khet ke pas gram mudra | Approved | 0 | 0 | 2025-10-02
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035329223 — Jirnodhar nirman kary Horal harijan ke khet ke pas gram barra | Approved | 0 | 0 | 2025-10-02
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035329224 — Jirnodhar nirman kary Chokidar ke khet ke pas barra | Approved | 0 | 0 | 2025-10-02
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1748007015/WC/22012035329225 — Jirnodhar nirman kary silawan nale par mudra | Approved | 0 | 0 | 2025-10-02