## Work List
Exported on: 2026-09-06 18:24:47
Filters applied:
Data source: VBGRAMG
District: ASHOK NAGAR
Block: All
Panchayat: KUJRAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MUNGAOLI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1748007016/IF/22012034391135 — GP Khujrai Sadak Kinare Plantation RatBhanpur se Railway Station Marg par | Ongoing | 335000 | 0 | 2018-02-18
MUNGAOLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748007016/IF/22012034407001 — GP Kujrai Hiteshi kup Nirman Deshraj/Fodal | Ongoing | 200000 | 0 | 2018-06-01
MUNGAOLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748007016/IF/22012034407002 — Gp Kujrai Hiteshi kup nirman Vijay singh/Bihari | Ongoing | 200000 | 0 | 2018-06-01
MUNGAOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748007016/IF/22012034557070 — hiteshi kapildhara komal bai/pahalwan singh | Ongoing | 200000 | 0 | 2020-05-19
MUNGAOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748007016/IF/22012034566899 — kapildhara koop nirman sangram/sankar | Ongoing | 259724.75 | 0 | 2020-06-13
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748007016/IF/22012035237281 — khettalab nirman kary pratap/ sukhlal | Ongoing | 380142.13 | 0 | 2024-06-27
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748007016/IF/22012035304606 — Khettalab nirman kary surendra singh urf pal singh sikkh | Approved | 380142.13 | 0 | 2025-01-24
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748007016/IF/22012035354406 — Khettalab nirman kary khillu/ birja | Approved | 351377.54 | 0 | 2025-04-02
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748007016/IF/22012035553717 — Khettalab nirman kary chhaya/ nakul raghuwanshi | Approved | 351377.54 | 0 | 2025-04-14
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/3924779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106295206 | Ongoing | 27000 | 0 | 2022-08-02
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4031188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149092499 | Ongoing | 27000 | 0 | 2022-07-31
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4034593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127369283 | Ongoing | 27000 | 0 | 2022-08-18
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4063244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115253214 | Ongoing | 27000 | 0 | 2022-08-21
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4063245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115253326 | Ongoing | 27000 | 0 | 2022-08-21
MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4115581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115253273 | Ongoing | 27000 | 0 | 2022-08-21
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4478611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151937868 | Ongoing | 27000 | 0 | 2024-06-18
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4478661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151938777 | Ongoing | 27000 | 0 | 2024-06-18
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4491920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152034341 | Ongoing | 27000 | 0 | 2024-07-27
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4544584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106763591 | Ongoing | 27000 | 0 | 2025-01-13
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4565411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116325931 | Ongoing | 27000 | 14400 | 2025-02-14
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4634380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180088 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4821500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113777268 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4828876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180571 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/4833040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149095796 | Ongoing | 27000 | 0 | 2025-02-12
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5282765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106323464 | Ongoing | 27000 | 9000 | 2025-04-09
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5289628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126522603 | Ongoing | 27000 | 0 | 2025-04-09
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5316408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117171386 | Ongoing | 27000 | 0 | 2025-04-10
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5331528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129178587 | Ongoing | 27000 | 0 | 2025-04-10
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5333240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126461165 | Ongoing | 27000 | 0 | 2025-04-10
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5530625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152078741 | Ongoing | 27000 | 0 | 2025-05-01
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5628443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152035658 | Ongoing | 27000 | 0 | 2025-06-05
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5667941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149428349 | Ongoing | 27000 | 0 | 2025-08-27
MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/5668077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129178053 | Ongoing | 27000 | 0 | 2025-08-27
MUNGAOLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/574214 — Construction of IAY House -IAY REG. NO. MP1173561 | Ongoing | 27000 | 0 | 2018-11-21
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6176029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129379064 | Ongoing | 27000 | 8766 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6176163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129177764 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6176248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117504150 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6176292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114212369 | Ongoing | 27000 | 10800 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6177174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127640794 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6178027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129181556 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6178656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129377499 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6178902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116337473 | Completed | 23490 | 0 | 2026-04-19 | 2026-07-31
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6179117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129342957 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6179639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129177913 | Ongoing | 27000 | 5400 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6179950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180496 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6181506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126634510 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6183443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116338894 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6183546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179167 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6183595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127639432 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6183942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127370927 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6184039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129178278 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6185712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129376739 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6186187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117254440 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6186439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114644567 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6186687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129181456 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6186996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179775 | Ongoing | 27000 | 6966 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6187002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149435299 | Ongoing | 27000 | 3720 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6187096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121965721 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6187315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122711384 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6188929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114483699 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6190217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180666 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6190713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130048149 | Completed | 23490 | 0 | 2026-04-19 | 2026-07-31
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6191830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106735866 | Ongoing | 27000 | 600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6191931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180779 | Ongoing | 27000 | 5520 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6192342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129181066 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6192366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129372766 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6192859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129380408 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6193318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129379354 | Ongoing | 27000 | 5520 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6193744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106310789 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6194261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129378139 | Ongoing | 27000 | 5520 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6194547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129343458 | Ongoing | 27000 | 12600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6194635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116322076 | Ongoing | 27000 | 6966 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6196481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114646581 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6197504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180199 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6197671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129375881 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6198109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130048026 | Ongoing | 27000 | 5520 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6198377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179292 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6198743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130047540 | Ongoing | 27000 | 6300 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6199258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123493977 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6200810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106743794 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6201076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179990 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6201656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121976144 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6202625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127640175 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6203996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116337272 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6204014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129375228 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6204798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179891 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6204846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129373514 | Completed | 23490 | 0 | 2026-04-19 | 2026-07-31
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6205044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123489279 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6205124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134464938 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6207245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117508701 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6207252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179530 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6207582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126655787 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6207942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122695477 | Ongoing | 27000 | 12600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6208984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126624618 | Completed | 23490 | 0 | 2026-04-19 | 2026-07-31
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6209974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123487287 | Ongoing | 27000 | 5520 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6210172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130047271 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6210803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114215091 | Ongoing | 27000 | 3600 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6211042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130047440 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6211076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179412 | Completed | 23490 | 0 | 2026-04-19 | 2026-07-31
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6211605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126639416 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6213112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114655659 | Ongoing | 27000 | 5520 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6213552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129371759 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6213740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149470614 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6214512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129178859 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6216273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129178440 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6216554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126509542 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6216559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123412977 | Ongoing | 27000 | 0 | 2026-04-19
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6217248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116784321 | Ongoing | 27000 | 9000 | 2026-04-19
MUNGAOLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/623951 — Construction of IAY House -IAY REG. NO. MP1297900 | Ongoing | 27000 | 0 | 2018-11-21
MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748007016/IF/IAY/6378080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129179643 | Approved | 27000 | 0 | 2026-08-14
MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748007016/WC/22012035253748 — Samudayik khettalab nirman kary hanuman mandir ke pas | Approved | 380142.13 | 0 | 2025-01-24
MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1748007016/WC/22012035294506 — Dugwell Recharge pit dhanvati/ mahesh ahirwar ke koop ke pas | New | 0 | 0 | 2025-04-14
MUNGAOLI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1748007027/DP/22012034423870 — block pantation shantidham parisar khajurai | Ongoing | 342000 | 0 | 2018-12-10