## Work List
Exported on: 2026-09-14 07:52:33
Filters applied:
Data source: VBGRAMG
District: ALIRAJPUR
Block: All
Panchayat: BADGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHABRA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721006003/IF/22012034457698 — KAPIL DHARA KOOP KAMTI MANA BADGAON | Ongoing | 235670.79 | 0 | 2019-10-01
BHABRA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721006003/IF/22012034458187 — KAPIL DHARA KOOP PANAKI MAGAN BADGAON | Ongoing | 234458.62 | 0 | 2019-09-21
BHABRA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721006003/IF/22012034458188 — KAPIL DHARA KOOP NURA BALU BADGAON | Ongoing | 234458.62 | 0 | 2019-09-21
BHABRA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721006003/IF/22012034500485 — KAPIL DHARA KOOP BHURCHAND BHULI BORKARA BDAGOAV | Ongoing | 234458.62 | 0 | 2019-11-22
BHABRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035013627 — NANDAN FALODHAN HORTI MUKESH REMTIYA BORKARA BADGAON 2022-23 | Ongoing | 124684.2 | 0 | 2022-09-06
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131435 — NANDAN FALODHAN GP KANIYA LALJI BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131443 — NANDAN FALODHAN GP DINESH VIRSINGH BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131449 — NANDAN FALODHAN GP DHANA NANAKA BORKARA BADGAON 2023-24 | Ongoing | 139501.4 | 6300 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131455 — NANDAN FALODHAN GP KESHA NANSINGH BORKARA BADGAON 2023-24 | Ongoing | 139501.4 | 8400 | 2023-09-05
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131457 — NANDAN FALODHAN GP BACHCHU GULAB BORKARA BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-09-12
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131462 — NANDAN FALODHAN GP GAVA BIJIYA BORKARA BADGAON 2023-24 | Ongoing | 139501.4 | 1500 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035131791 — NANDAN FALODHAN GP GALIYA SOMALA BADGAON 2023-24 | Ongoing | 139501.4 | 2400 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035133399 — NANDAN FALODHAN NRLM BADIYA VALIYA BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-09-05
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035133401 — NANDAN FALODHAN NRLM NANDULAL VALIYA BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035133403 — NANDAN FALODHAN NRLM MANGA KALIYA BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-09-12
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035133407 — NANDAN FALODHAN NRLM SHANKAR JAMSINGH BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-08-29
BHABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1721006003/IF/22012035133409 — NANDAN FALODHAN NRLM VIKARAM JAMSINGH BADGAON 2023-24 | Ongoing | 139501.4 | 0 | 2023-08-29
BHABRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3256180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2982752 | Approved | 27000 | 0 | 2021-03-30
BHABRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3256515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3079287 | Approved | 27000 | 0 | 2021-03-30
BHABRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3256636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3111132 | Approved | 27000 | 0 | 2021-03-30
BHABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3267317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4775372 | Approved | 27000 | 0 | 2021-05-24
BHABRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3270500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4994400 | Approved | 27000 | 0 | 2020-11-17
BHABRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3270551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4997540 | Approved | 27000 | 0 | 2020-11-10
BHABRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3274942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5301344 | Approved | 27000 | 0 | 2020-11-10
BHABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/3275692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5347950 | Approved | 27000 | 0 | 2021-05-24
BHABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/5172306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149166200 | Completed | 23490 | 0 | 2025-07-29 | 2026-07-28
BHABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/5582011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149215627 | Physically Completed | 27000 | 14100 | 2025-09-24 | 2026-09-01
BHABRA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/650151 — Construction of IAY House -IAY REG. NO. MP3108098 | Approved | 27000 | 0 | 2017-02-17
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95451 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/1081 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95457 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/1095 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95458 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/1096 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95459 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/1099 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95460 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/1107 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95466 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/1141 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95469 — Construction of IAY House -IAY REG. NO. MP-21-006-003-001/7821 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721006003/IF/IAY/95471 — Construction of IAY House -IAY REG. NO. MP-21-006-003-002/1154 | Approved | 27000 | 0 | 2015-10-20
BHABRA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1721006003/WC/22012035171726 — NISTAR TALAB BADGAON 2024-25 | New | 0 | 0 | 2024-01-26
BHABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1721006003/WC/22012035254966 — NISTAR TALAB NIRMAN NAWAD FALIYA BUDIYA KE KHET KE PASS BADGAON | Ongoing | 2452295.78 | 48900 | 2025-04-08
BHABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1721006003/WC/22012035254972 — NISTAR TALAB NAWAD FALIYA GUMAN BHUWAN KE KHET KE PASS BADGAON | Ongoing | 1908004.29 | 11232 | 2025-05-06
BHABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1721006003/WC/22012035317155 — NISTAR TALAB AGAN RAMCHAND K KHET PASS MAVDA FALIYA GP BADGAON 2025 | Approved | 1048058.61 | 0 | 2025-05-10