## Work List
Exported on: 2026-09-11 02:51:49
Filters applied:
Data source: VBGRAMG
District: SINGRAULI
Block: All
Panchayat: GHOGHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHITRANGI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1715004049/DP/22012034622501 — BRIKSHAROPAN MS SCHOOL GHOGHARA ME | Approved | 0 | 0 | 2024-07-01
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1715004049/IF/22012035510893 — KHET TALAB RAMLAKHAN BAIS KE BHUMI PAR GHOGHARA | Approved | 0 | 0 | 2025-04-14
CHITRANGI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1715004049/IF/22012035548843 — dugwell nirman khajanti bais ke koop me | Approved | 0 | 0 | 2025-04-14
CHITRANGI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1715004049/IF/22012035548852 — dugwell nirman hariprasad kol ke koop par | Approved | 0 | 0 | 2025-04-14
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1715004049/IF/22012035548862 — form pond rambahor bais ke khet me | Approved | 0 | 0 | 2025-04-14
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035598785 — EK BAGIYA MAA KE NAAM CHAMELIYA DEVI | Approved | 200628.58 | 0 | 2025-08-01
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035599377 — EK BAGIYA MAA KE NAAM PHULPATIYA DEVI BAIS | Ongoing | 200628.58 | 0 | 2025-09-09
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035599382 — EK BAGIYA MAA KE NAAM USHA DEVI BAIS | New | 0 | 0 | 2025-08-01
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035599388 — EK BAGIYA MAA KE NAAM SANGEETA DEVI | Ongoing | 200628.58 | 0 | 2025-09-09
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035599394 — EK BAGIYA MAA KE NAAM SUBHAGIYA DEVI BAIS | Ongoing | 200628.58 | 0 | 2025-09-09
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035601903 — EK BAGIYA MAA KE NAAM DURGAWATI BAIS | Approved | 0 | 0 | 2025-08-01
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035601919 — EK BAGIYA MAA KE NAAM PUSHPA DEVI BAIS | New | 0 | 0 | 2025-08-01
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715004049/IF/22012035601935 — EK BAGIYA MAA KE NAAM SANGITA DEVI BAIS | Approved | 0 | 0 | 2025-08-01
CHITRANGI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/226107 — Construction of IAY House -IAY REG. NO. MP1245785 | Ongoing | 28500 | 0 | 2018-12-21
CHITRANGI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/2459378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3422083 | Approved | 28500 | 0 | 2020-05-06
CHITRANGI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3061837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4041662 | Approved | 28500 | 0 | 2020-12-09
CHITRANGI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3282962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4022121 | Approved | 28500 | 0 | 2021-10-25
CHITRANGI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3283135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4065956 | Approved | 28500 | 0 | 2021-10-25
CHITRANGI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3286785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5542241 | Approved | 28500 | 0 | 2021-10-25
CHITRANGI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3319055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3980369 | Approved | 28500 | 0 | 2021-11-03
CHITRANGI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3650042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4045243 | Approved | 28500 | 0 | 2022-03-28
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3900225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149527778 | Approved | 28500 | 0 | 2022-04-27
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/3914599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151312265 | Approved | 28500 | 0 | 2022-05-03
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4127738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5370068 | Approved | 28500 | 0 | 2022-05-19
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4127739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5374857 | Approved | 28500 | 0 | 2022-05-19
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4127790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3992393 | Approved | 28500 | 0 | 2022-05-19
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4173600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126238689 | Approved | 28500 | 0 | 2022-06-08
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4239959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150205441 | Approved | 28500 | 0 | 2022-06-16
CHITRANGI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4409672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146821408 | Approved | 28500 | 0 | 2022-06-16
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4645314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137066388 | Ongoing | 28500 | 0 | 2025-11-03
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4664958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150119517 | Approved | 28500 | 0 | 2024-09-11
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4832651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146822045 | Ongoing | 28500 | 0 | 2025-01-28
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4832652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146822390 | Ongoing | 28500 | 0 | 2025-11-18
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4832655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146823692 | Ongoing | 28500 | 0 | 2025-06-27
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4835685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150204494 | Approved | 28500 | 0 | 2024-10-03
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4835687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150205494 | Ongoing | 28500 | 0 | 2025-02-20
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4836284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151276519 | Approved | 28500 | 0 | 2024-09-28
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4837671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151592674 | Ongoing | 28500 | 0 | 2025-01-28
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4890716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146819181 | Approved | 28500 | 0 | 2024-09-09
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/4892161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148970319 | Ongoing | 28500 | 0 | 2025-03-07
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5357774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124493522 | Approved | 28500 | 0 | 2025-02-19
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5366674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146822190 | Approved | 28500 | 0 | 2025-02-19
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5371990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137066352 | Approved | 28500 | 0 | 2025-02-19
CHITRANGI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5373979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150204736 | Approved | 28500 | 0 | 2025-02-19
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5374778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125523306 | Ongoing | 28500 | 0 | 2025-05-24
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5589165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149527837 | Ongoing | 28500 | 0 | 2025-11-03
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5721335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142176266 | Completed | 24795 | 0 | 2026-03-01 | 2026-08-13
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5724169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125523629 | Approved | 28500 | 0 | 2025-04-16
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5733056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142176566 | Ongoing | 28500 | 0 | 2026-02-01
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5877474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146251927 | Approved | 28500 | 0 | 2025-09-09
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/5877549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146250212 | Approved | 28500 | 0 | 2025-09-09
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6011688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094880 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6011960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094882 | Ongoing | 28500 | 0 | 2026-08-06
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094766 | Ongoing | 28500 | 18000 | 2026-07-05
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152095034 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094779 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094769 | Ongoing | 28500 | 4200 | 2026-07-30
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094767 | Ongoing | 28500 | 9000 | 2026-07-05
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094876 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6012416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094883 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6014658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094029 | Ongoing | 28500 | 0 | 2026-08-21
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6014835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094030 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6018960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152097280 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6019230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094107 | Ongoing | 28500 | 9000 | 2026-08-06
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6024041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094399 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6026456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094166 | Ongoing | 28500 | 0 | 2026-08-21
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6026811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094170 | Ongoing | 28500 | 0 | 2026-04-09
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6026908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094169 | Ongoing | 28500 | 0 | 2026-08-21
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094772 | Ongoing | 28500 | 9000 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094773 | Ongoing | 28500 | 9000 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094776 | Ongoing | 28500 | 0 | 2026-06-15
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094778 | Ongoing | 28500 | 9000 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094781 | Ongoing | 28500 | 9000 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094875 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094877 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094878 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094879 | Ongoing | 28500 | 9000 | 2026-07-22
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094881 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094904 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094905 | Ongoing | 28500 | 0 | 2026-05-27
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094906 | Ongoing | 28500 | 0 | 2026-08-21
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094907 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094908 | Ongoing | 28500 | 0 | 2026-08-21
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094909 | Ongoing | 28500 | 0 | 2026-05-13
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094911 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094912 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094913 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094914 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094915 | Ongoing | 28500 | 4500 | 2026-07-22
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094916 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094917 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094918 | Ongoing | 28500 | 0 | 2026-06-15
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6027919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094920 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6028463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094400 | Ongoing | 28500 | 0 | 2026-08-06
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6028476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152095056 | Ongoing | 28500 | 0 | 2026-09-05
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6028477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152095071 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6028761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094167 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6028762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094168 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6033803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094768 | Ongoing | 28500 | 9000 | 2026-07-22
CHITRANGI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6033804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094771 | Approved | 28500 | 0 | 2026-02-23
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6033805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094910 | Ongoing | 28500 | 0 | 2026-05-13
CHITRANGI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1715004049/IF/IAY/6035156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094108 | Ongoing | 28500 | 0 | 2026-04-09
CHITRANGI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715004049/WC/22012035251315 — CHEK DEM NIRMAN TADIYA NALA ME | Approved | 0 | 0 | 2025-01-25
CHITRANGI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1715004049/WC/22012035251316 — CHEK DEM NIRMAN GHOGHARA PATEHRA NALA RAMPATI SAKET KE GHAR KE PASS | Approved | 0 | 0 | 2025-01-25