## Work List
Exported on: 2026-09-15 00:09:01
Filters applied:
Data source: VBGRAMG
District: AGAR-MALWA
Block: All
Panchayat: MANASA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1719002012/AV/22012034535364 — gaushala nirman colony manasa | Ongoing | 3784582.21 | 0 | 2020-09-20
NALKHEDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002012/DP/22012034603153 — वसुधा वंदन योजना हनुमान मंदिर परिसर मनासा | Ongoing | 55847.4 | 0 | 2023-10-05
NALKHEDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1719002012/DP/22012034622665 — वृक्षारोपण गौशाला के शमशान परिसर मे मनासा | Approved | 0 | 0 | 2024-04-14
NALKHEDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1719002012/DP/22012034624258 — वृक्षारोपण शांतीधाम के पास मनासा | Ongoing | 453563.17 | 0 | 2024-07-22
NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1719002012/IF/22012034427711 — plantetion khet ki med par | Ongoing | 190000 | 0 | 2019-02-12
NALKHEDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002012/IF/22012034685474 — कपिल धारा कूप निर्माण कामू बाई पति एलामसिंह | Ongoing | 247839.67 | 0 | 2021-05-24
NALKHEDA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002012/IF/22012034685477 — कपिल धारा कूप निर्माण गोकुलसिंह पिता पूरसिंह | Ongoing | 247839.67 | 0 | 2021-05-24
NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719002012/IF/22012035515980 — GJSA डगवेल रिचार्ज गिरवरसिंह रामलाल मनासा | Approved | 0 | 0 | 2025-04-14
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719002012/IF/22012035622408 — cc road nirman karya sati mata mandir se gokul singh ke makan ki or manasa | New | 0 | 0 | 2025-09-01
NALKHEDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/3715331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106238925 | Ongoing | 27000 | 0 | 2022-06-27
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/3723195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119682246 | Completed | 23490 | 0 | 2026-03-20 | 2026-08-17
NALKHEDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4224473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116185212 | Ongoing | 27000 | 0 | 2022-07-25
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4520716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115999120 | Completed | 23490 | 0 | 2025-03-14 | 2026-08-17
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4520717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115999164 | Completed | 23490 | 0 | 2025-03-14 | 2026-08-17
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4521614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117298059 | Completed | 23490 | 0 | 2025-01-30 | 2026-08-17
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4521737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117441734 | Approved | 27000 | 0 | 2024-09-11
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4521848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116212670 | Ongoing | 27000 | 0 | 2025-01-30
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4522298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119683340 | Ongoing | 27000 | 0 | 2024-11-05
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4522378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868147 | Completed | 23490 | 0 | 2025-01-30 | 2026-08-17
NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4751129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117261630 | Ongoing | 27000 | 0 | 2025-01-30
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4755609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117821896 | Ongoing | 27000 | 0 | 2026-05-19
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4947104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116153927 | Physically Completed | 23490 | 0 | 2025-04-10 | 2026-08-09
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4951063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117570631 | Physically Completed | 23490 | 0 | 2025-04-10 | 2026-08-09
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4953936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120582015 | Physically Completed | 23490 | 0 | 2025-04-10 | 2026-08-09
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/4961681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124821475 | Ongoing | 27000 | 2100 | 2025-04-10
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5153738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116486902 | Ongoing | 27000 | 4200 | 2025-04-10
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5160283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180835 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-17
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5174797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116455448 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-17
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5182903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116560365 | Physically Completed | 23490 | 0 | 2025-04-10 | 2026-07-19
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5187501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119688303 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-17
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5189729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116457633 | Physically Completed | 23490 | 0 | 2025-04-10 | 2026-07-19
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5193122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646187 | Ongoing | 27000 | 0 | 2025-04-10
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5197337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116447494 | Ongoing | 27000 | 0 | 2025-04-10
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5204475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180137 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-17
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5221168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124545163 | Physically Completed | 23490 | 4200 | 2025-04-10 | 2026-08-02
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5222348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122754452 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-17
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5461753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180310 | Ongoing | 27000 | 0 | 2026-02-23
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5463412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116420270 | Physically Completed | 23490 | 0 | 2026-02-23 | 2026-07-19
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5654278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117789327 | Approved | 27000 | 0 | 2025-04-21
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5668078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117570737 | Ongoing | 27000 | 0 | 2026-02-23
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/5829733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868221 | Physically Completed | 27000 | 4200 | 2026-02-23 | 2026-08-30
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6004852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117269997 | Ongoing | 27000 | 8400 | 2026-07-22
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6005009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180585 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6005712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117814543 | Ongoing | 27000 | 0 | 2026-09-07
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6006425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117813193 | Ongoing | 27000 | 0 | 2026-09-07
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6006698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119688563 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6006699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119688684 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6006862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646777 | Ongoing | 27000 | 0 | 2026-09-06
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6007405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868253 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6007413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118181532 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6008107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646913 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6008517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119661166 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6010251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118182439 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6010254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812722 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6011694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116456288 | Ongoing | 27000 | 8400 | 2026-07-22
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6012175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117271654 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6012221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117269976 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6012265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117269971 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6012393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118178518 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6012758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118181075 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6013230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117294404 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6016438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812861 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6017526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868353 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6017584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118033477 | Ongoing | 27000 | 0 | 2026-08-13
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6017867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646566 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6017913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646713 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6017977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868047 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6018004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646590 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6018049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646743 | Ongoing | 27000 | 8400 | 2026-07-22
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6018089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646671 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6018122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117966747 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6018183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646040 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6018231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646065 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6019197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123488530 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6019346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119688797 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6019476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121616129 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6020234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117290431 | Ongoing | 27000 | 0 | 2026-08-13
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6020775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123231148 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6021112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646959 | Ongoing | 27000 | 0 | 2026-09-07
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6021346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118182965 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6021391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868282 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6021396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117825139 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6022273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123230643 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6023427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118328950 | Ongoing | 27000 | 0 | 2026-09-06
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6023613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119687269 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6023668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119686606 | Ongoing | 27000 | 8400 | 2026-07-23
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6024076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118178197 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6024858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117813033 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6024953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117813017 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6025184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123231803 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6026353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117261608 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6026928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119688437 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6034433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118179381 | Ongoing | 27000 | 0 | 2026-09-07
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6034434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118179658 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6034888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868428 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6035217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123443464 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6035230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118181768 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6035743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117274667 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6036411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118157531 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6037910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116560319 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121603449 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116489495 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117266174 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117271663 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117275592 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812763 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116455330 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116455405 | Ongoing | 27000 | 4200 | 2026-07-22
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117791313 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118177806 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6038757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119686957 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812681 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116457915 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117647017 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116447549 | Ongoing | 27000 | 0 | 2026-08-13
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116185123 | Ongoing | 27000 | 22200 | 2026-07-02
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868393 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6039946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123236115 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6040044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117415607 | Ongoing | 27000 | 4200 | 2026-07-22
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6040279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812878 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6040280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812917 | Ongoing | 27000 | 0 | 2026-09-06
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6040281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812968 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6040452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117276291 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6040802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117261591 | Ongoing | 27000 | 0 | 2026-07-22
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6043395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118157654 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6044103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117436345 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6044129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117789309 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6044130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117789337 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6044689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118033508 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6044772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117274676 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6044939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118200153 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6045120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119686480 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6045251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116412677 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6045538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117413243 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6049641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123169220 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6052086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117266202 | Approved | 27000 | 0 | 2026-03-14
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6053608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117647045 | Ongoing | 27000 | 0 | 2026-09-07
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6237567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118182699 | Approved | 27000 | 0 | 2026-02-18
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6237584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646701 | Approved | 27000 | 0 | 2026-03-11
NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6237626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119682769 | Approved | 27000 | 0 | 2026-03-26
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6237744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117646472 | Approved | 23490 | 0 | 2026-05-04
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6237799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117821864 | Approved | 23490 | 0 | 2026-05-20
NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002012/IF/IAY/6382852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115999180 | Approved | 27000 | 0 | 2026-08-17
NALKHEDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719002012/LD/22012034589663 — खेल मैदान प्राथमिक विद्यालय के पास नाथू खेड़ी | Ongoing | 152904.04 | 0 | 2023-10-07
NALKHEDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002012/RC/22012034849095 — cc road nirman karya sati mata mandir se gokul singh ke makan ki or manasa | Approved | 98850 | 0 | 2025-09-01
NALKHEDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002012/RC/22012034849099 — cc road nirman karya gokul singh ke makan se holi tekra ki or manasa | Approved | 61200 | 0 | 2025-08-15
NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1719002012/RS/22012034502084 — Samudayik swachhata parisar manasa | Ongoing | 45000 | 0 | 2020-12-02
NALKHEDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1719002012/RS/22012034684345 — सामुदायिक स्वच्छ्ता परिसर निर्माण शिशु मंदिर विध्यालय के पास मनासा | Ongoing | 45000 | 0 | 2023-09-07
NALKHEDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1719002012/WC/22012034476497 — पोधा रोपण नविन सामुदिक भवन देवनारायण मंदिर नाथूखेडी | Ongoing | 373989.79 | 0 | 2019-08-24
NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719002012/WC/22012035269303 — JGSA 2025 डग वेल रिचार्ज पीट सार्वजनिक कुप नाथुखेडी | Physically Completed | 25899.46 | 0 | 2025-04-26 | 2026-08-10
NALKHEDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719002012/WH/22012034940049 — नमामि गंगे परियोजना अंतर्गत गौशाला के पास तालाब जीर्णोद्वार कार्य ग्राम पंचायत मनासा | Ongoing | 354224.45 | 0 | 2024-07-22
NALKHEDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719002012/WH/22012034941842 — नमामि गंगे परियोजना अंतर्गत गौशाला के पास तालाब जीर्णोद्वार कार्य ग्राम पंचायत मनासा | Approved | 0 | 0 | 2024-04-14
NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719002012/WH/22012034943429 — तलाई जिर्णोद्वार बडा नाला के पास नाथुखेडी | Ongoing | 445224.35 | 0 | 2025-04-26