## Work List
Exported on: 2026-10-10 19:39:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: GOONJH
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / AMBAH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701001007/AV/5000 — Aanganwadi Bhawan Gadi Goonj | Completed | 180000 | 140688 | 2019-03-08 | 2021-11-09
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/DP/130 — व़क्षारोपण कार्य सवसुख का पुरा सिवदावन | Completed | 480000 | 29402 | 2008-10-09 | 2014-08-07
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/DP/131 — रतन ज्‍योति रोपएण्‍ण काय्र | Completed | 335000 | 13419 | 2008-12-17 | 2014-08-07
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/DP/160 — निर्मल वाटिका निर्माण कार्य | Completed | 0 | 38800 | 2010-08-04 | 2014-08-07
MORENA / AMBAH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/DP/22012034228681 — Gram Van Bricharopad Kary Sabsukh Ka Pura Goonj Bandha | Completed | 1919002 | 901126.47 | 2016-01-30 | 2025-04-27
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/DP/43 — ब्रक्षारोपण | Completed | 480000 | 23286 | 2008-09-15 | 2014-08-07
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/DP/44 — ब्रक्षारोपण | Completed | 30000 | 5821.68 | 2008-09-23 | 2014-08-07
MORENA / AMBAH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/DP/9993629788 — Gram Van Kary Goonj | Completed | 1919002 | 30528 | 2015-11-25 | 2016-01-30
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001007/FP/22012034629032 — Kaccha Nala Nirman kary Sabsukh Ka Pura Puliya Se Kalika Ki Puliya ki Or Goonj | Completed | 539861.43 | 383818 | 2023-05-04 | 2026-03-17
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701001007/FP/22012034632310 — Nala Nirman khar se Gwan Ki ore Sabsukh Ka Pura | Completed | 46650 | 45968 | 2023-08-12 | 2023-12-30
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701001007/FP/22012034640961 — 15 Van Bitt Nala Nirman Kary Bare Lal Ke Khet Se Gavn Ki Or Village Sabsukh ka Pura GP Goonj | Completed | 45000 | 43740 | 2024-08-24 | 2024-10-10
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001007/FP/22012034640962 — 15 Van Bitt Nala Nirman Kary Aderam ke Ghar Se DP Ki Or Sabsukh Ka Pura GP Goonj | Completed | 19800 | 18954 | 2024-08-24 | 2024-10-10
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701001007/FP/22012034641662 — 15 Van Bitt Nala Nirman Kary Main Road Se Naresh Ke Ghar Ki Or GP Goonj | Completed | 26100 | 25758 | 2025-02-12 | 2025-04-27
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/1000035391 — Cattel Shed Kamal Singh / Gajendra Singh Sub Sukh | Completed | 70500 | 64664 | 2013-09-14 | 2016-09-22
MORENA / AMBAH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/115 — मेड वंधान भोगीराम | Completed | 0 | 12566 | 2011-12-18 | 2014-08-14
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701001007/IF/22012034350109 — Platation MANYA ka Shidha Bandha goonjh | Completed | 335000 | 10492 | 2017-06-14 | 2017-07-23
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701001007/IF/22012034350123 — Platation Karya Shidh Baba se Bandha Tak Goonjh | Completed | 335000 | 7224 | 2017-06-14 | 2017-07-23
MORENA / AMBAH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/22012034859590 — Bad Rahat Aawas Nahar Singh / Barelal Village Subsukh ka Pura GP Goonj | Completed | 17370 | 16105 | 2022-05-07 | 2022-06-15
MORENA / AMBAH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/22012034859596 — Bad Rahat Aawas Bhura / Churamani Village Subsukh ka Pura GP Goonj | Completed | 17370 | 15912 | 2021-10-20 | 2022-05-15
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/22012035453048 — khet talab karya ramdas ke khet me goonjh | Completed | 147621.16 | 91417.32 | 2025-05-05 | 2026-01-13
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/22012035453228 — khet talab nirman bhagwan singh ke khet me goonjh | Completed | 147621.16 | 91040.4 | 2025-05-05 | 2026-01-13
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/22012035453382 — khet talab nirman rambaran ke khet me goonjh | Completed | 147621.16 | 111447 | 2025-05-05 | 2026-01-28
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/22012035453443 — khet talab nirman vishvnath ke khet me goonjh | Completed | 147621.16 | 98919 | 2025-05-05 | 2026-01-28
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/241 — Med Bandhan Shaskiya Bhoomi Par Goonj | Completed | 21052 | 21384 | 2013-03-05 | 2014-10-09
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/242 — Med Bandhan Shashkiy Bhoomi Par Sub Sukha ka pura Goonj | Completed | 27459 | 27720 | 2013-02-14 | 2014-10-09
MORENA / AMBAH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/80 — मेड वन्‍धान कार्य वि शम्‍वर पुञ बाबू | Completed | 0 | 35136 | 2011-08-17 | 2014-08-07
MORENA / AMBAH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001007/IF/81 — मेड वन्‍धान कार्य मान सिह पुञ मनीराम | Completed | 0 | 13176 | 2011-08-31 | 2014-08-14
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926708584 — cattel shed naresh/ vishalsingh goonjh | Completed | 70500 | 62373 | 2014-02-28 | 2016-09-25
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926709874 — Cattel Shed Kaptan Singh/ Gajenrdh Singh Sabsukh K | Completed | 70500 | 33800 | 2014-02-28 | 2015-10-15
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926713788 — Cattle Shed Devendra/haricharan | Completed | 70500 | 50296 | 2014-03-05 | 2016-12-06
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926713791 — Cattle Shed Ramvilash/Ramgopal Gardhi | Completed | 70500 | 58774 | 2014-03-05 | 2016-11-22
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926713796 — Cattle Shed Ashok/Ram Singh Sabsukh Ka pura | Completed | 70500 | 69311.77 | 2014-03-05 | 2016-09-25
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926713800 — Cattle Shed Ganga Singh/Hubblal Bandha | Completed | 70500 | 56524 | 2014-03-05 | 2015-10-15
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926713819 — Cattle Shed Damber/Bhagari | Completed | 70500 | 58718 | 2014-03-05 | 2016-09-25
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9926713825 — cattle shed kaliyan/radakirsana goonjh | Completed | 70500 | 46112 | 2014-03-05 | 2015-08-15
MORENA / AMBAH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9993673883 — cattle shed bhurisingh s/o parashram parmar | Completed | 70500 | 68753.77 | 2015-09-15 | 2016-09-25
MORENA / AMBAH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001007/IF/9993673912 — Cattle shed Ramsebak Singh/ ParsramSingh Parmar Bandha | Completed | 70500 | 70344 | 2015-09-15 | 2016-09-25
MORENA / AMBAH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/1908043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5079704 | Completed | 15660 | 12528 | 2018-12-13 | 2019-07-02
MORENA / AMBAH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/1925411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5743145 | Completed | 17100 | 15284 | 2018-12-13 | 2020-12-04
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/263356 — Construction of IAY House -IAY REG. NO. MP3125306 | Completed | 15030 | 15081 | 2017-03-16 | 2018-04-11
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/273835 — Construction of IAY House -IAY REG. NO. MP3109165 | Completed | 15030 | 15253 | 2017-03-16 | 2018-04-11
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/594984 — Construction of IAY House -IAY REG. NO. MP3162817 | Completed | 15030 | 15081 | 2017-03-16 | 2018-04-11
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/775322 — Construction of IAY House -IAY REG. NO. MP3691985 | Completed | 15030 | 14448 | 2017-05-01 | 2018-06-11
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/775575 — Construction of IAY House -IAY REG. NO. MP3706990 | Completed | 15030 | 15480 | 2017-05-01 | 2018-04-11
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001007/IF/IAY/87213 — Construction of IAY House -IAY REG. NO. MP-01-001-007-001/5 | Completed | 14310 | 14066 | 2016-11-21 | 2018-06-11
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/235 — मैढ बंधान कार्य दीमान सिंह | Completed | 0 | 23550 | 2010-08-17 | 2010-11-01
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/236 — मैढ बंधान कार्य मान सिंह | Completed | 0 | 17300 | 2010-08-17 | 2010-11-08
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/237 — मैढ बंधान कार्य रामलक्षिन | Completed | 0 | 25200 | 2010-08-17 | 2010-10-09
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/238 — मैढ बंधान कार्य बेताल / तोताराम | Completed | 0 | 20350 | 2010-08-17 | 2010-08-17
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/239 — मैढ बंधान कार्य विजय सिंह | Completed | 0 | 21900 | 2010-08-16 | 2009-04-01
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/240 — मैढ बंधान कार्य सबसुख का पुरा | Completed | 0 | 68206 | 2010-08-17 | 2011-06-25
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/241 — मैढ बंधान कार्य ग्‍याराम | Completed | 0 | 18250 | 2010-04-27 | 2010-09-17
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/242 — मैढ बंधान कार्य भगवान सिंह | Completed | 0 | 16700 | 2010-06-13 | 2010-07-18
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/243 — मैढ बंधान कार्य रामदास | Completed | 0 | 23100 | 2010-04-27 | 2010-11-08
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/244 — मैढ बंधान कार्य रामरूप | Completed | 0 | 22100 | 2010-05-03 | 2010-09-24
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/245 — मैढ बंधान कार्य हरिविलास | Completed | 0 | 25200 | 2010-05-03 | 2010-07-18
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/246 — मैढ बंधान कार्य विजय सिंह | Completed | 0 | 24900 | 2010-05-03 | 2010-10-07
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/318 — मैढ बंधान कार्य सवसुख का पुरा | Completed | 0 | 17500 | 2010-10-24 | 2010-10-24
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/337 — मैढ बंधान कार्य बदन सिंह / जगराम सिंह | Completed | 0 | 13600 | 2010-11-23 | 2010-04-01
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/338 — मेड वन्‍धान कार्य लेखराज पुञ वटूरी | Completed | 0 | 33900 | 2010-11-09 | 2010-04-01
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/367 — मेढवंधान कार्य | Completed | 0 | 26400 | 2011-01-04 | 2011-01-01
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/368 — मेढवंधान कार्य | Completed | 0 | 24500 | 2011-01-18 | 2011-01-18
MORENA / AMBAH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701001007/LD/371 — मेड वन्‍धान कार्य शासकीय जमीन | Completed | 0 | 18300 | 2011-08-31 | 2014-08-14
MORENA / AMBAH | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701001007/PG/9425888708 — Khail Maidan Goonj | Completed | 500000 | 142318 | 2017-01-16 | 2019-03-31
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034169475 — Panch Parmeswar CC Road Nali Sahit Feran ke Makan | Completed | 62360 | 53331.2 | 2013-08-03 | 2015-07-28
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001007/RC/22012034193137 — Mitti Bajari Antrik Road Nirman Karay main road Se | Completed | 492000 | 429739.8 | 2013-12-27 | 2016-01-06
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034193141 — Conversion Road Nali Sahit Main Road Se JalSingh k | Completed | 98937 | 82890 | 2013-12-14 | 2014-09-02
MORENA / AMBAH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034283748 — PP Road Bijali Ghar Se Natthi Singh ke Ghar Ki or Goonj | Completed | 75427 | 73156 | 2015-10-22 | 2016-01-06
MORENA / AMBAH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034295093 — PP CC Road Nali Sahit Raghuveer ke Makan Se Bijendra ke Makan ki Or Goonj | Completed | 92500 | 84891 | 2016-01-05 | 2016-09-25
MORENA / AMBAH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034329909 — cc road ramgiyan harjan ke makan se bijendra parmar ke makan tak | Completed | 144540 | 138330 | 2017-03-07 | 2017-11-01
MORENA / AMBAH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701001007/RC/22012034340940 — Mitti Bajri Sudur Road Sabsukh Ka Pura Goonjh | Completed | 1100000 | 246583.6 | 2017-06-08 | 2021-02-10
MORENA / AMBAH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034341054 — cc road p m road serambilash ke makan tak goojh | Completed | 60187 | 8256 | 2017-06-10 | 2017-08-20
MORENA / AMBAH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034368015 — dpr cc ropad maha dev ke makanse babu singh ke makan tak badha goonjh | Completed | 97700 | 82788 | 2017-12-26 | 2018-06-27
MORENA / AMBAH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034381962 — DPR CC road kharee se ajab singh ke makan tak bandha goongh | Completed | 16950 | 16512 | 2018-02-01 | 2018-07-15
MORENA / AMBAH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034397990 — DPR CC Road NIrman Babu Singh ke Ghar Se CC Road Tak Village Bandha Gp Goonj | Completed | 62775 | 62688 | 2019-03-04 | 2019-07-02
MORENA / AMBAH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034446477 — CC ROAD NIRMAN KALIYAN KE MAKAN SE VIJENDRA KE MAKAN TAK BANDHA GOONJH | Completed | 27900 | 27396 | 2019-03-05 | 2019-09-15
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034531756 — DPR Road Nali Nirman Khari Road Se Ramakant Singh Tomar Ke Makan Tak Bandha | Completed | 46500 | 50160 | 2020-08-22 | 2020-10-30
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034531904 — DPR CC Road Nirman Rambir Harijan ke Makan Se Makhan Harijan Ke Makan Tak Bandha | Completed | 48825 | 48450 | 2020-08-22 | 2020-10-30
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034583595 — 15 Van Bitt CC Road Nali Nirman PM Road Se Ramnarayan Sharma ke Ghar Tak Gadi Goonj | Completed | 30000 | 29722 | 2022-02-10 | 2022-04-02
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034583598 — 15 Van Bitt CC Road Nali Nirman Viswnath ke Gaunda Se Satyram ke Ghar ki Or Gadi | Completed | 38000 | 36477 | 2022-02-10 | 2022-04-02
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034583599 — 15 Van Bitt CC Road Nali Nirman Main Road Se Udayveer Singh Ke Ghar Tak Bandha | Completed | 42000 | 40530 | 2022-02-10 | 2022-03-30
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034637754 — CC Road Nali Nirman Het Singh Ke Ghar Se Beerendra ke Ghar ki Or Sab Sukh Ka Pura Goonj | Completed | 22500 | 17238 | 2023-07-20 | 2023-12-30
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701001007/RC/22012034648276 — Sudur / Khet Sadak Nirman Datiya Siddha Sthal Se Many Main Raod Tak Goonj | Completed | 2264673.72 | 2224222.47 | 2024-02-10 | 2025-11-05
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034648282 — 15 Van Bitt CC Road Nali Sahit Beerendra Ke Gahr Se Vishwanath Ke Gahr ki Or Sabsukh Ka Pura Goonj | Completed | 66500 | 62543 | 2023-10-06 | 2024-03-15
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034832821 — 15 Van Bitt CC Road Nirman Jitendra ke Ghar Se Bhagwan Lal Ke Ghar ki Or GP Goonj | Completed | 96000 | 92340 | 2025-02-05 | 2025-04-04
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034836615 — 15 Van Bitt CC Road Main Kharanja Se Churamani ke Ghar Ki Or Sabsukh Ka Pura GP Goonj | Completed | 94600 | 94221 | 2025-03-28 | 2025-12-18
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/22012034836616 — 15 Van Bitt CC Road Nali Sahit Main Road Se Ranchhor Sharma ke Ghar ki Or Gadhi Goonj | Completed | 37600 | 37584 | 2025-03-28 | 2025-06-19
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001007/RC/245 — पंच परमेश्‍वर सी सी | Completed | 0 | 260855 | 2012-04-01 | 2014-09-02
MORENA / AMBAH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001007/RC/85 — सी सी खंरजा निर्माण कार्य सबसुख का पुरा | Completed | 145000 | 67757 | 2009-07-20 | 2009-08-27
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034202507 — NBA Toilet Naresh /Vishambar Sabsukh Ka Pura | Completed | 1772 | 1772 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034209331 — NBA Toilet Mevaram /Vansi Sabsukh Ka Pura Goonjh | Completed | 1772 | 1772 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034209333 — NBA Toilet Mansaram Bhagbant Sabsukh Ka Pura Goon | Completed | 1772 | 1772 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034209339 — NBA Toilet Sandip Sharma/Shrikrishan Sharma Gardhi | Completed | 1772 | 1772 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250669 — NBA Toilet Omprakesh/ Dheersingh Gardhi (Goonjh) | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250796 — NBA Toilet UemeshSharma /RamsanehiSharmaGardhi (Go | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250801 — NBA Toilet RammuratiSharma/RamkaranSharmaGardhi (G | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250854 — NBA ToiletRajbeerSharma/ Ramdin Sharma Gardhi (Goo | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250857 — NBA ToiletRajenrdhSharma/ MalgajiSharma Gardhi (Go | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250881 — NBA Toilet BhuDevi /RameshSharma Gradhi (Goonjh) | Completed | 5400 | 5400 | 2014-07-19 | 2015-07-28
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250884 — NBA Toilet Amle Sharma /SatynarayanSharma Gardhi ( | Completed | 5400 | 5400 | 2014-07-19 | 2015-07-28
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250885 — NBA Toilet Meera Bai / Kaliyan Sharma Gardhi (Goon | Completed | 5400 | 5400 | 2014-07-19 | 2015-07-28
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250887 — NBA Toilet RameshSharma / Ramgopal Sharma Gardhi ( | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250888 — NBA Toilet Nathilal Sharma / Gardhi (Goonjh) | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250889 — NBA Toilet Ranchor Sharma / Gardhi (Goonjh) | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/22012034250891 — NBA Toilet Ramotar Sharma Gardhi (Goonjh) | Completed | 5400 | 5400 | 2014-07-19 | 2015-08-15
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701001007/RS/22012034503488 — Samudayak Swachchhata Parishar Nirman Kary Amardas Baba Hanuman Ji Mandir | Completed | 43000 | 42813 | 2020-12-14 | 2021-08-31
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701001007/RS/22012034562552 — Samudayik Sochalay Nirman Mohan Das Baba Mandir Bandha | Completed | 43000 | 40530 | 2021-10-20 | 2022-03-25
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64377 — NBA TOLITE MANSHARAM SO/BHAGBANT SABSUKH KA PURA | Completed | 4400 | 4400 | 2013-12-04 | 2016-05-09
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64386 — NBA TOILET MEBARAM SO/BANSHILAL SABSUKH KA PURA | Completed | 4400 | 4400 | 2013-12-05 | 2016-05-09
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64657 — NBATOILET KHARGO/ VANKHANDI SABSUKH KA PURA GOONJH | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64670 — NBATOILET RESHAM BAI/SHIVRAM sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64765 — NBATOILET RAMBHOG SHARMA SO/RAMKARAN SHARMA | Completed | 4400 | 4400 | 2014-02-06 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64769 — NBATOILET RAMBEER SHARMA SO/DURGAPRASAD SHARMA | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64771 — NBATOILET HARICHARAN SHARMA SO/CHETRAMSHARMA | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64773 — NBATOILET RAMNARAYAN SHARMA SO/RAMSINGH SHARMA | Completed | 4400 | 4400 | 2014-02-06 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64775 — NBATOILET KAPTAN SHARMA SO/RAMCHTRA SHARMA | Completed | 4400 | 4400 | 2014-01-21 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64777 — NBATOILET PAVAN SHARMA SO/RAMPRAKESH SHARMA | Completed | 4400 | 4390 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64779 — NBATOILET HARISHANKAR SHARMA SO/RAMBABU SHARMA | Completed | 4400 | 4400 | 2014-01-21 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/64784 — NBATOILETSIYARAM SHARMA SO/JAGRAM SHARMA | Completed | 4400 | 4400 | 2014-01-21 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66355 — NBA Shyambihari S/o jorsing Sabsukh Ka Pura Goonjh | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66359 — NBA Rajbeer S/oMansingh Sabsukh ka Pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66361 — NBA KubarSingh S/o Ramdeen sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66368 — NBA RamlachinS/o Ratansingh sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66372 — NBA Dolatram S/o Ramsingh sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66373 — NBA SugreebS/o Ramlachin sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66375 — NBA Vikram S/o Ramsebak sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66376 — NBA Khacheru S/o Tejsingh sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/66378 — NBA Rambeti S/o Ramdeen sabsukh ka pura | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79686 — NBA TOILET NARESH/VISHAMBAR SABSUKH KA PURA GOONJH | Completed | 4400 | 4400 | 2013-12-07 | 2016-05-09
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79806 — NBA TOILET RAMLACHIN / RAMDIN GARDHI GOONJH | Completed | 4400 | 3086 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79809 — NBA TOILET MUNNALAL RATHOR / JAGRAM RATHOR GARDHI | Completed | 4400 | 4400 | 2014-02-06 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79810 — NBA TOILET SHYAMSUNDAR SHARMA / BHAGBAN SHARMA GAR | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79811 — NBA TOILET RANBEER SHARMA / MALGAJI SHARMASHARMA G | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79812 — NBA TOILET KISHANPRASAD SHARMA / BANSHI SHARMAGARD | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79813 — NBA TOILET MANOJ SHARMA / RAMSHANKAR SHARMAGARDHI | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79814 — NBA TOILET RAMKHILADI SHARMA / MUKUT SHARMA GARDHI | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79815 — NBA TOILET PARIMAL SHARMA / RAMJILAL SHARMA GARDHI | Completed | 4400 | 4400 | 2014-02-06 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79816 — NBA TOILET RAMPRAKESH SHARMA / RAMCHANRD SHARMAGAR | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79817 — NBA TOILET SUNDARI SHARMA / MAYARAM SHARMAGARDHI G | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79818 — NBA TOILET SANDEEP SHARMA / SHRIKRISHAN SHARMA GAR | Completed | 4400 | 4400 | 2013-12-05 | 2016-05-09
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79819 — NBA TOILET VISHWANATH SHARMA / RAMBABU SHARMA GAR | Completed | 4400 | 4400 | 2013-12-07 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79820 — NBA TOILET SATYRAM SHARMA / BHAGIRATH SHARMA GARDH | Completed | 4400 | 4400 | 2014-01-22 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79821 — NBA TOILET RAMSHANKAR SHARMA /MATAPRASAD SHARMA G | Completed | 4400 | 4400 | 2014-01-21 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79822 — NBA TOILET HARIPRASAD SHARMA / RAMSEBAK SHARMA GAR | Completed | 4400 | 4400 | 2014-02-06 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001007/RS/79823 — NBA TOILET DINESH SHARMA / RAMBHAROSI SHARMA GARDH | Completed | 4400 | 4400 | 2013-12-05 | 2014-08-26
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701001007/SK/599 — Bharat Nirman Rajeev Gandhi Sewa Kendra,GOONJH | Completed | 1450000 | 860430.8 | 2013-09-20 | 2022-08-10
MORENA / AMBAH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/1192 — Nala Bandhan Subsukh Ka pura Gooj | Completed | 99000 | 98868 | 2012-09-24 | 2015-11-05
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/209 — सोकपिट गडडा रामनिवास के दरवाजे | Completed | 11200 | 6300 | 2008-11-01 | 2014-08-07
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/213 — सोकपिट गडडा गदी रामदीन के थोक | Completed | 335000 | 7362 | 2009-02-22 | 2014-08-07
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/214 — सोकपिट गडडा गढी स्‍कूल वाला हेड पम्‍प | Completed | 335000 | 7362 | 2009-02-22 | 2014-08-07
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/215 — सोकपिट गडडा गुज सुखका पुूराोवासे केमाप | Completed | 235000 | 6270 | 2009-02-16 | 2014-08-07
MORENA / AMBAH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/22012034708817 — Talab Nirman Kary parmar ki Khadi | Completed | 1477772.11 | 498144 | 2021-05-27 | 2022-12-25
MORENA / AMBAH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701001007/WC/22012034779945 — NAVEEN TALAB NIRAMAN BAVESHWARI NARIYA GOONJH | Completed | 1482138.28 | 1330883.38 | 2021-07-12 | 2025-03-31
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701001007/WC/22012035026698 — Bund Nirman Kary Uncha Teela Nariya ke Pas Goonj | Completed | 830325.37 | 725279.6 | 2023-05-06 | 2025-07-12
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701001007/WC/22012035096089 — Any Cut Nirman kary Chhukan Wali Nariya Datiya Siddh | Completed | 1415458.37 | 1390471 | 2023-09-08 | 2024-04-09
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701001007/WC/22012035096090 — Any Cut Nirman kary Hingota Wali Nariya Datiya Siddha | Completed | 1400901.03 | 1376846 | 2023-09-06 | 2024-09-03
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701001007/WC/22012035096091 — Any Cut Nirman Kary Bade Neenv ka Ped Datiya Siddh | Completed | 1398618.33 | 1374624 | 2023-09-06 | 2024-10-10
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1701001007/WC/22012035155040 — NAVEEN GALI PILUG GOONJH | Completed | 848986.77 | 789433 | 2024-03-03 | 2025-03-31
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001007/WC/22012035155044 — BOND NIRMAN KARY SANIDEV MANDIR KE PASS GOONJH | Completed | 970834.52 | 883243 | 2024-03-03 | 2025-03-31
MORENA / AMBAH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701001007/WC/340 — नालाबंधान सवसुखकापुरा | Completed | 0 | 129564 | 2011-01-25 | 2011-06-18
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/73 — सोख्‍ता गडडा | Completed | 0 | 0 | 2008-05-16 | 2008-05-16
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001007/WC/74 — सोख्‍ता गडडा | Completed | 0 | 0 | 2008-05-23 | 2008-05-23
MORENA / AMBAH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701001007/WC/9993632132 — Khait Talab Sub Sukha Ka Pura Goonj 4 | Completed | 30000 | 7008 | 2013-06-08 | 2015-11-05