## Work List
Exported on: 2026-09-03 15:40:07
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: MAHURI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701001054/AV/22012034580519 — Dining Hall Nirman, P.S. Mahuri | Deleted | 0 | 0 | 2021-04-14
MORENA / AMBAH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701001054/AV/4992 — Aanganwadi Bhawan | Deleted | 0 | 0 | 2016-04-14
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/101 — व़क्षारोपण पीएमरोड मई | Completed | 46000 | 6710 | 2008-09-13 | 2013-03-06
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/112 — व़क्षारोपण महूरी सिचाई का कार्य | Completed | 2000 | 9180 | 2008-09-22 | 2014-08-14
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/114 — व़क्षारोपण की साफ सफाई च निदाई गुढाई महुरी हनुमान जी मंदिर | Completed | 15000 | 24978 | 2008-11-03 | 2014-08-14
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/125 — वक्षारोपण कायर् निमार्सग् कसिहािय | Deleted | 0 | 0 | 2009-02-12
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/135 — तार फेसिंग व़क्षारोपण कार्य महूरी मदिंर हनुमान जी का मंन्दिर | Completed | 471000 | 601494 | 2009-02-14 | 2014-08-14
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/138 — व़क्षारोपड हनुमान जी मदिर महुरी | Completed | 0 | 71733 | 2008-09-15 | 2014-08-14
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/14 — व्रक्षारोपण | Completed | 425500 | 156437.28 | 2008-07-29 | 2014-08-14
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/146 — व्रक्षारोपण हरियाली महोत्‍सव महूरी हनुमान जी मन्‍दिर महूरी | Deleted | 0 | 0 | 2008-04-01
MORENA / AMBAH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/147 — वक्षा रोपड कार्य हनूमान जी मीदिर महूरी | Deleted | 0 | 0 | 2009-10-16
MORENA / AMBAH | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701001054/DP/22012034234557 — Group Plantation Mahuri | Completed | 159000 | 40262 | 2016-08-06 | 2020-09-21
MORENA / AMBAH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701001054/DP/22012034238158 — Shanti Dham Nirman Karya Mahuri | Completed | 180000 | 178587 | 2017-02-16 | 2019-08-24
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701001054/DP/22012034597296 — Vasudha Vandha-Amrit Vatika, Pani ke tanki ke pas, Mahuri GP Mahuri | Ongoing | 55847.4 | 6386 | 2023-09-13
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001054/FP/22012034625699 — Nala Nirman Ramvilash Ke Makan Se Jagdish Ke Makan Tak Mahuri | Completed | 43350 | 42846 | 2021-08-12 | 2022-01-03
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001054/FP/22012034628069 — Nala Nirman Satyapal Ke Makan Se Beerendra Singh ke Makan Tak, Mai | Closed | 32850 | 0 | 2022-02-11
MORENA / AMBAH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001054/FP/22012034630724 — Nala Nirman kary Ramniwas ke Makan Se Kesahv ke Makan Tak | Closed | 0 | 0 | 2022-08-15
MORENA / AMBAH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001054/FP/22012034630725 — Nala Nirman kary Ramniwas ke Makan Se Kesahv ke Makan Tak | Completed | 60750 | 60180 | 2022-11-20 | 2022-12-30
MORENA / AMBAH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701001054/FP/22012034631604 — Kaccha nala Nirman, Lafoora ke makan se Nadi tak, Mahuri | Closed | 0 | 0 | 2022-08-15
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701001054/FP/22012034632104 — Nala Nirman Pancham Singh Ke Makan Se Ramkhiladi Ke Makan Tak Mahuri | Completed | 36000 | 35558 | 2023-07-24 | 2024-06-30
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701001054/FP/22012034636998 — 15 Van Bitt Nala Nirman Kary Sonu Ke Makan Se Mandir Tak Khyaliram Ka Pura Mahuri | Completed | 68400 | 67958 | 2024-03-11 | 2024-09-02
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701001054/FP/22012034638775 — Nala Nirman Sonu Ke Makan Se Pooran Ke Khet Tak | Completed | 27300 | 26070 | 2024-03-11 | 2024-09-02
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001054/IF/1000040361 — Cattel Shed Brijraj Singh / Ramdeen Mahuri | Completed | 61000 | 58919.39 | 2013-09-28 | 2017-01-25
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001054/IF/1000040372 — Cattel Shed Ajay Singh / Jandel Singh Mai Mahuri | Completed | 61000 | 52384.81 | 2013-09-28 | 2016-12-06
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001054/IF/1000040381 — Cattel Shed Vishal Singh / Uttam Singh Mahuri | Completed | 61000 | 59944.67 | 2013-09-28 | 2017-06-12
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001054/IF/1000040386 — Cattel Shed Shiv Singh / Ramdeen Singh Mai Mahuri | Completed | 61000 | 60514.58 | 2013-09-28 | 2017-04-25
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001054/IF/1000040390 — Cattel Shed devendra singh / ramdeen singh Mai Ma | Completed | 61000 | 62261.66 | 2013-09-28 | 2017-01-25
MORENA / AMBAH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701001054/IF/1000040394 — Cattel Shed Girraj Singh / Mukut Singh Mai Mahuri | Completed | 61000 | 56231.39 | 2013-09-28 | 2016-12-06
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/156 — मेंडबंधान कार्य देवेन्‍द्रि‍संह/रामदीनि‍संह महूरी | Completed | 26000 | 19008 | 2012-07-25 | 2014-08-14
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/171 — मेडबंधान कार्य मुकुट/रोशनि‍संह महूरी | Completed | 39000 | 38016 | 2012-08-08 | 2014-08-14
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/172 — मेडबंधान कार्य नीरजदेवी/हरेन्‍द्रि‍संह मई महूरी | Completed | 45611 | 44352 | 2012-08-01 | 2014-08-14
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/173 — मेंडबंधान कार्य ि‍शवि‍संह/रामदीन मई महूरी | Completed | 45611 | 45936 | 2012-07-18 | 2014-08-14
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701001054/IF/22012034350464 — plantation primary and middle school and road kinare | Completed | 335000 | 16072 | 2017-06-15 | 2020-09-21
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701001054/IF/22012034350492 — plantation pmay road kinare bumiya mandir middle school | Completed | 335000 | 16038 | 2017-06-15 | 2020-09-21
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701001054/IF/22012034383336 — Group Plantation Mahuri | Closed | 0 | 0 | 2017-10-02
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701001054/IF/22012034871676 — NADEP Nirman, Omkar/Brelal, Mahuri | Completed | 15603.26 | 14874 | 2021-11-18 | 2023-06-27
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701001054/IF/22012034871679 — NADEP Nirman, Ramkhtyar/Samle, Mahuri | Completed | 15603.26 | 14874 | 2021-11-18 | 2023-06-27
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701001054/IF/22012034871681 — NADEP Nirman, Malkhan/Ramnath, Mahuri | Completed | 15603.26 | 14874 | 2021-11-22 | 2023-06-27
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701001054/IF/22012034871685 — NADEP Nirman, Devendra/Sumer, Mahuri | Completed | 15603.26 | 14874 | 2021-11-22 | 2023-06-27
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701001054/IF/22012034871686 — NADEP Nirman, Govind/Udal, Mahuri | Completed | 15603.26 | 14874 | 2021-11-18 | 2023-06-27
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035329084 — Farm pond Udal/Amar Singh Mahuri GP Mahuri | Physically Completed | 147621.16 | 129970.6 | 2025-04-27 | 2026-04-16
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035354552 — Khet Talab Nirman Jagdish Mahuri GP Mahuri | Physically Completed | 147621.16 | 125373.87 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035354562 — Khet Talab Nirman Kashiram Mai GP Mahuri | Approved | 147621.16 | 0 | 2025-04-14
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035377210 — Khet Talab Nirman Sishupal/Parimal Mahuri GP Mahuri | Completed | 147621.16 | 106749 | 2025-05-01 | 2025-11-01
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035424422 — Khet Talab Pancham Singh/Ramdas Mahuri GP Mahuri | Physically Completed | 147621.16 | 131122.9 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035424447 — Khet Talab Ramsewak/Rambaran Mahuri GP Mahuri | Completed | 147621.16 | 105183 | 2025-05-01 | 2025-11-01
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035424458 — Khet Talab Pannalal/Vijay Singh Mahuri GP Mahuri | Suspended | 147621.16 | 261 | 2025-05-01
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035424470 — Khet Talab Ramotar/Ramkishun Mahuri GP Mahuri | Completed | 147621.16 | 105966 | 2025-05-01 | 2025-11-01
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035424490 — Khet Talab Vishambar/Hariram Mahuri GP Mahuri | Completed | 147621.16 | 106749 | 2025-05-01 | 2025-11-01
MORENA / AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701001054/IF/22012035426963 — Dugwell Recharge Ramakhtyar/Badan singh Mahuri GP Mahuri | Physically Completed | 28237.92 | 24800.24 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701001054/IF/22012035426979 — Dugwell Recjarge Amarsingh/Samle Mahuri GP Mahuri | Physically Completed | 28237.92 | 24800.24 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701001054/IF/22012035427003 — Dugwell Recharge Sumer singh/Narayan singh Mahuri GP Mahuri | Physically Completed | 28237.92 | 24800.24 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701001054/IF/22012035427017 — Dugwell Recharge Radheshyam/Haripal Mahuri GP Mahuri | Physically Completed | 28237.92 | 24800.24 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035446316 — Khet Talab Nirman Hariom/Ramnath Mahuri GP Mahuri | Suspended | 147621.16 | 261 | 2025-05-02
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035446356 — Khat Talab Nirman Makhan Lal/Ramnath Mahuri GP Mahuri | Suspended | 147621.16 | 261 | 2025-05-02
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035446422 — Khet Talab Nirman Shyamveer/Jashram Mahuri GP Mahuri | New | 0 | 0 | 2025-04-14
MORENA / AMBAH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/22012035446524 — Khet Talab Shyamveer/Jasram Mahuri GP Mahuri | Physically Completed | 147621.16 | 131122.9 | 2025-05-01 | 2026-04-16
MORENA / AMBAH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/IF/261 — 1701001054/IF/261 | Completed | 50364 | 45936 | 2012-08-16 | 2014-08-14
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/193452 — Construction of IAY House -IAY REG. NO. MP-01-001-054-001/27B | Completed | 14310 | 12664 | 2017-09-29 | 2020-07-18
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/193453 — Construction of IAY House -IAY REG. NO. MP-01-001-054-001/6 | Completed | 14310 | 4876 | 2017-09-29 | 2020-07-18
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/279217 — Construction of IAY House -IAY REG. NO. MP3946852 | Completed | 15030 | 15238 | 2017-02-03 | 2020-02-10
MORENA / AMBAH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4320952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126934354 | Completed | 18360 | 17901 | 2022-09-27 | 2023-06-27
MORENA / AMBAH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4334204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133747338 | Completed | 18360 | 17901 | 2022-09-27 | 2023-06-27
MORENA / AMBAH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4374846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133748073 | Completed | 18360 | 18003 | 2022-11-06 | 2023-07-05
MORENA / AMBAH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4383176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133746980 | Completed | 18360 | 17748 | 2022-11-22 | 2023-08-15
MORENA / AMBAH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4528291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133746398 | Physically Completed | 23490 | 22086 | 2025-01-10 | 2026-03-29
MORENA / AMBAH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4528672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100024 | Physically Completed | 23490 | 22086 | 2025-01-10 | 2026-03-29
MORENA / AMBAH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/4719196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100029 | Approved | 23490 | 0 | 2024-09-23
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/529022 — Construction of IAY House -IAY REG. NO. MP2774566 | Completed | 15030 | 15378 | 2017-02-18 | 2018-08-14
MORENA / AMBAH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/546076 — Construction of IAY House -IAY REG. NO. MP3243906 | Completed | 15030 | 15402 | 2017-02-18 | 2018-05-20
MORENA / AMBAH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701001054/IF/IAY/567252 — Construction of IAY House -IAY REG. NO. MP3942905 | Completed | 15030 | 14460 | 2017-09-22 | 2018-06-11
MORENA / AMBAH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/100 — पी एम रोड से रामदीन का पूरा पहूच मार्ग | Completed | 0 | 166478 | 2009-07-27 | 2014-08-14
MORENA / AMBAH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/109 — मिटट्री मुरम हनुमान जी मन्‍दीर से लक्षी का पुरा | Completed | 0 | 48412 | 2009-09-25 | 2014-08-14
MORENA / AMBAH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/14 — िमटटी मुरम रोड | Completed | 437400 | 194435 | 2008-07-10 | 2014-08-14
MORENA / AMBAH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/20 — िमटटी मुरम रोड | Completed | 463700 | 189387 | 2008-06-19 | 2014-08-14
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034162815 — Panch Parmeswar Mahaveer Singh ke Darwaje se Gopal Singh Baraitha tak 250 Meeter Mahuri | Deleted | 0 | 0 | 2013-04-14
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/22012034162816 — Mitti Graval Road Surendra Singh ke Darwaje se Dulare Singh ke Pura tak 800 Meeter Mahuri | Deleted | 0 | 0 | 2013-04-14
MORENA / AMBAH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169778 — Conversion CC Road Nali Sahit Mahaveer Gurjar ke D | Completed | 116160 | 98133.9 | 2013-06-05 | 2015-07-08
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169841 — Panch Parmeswar CC road nali Sahit Matadeen Sharma ke Darwaje Se Hanuman Ji Mandir Tak Khyaliram Ka | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169842 — Panch Parmeswar CC Road Main Road se Shivji ke Mandir tak Ramdeen Ka Pura Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169843 — Panch Parmeswar CC Road Nali Sahit Munna Singh Tomar ke Darwaje se Munni Lal Sharma ke Darwaje Tak M | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169844 — Panch parmeswar CC road Nali Sahit Gov PS School Se Baretha Mohalla Tak Mahuri | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169846 — Conversion CC Road Nali Sahit Rajendra ke Darwaje se Keshari Harijan Basti Tak Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169847 — Panch Parmeswar CC road Nali Sahit Main Kharanja se Daulat Ram ke Darwaje Tak Mahuri | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169848 — Panch Parmeswar CC Road Nali Sahit Jagdeesh ke Darwaje se Hanuman Ji Ke Mandir Tak Mahuri | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169849 — Panch parmeswar CC road nali Sahit Ramdhar Singh ke Darwaje se Fool Singh Baretha ke Darwaje Tak Mah | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169850 — Panch Parmeswar CC Road Nali Sahit Devendra Singh ke Darwaje se Akle ke Darwaje Tak Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034169852 — Panch Parmeswar CC road Nali Sahit Nehpal Ke Darwaje se Shri Lal ke Darwaje Tak Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/22012034169853 — Mitti Bajari Road Cheetal ke Darwaje se Jahar Singh ke Kua Tak Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/22012034169854 — Mitti Bajari Mitti Bharai Road Surendra Singh ke Darwaje Se Dulare Singh ke Pura Tak Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034288501 — PP CC Road Nali Sahit Mata ke Mandir Se Baraitha ke Makan ki Or Mahuri | Completed | 299473 | 282853 | 2015-12-19 | 2016-07-20
MORENA / AMBAH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034330318 — cc road niramad munni ke makan se kesab singh ke makan tak gram mai | Completed | 28762 | 26084 | 2017-03-09 | 2017-10-15
MORENA / AMBAH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034351924 — cc road nirmad sultan singh bhaduriya ke makan se satyapal ke makan tak | Completed | 26550 | 26488 | 2017-09-07 | 2017-10-15
MORENA / AMBAH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034397702 — DPR CC Road NIrman Harendra ke makan Se Hanuman Mandir Tak Village & GP Mahuri | Completed | 27900 | 27200 | 2019-02-15 | 2019-07-10
MORENA / AMBAH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034397706 — Dpr CC Road Nirman Chimman Singh Kushwah ke Makan Se Mahaveer ke Makan Tak Village & GP Mahuri | Completed | 34875 | 33544 | 2019-01-14 | 2019-08-10
MORENA / AMBAH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034508677 — DPR CC Road Nali Nirman Khyaliram ka Pura | Completed | 41250 | 41706 | 2020-02-05 | 2020-05-10
MORENA / AMBAH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034508680 — DPR CC Road Nali Nirman Randin ka Pura | Completed | 49500 | 34686 | 2020-02-03 | 2020-06-08
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034525479 — DPR CC Road Nirman Pooran Gurjar ke Makan Se Mandir Tak, Khyaliram ka Pura | Completed | 63180 | 62890 | 2020-07-03 | 2020-08-20
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034525481 — DPR CC Road Nirman Aam Rasta Se Ballu Ke Makan Tak Ramdin Ka Pura | Completed | 8910 | 8360 | 2020-06-26 | 2020-08-20
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701001054/RC/22012034526194 — Khet sadak Nirman,Mahuri se shantidham tak, Mahuri | Closed | 0 | 0 | 2020-04-20
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034536122 — DPR CC Road Nali Nirman Madhymik Vidhyalay Mahuri Se Khar Tak Mahuri | Completed | 38250 | 38000 | 2020-09-11 | 2020-11-20
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034536124 — DPR CC Road Nali Nirman Amar Singh Ke Makan Se Udal Ke Makan Tak Mahuri | Completed | 18326 | 20520 | 2020-09-11 | 2020-11-30
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701001054/RC/22012034540364 — Sudur Sampark Sadak Nirman, Mai Road Se Ramdeen ka Pura tak, GP Mahuri | Completed | 1495334.5 | 1346468.14 | 2020-09-24 | 2021-06-20
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034541950 — 15 Van Bitt CC Road Nirman Pancham ke Makan Se Hotam ke Makan Tak Mahuri | Completed | 29452 | 29260 | 2020-09-27 | 2021-01-10
MORENA / AMBAH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034607010 — 15 Van Bitt CC Road Nali Nirman Keshav Ke Makan Se Munni Ke Makan Tak Mai | Completed | 25200 | 21423 | 2022-03-02 | 2022-05-10
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034629102 — CC ROAD Avam Nali Nirman Kalicharan Ke Makan Se Akhilesh Jatav Ke Makan Tak Avam Dayaram Mahor Ke | Completed | 30900 | 30719 | 2023-08-14 | 2024-06-30
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034651392 — 15 Van Bitt CC Road Nirman Vasudev ke Makan Se Ramvilash ke Makan Tak GP Mahuri | Closed | 0 | 0 | 2023-04-14
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034651395 — 15 Van Bitt CC Road Nirman Vasudev ke Makan Se Ramvilash ke Makan Tak GP Mahuri | Completed | 67350 | 67289 | 2023-09-11 | 2024-06-30
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701001054/RC/22012034666587 — Khet Sadak Nirman, Ramkhtyar Pura se Mahesh ke khet tak, Mahuri GP Mahuri | Completed | 2479508.87 | 2271186.83 | 2023-10-08 | 2025-07-22
MORENA / AMBAH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034679754 — C.C.Road Avam Nali Nirman Primary school se Mahaver Gurjar ke Makan Tak,Mahuri | Completed | 57000 | 56598 | 2024-03-11 | 2024-10-01
MORENA / AMBAH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/22012034835027 — 15 Ban Bitt CC Road PM Road Se Samudayik Bhawan Tak GP Mahuri | Completed | 53700 | 43326 | 2025-04-15 | 2025-07-22
MORENA / AMBAH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/225 — पंचपरमेश्‍वर सीसी खरंजा निर्माण स्‍कूल से महावीर के द्वार तक महूरी | Completed | 126303 | 126084.6 | 2012-03-14 | 2015-06-26
MORENA / AMBAH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701001054/RC/51 — सी.सी.खरंजा निर्माण कार्य | Completed | 0 | 52992.96 | 2009-01-11 | 2009-02-05
MORENA / AMBAH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701001054/RC/84 — मिटटी मुरम रोड हनुमान जी मंन्दिर पहुचा मार्ग | Completed | 471000 | 158484.18 | 2009-07-15 | 2014-08-14
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034236310 — N.B.A.Toilet shivraj singh/chhote singh | Completed | 5400 | 5400 | 2014-07-31 | 2015-08-19
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034236323 — N.B.A.Toiletpremsingh/ankale | Deleted | 5400 | 0 | 2014-04-01
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034236333 — N.B.A. toilet asharam/nahene | Deleted | 5400 | 0 | 2014-04-01
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034236342 — N.B.A. toilet satrughan/bheekaram | Deleted | 0 | 0 | 2014-05-28
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034236355 — N.B.A. toilet ramvilash/betal | Deleted | 5400 | 0 | 2014-04-01
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034238773 — N.B.A.Toilet Dharmendra singh /veerendra singh | Completed | 5400 | 5400 | 2014-07-31 | 2015-08-19
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034238798 — N.B.A. Toilet Gyan singh /raghuvir singh | Deleted | 5400 | 0 | 2014-04-01
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034254292 — NBAtoilet vishal singh/ uttam singh | Completed | 5400 | 5400 | 2014-07-31 | 2015-08-19
MORENA / AMBAH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701001054/RS/22012034254548 — N.B.A. Toilet gangeet singh/balbhadur singh | Completed | 5400 | 5400 | 2014-07-31 | 2015-08-19
MORENA / AMBAH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701001054/RS/22012034498289 — Samudayik Sochalay Mahuri | Completed | 43000 | 42831 | 2021-01-15 | 2021-04-15
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701001054/RS/22012035133934 — Nala Nirman Ramvilash ke Makan se Dharmu Baba Tak Mahuri | Approved | 0 | 0 | 2024-08-15
MORENA / AMBAH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701001054/RS/22012035133935 — Nala Nirman Ramvilash ke makan se Dharmu Baba Tak Mahuri | Completed | 78750 | 78354 | 2025-01-17 | 2025-07-22
MORENA / AMBAH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701001054/WC/113 — तालाब गहरीकरण | Completed | 80000 | 72460 | 2008-06-01 | 2009-02-17
MORENA / AMBAH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701001054/WC/22012034439033 — तालाब निर्माण कार्य महूरी | Closed | 0 | 0 | 2018-10-02
MORENA / AMBAH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701001054/WC/22012034628661 — Sokhta Gadda Nirman kary 05 | Closed | 0 | 0 | 2021-01-27
MORENA / AMBAH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701001054/WC/22012034643521 — Earthan Bund Nirman, Panchi ke Nariya, Mahuri | Completed | 600729.32 | 425087 | 2021-04-23 | 2023-04-10
MORENA / AMBAH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701001054/WC/22012034750423 — Water Harvesting, M.S. Mai, GP Mahuri | Closed | 27770.12 | 0 | 2021-04-01
MORENA / AMBAH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701001054/WC/22012034750431 — Watrer Harvesting, Anganwadi No.93, Mahuri | Completed | 20940.83 | 16888.78 | 2021-06-22 | 2022-10-01
MORENA / AMBAH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701001054/WC/22012034750442 — Sokpit Nirman (Panna lal, Mahadev mandir, Baretha Mohalla, Murli patel-04 No) Mahuri | Closed | 76925.58 | 0 | 2021-04-01
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001054/WC/22012035032925 — GWIMP gali plug Nirman, Madho ke khet ke pas, Mahuri | Completed | 205630.64 | 177342 | 2023-05-05 | 2023-09-23
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001054/WC/22012035032928 — GWIMP Gali plug Nirman, Pappu ke khet ke pas, Mahuri | Completed | 155097.98 | 137426 | 2023-05-08 | 2023-09-23
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701001054/WC/22012035032930 — GWIMP Gali plug Nirman, Mata Mandir ke pas, Mahuri | Completed | 648784.98 | 524420.48 | 2023-09-20 | 2026-01-31
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701001054/WC/22012035120381 — Talab Nirman, Middle school ke peeche, Mai GP Mahuri | Ongoing | 1421814.62 | 781097 | 2023-10-07
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701001054/WC/22012035120383 — Talab Nirman, Pakki par ke pas Mai, GP Mahuri | Physically Completed | 1454074.82 | 1332817.46 | 2023-10-07 | 2026-04-19
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701001054/WC/22012035120388 — Talab nirman, Churhela wale khar par, Mai | Closed | 0 | 0 | 2023-08-15
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701001054/WC/22012035120389 — Talab Nirman, Dhai wale khar par, Mai | Closed | 0 | 0 | 2023-08-15
MORENA / AMBAH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001054/WC/22012035166985 — anicut nirman karya kol bala nala ke pass | Physically Completed | 1479037.21 | 1328539 | 2024-03-11 | 2026-04-19
MORENA / AMBAH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701001054/WC/22012035212816 — Parculation Tank Nirman Adiram ke khet ke pas Churahela wala khar Mai GP Mahuri | Ongoing | 1470194.77 | 90288 | 2024-07-29
MORENA / AMBAH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701001054/WC/22012035212848 — Talab Nirman Dhai wala khar Mai GP Mahuri | Ongoing | 1474494.01 | 7290 | 2024-07-29
MORENA / AMBAH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701001054/WC/274 — सोक पिट निर्माण कार्य | Completed | 0 | 0 | 2008-04-01 | 2013-03-06
MORENA / AMBAH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701001054/WC/9993633046 — Talab Gahreekaran Bhumia Mandir ke Pas Mai | Deleted | 0 | 0 | 2013-01-26
MORENA / AMBAH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701001054/WH/22012034332149 — Renovation of Bund | Completed | 91000 | 84308 | 2018-02-21 | 2018-12-20