## Work List
Exported on: 2026-09-07 11:06:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BUDHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / PORSA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701002001/FP/22012034367526 — नाला निर्माण कार्य भबर सिंह के मकान से मेन नाले तक विनोद के मकान ओर मुकेश के मकान तक बुधारा | Ongoing | 1301170.39 | 0 | 2020-12-08
MORENA / PORSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701002001/IF/22012035279998 — खेत तालाब निर्माण क्षत्रशाल के खेत के पास बुधारा | Approved | 473363.74 | 0 | 2024-10-02
MORENA / PORSA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701002001/IF/22012035308498 — khet talab nirman keshkali k khet me budhara | Ongoing | 485223.15 | 0 | 2025-06-26
MORENA / PORSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701002001/IF/22012035308500 — Khet Talab NIrman nitin k khet me budhara | Ongoing | 496723.41 | 0 | 2025-03-30
MORENA / PORSA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701002001/IF/22012035608989 — EK BAGIYA MAA KE NAAM SUSHEELA MP-01-002-001-001/1644 | Ongoing | 266577.25 | 0 | 2025-11-17
MORENA / PORSA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701002001/IF/IAY/720316 — Construction of IAY House -IAY REG. NO. MP1717624 | Approved | 27000 | 0 | 2017-03-19
MORENA / PORSA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701002001/IF/IAY/766507 — Construction of IAY House -IAY REG. NO. MP3260303 | Approved | 27000 | 0 | 2017-03-19
MORENA / PORSA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1701002001/LD/22012034475132 — चारागाह विकास गोशाला बुधारा | Ongoing | 750924.49 | 0 | 2020-01-31
MORENA / PORSA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701002001/RC/22012034474314 — CC ROAD BALLI KE MAKAN SE DLU KE MAKAN KI | Ongoing | 10594 | 0 | 2019-10-04
MORENA / PORSA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701002001/RC/22012034527716 — khet sadak nirman karya mehdora road se budhara road hote hue porsa road se kheriya tak | Ongoing | 1498938.25 | 0 | 2020-09-28
MORENA / PORSA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701002001/RC/22012034827289 — mitti bajari road ki marmat karya mehdora road se budhara ki or | Approved | 7500 | 0 | 2024-08-15
MORENA / PORSA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701002001/WC/22012034616066 — sokhta gadda ramjilal mohalla | Ongoing | 18200.42 | 0 | 2021-07-26
MORENA / PORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701002001/WC/22012034763916 — Check dem 789 n.3 | Ongoing | 1448041.21 | 0 | 2024-03-16
MORENA / PORSA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1701002001/WC/22012034767948 — ARDHAN DAM NIRAMAN RAMU KE KHET KE PASS | Ongoing | 1499487.84 | 0 | 2021-12-04
MORENA / PORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701002001/WC/22012034865700 — cc chech dam no.13 | Ongoing | 1482698.3 | 0 | 2024-03-16
MORENA / PORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701002001/WC/22012034865706 — cc chech dam no.14 | Ongoing | 1484536.29 | 0 | 2024-03-16
MORENA / PORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701002001/WC/22012034868110 — CC CHECK DAM NO.18 | Ongoing | 1493182.17 | 0 | 2024-03-16
MORENA / PORSA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701002001/WC/22012034868300 — gali plag budhra | Ongoing | 1499327.13 | 0 | 2021-12-04
MORENA / PORSA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701002001/WC/22012034941614 — AMRIT SAROVAR MAHENDRA KE KHET KE PAAS | Ongoing | 2473471.61 | 0 | 2022-06-09
MORENA / PORSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701002001/WC/22012035167587 — gali plug nirman kary Badi karar ke pass gram panchayat budhara | Ongoing | 379567.87 | 0 | 2024-03-12
MORENA / PORSA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701002001/WC/22012035167597 — gali plug nirman kary srikrishan ke khet ke pass gram panchayat budhara | Ongoing | 379567.87 | 0 | 2025-07-17
MORENA / PORSA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701002001/WC/22012035255561 — नवीन तालाब निर्माण कार्य छत्रपाल के खेत के पास तरसमा | Approved | 0 | 0 | 2025-01-26
MORENA / PORSA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701002001/WC/22012035255563 — नवीन तालाब निर्माण कार्य शासकीय जमीन पर बुधारा | Ongoing | 784036.19 | 0 | 2025-03-30
MORENA / PORSA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701002001/WC/22012035255577 — नवीन तालाब निर्माण कार्य छत्रपाल के खेत के पास बुधारा | Ongoing | 1485615.42 | 0 | 2025-03-30