## Work List
Exported on: 2026-10-10 14:11:59
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BHANPUR
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701003003/AV/22012034368524 — shanti dham bhanpur | Completed | 245000 | 19264 | 2017-10-27 | 2018-07-25
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701003003/DP/22012034237879 — शांतिधाम निर्माण-जैतपुर भानपुर | Completed | 180000 | 162250 | 2017-02-05 | 2017-09-10
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003003/FP/22012034360271 — नाली निर्माण कार्य - रामे के घर से बेलनपुरी मंदिर, पुलिया की ओर। | Completed | 1261000 | 780533.06 | 2017-12-09 | 2018-12-28
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003003/IF/22012034345283 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य जैतपुर चम्बल | Completed | 335028 | 10996 | 2017-06-29 | 2019-11-20
MORENA / MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003003/IF/449 — मेढवंधान रामचरन | Completed | 24000 | 23558 | 2012-09-18 | 2016-01-01
MORENA / MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701003003/IF/450 — मेढवंधान | Completed | 14000 | 17326 | 2012-09-25 | 2016-01-01
MORENA / MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701003003/IF/451 — मेढवंधान | Completed | 14000 | 19620 | 2012-09-25 | 2016-01-01
MORENA / MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003003/IF/452 — मेढवंधान | Completed | 24400 | 23064 | 2012-09-18 | 2016-03-01
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003003/IF/9993692500 — पशुशैड निर्माण - फूल सिंह / शिव सिंह | Completed | 91000 | 66985 | 2015-12-06 | 2017-09-15
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003003/IF/9993692504 — पशुशैड निर्माण - जगदीश/कन्‍हईलाल | Completed | 91000 | 69384 | 2015-12-06 | 2017-09-15
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003003/IF/9993692527 — पशुशैड निर्माण -बकीलसिंह/हुकमसिंह | Completed | 91000 | 71135 | 2015-12-06 | 2017-09-15
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003003/IF/9993692534 — पशुशैड निर्माण - बीरेन्‍द्र सिंह/लज्‍जाराम | Completed | 91000 | 69935 | 2015-12-06 | 2017-09-15
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003003/IF/9993692538 — पशुशैड निर्माण - रामेश्‍वर/कम्‍मोद | Completed | 91000 | 73427 | 2015-12-06 | 2017-09-15
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003003/IF/IAY/541997 — Construction of IAY House -IAY REG. NO. MP3123184 | Completed | 15030 | 15570 | 2017-02-01 | 2018-07-26
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003003/IF/IAY/764275 — Construction of IAY House -IAY REG. NO. MP3158586 | Completed | 15030 | 12444 | 2017-04-29 | 2018-10-25
MORENA / MORENA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003003/LD/3799401360 — मेढबंधान कार्य - सुजान सिंह / धनीराम | Completed | 15500 | 14600 | 2013-08-31 | 2015-07-15
MORENA / MORENA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003003/LD/3799401361 — मेढबंधान कार्य - टुण्‍डा/गोपाल | Completed | 17600 | 10220 | 2013-08-05 | 2016-01-01
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003003/PG/22012034365394 — खेलमेैदान निर्माण कार्य - राजाघाट भानपुर | Completed | 186600 | 1032 | 2017-10-27 | 2018-07-25
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003003/RC/002 — सी सी रोड खंरजा निर्माण कार्य | Completed | 474000 | 48940 | 2008-11-20 | 2009-09-26
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/1119 — कार्य का नाम सी सी खरंजा | Completed | 0 | 59817 | 2012-02-22 | 2012-03-06
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/1120 — कार्य का नाम सी सी खरंजा | Completed | 0 | 63925 | 2012-03-06 | 2012-03-22
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/1121 — कार्य का नाम सी सी खरंजा नाली निर्माण | Completed | 0 | 63293 | 2012-03-23 | 2012-04-07
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/22012034162089 — सी सी खरंजा एवं नाली निर्माण कार्य पंचपरमेश्‍वर पट | Completed | 79673 | 76858 | 2013-06-28 | 2016-09-19
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003003/RC/22012034283308 — पत्थर खरंजा निर्माण कार्य - सरनाम सिंह व बैजनाथ के मकान से जण्डेल के मकान की ओर | Completed | 289000 | 166473 | 2015-09-09 | 2017-09-15
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003003/RC/22012034328040 — सुदुर ग्राम संपर्क सड़क निर्माण - हाईवे रोड से नारायण गिरि मंदिर जैतपुरा तक भानपुर | Completed | 1100000 | 448066.14 | 2017-02-23 | 2018-09-07
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/22012034336328 — सी सी खरंजा एवं नाली निर्माण कार्य - रामवरन के घर से कल्लो के घर तक ग्राम जैतपुर | Completed | 60000 | 59684 | 2017-05-21 | 2017-09-24
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/22012034445936 — सीसी. खरंजा एवं नाली निर्माण कार्य - जगदीश के घर से रामधन के घर तक ग्राम जेतपुर | Completed | 69255 | 67608 | 2019-02-23 | 2019-05-21
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/22012034472049 — सी.सी. खरंजा एवं नाली निर्माण कार्य - ओमप्रकाश के घर से राकेश के घर तक भानपुर | Completed | 76950 | 68464 | 2019-08-20 | 2019-12-18
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/22012034526153 — सी.सी. खरंजा नाली सहित निर्माण कार्य मैन रोड से महेन्द्र व बकीला के घर से निरंजन के घर तक | Completed | 69232 | 60420 | 2020-06-25 | 2020-08-18
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003003/RC/22012034540055 — सी.सी. खरंजा नाली संिहत मैन रोड से भवूती के घर तक | Completed | 39900 | 33060 | 2020-09-29 | 2021-01-03
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003003/RC/303 — पत्‍थर खरजा निर्माण कार्य | Completed | 0 | 133762 | 2009-07-02 | 2016-01-15
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003003/RC/317 — पत्‍थर खरजा निर्माण कार्य भानपुरा | Completed | 0 | 0 | 2008-04-01 | 2008-04-01
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003003/WC/01 — सोख्‍ता गडडा रोड किनारे राजघाट पास | Completed | 11500 | 9180 | 2008-05-01 | 2008-01-26
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034432236 — नवीन तालाब निर्माण कार्य - | Completed | 1089738.18 | 1041855.66 | 2019-10-18 | 2020-08-01
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003003/WC/22012034444253 — नवीन तालाब निर्माण कार्य खार में जेतपुर भानपुर | Completed | 1384000 | 1252432.75 | 2019-03-08 | 2019-09-15
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034487799 — तालाब निर्माण कार्य - ग्राम जैतपुर मे कुई के खार पर। | Completed | 1327324.38 | 1201092.9 | 2020-07-23 | 2020-12-03
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003003/WC/22012034557636 — तालाब निर्माण कार्य घूघस के खार में भानपुर | Completed | 1365931.68 | 1180266.49 | 2020-06-27 | 2020-12-03
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003003/WC/22012034581535 — नवीन तालाब निर्माण कच्ची नहर की खार में ग्राम पंचायत भानपुर | Completed | 1447411.61 | 1224990 | 2020-09-13 | 2023-02-28
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637393 — nws earthan dam ali baba ke pass | Completed | 1499871.19 | 1492112 | 2021-04-28 | 2021-10-06
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637398 — nws eartham dam ghana khjaar me | Completed | 1493931.06 | 1485306 | 2021-04-28 | 2021-12-23
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637401 — nws earthan dam shreewas ke khet ke pass | Completed | 1498633.64 | 1498336 | 2021-04-28 | 2021-12-23
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637402 — nws earthna dam jhori ke nare me | Completed | 1485241.48 | 1469804 | 2021-04-28 | 2021-10-06
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637405 — nws earthan dam mandir ke pass | Completed | 1495362.23 | 1489222 | 2021-04-28 | 2022-07-23
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637406 — nws check dam lembo khar me | Completed | 1496376.41 | 1475852 | 2021-04-28 | 2021-09-12
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637407 — nws check dam puliya ke pass | Completed | 1494521.43 | 1469252 | 2021-04-28 | 2021-09-12
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012034637410 — nws check dam jhikuta nara me | Completed | 1497556.92 | 1476726 | 2021-04-28 | 2021-09-12
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003003/WC/22012034637414 — nws gully plug umar wala nra me | Completed | 1469126.31 | 1292422 | 2021-04-28 | 2022-11-19
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003003/WC/22012034637415 — nws gully plug bogoa ke nare me | Completed | 1483434.81 | 1296897 | 2021-04-28 | 2022-11-19
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003003/WC/22012034637417 — nws gull plug jhagru me | Completed | 1492976.41 | 1255188 | 2021-04-28 | 2022-11-19
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003003/WC/22012034637419 — nws gully plug karil wale me | Completed | 1496236.82 | 926400 | 2021-04-28 | 2022-11-19
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713025 — nws earthan dam uchi chadi ke pass | Completed | 1498326.98 | 1223332.42 | 2021-10-22 | 2024-01-11
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713029 — nws earthan dam karil ke pass | Completed | 1499431.2 | 1328184.62 | 2021-10-12 | 2024-01-11
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713036 — nws check dam kary kimliya wale me | Completed | 1498748.15 | 1480344.24 | 2021-11-03 | 2023-10-03
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713039 — nws check dam kary lamba wala khaar me | Completed | 1495603.96 | 1475230 | 2021-06-04 | 2022-04-30
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713045 — nws check dam kary tedo khaar me | Completed | 1497966.09 | 1464222.24 | 2021-11-03 | 2023-10-03
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003003/WC/22012034713049 — nws check dam kary babul ke pass wale me | Completed | 1498986.43 | 1478827.49 | 2021-11-03 | 2023-10-03
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713058 — NWS earthan dam kary tapu ke pass me | Completed | 1497410.86 | 1466886 | 2021-06-04 | 2022-05-31
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003003/WC/22012034713065 — nws gully plug kary babu ke behad me | Completed | 1496310.71 | 863184 | 2021-10-22 | 2023-12-12
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701003003/WC/22012034713070 — nws gully plug kary bhamar ke pass | Completed | 1497023.56 | 1024344 | 2021-10-22 | 2023-12-12
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003003/WC/22012034926271 — nws/ctr earthan dam kary damo ke behd me | Completed | 1481327.54 | 1403229.48 | 2022-04-21 | 2023-10-03
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701003003/WC/22012034926282 — nws/ctr earhan dam kary hariya ke nare me | Completed | 1471363.38 | 1284173.67 | 2022-04-21 | 2024-06-26
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003003/WC/22012034926289 — nws/ctr earhan dam kary pamdi ke pass | Completed | 1491233.32 | 1430415.68 | 2022-04-21 | 2023-07-12
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003003/WC/22012034926345 — Nws/ctr earthan dam kary atto ke nare me | Completed | 1484644.2 | 1448842.77 | 2022-04-21 | 2023-07-05
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012035150942 — nws anicut nirman kary purani puliya ke pass | Completed | 1465801.47 | 1426145.32 | 2024-03-12 | 2024-12-02
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003003/WC/22012035150944 — nws anicut nirman kary barenda ke khaar me | Completed | 1469225.52 | 1375558 | 2024-03-12 | 2026-01-19