## Work List
Exported on: 2026-10-26 13:33:00
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BARETHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / MORENA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1701003007/AV/22012034465085 — गोशाला निर्माण | Completed | 2771628.29 | 2585497.42 | 2019-08-26 | 2021-04-01
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701003007/AV/22012034535255 — शांतिधाम निर्माण कार्य चेंटा | Completed | 283566.25 | 283141.04 | 2021-01-13 | 2022-02-10
MORENA / MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003007/AV/22012034665089 — शांतिधाम निर्माण कार्य बरेथा मे | New | 0 | 0 | 2025-01-24
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003007/DP/01 — व़क्षारोपण रोड किनारे बरै‍था | Completed | 466250 | 8670 | 2008-09-24 | 2008-04-14
MORENA / MORENA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003007/DP/22012034232847 — ब़क्षारोपण कार्य हाई स्‍कूल कैम्‍पस बरेथा | Completed | 159000 | 43019.25 | 2016-07-18 | 2020-12-09
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701003007/DP/22012034237625 — शांतिधाम निर्माण कार्य चेंटा बरेथा | Deleted | 245000 | 0 | 2017-02-01
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034494855 — वृक्षारोपण कार्य गोशाला एवं मंदिर सरोवर बारेथा | Ongoing | 677985.75 | 321478.57 | 2020-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003007/DP/22012034544403 — maa ki bagiya gov. primary school chenta | Completed | 20945.35 | 2316 | 2022-02-11 | 2023-07-11
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003007/DP/22012034544405 — maa ki bagiya gov.middle school chenta | Closed | 21445.35 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034545776 — Samudayak posan vatika baretha | Deleted | 0 | 0 | 2022-01-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034545777 — Samudayak posan vatika baretha | Closed | 685575.78 | 0 | 2022-01-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034545778 — Samudayak posan vatika baretha | Deleted | 0 | 0 | 2022-01-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034548576 — देवर्णय | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034548587 — देवारण्य निर्माण कार्य ग्राम पंचायत बरेथा | Closed | 685575.78 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Medicinal Plantation in Community land / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034551883 — देवारण्य योजना गोशाला के पास बरेथा | Closed | 0 | 0 | 2022-01-26
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003007/DP/22012034602653 — व्रक्षारोपण कार्य गौशाला के पास बरेथा मेरी माटी मेरा देश | Closed | 55847.4 | 0 | 2023-04-14
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Medicinal Plantation in Community land / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701003007/DP/22012034614539 — सामुदायिक पोषण वाटिका बरेथा | Ongoing | 427106.07 | 1944 | 2024-06-25
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034344331 — सार्वजनिक व्रक्षारोपण कार्य बरेथा रोड् से चेटा की और | Completed | 335000 | 15332 | 2017-07-01 | 2020-12-17
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034344338 — सार्वजनिक व्रक्षारोपण कार्य शाती धाम चेटा हनुमान मन्दिर बरेथा | Completed | 335000 | 12212 | 2017-07-01 | 2018-05-27
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034354163 — सार्वजनिक परिसर व्रक्षारोपण निर्माण कार्य डेयरी से मंदिर की ओर रोड किनारे | Completed | 335000 | 12212 | 2017-07-01 | 2018-05-27
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034354169 — व्रक्षारोपण निर्माण कार्य मंदिर से रोड किनारे चेटा की ओर | Completed | 335000 | 13245.5 | 2017-07-01 | 2020-12-12
MORENA / MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034665738 — निजी खेत में फलोद्यान रामनिवास /गुलाब सिंह ग्राम चेटा | Closed | 144181.62 | 0 | 2021-01-21
MORENA / MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034665739 — निजी खेत में फलोद्यान राजवीर /केदार सिंह ग्राम चेटा | Closed | 144181.62 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012034667522 — निजी खेत मैं फलोद्यान वीरेंद्र सिंह /लाखन सिंह | Ongoing | 144181.62 | 93687.76 | 2022-02-11
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034733548 — नाडेप निर्माण मिथलेस /दिलीप | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034733554 — नाडेप निर्माण कमलकिशोर/ शंकरलाल | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034733564 — नाडेप निर्माण बनवारी/जौहरीलाल | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034854808 — नाडेप निर्माण राघवेंद्र /रतन सिंह ग्राम चेटा | Completed | 18552.12 | 16415 | 2021-11-09 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034854809 — नाडेप निर्माण ब्रजेन्द्र /भगवान् सिंह ग्राम चेटा | Completed | 18552.12 | 16415 | 2021-11-09 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034854811 — नाडेप निर्माण अजयपाल /प्रयागसिंह ग्राम चेटा | Completed | 18552.12 | 16415 | 2021-11-09 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034855538 — नाडेप निर्माण राजवीर/रतन सिंह ग्राम चेटा | Completed | 18552.12 | 16415 | 2021-11-09 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034905653 — nadep nirmarn dadhiram/fundi chenta | Completed | 18552.12 | 16608 | 2021-11-23 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034905658 — nadep nirmarn bhart/duarika chenta | Completed | 18552.12 | 16608 | 2021-11-23 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034905688 — nadep nirman gavda/tikaram gram chenta | Completed | 18552.12 | 16608 | 2021-11-23 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034905736 — nadep nirman parshotam/fundi gram chenta | Completed | 18552.12 | 15836 | 2021-11-29 | 2022-08-12
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003007/IF/22012034906587 — nadep nirman manoj kumar/garsingh gram chenta | Completed | 18552.12 | 16608 | 2021-11-23 | 2022-08-12
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003007/IF/22012035438057 — khet talab nirmaan karya Manoj Shree chand, Baretha | Ongoing | 147621.16 | 261 | 2025-05-03
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003007/IF/22012035452976 — Khet Talab Nirmaan Karya Ramakant S/O Asharam Singh | Ongoing | 147621.16 | 522 | 2025-05-04
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003007/IF/22012035498999 — Dugwell Richarge Pit Nirmaan Karya Devendra S/O Jor Singh | Ongoing | 25899.46 | 4698 | 2025-05-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003007/IF/22012035499259 — Dugwell Richarge Pit Nirmaan Karya Kuldeep Singh S/O Naval Singh | Approved | 25899.46 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003007/IF/22012035499275 — Dugwell Richarge Pit Nirmaan Karya Dipendra Singh S/O Hariom Singh | Ongoing | 25899.46 | 3132 | 2025-05-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003007/IF/22012035499291 — Dugwell Richarge Pit Nirmaan Karya Vishwanath Singh S/O Jayram Sikarwar | Approved | 25899.46 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701003007/IF/22012035499303 — Dugwell Richarge Pit Nirmaan Karya Ran Singh S/O Ramdas Rathor | Approved | 25899.46 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012035636177 — Ek Bagiya Maa Ke Naam PREETI JADON 302034017 | Ongoing | 283818.64 | 1566 | 2025-12-11
MORENA / MORENA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012035659579 — Ek Bagiya Maa Ke Naam USHA/DHEER SINGH 118028515 | Ongoing | 283818.64 | 0 | 2026-05-07
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012035659584 — Ek Bagiya Maa Ke Naam JAINSHREE/SOHANLAL 107004554 | Ongoing | 283818.64 | 0 | 2026-01-31
MORENA / MORENA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003007/IF/22012035659587 — Ek Bagiya Maa Ke Naam NIRMALA DEVI PARMAR/DASRATH SINGH 119920460 | Ongoing | 283818.64 | 0 | 2026-05-07
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728272 — पशु शेट निर्माण कार्य मुरारीलाल /वीधाराम बघेल | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728283 — पशु शेट निर्माण कार्य राधेश्याम /रतन सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728299 — पशु शेट निर्माण कार्य राधेश्याम /रतन सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728302 — पशु शेट निर्माण कार्य रामसेवक /शंकर लाल शर्मा | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728304 — पशु शेट निर्माण कार्य रामऔतार/रामेश्वर बघेल | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728308 — पशु शेट निर्माण कार्य अशोक /शंकरलाल शर्मा | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728310 — पशु शेट निर्माण कार्य बटूरी परमार /बेनीराम | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728316 — पशु शेट निर्माण कार्य मुकेश सिंह /हुकम सिंह परमार | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728319 — पशु शेट निर्माण कार्य जोर सिंह /रघुनाथ सिंह परमार | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728322 — पशु शेट निर्माण कार्य पुष्पेंद्र सिंह /मकरंद सिंह परमार | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728325 — पशु शेट निर्माण कार्य हाकिम जाटव /दुआरिका | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728490 — पशु शेट निर्माण राजवीर बघेल /पदमन बघेल | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003007/IF/9993728499 — पशु शेट निर्माण जसरथ सिंह /केदार सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/1908848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4161658 | Completed | 15660 | 14640 | 2018-11-26 | 2019-05-15
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/1909110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4482176 | Completed | 15660 | 15684 | 2018-11-26 | 2019-04-23
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/1909422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4961085 | Completed | 15660 | 14628 | 2018-11-26 | 2019-05-15
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/1937275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5068308 | Completed | 15660 | 14628 | 2018-11-26 | 2019-05-15
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/34797 — Construction of IAY House -IAY REG. NO. MP-01-003-007-001/110 | Completed | 14310 | 5100 | 2017-03-10 | 2018-04-04
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/34798 — Construction of IAY House -IAY REG. NO. MP-01-003-007-001/111 | Completed | 14310 | 4098 | 2017-03-19 | 2018-04-04
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/34799 — Construction of IAY House -IAY REG. NO. MP-01-003-007-001/133 | Completed | 14310 | 10290 | 2017-03-19 | 2018-04-04
MORENA / MORENA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/3660993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125254954 | Completed | 18360 | 18099 | 2023-05-10 | 2024-10-22
MORENA / MORENA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/4200470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126443960 | Completed | 18360 | 16044 | 2023-08-21 | 2024-10-22
MORENA / MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/4525679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125255364 | Completed | 23490 | 21933 | 2024-11-04 | 2026-05-21
MORENA / MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/4528961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142995682 | Completed | 23490 | 21933 | 2024-10-25 | 2026-05-21
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/460532 — Construction of IAY House -IAY REG. NO. MP1698768 | Completed | 15030 | 14394 | 2017-02-18 | 2018-07-10
MORENA / MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/4918960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125254061 | Completed | 23490 | 23121 | 2025-03-20 | 2026-05-21
MORENA / MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/4918961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125255940 | Completed | 23490 | 23013 | 2025-03-21 | 2026-05-21
MORENA / MORENA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/4923953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149046170 | Completed | 23490 | 23274 | 2025-03-11 | 2026-05-21
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/507190 — Construction of IAY House -IAY REG. NO. MP2348065 | Completed | 15030 | 14352 | 2017-02-09 | 2018-07-10
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/520328 — Construction of IAY House -IAY REG. NO. MP2562062 | Completed | 15030 | 14262 | 2017-02-18 | 2018-07-30
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/53207 — Construction of IAY House -IAY REG. NO. MP-01-003-007-001/248 | Completed | 14310 | 4068 | 2017-03-10 | 2018-04-04
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/5748472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149046098 | Completed | 23490 | 22707 | 2025-08-25 | 2026-05-21
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/66252 — Construction of IAY House -IAY REG. NO. MP-01-003-007-001/105 | Completed | 14310 | 3066 | 2017-01-20 | 2018-04-04
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/66260 — Construction of IAY House -IAY REG. NO. MP-01-003-007-001/73 | Completed | 14310 | 10260 | 2017-03-10 | 2018-04-04
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/744039 — Construction of IAY House -IAY REG. NO. MP2346102 | Completed | 15030 | 13684 | 2017-04-26 | 2018-10-25
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/745015 — Construction of IAY House -IAY REG. NO. MP2373075 | Completed | 15030 | 13684 | 2017-04-26 | 2018-10-26
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/750265 — Construction of IAY House -IAY REG. NO. MP2550394 | Completed | 15030 | 14728 | 2017-04-26 | 2018-10-25
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003007/IF/IAY/776040 — Construction of IAY House -IAY REG. NO. MP3735783 | Completed | 15030 | 14716 | 2017-04-26 | 2018-10-03
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1701003007/LD/22012034469340 — चाराहगाह विकास कार्य ग्राम पंचायत बरेठा | Ongoing | 750924.49 | 671999.62 | 2020-01-17
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003007/RC/01 — मिटटी रोड आरौली शिवलालपुरा तक | Completed | 483500 | 20825 | 2008-05-23 | 2015-07-23
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034183029 — सी सी खरंजा एवं नाली निर्माण कार्य - हरिजन बस्‍ती | Completed | 83982 | 71694 | 2013-09-26 | 2015-01-05
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034183906 — सी सी खरंजा एवं नाली निर्माण कार्य - बनखण्‍डी मंदि | Completed | 602000 | 104385 | 2013-09-26 | 2015-01-05
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034208825 — सी. सी. खरंजा एंव नाली निर्माण - दर्शनसिंह के मकान | Completed | 116517 | 111652 | 2014-03-01 | 2015-01-05
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034218879 — सी. सी. खरंजा एंव नाली निर्माण - रामौतार के घर स | Completed | 84110 | 86606 | 2014-05-26 | 2015-07-01
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034218885 — सी. सी. खरंजा एंव नाली निर्माण - जाटव मौह्ल्ला रतन | Completed | 172330 | 130350 | 2014-05-26 | 2015-07-01
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034218889 — सी. सी. खरंजा .एंव नाली निर्माण - गजराज के मकान से | Completed | 116012 | 82668 | 2014-05-26 | 2015-07-01
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034285301 — सी सी खरंजा एवं नाली निर्माण् पुरसोत्तम के द्वार से मौहन सिंह के द्वार की ओर 2 कमल सिंह के द्वार से | Completed | 62258 | 61846 | 2015-12-07 | 2016-06-25
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034285303 — सी सी खरंजा एवं नाली निर्माण -1 रामानंनद के मकान से कमल सिंह परमार के मकान तक 2 रामभरत के मकान | Completed | 90366 | 90339 | 2015-10-13 | 2016-06-25
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034297302 — सी सी खरंजा एवं नाली निर्माण कार्य - अलवीर के मकान से मैनरोड की तरफ एवं मैनरोड से मंदिर की तरफ बरैथा | Completed | 91000 | 90592 | 2016-01-25 | 2017-10-22
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034297303 — सी सी खरंजा एवं नाली निर्माण - मैनरोड से मुरारी के घर की तरफ देवलाल का पुरा | Completed | 62000 | 57339 | 2016-01-25 | 2017-08-22
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309014 — पत्थर खरंजा हरिशंकर शर्मा घर से वनखंडी मंदिर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309038 — पत्थर खरंजा रामनिवास परमार के घर से मुन्नी बाल्मिक के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309058 — सी सी खरंजा मदन लाल घर से समसान घाट की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309061 — सी सी खरंजा रामप्रकाश के घर से मोतीराम गहलोत के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309063 — सी सी खरंजा जगराम गहलोत के घर से रामजीवन के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309065 — सी सी खरंजा हरिशंकर शर्मा के घर से लटूरी परमार के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309069 — खेत सड़क निर्माण डेरी से सुरेश परमार के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309072 — खेत सड़क निर्माण मैंन रोड से चक्रपान सिंह के पूरा की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309074 — खेत सड़क निर्माण चक्रपान सिंह के पूरा से पंचम सिंह के पूरा की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034309076 — पत्थर खरंजा रामनिवाश परमार के घर से मुन्नी बाल्मीक के घर की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034324964 — सी सी खरंजा एवं नाली निर्माण - लज्‍जाराम के मकान से अशोक के मकान तक बरेथा | Completed | 162300 | 102568 | 2017-03-10 | 2017-07-14
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034325299 — सुदूर ग्राम संपर्क सडक निर्माण - चैंटा मैनरोड से दयालदास का पुरा एवं जगन्‍नाथ के पुरा की ओर बरेथा | Completed | 1100000 | 842642.1 | 2017-02-14 | 2019-02-07
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034331401 — सी सी खरंजा एवं नाली निर्माण - रामप्रकाश जाटव के घर से मोतीराम के घर तक बरेथा | Completed | 118755 | 115928 | 2017-04-06 | 2017-07-14
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034331405 — सी सी खरंजा एवं नाली निर्माण कार्य - भारत गली एवं मंगल के घर से बदाई के घर एवं शमशानघाट | Completed | 71178 | 71724 | 2017-05-09 | 2017-07-26
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034331410 — सी सी खरंजा एवं नाली निर्माण कार्य - हैण्डपम्प से सुरेश के घर तक शिवलाल का पुरा बरेथा | Completed | 28859 | 27864 | 2017-05-12 | 2017-07-14
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003007/RC/22012034340963 — सुदूर ग्राम सम्पर्क सड़क निर्माण कार्य मैन रोड बरेथा से पंचम सिंह का पुरा एबं पृथवी पूरा | Completed | 1498000 | 1287012.36 | 2017-06-09 | 2021-01-20
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034340967 — सी सी खरंजा निर्माण कार्य रामोतार के घर से देवीराम के घर तक टीकाराम का पूरा | Completed | 76000 | 73444 | 2017-06-12 | 2017-07-26
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034348284 — सी सी खर्ंजा ऐब् नाली निर्माण कार्य जसबंत के घर से रामगोविन्द के घर तक अंतराम का पुरा | Completed | 110000 | 106812 | 2017-09-16 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034362362 — C.C.Road avam Nali Nirman, Hakim ke Ghar se Jagdish ke Ghar tak avam Mandir se Kaptan ke Ghar tak, P | Completed | 94320 | 93740 | 2017-10-02 | 2018-04-23
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034362364 — C.C.Road avam nali nirman, Mandir se Rajaram ke makan tak, Chakrapan ka pura | Completed | 57750 | 57276 | 2017-10-02 | 2018-04-12
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034367116 — सी सी खरंजा एवं नाली निर्माण कार्य कपतान सिंह के मकान से बाबूलाल के घर तक महाराज सिंह का पूरा | Completed | 82000 | 80324 | 2017-12-04 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034367890 — सी सी खरंजा एवं नाली निर्माण कार्य नहर से रामप्रकाश ऐब् स्कूल तक चितामनि का पुरा | Completed | 67260 | 67252 | 2018-02-02 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034367892 — सी सी खरंजा एवं नाली निर्माण कार्य नहर से मातादीन बैजनाथ ऐब रामजीलाल से कल्यान सिह चितामन का पुरा | Completed | 82305 | 70644 | 2018-03-12 | 2018-07-30
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034367895 — सी सी खरंजा एवं नाली निर्माण कार्य नहर से बारेलाल के घर तक देवहंश का पुरा | Deleted | 52763 | 0 | 2018-08-14
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034373402 — सी.सी. खरंजा एवं नाली निर्माण कार्य - नहर से भागीरथ के घर तक देवहंस का पुरा। | Deleted | 82912 | 0 | 2018-08-14
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034382382 — सी.सी. खरंजा एवं नाली निर्माण कार्य - श्रीकृष्ण के घर से प्रमोद के घर तक। | Completed | 22612 | 17748 | 2018-04-07 | 2018-12-18
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034382383 — सी.सी. खरंजा एवं नाली निर्माण कार्य - लटूरी सिंह के मकान से गंगा सिंह के घर तक। | Completed | 38692 | 29580 | 2018-04-26 | 2018-10-27
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034390720 — सी सी रोड राजेंद्र के घर से राजकुमार के घर तक | Completed | 48675 | 32712 | 2018-06-26 | 2018-10-27
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034390721 — सी सी रोड रतन गिरी के घर से राजेंद्र बघेल के घर तक | Completed | 22125 | 17748 | 2018-06-26 | 2018-10-27
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034395209 — सी.सी.खरंजा एवं नाली निर्माण कार्य - नहर से भागीरथ के घर तक, देवहंस का पुरा, बरेथा | Completed | 82912 | 69252 | 2018-10-01 | 2018-12-05
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034395210 — सी.सी.खरंजा एवं नाली निर्माण कार्य - नहर से बारेलाल के घर तक, देवहंस का पुरा, बरेथा | Completed | 52762 | 46980 | 2018-10-01 | 2018-12-05
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034397336 — सी.सी.खरंजा एवं नाली निर्माण कार्य - मोहम्मद शाह के मकान से प्रकाश के मकान तक, देवलाल का पुरा, बरेथा | Completed | 13275 | 12354 | 2019-02-11 | 2019-03-07
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034397340 — सी.सी.खरंजा एवं नाली निर्माण कार्य - आलम शाह के मकान से शिवनारायण के मकान तक, देवलाल का पुरा, बरेथा | Completed | 19912 | 15138 | 2019-01-25 | 2019-03-07
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034397342 — सी.सी.खरंजा एवं नाली निर्माण कार्य - विद्याराम से रामदास के घर की ओर आरोली का पुरा, बरेथा | Completed | 97987 | 81780 | 2019-01-05 | 2019-02-20
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034435061 — सी सी रोड एबम नाली निर्माण हरिचरन के घर तक चिंतामन का पुरा | Completed | 19912 | 16182 | 2019-01-18 | 2020-02-15
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034444543 — सी.सी. खरंजा एवं नाली निर्माण कार्य - जगन्नाथ के पुरा से पंचायत भवन एवं महावीर के घर तक। | Completed | 223125 | 222780 | 2019-02-20 | 2019-08-28
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034444570 — सीसी. खरंजा एवं नाली निर्माण कार्य - राजू के घर से मंदिर की ओर बनखण्डी, बरेथा | Completed | 38250 | 38080 | 2019-02-25 | 2019-07-22
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034447254 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मुन्ना शाह के मकान से पूजाराम राठौर एवं अमर सिंह के मकान तक, ट | Completed | 35400 | 33872 | 2019-03-06 | 2020-02-15
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034447256 — सी.सी. खरंजा एवं नाली निर्माण कार्य - हैण्डपम्प से मंदिर तक | Completed | 6638 | 5220 | 2019-03-06 | 2019-04-20
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034447260 — सी.सी. खरंजा एवं नाली निर्माण कार्य - शंकर कोरी के मकान से सोनेराम के मकान की ओर | Completed | 15390 | 12260 | 2019-03-06 | 2020-02-15
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034462727 — सी सी रोड व् नाली निर्माण लक्मन वाल्मिक के घर से पंचायत भवन की और बरेथा | Completed | 223125 | 223156 | 2019-03-09 | 2019-08-28
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034471243 — सी सी खरंजा एवं नाली निर्माण मैंन रोड से पट्पुरा तक बरेथा | Completed | 114750 | 114752 | 2019-08-05 | 2019-10-10
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034471257 — सीमेन्ट कॉक्रीट खरंजा एवं नाली निर्माण कार्य राजवीर के मकान से मोहन कोरी के मकान के और जगन्नाथ का पु | Completed | 20700 | 18128 | 2019-10-30 | 2020-02-15
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034471259 — सीमेन्ट कॉक्रीट खरंजा एवं नाली निर्माण कार्य स्वराज भवन से laxman वाल्मीकि के घर तक बरेथा | Completed | 41400 | 38544 | 2019-08-29 | 2020-02-15
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034525666 — cc रोड एवं नाली निर्माण कार्य -रामनिवास परमार के घर से वाल्मीक के पूरा तक चेरा | Completed | 133875 | 132620 | 2020-07-02 | 2020-08-20
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034525668 — cc रोड एवं नाली निर्माण कार्य -cc रोड से जगराम एवं जय सिंह क घर के और चेरा | Completed | 76500 | 76380 | 2020-07-18 | 2021-01-25
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034525669 — cc रोड एवं नाली निर्माण कार्य - मैंन रोड से श्रीलाल महोर के घर तक चेरा | Completed | 25920 | 25840 | 2020-07-18 | 2020-09-23
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034525671 — cc रोड एवं नाली निर्माण कार्य - रामचंद्र के घर से रामदास के घर तक मुकंदी का पूरा | Completed | 38250 | 38190 | 2021-02-03 | 2021-03-05
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540218 — सी.सी. खरंजा नाली सहित नट के घर से मुरारी परमार के के घर की ओर | Completed | 75000 | 74860 | 2020-09-24 | 2021-02-20
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540219 — सी.सी. खरंजा नाली सहित रामजीलाल प्रजापति के घर से ग्याप्रसाद के घर की ओर | Completed | 37500 | 37455 | 2020-10-29 | 2021-06-05
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540220 — सी.सी. खरंजा नाली सहित परसोत्तम जाटव के घर से दयाराम माहौर के घर की ओर | Completed | 22500 | 22420 | 2020-09-25 | 2021-01-25
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540221 — सी.सी. खरंजा नाली सहित कृपाराम का पुरा | Completed | 38250 | 37985 | 2020-09-24 | 2022-02-10
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540223 — सी.सी. खरंजा नाली सहित मदन पुजारी के घर से रामनिवास जाटव के घर की ओर | Completed | 76500 | 75240 | 2020-09-25 | 2020-12-17
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540893 — सी.सी. खरंजा मैन रोड से धीरा जोशी के घर तक | Completed | 11475 | 11400 | 2020-09-25 | 2020-12-17
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034540894 — सी.सी. खरंजा मैन रोड से शिवराज के घर तक | Completed | 22950 | 22800 | 2020-09-25 | 2020-12-17
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034587080 — सी . सी. खरंजा एवं नाली निर्माण कार्य स्वराज भवन से टीकाराम कोरी के घर की और मैंन रोड की और | Deleted | 169350 | 0 | 2021-08-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034587083 — सी . सी. खरंजा एवं नाली निर्माण कार्य सतीश के घर से मंदिर की और | Completed | 54750 | 53461 | 2021-10-22 | 2022-01-04
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034587291 — सी. सी. नाला निर्माण कार्य स्वराज भवन से टीकाराम कोरी के घर और मैन रोड के और | Ongoing | 169350 | 0 | 2021-08-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034588998 — सी. सी. रोड एव नाली निर्माण कार्य मेनरोड से आरोली एव सिरोमनि का पुरा | Completed | 137250 | 134907 | 2021-10-22 | 2022-01-07
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034588999 — सी. सी. रोड एव नाली निर्माण कार्य देवलाल का पुरा | Completed | 138300 | 135872 | 2021-10-22 | 2022-01-07
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034627920 — सी. सी. खरंजा एवं नाली निर्माण जोमदार का पुरा | Completed | 106500 | 104380 | 2023-05-01 | 2023-12-07
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034641905 — सीसी खरंजा एवं नाली निर्माण कार्य तोमर के घर से गोपाल के घर तक | Completed | 50400 | 43537 | 2023-09-30 | 2024-01-05
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034641907 — सीसी खरंजा एवं नाली निर्माण कार्य नट के घर से हरिजन मौहल्ला रतन सिंह का पुरा | Completed | 54300 | 52819 | 2023-10-03 | 2024-03-09
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/22012034641910 — सीसी खरंजा एवं नाली निर्माण कार्य किशन के घर से मंदिर की ओर रतन सिंह का पुरा | Completed | 104250 | 82433 | 2023-10-04 | 2024-01-05
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003007/RC/360 — सीमेंट कांक्रीट खरंजा निर्माण कार्य बरेथा | Completed | 0 | 34014 | 2009-06-18 | 2015-07-01
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003007/RS/22012034504594 — सामुदायिक स्वछता परिसर ग्राम पंचायत बरेथा | Completed | 43000 | 41777 | 2020-12-26 | 2021-06-09
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003007/RS/22012034532619 — कचरा भण्डार केंद्र (सेग्रीगेशन शेड ) | Completed | 628297.23 | 588105.59 | 2021-11-09 | 2023-06-28
MORENA / MORENA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003007/RS/22012035136996 — सामुदायिक स्वच्छता परिसर निर्माण कार्य - बरेथा | Ongoing | 81037 | 19575 | 2025-07-24
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003007/WC/22012034380233 — TALAB GARIKAAN | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034432234 — नवीन तालाब निर्माण कार्य - | Closed | 0 | 0 | 2019-01-26
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034447569 — चैक डैम निर्माण कार्य - बरेथा | Completed | 1496249 | 1489072.26 | 2019-03-09 | 2019-06-27
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034449943 — check dam | Closed | 0 | 0 | 2019-01-26
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034472390 — check dam | Completed | 1482933.89 | 1446848 | 2019-07-27 | 2020-05-26
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034490782 — Nws earthen dam bare.vihad ke pass | Completed | 1478405.75 | 1415282 | 2019-10-10 | 2020-09-14
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034490784 — Nws check dam bare.pipal Wala nala | Completed | 1477904.83 | 1449404 | 2019-10-02 | 2020-05-06
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034507350 — अद्र्वन डेम बरेथा सड़क के पास | Closed | 1442387.6 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034507353 — अद्र्वन डेम बेहड में बरेथा | Closed | 1421338.17 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034507354 — अद्र्वन डेम बरेथा नाले के पास | Closed | 1441762.14 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034508921 — एन.डब्ल्यू एस. चैक डेम बरैथा गाॅव वाला नाला | Deleted | 0 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034508922 — एन.डब्ल्यू एस. चैक डेम बरैथा गाॅव वाला नाला | Closed | 0 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034544138 — Nws check dam bare. nare mai | Closed | 1498414.05 | 0 | 2020-01-26
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034544139 — Nws check dam 2 bare. nare mai | Closed | 1497066.28 | 0 | 2020-01-26
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003007/WC/22012034576453 — खेत तालाब निर्माण कार्य मंदिर सरोवर योजना राधा कृष्ण बांके जी मंदिर की शासकीय भूमि पर | Deleted | 0 | 0 | 2020-04-14
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003007/WC/22012034577144 — मंदिर सरोवर राधाकृष्ण बांके जी मंदिर की शासकीय भूमि पर तालाब निर्माण कार्य बरेथा | Completed | 1461393.35 | 1421109.98 | 2020-12-31 | 2021-06-21
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034581197 — Nws check dam baretha gaau ke pass | Completed | 1462079.42 | 1410608 | 2020-09-12 | 2021-01-12
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034581199 — Nws check dam baretha vale khar ke pass | Completed | 1462281.11 | 1442236 | 2020-09-12 | 2021-01-12
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034587268 — nws check dam umarai bale khar par baretha | Completed | 1463534.02 | 1432930 | 2020-09-29 | 2021-01-27
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034587269 — nws check dam maharaj singh pura ke pass baretha | Completed | 1463534.02 | 1437490 | 2020-09-29 | 2021-02-05
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034587270 — nws earthen dam aaroli ke pass baretha | Completed | 1499322.79 | 1433159.48 | 2020-09-29 | 2021-03-03
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034587271 — nws earthen dam devlal ke pura ke pass | Completed | 1499208.71 | 1447826 | 2020-09-29 | 2021-03-11
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606975 — check dam gu shala ke pass | Completed | 1493339.68 | 1466510.87 | 2021-04-23 | 2021-09-12
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606977 — check dam pepal wale nare ke pass | Completed | 1495820.95 | 1452495.72 | 2021-04-09 | 2021-09-12
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606979 — check dam bari khar ke pass | Completed | 1494002.9 | 1460503.31 | 2021-02-26 | 2021-05-18
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606980 — check dam maharaj singh kde pura ke niche | Completed | 1490015.6 | 1456782 | 2021-02-26 | 2021-09-12
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606981 — check dam bhumiya bale khar ke pass | Completed | 1484997.41 | 1453930.32 | 2021-02-26 | 2021-09-16
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606982 — check dam singh bale khar ke pass | Completed | 1483021.74 | 1454396 | 2021-02-26 | 2021-12-23
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606983 — check dam pura ke pass | Completed | 1488699.61 | 1456994 | 2021-02-26 | 2021-05-18
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606984 — talav nirman ashram ke khet ke pass | Completed | 1483265.7 | 1431052.35 | 2021-02-26 | 2021-06-23
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606986 — talav nirman vidha kori ke khet ke pass | Completed | 1487108.44 | 1424908.28 | 2021-02-26 | 2022-07-11
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034606988 — naveen talab remja bale khet ke pass | Closed | 1497833.35 | 0 | 2021-02-26
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003007/WC/22012034616337 — सोकपिट निर्माण कार्य सियाराम पातीराम के घर के पास( slwm ) | Ongoing | 18200.38 | 1158 | 2021-04-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003007/WC/22012034616339 — सोकपिट निर्माण कार्य ठकुरी जय सिंह के घर के पास( slwm ) | Ongoing | 18200.38 | 1158 | 2021-04-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674061 — check dam jomdar ke pura ke niche | Deleted | 0 | 0 | 2021-04-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674065 — nws check dam bhori bale | Completed | 1499034.41 | 1444855 | 2021-05-21 | 2021-11-03
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674069 — nws check dam rakesh mheta | Completed | 1499908.21 | 1487105 | 2021-05-21 | 2021-12-23
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674074 — nws check dam rama mehta | Completed | 1498547.41 | 1427304 | 2021-05-21 | 2021-09-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674082 — nws talab nirman karya kishori mehta | Completed | 1499325.02 | 1422843.32 | 2021-05-19 | 2022-01-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674085 — nws talab nirman karya gabdu ke khet ke pass | Completed | 1498020.23 | 1451271.44 | 2021-05-19 | 2022-01-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034674090 — nws talab nirman karya ganesh mahesh | Completed | 1499782.3 | 1442590 | 2021-05-19 | 2022-05-11
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003007/WC/22012034674092 — nws gully plug pushpendra | Completed | 1497066.36 | 1031272 | 2021-10-22 | 2022-11-09
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003007/WC/22012034674094 — nws gully plug beju ke khet ke pass | Completed | 1491662.22 | 1193206 | 2021-05-19 | 2022-11-07
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003007/WC/22012034674096 — nws gully plug prem kori ke khet | Completed | 1492756.03 | 975840 | 2021-11-09 | 2022-11-09
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003007/WC/22012034674099 — nws gully plug kishori balmik ke khet ke pass | Completed | 1497153.06 | 1111458 | 2021-05-19 | 2022-11-09
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003007/WC/22012034686403 — सोकपिट निर्माण कार्य हेमंत शर्मा के घर के पास देवीलाल का पुरा | Closed | 18443.75 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003007/WC/22012034686418 — sokpit nirmaan kary munnaa sharma ke ghar ke pass devilaal ka puraa | Completed | 18443.75 | 14904.19 | 2021-10-07 | 2023-02-28
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003007/WC/22012034686422 — sokpit nirmaan kary dharam singh ke ghar ke pass ratan singh ka puraa | Completed | 18443.75 | 14325.13 | 2021-09-18 | 2023-07-10
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003007/WC/22012034686425 — sokpit nirmaan radheshyaam sharma ke ghar ke pass devilaal ka puraa | Closed | 18443.75 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003007/WC/22012034775408 — रूफ वाटर हार्वेस्टिंग प्रयामारी स्कूल बरेथा | Closed | 22823.53 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034857043 — nws/ctr check dam nirman bhupendra ke khet ke pass baretha | Completed | 1496003.8 | 1468266 | 2021-11-09 | 2023-03-17
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012034872651 — ctr/nws talab nirman karya thasildar ke khet ke pass baretha | Completed | 1496419.72 | 1440218 | 2021-11-17 | 2022-09-24
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012034994791 — nws talab nirman kary mansingh ke khet ke pass | Completed | 1477031.13 | 1423517.23 | 2022-09-17 | 2024-07-01
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012034994794 — nws talab nirman kary bachhu ke khet ke pass | Completed | 1493367.17 | 1437628.44 | 2023-05-06 | 2024-01-11
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012034999234 — nws talab nirman kary damodar ke khet ke pass | Completed | 1497245.51 | 1417710.65 | 2023-07-21 | 2024-01-11
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012034999236 — nws talab nirman kary bohta bai ke khet ke pass | Closed | 1470959.24 | 0 | 2022-08-16
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012034999237 — nws talab nirman kary lomdar ke pura ke niche | Completed | 1482831.17 | 1415648.99 | 2023-06-12 | 2024-01-11
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035057565 — anicut nirman kary hingota kala khaar ke pass | Completed | 1481814.52 | 1424589 | 2023-08-29 | 2024-08-28
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035057566 — anicut nirman kary kaaro khaar ke pass | Closed | 0 | 0 | 2023-04-01
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035091598 — check dem nirman kary bde khaar me | Deleted | 0 | 0 | 2023-04-14
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003007/WC/22012035136972 — AH talab nirman kary gopali ke khet ke pass | Completed | 1409003.48 | 1337297 | 2023-10-07 | 2024-03-19
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003007/WC/22012035136976 — AH talab nirman kary sundarkalan behad ke pass | Ongoing | 1432940.73 | 867643.65 | 2023-10-09
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003007/WC/22012035136986 — AH earthan bund nirman kary lakhan singh ke khet ke pass | Closed | 1137348.83 | 0 | 2023-08-16
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035147764 — Anicut Nirman Karya Ooda ke Khar me | Closed | 0 | 0 | 2023-10-02
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035147765 — Anicut Nirman Karya Peepal Wale Khar me | Closed | 0 | 0 | 2023-10-02
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035147766 — Anicut Nirman Karya Bharel Ke Behad me | Completed | 1493349.1 | 1429447 | 2024-01-26 | 2024-11-04
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003007/WC/22012035147767 — Anicut Nirman Karya Teer me | Completed | 1459085.49 | 1410392 | 2024-01-26 | 2024-11-04
MORENA / MORENA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003007/WC/22012035189008 — NWS Talab Nirman Karya Bhuda Behad Ke Pass | Ongoing | 1434263.43 | 1376056.64 | 2024-03-15
MORENA / MORENA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701003007/WC/22012035189009 — NWS Talab Nirman Karya Johiya Jagdeesh ke Khet Ke Pass | Ongoing | 1445369.08 | 1362559.52 | 2024-03-15
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012035214072 — nws talab nirman karya bandhia behad ke pass | Ongoing | 1456284.95 | 1284612.78 | 2025-04-18
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012035214073 — nws talab nirman karya chabija behad me | New | 0 | 0 | 2024-06-08
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003007/WC/22012035214074 — nws talab nirman karya chabija behad me | Physically Completed | 1460258.8 | 1211367.45 | 2024-07-20 | 2026-06-12
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003007/WC/22012035317265 — Naveen talab nirmaan karya Sidhh Baba Behad ke pass | Approved | 0 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003007/WC/22012035317266 — Naveen talab nirmaan karya Kher ke Behad ke pass | Approved | 0 | 0 | 2025-04-14
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701003007/WH/155 — स्‍टाम्‍प डेम निर्माण बरेठा | Completed | 171000 | 1227044.08 | 2009-02-18 | 2017-11-10
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034452234 — तलाव जीर्णोध्दार चेंटा | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034452235 — तलाव जीर्णोध्दार बरेथा | Closed | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034452236 — तलाव जीर्णोध्दार महाराजसिंह का पुरा बरेथा | Closed | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034452238 — तलाव जीर्णोध्दार चिंतामन का पुरा बरेथा | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034920071 — तालाब जीर्णोद्धार कार्य चेंटा | Deleted | 161085 | 2316 | 2022-03-23
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034920104 — तालाब जीर्णोद्धार कार्य बरेथा | Closed | 145730 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034920107 — तालाब जीर्णोद्धार कार्य महाराज सिंह का पुरा | Closed | 136477 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003007/WH/22012034920191 — तालाब जीर्णोद्धार चिंतामन का पुरा | Deleted | 151452 | 1158 | 2022-03-23
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701003007/WH/34 — स्‍टॉप डेम | Completed | 171000 | 123658 | 2009-01-30 | 2017-11-10
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701003007/WH/35 — 1701003007/WH/35 | Deleted | 11500 | 0 | 2009-01-30