## Work List
Exported on: 2026-09-03 21:00:07
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: JATAWAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003030/AV/22012034538577 — शान्तिधाम निर्माण कार्य मय टीनशेड सहित ग्राम जनकपुर | Deleted | 285409.48 | 2280 | 2020-09-28
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701003030/AV/4175 — Aanganbadi/Other Rural Infrastructure,MORENA | Completed | 297768 | 277656 | 2016-01-19 | 2020-05-20
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003030/DP/22012034328715 — वृक्षारोपण कार्य। | Closed | 0 | 0 | 2017-10-02
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003030/DP/22012034328980 — शांतिधाम निर्माण कार्य - पुराना गांव जतावर। | Completed | 180000 | 179900.78 | 2017-12-27 | 2018-07-04
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003030/DP/22012034542981 — माँ की बगिया शा. मा. वि. जनकपुर जतावर | Completed | 20445.35 | 16080 | 2022-02-16 | 2022-11-20
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003030/DP/22012034544717 — माँ की बगिया शा प्रा वि जतावर | Completed | 20445.35 | 16080 | 2022-02-16 | 2022-08-16
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003030/DP/22012034544718 — माँ की बगिया शा प्रा वि जनकपुर जतावर | Closed | 0 | 0 | 2021-10-02
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003030/DP/22012034602785 — व्रक्षारोपण कार्य माता का मंदिर एवम टंकी के पास जतावर मेरी माटी मेरा देश | Closed | 0 | 0 | 2023-04-14
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003030/FP/22012034202862 — नाली निर्माण कार्य - भागीरथ गुर्जर के मकान से तालाब की ओर | Completed | 206000 | 166659.62 | 2015-10-26 | 2016-09-27
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Diversion Channel / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034204624 — नाली निर्माण कार्य जतावर आशाराम पाठक के माकन से द्वार तक | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003030/FP/22012034360443 — नाली निर्माण कार्य - नहर से कुंअरपाल के घर तक, जतावर | Completed | 1258000 | 1210422.02 | 2017-12-27 | 2020-05-20
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034363873 — नाला निर्माण कार्य कच्छपुरा से नदी की और | Completed | 1335500.82 | 1264876.89 | 2019-11-23 | 2021-02-10
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034364649 — नवीन नाला निर्माण कार्य रामवीर जाटव के मकान से पंचायत भवन की और | Closed | 0 | 0 | 2020-01-26
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701003030/FP/22012034630747 — pathar nala nirman karya pani ki tanki se shantidham ki aur | Completed | 1251686.85 | 1077784.51 | 2022-12-03 | 2023-07-07
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034631331 — पत्थर नाला एवं कच्चा नाला निर्माण कार्य - पंचायत भवन एवं माता मंदिर से पंचाराम कुशवाह के घर की ओर | Completed | 1363377.55 | 1254255.5 | 2023-05-06 | 2023-07-19
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034631606 — पत्थर नाला एवं कच्चा नाला निर्माण कार्य पंचायत भवन एवं माता मंदिर से पंचाराम कुशवाह के घर की ओर | Deleted | 0 | 0 | 2022-10-02
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034632258 — पत्थर नाला एवं कच्चा नाला निर्माण कार्य जहाॅन सिंह के द्वार से नाथू कुशवाह के घर की ओर | Closed | 0 | 0 | 2022-10-02
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034632774 — पत्थर नाला एवम कच्चा नाला निर्माण कार्य जहान सिंह के द्वार से नाथू कुशवाह के घर की ओर | Completed | 1386066.98 | 1318861.37 | 2023-06-05 | 2024-10-29
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034632940 — कच्चा एवं पक्का नाला निर्माण कार्य माधौ मिस्त्री बघेल के घर से विन्द्रावन बघेल के घर की ओर | Completed | 1474502.77 | 1375561.27 | 2023-08-03 | 2024-10-29
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034634788 — पत्थर नाला एवम कच्चा नाला निर्माण कार्य बेताल सिंह के कुआ की ओर से जगदीश बघेल के कुआ की ओर | Completed | 1487132.47 | 1356396.24 | 2023-10-08 | 2024-10-29
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003030/FP/22012034634789 — पत्थर नाला एवम कच्चा नाला निर्माण कार्य राजेंद्र कुशवाह के घर से मुंशी बघेल के खेत एवम रोड की ओर | Completed | 1480970.5 | 1315303.24 | 2023-10-08 | 2025-12-18
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701003030/FP/9977522106 — नाली निर्माण कार्य - सिददार के मकान से रामविलास के | Completed | 275310 | 212933 | 2013-09-30 | 2015-01-01
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701003030/FP/9977522193 — नाली निर्माण कार्य - बैजनाथ के घर से डेरी की ओर | Completed | 194244 | 155954 | 2014-01-24 | 2015-07-23
MORENA / MORENA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cross Bund / Construction of Earthen graded Bund for Community | Works for Flood Control and Protection | 1701003030/FP/9977522693 — नाली निर्माण कार्य प्रकाश के द्वार से मुन्‍नालाल श | Completed | 232364 | 224732 | 2014-06-10 | 2015-07-23
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003030/FP/9977522694 — नाली निर्माण कार्य - नहर से स्‍कूल की ओर जतावर | Completed | 516364 | 130479 | 2014-08-16 | 2016-09-26
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003030/IF/22012034344869 — सार्वजनिक परिसर मे व्रक्षारोपण कार्य नहर ऐब रोड किनारे जतावर | Completed | 335000 | 40702 | 2017-06-24 | 2020-12-09
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003030/IF/22012034359931 — Plantation Janakpur Road se School avam Bhagirath ke Ghar tak, Janakpur | Closed | 335000 | 0 | 2017-07-01
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003030/IF/22012035303321 — खेत तालाब निर्माण कार्य रामऔतार पुत्र श्री भीखाराम | Ongoing | 422356.09 | 261 | 2025-04-22
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003030/IF/9993695809 — pashu shait indra singh /mohan singh gurjar | Deleted | 91000 | 0 | 2015-12-14
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003030/IF/9993696481 — पशु-शेड निर्माणकार्य देवेन्द्र सिंह पुत्र शंकर सिंह | Deleted | 91000 | 0 | 2015-12-15
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003030/IF/9993725673 — पशु शेड निर्माण कार्य लालजीत हथयिार सिह जनकपुर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/1889111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5020856 | Completed | 15660 | 14616 | 2018-09-11 | 2019-04-23
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/1890075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5673799 | Completed | 15660 | 14616 | 2018-09-11 | 2019-04-23
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/1924991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5093218 | Completed | 15660 | 14616 | 2018-09-11 | 2019-04-23
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3891116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147737417 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-28
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3891118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147737454 | Completed | 18360 | 18156 | 2022-05-20 | 2022-10-31
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3891120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147737512 | Completed | 18360 | 18156 | 2022-05-20 | 2022-10-13
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3891121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147737561 | Completed | 18360 | 18156 | 2022-05-20 | 2023-02-06
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3894333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147836638 | Completed | 18360 | 18156 | 2022-05-20 | 2022-12-22
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3894334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147836677 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-03
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3915960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126512181 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-28
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3915973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126514420 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-04
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3915994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126516480 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-04
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3915997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126517242 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-04
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3916068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126527257 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-03
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3916099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126532286 | Completed | 18360 | 14484 | 2022-05-20 | 2022-12-30
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3916152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126544178 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-03
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3987185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126533082 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-28
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3988802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126577822 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-28
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3991731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126513793 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-03
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/3991738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126515795 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-04
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/4027435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147354621 | Completed | 18360 | 18156 | 2022-05-20 | 2022-11-03
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/4027437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147354663 | Completed | 18360 | 18156 | 2022-05-20 | 2022-10-13
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/4032571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127197422 | Completed | 18360 | 18156 | 2022-05-20 | 2022-10-13
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/53128 — Construction of IAY House -IAY REG. NO. MP-01-003-030-001/93 | Completed | 14310 | 14195 | 2017-01-19 | 2018-04-20
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/53134 — Construction of IAY House -IAY REG. NO. MP-01-003-030-001/73S | Completed | 14310 | 3006 | 2016-12-21 | 2017-01-11
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/552138 — Construction of IAY House -IAY REG. NO. MP3422497 | Completed | 15030 | 15330 | 2017-02-06 | 2018-04-07
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/553218 — Construction of IAY House -IAY REG. NO. MP3454995 | Completed | 15030 | 15330 | 2017-02-06 | 2018-04-07
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/706182 — Construction of IAY House -IAY REG. NO. MP1516296 | Completed | 15030 | 14448 | 2017-04-14 | 2018-05-22
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/744460 — Construction of IAY House -IAY REG. NO. MP2357231 | Completed | 15030 | 14448 | 2017-04-14 | 2018-05-22
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/769309 — Construction of IAY House -IAY REG. NO. MP3401417 | Approved | 27000 | 0 | 2017-03-20
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/776332 — Construction of IAY House -IAY REG. NO. MP3753841 | Completed | 15030 | 14448 | 2017-04-14 | 2018-05-22
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/776505 — Construction of IAY House -IAY REG. NO. MP3765038 | Approved | 27000 | 0 | 2017-03-20
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/785718 — Construction of IAY House -IAY REG. NO. MP1520139 | Completed | 15480 | 14448 | 2017-04-14 | 2018-05-22
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/799408 — Construction of IAY House -IAY REG. NO. MP2536303 | Completed | 15480 | 14448 | 2017-04-14 | 2018-05-22
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003030/IF/IAY/799642 — Construction of IAY House -IAY REG. NO. MP2572029 | Approved | 27000 | 0 | 2017-04-01
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/1236 — पत्‍थर खराज निर्माण कार्य | Deleted | 438000 | 0 | 2012-01-26
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/16 — सी सी खरंजा निर्माण कार्य | Completed | 495000 | 98585 | 2009-01-02 | 2010-03-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034155692 — पत्‍थर खरजा निर्माण कार्य जतावर | Completed | 438000 | 93664 | 2012-06-19 | 2014-03-02
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034157441 — पत्‍थर खरजा निर्माण | Completed | 464000 | 73075.3 | 2013-01-25 | 2016-03-04
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034159527 — पंच परमेश्‍वर सी सी खरजा निर्माण | Completed | 280343 | 176675.22 | 2013-02-15 | 2016-03-04
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034172045 — सी सी खरंजा एवं नाली निर्माण र् कार्य विधाराम का मौहल्‍ला जनकपुर | Deleted | 51889 | 0 | 2013-01-28
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034177847 — सी सी खरंजा एवं नाली निर्माण कार्य हनुमानजी के मंद | Completed | 50961 | 42977 | 2013-09-30 | 2016-09-19
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Inter-locking Cement Block Road / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034196360 — सी सी खरंजा निर्माण कार्य - बैजनाथ सिंह बघेल के मक | Completed | 59281 | 51322 | 2014-02-06 | 2016-09-26
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034204451 — सी सी खरंजा एवं नाली निर्माण कार्य - प्रेमसिंह के | Completed | 44326 | 42091 | 2014-03-05 | 2015-07-23
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034227883 — पत्‍थर खरंजा निर्माण कार्य - नहर से सिददार के पुरा | Completed | 507000 | 144081.48 | 2014-09-20 | 2015-07-23
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034284039 — पत्थर खरंजा निर्माण - मैनरोड़ से प्रताप के मकान की क्रमशः नत्थी फकीरा, भारत सिंह औतार बाबा सत्रुघन म | Completed | 472000 | 423404.35 | 2015-09-16 | 2016-09-25
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034292901 — cc kharanja and nali nirman ramswarup k ghar se pothiram k ghar ki or | Completed | 96227 | 87036 | 2015-12-19 | 2016-05-19
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034292931 — patthar kharanja otar k ghar se pancham singh k ghar ki or | Completed | 714000 | 227784 | 2015-12-19 | 2016-05-20
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034292987 — patthar kharanja otar k ghar se pancham singh k ghar tak | Deleted | 0 | 0 | 2015-10-02
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034295374 — सी. सी. खरंजा एंव नाली नर्माण कार्य - जबर सिंह के घर से धुआराम गुर्जर के घर की और जनकपुर | Completed | 96127 | 92799 | 2016-01-05 | 2016-05-20
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034296868 — पत्थर खरंजा मैंन रोड से पतिराम के घर की और | Completed | 370000 | 93492 | 2016-01-19 | 2016-05-20
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034296871 — पत्थर खरंजा मैंन रोड से रामस्वरूप के घर एव पुरा की और | Completed | 685000 | 51357 | 2016-01-19 | 2016-05-20
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034307010 — सी सी खरंजा निर्माण कार्य भारत सिह घर से दिनेश के घर की ओर जनकपुर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034307012 — सी सी खरंजा निर्माण कार्य मैन रोड से गिर्राज के व्दवार से बेताल के व्दवार की ओर जनकपुर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034307014 — सी सी खरंजा निर्माण कार्य सिध्दबाबा का पुरा जनक पुर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034307030 — पत्थर खरंजा निर्माण कार्य सोबरन के मकान से पंचायत भवन एवं मढवारी माता की ओर जतावर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034307034 — पत्थर खरंजा निर्माण मेनरोड से मुन्ना व रामस्वरूप की ओर जनकपुर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034307037 — पत्थर ख्‍रंजा निर्माण कार्य सिध्दार के पुरा से धोरागिरि की ओर जतावर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034307747 — सी सी खरंजा निर्माण कार्य मैन रोड से इंन्द्रसिह के पुरा की ओर जनकपुर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034307749 — पत्थर खरंजा निर्माण कार्य धोरागिर से कछ पुरा की ओर जतावर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034307752 — सी सी खरंजा निर्माण कार्य धर्मजीत का पुरा जतावर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034320884 — सुदूर ग्राम संपर्क सड़क निर्माण- जनकपुर रोड़ से शंकर सिंह के पुरा तक जतावर | Completed | 1224000 | 1183038.2 | 2017-01-28 | 2018-12-27
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034327063 — C.C.Kharanja Avam Nali Nirman, Darshan ke Ghar se Ramsingh ke Ghar tak, Jatawar | Completed | 47000 | 46043 | 2017-03-25 | 2017-06-20
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034330894 — सी .सी. रोड भारत के घर से दिनेश के घर की ओर | Completed | 34627 | 34488 | 2017-03-15 | 2017-04-13
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034334868 — C.C.Road avam Nali Nirman, Bharat Singh ke Ghar se Dinesh ke Ghar Tak, Janakpur | Deleted | 35000 | 0 | 2017-04-02
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034334869 — C.C.Kharanja avam nali Nirman, Hathiyar Singh ke Ghar se Layak ke Ghar tak, Janakpur | Deleted | 23100 | 0 | 2017-04-02
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034334875 — C.C.Road avam Nali Nirman Gajendra ke Ghar se Mukesh ke Ghar tak, Janakpur | Deleted | 33000 | 0 | 2017-04-02
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034335114 — C.C.Kharanja Avam Nali Nirman, Hathiyar singh ke Ghar se Layak Singh Ke Ghar tak, Janakpur | Deleted | 23500 | 0 | 2017-01-26
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034335217 — सी सी खरंजा एवं नाली निर्माण कार्य - हथियार सिंह के घर से लायक सिंह के घर तक जनकपुर जतावर | Completed | 28035 | 23048 | 2017-04-21 | 2017-05-10
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034335226 — सी सी खरंजा एवं नाली निर्माण कार्य -गजेन्‍द्र के घर से मुकेश के घर तक जनकपुर | Completed | 32703 | 32508 | 2017-04-21 | 2017-07-01
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034335228 — सी सी खरंजा एवं नाली निर्माण कार्य - रामनिवास के घर भूरा एवं रघुना के घर तक जनकपुर | Completed | 38475 | 38356 | 2017-06-08 | 2017-07-01
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034335229 — सी सी खरंजा एवं नाली निर्माण कार्य - रामनरेश के घर से राधेश्‍याम के घर तक जनकपुर | Completed | 34627 | 34572 | 2017-06-08 | 2017-06-28
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034340665 — सुदूर ग्राम संपर्क सड़क निर्माण - नहर से कछपुरा तक जतावर | Deleted | 1443000 | 0 | 2017-05-25
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034343842 — सी सी खरंजा एवं नाली निर्माण - जनकपुर रोड से इन्‍द्र सिंह के घर तक जतावर | Completed | 34590 | 34400 | 2017-08-17 | 2017-09-07
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034343844 — सी सी खरंजा एवं नाली निर्माण - भरोसी के घर से राधाकिशन के घर तक कुशवाहपुरा जतावर | Completed | 19237 | 19436 | 2017-08-29 | 2017-09-07
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034343845 — सी सी खरंजा एवं नाली निर्माण - धर्मजीत का पुरा जतावर | Completed | 46800 | 46784 | 2017-08-16 | 2017-09-07
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034360947 — सी सी खरंजा निर्माण - दाताराम की दुकान से पंचायत भवन की ओर जतावर | Completed | 121500 | 121088 | 2017-09-26 | 2017-11-14
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034366713 — सी.सी. सडक एवं नाली निर्माण कार्य - सिद्ध बाबा मंदिर से करतार एवं रामवरन के घर तक जनकपुर | Completed | 48093 | 47644 | 2017-11-21 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034366715 — सी.सी. सडक एवं नाली निर्माण कार्य - सुदुर सडक से बाबू के घर तक जनकपुर | Completed | 34627 | 34056 | 2018-01-16 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034366716 — सी.सी. सडक एवं नाली निर्माण कार्य - देशराज के द्वार से रामजी के घर तक जनकपुर | Completed | 32703 | 32680 | 2017-11-21 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034366717 — सी.सी. सडक एवं नाली निर्माण कार्य - महेन्द्र राठौर के घर से हिमांचल राठौर के घर तक जनकपुर | Completed | 67331 | 67080 | 2018-01-10 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034375625 — धुंआराम के घर से शत्रुहन के घर तक जनकपुर। | Completed | 40398 | 39560 | 2018-01-10 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034380654 — सी.सी. सडक एवं नाली निर्माण - सुदुर सडक से टीकाराम का पुरा | Completed | 50017 | 49880 | 2018-01-16 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034380655 — सी.सी. सडक एवं नाली निर्माण - जगदीश बघेल के मकान से माधौ सिंह के घर तक | Completed | 37320 | 36808 | 2018-02-06 | 2018-04-23
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034380656 — सी.सी. सडक एवं नाली निर्माण - गुड्डा के मकान से हनुमान मंदिर धोरा गिरि तक | Completed | 75600 | 77430 | 2018-10-05 | 2018-12-09
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034380836 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मैन रोड से देवनारायण मंदिर तक। | Completed | 26000 | 25800 | 2018-02-06 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034383878 — सी.सी. खरंजा एवं नाली निर्माण कार्य - कुंअरपाल के घर से सोनेराम के घर तक | Completed | 28856 | 28896 | 2018-02-20 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034384454 — सी सी रोड जनकपुर रोड से लोटन सिंह का पुरा | Completed | 28800 | 28724 | 2018-03-06 | 2018-07-07
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034385214 — सी सी रोड जनकपुर से राम स्वरुप का पुरा | Completed | 25920 | 25752 | 2018-04-07 | 2018-07-07
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034396258 — सी सी रोड एवं नाली निर्माण जनकपुर रोड से पंजाब मडले के द्वार तक | Completed | 50906 | 50634 | 2018-10-05 | 2018-12-26
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034396268 — सी सी रोड निर्माण जनकपुर रोड से मुन्नालाल के घर तक | Completed | 82800 | 84042 | 2018-10-05 | 2018-12-09
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034396303 — सी सी रोड एवं नाली निर्माण जनकपुर रोड से भोलेराम के पूरा तक | Completed | 61087 | 60900 | 2018-10-05 | 2018-12-09
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034396306 — सी सी रोड एवं नाली निर्माण वृन्दावन के द्वार से शिव सिंह के घर तक | Completed | 48870 | 48372 | 2018-12-27 | 2019-04-23
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034434438 — सी सी रोड एबम नाली निर्माण सुदूर रोड से राजाराम के द्वार तक | Completed | 52942 | 52200 | 2019-02-07 | 2019-06-26
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034443981 — सी सी रोड व् नाली निर्माण जनकपुर रोड से पोहप सिंह के द्वार तक | Completed | 50906 | 50982 | 2019-02-24 | 2019-04-10
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034445337 — सी सी रोड व् नाली निर्माण मेन रोड आँगन वाड़ी से पी एस शाला तक कछपुरा | Completed | 61087 | 61040 | 2019-02-24 | 2019-08-01
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034469724 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मैन रोड से मुन्शी एवं भगवान सिंह के घर तक जनकपुर | Completed | 39900 | 39600 | 2019-07-19 | 2019-09-04
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034469725 — सी.सी. खरंजा एवं नाली निर्माण कार्य - प्रकाश के घर से बाबू सिंह के घर तक जतावर | Completed | 99750 | 99792 | 2019-07-29 | 2019-09-04
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034469727 — सी.सी. खरंजा एवं नाली निर्माण कार्य - नहर से पूरन एवं फूल सिंह के घर तक जतावर | Completed | 39900 | 39424 | 2019-07-27 | 2019-09-04
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034471268 — सी सी खरंजा एवं नाली निर्माण कार्य सुरेन्द्र सिंह का पूरा जतावर | Completed | 39900 | 39776 | 2019-08-16 | 2019-09-04
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034471270 — सी सी खरंजा एवं नाली निर्माण कार्य मैंन रोड से हनुमान मंदिर एवं पानी की टंकी जनकपुर | Completed | 39900 | 39600 | 2019-08-30 | 2019-09-18
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034473899 — सी.सी. खरंजा नाली सहित मैन रोड से राजेन्द्र जाटव के घर तक | Completed | 31920 | 31680 | 2019-09-07 | 2019-10-17
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034473900 — सी.सी. खरंजा नाली सहित मैन रोड से महेश एवं हरिकंठ के घर तक व डाॅ0 गली व मैन रोड से रामदीन बघेल सिद्व | Completed | 99750 | 98912 | 2019-09-21 | 2019-10-21
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034475341 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मैन रोड से मुंशीलाल के घर तक | Completed | 11970 | 11616 | 2019-09-28 | 2019-10-18
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034502994 — सी.सी. खरंजा एवं नाली निर्माण कार्य - नेतराम के घर से महावीर के घर तक जनकपुर | Completed | 79800 | 79414 | 2019-11-02 | 2020-07-14
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034520560 — सुदूर ग्राम संपर्क सडक निर्माण कार्य पानी की टंकी से शांतिधाम की और | Closed | 0 | 0 | 2019-04-01
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034522167 — सुदूर ग्राम संपर्क सड़क निर्माण कार्य पानी की टंकी से शांतिधाम की और | Completed | 1479395.12 | 1409118.42 | 2020-05-29 | 2021-01-20
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034525587 — सी. सी. खरंजा एवं नाली निर्माण कार्य जीवाराम के घर से धीरज के घर तक जनकपुर | Completed | 31920 | 29640 | 2020-06-27 | 2020-08-17
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034525588 — सी. सी. खरंजा एवं नाली निर्माण कार्य मैंन रोड से रामजानकी मंदिर तक एवं मैंन रोड से आशाराम पाठक के घर | Completed | 31920 | 31540 | 2020-08-05 | 2020-10-14
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034525589 — सी. सी. खरंजा एवं नाली निर्माण कार्य मैंन रोड से सरनाम सिंह का पुरा | Completed | 39900 | 38760 | 2020-06-27 | 2020-08-17
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034525982 — सुदूर ग्राम सम्पर्क सड़क विद्याराम के पुरा से रामस्वरूप पुरा होते हुए नेतराम के पुरा तक | Completed | 1485341.16 | 968743.3 | 2020-06-27 | 2021-04-01
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034532595 — सी. सी, खरंजा निर्माण कार्य जंडेल सिंह के घर से सत्रुघन व् नथेसिंह के घर की और | Completed | 102000 | 98040 | 2020-08-06 | 2020-09-16
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034533894 — सी.सी.खरंजा एवं नाली निर्माण कार्य मैंन रोड मातादीन एवं लालजी कपूर सिंह के घर तक जनकपुर | Deleted | 97275 | 2280 | 2020-08-12
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034533895 — सी.सी.खरंजा एवं नाली निर्माण कार्य मैन रोड से भारत डाल सिंह रामसहाय के घर तक जनकपुर | Deleted | 98925 | 2280 | 2020-08-12
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034534216 — सी. सी. रोड एवं नाली निर्माण कार्य रामभजन की पुलिया से बलिराम के घर तक | Closed | 39900 | 0 | 2020-04-14
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034542138 — सुदूर ग्राम संपर्क सड़क पाठक के पूरा से तोगर के पूरा होते हुए सुरेंद्र के पूरा तक | Completed | 3413298.03 | 2976082.95 | 2020-12-16 | 2023-07-07
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034550067 — सी. सी. खरंजा एवं नाली निर्माण जगनाथ का पुरा जतवार का पुरा | Deleted | 48300 | 0 | 2020-01-26
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034568223 — सोकपिट निर्माण नथीलाल का हेण्डपम्प | Closed | 55500 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/22012034568228 — सी. सी. खरंजा एवं नाली निर्माण कार्य मैंन रोड से हलके एवं नथी के घर की और ग्राम जनकपुर | Completed | 55500 | 53654 | 2021-04-24 | 2021-09-06
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034589339 — सुदूर ग्राम /खेत सड़क जनकपुर से जतावर और धेरगिरी से कछपुरा तक | Closed | 0 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034589340 — सुदूरग्राम/ खेतसड़क संतोषी मास्टर जनकपुर से धर्मजीत का पुरा | Closed | 0 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034589341 — सुदूरग्राम/ खेत संतोषी मास्टर जनकपुर से धर्मजीत का पुरा | Deleted | 0 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034612591 — सुदूर ग्राम /खेत सड़क जनकपुर से जतवार,धोरागिरी से कच्छपुरा तक | Closed | 0 | 0 | 2022-01-26
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/22012034612592 — सुदूर ग्राम /खेत सड़क संतोषी मास्टर जनकपुर से धर्मजीत का पुरा | Completed | 1991620.31 | 1728586.32 | 2022-05-09 | 2025-03-18
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003030/RC/283 — पत्‍थ्‍ज्ञर ,खंरजा निर्माण कार्य धर्मजीत का पुरा | Completed | 257000 | 129451.88 | 2009-06-11 | 2011-09-25
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003030/RC/288 — पत्‍थर खरजा निर्माण धर्मजीत का पुरा | Completed | 0 | 143566.53 | 2009-06-13 | 2010-10-28
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003030/RC/531 — पत्‍थर खरजा निर्माण कार्य | Completed | 0 | 160578 | 2009-11-22 | 2016-03-04
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003030/RS/22012034506546 — सामुदायिक स्वछता परिसर हनुमान मंदिर ग्राम जनकपुर जतावर | Completed | 43000 | 42940 | 2021-02-06 | 2021-04-01
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1701003030/RS/22012034526609 — कचरा भण्डार केंद्र (सेग्रीगेशन शेड ) जतावर | Completed | 628297.23 | 585697.45 | 2021-11-09 | 2024-01-01
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003030/WC/01 — सोख्‍ता गडडा शीतला मंदिर के पास | Completed | 11200 | 7862 | 2008-06-09 | 2016-01-10
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003030/WC/02 — सोख्‍ता गडडा पाठकपुरा शाप्रावि | Completed | 11200 | 6560 | 2008-06-09 | 2016-01-10
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003030/WC/22012034386212 — नवीन तालाब निर्माण शांतिधाम के पास | Completed | 805000 | 752171.56 | 2018-02-17 | 2019-06-26
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003030/WC/22012034432269 — नवीन तालाब निर्माण कार्य - | Closed | 0 | 0 | 2019-01-26
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034616779 — सोकपिट निर्माण कार्य सिद्ध बाबा के पास जनकपुर slwm | Completed | 18200.38 | 16683 | 2021-02-19 | 2021-11-17
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034616781 — सोकपिट निर्माण कार्य मंदिरके पास जनकपुर slwm | Completed | 18200.38 | 15923 | 2021-02-19 | 2021-11-17
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646258 — सोकपिट निर्माण कार्य जंडेल सिंह /हतियार सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17219 | 2021-05-19 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646315 — सोकपिट निर्माण कार्य भगीरथ /मेंहताबसिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17219 | 2021-05-29 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646324 — सोकपिट निर्माण कार्य जवर सिंह/रामेस्वर के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17219 | 2021-05-29 | 2021-11-17
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646335 — सोकपिट निर्माण कार्य धुआराम/बैजनाथ सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17219 | 2021-05-29 | 2021-11-17
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646345 — सोकपिट निर्माण कार्य सत्रुघन/ बासुदेव के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-19 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646353 — सोकपिट निर्माण कार्य कपूर सिंह /औतार सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-19 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646360 — सोकपिट निर्माण कार्य जगदीश /बद्री सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-19 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646370 — सोकपिट निर्माण कार्य रामबरन /चित्र सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-19 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646379 — सोकपिट निर्माण कार्य मंगोसिंघ/शिवचरण सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17219 | 2021-05-29 | 2021-11-17
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646464 — सोकपिट निर्माण कार्य एदल सिंह /दुलेहराम के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646481 — सोकपिट निर्माण कार्य अतर सिंह /बद्री सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-29 | 2021-09-25
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646484 — सोकपिट निर्माण कार्य भारत सिंह /गोधन सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-19 | 2021-11-17
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646490 — सोकपिट निर्माण कार्य निरंजन सिंह / फकीर सिंह के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646492 — सोकपिट निर्माण कार्य नथी सिंह /गुलाब सिंह के घर के सामने ग्राम जनकपुर | Completed | 18382.8 | 17412 | 2021-05-29 | 2021-11-17
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646497 — सोकपिट निर्माण कार्य दधीराम /विशाल सिंह के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646499 — सोकपिट निर्माण कार्य रामस्वरूप /रामप्रसाद के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646503 — सोकपिट निर्माण कार्य सियाराम /रामेस्वर सिंह के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-04-01
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646506 — सोकपिट निर्माण कार्य जसरथ /पंछीराम के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003030/WC/22012034646510 — सोकपिट निर्माण कार्य कम्पोटर/रामजीलाल के घर के सामने ग्राम जनकपुर | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003030/WC/22012034649945 — नवीन तालाब निर्माण कार्य कच्छ पुरा के पास जतावर | Completed | 1473834.26 | 1325939 | 2021-05-30 | 2024-10-29
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003030/WC/22012034649951 — नवीन तालाब निर्माण कार्य भल्ली पुरा के पास जतावर | Completed | 1468672.34 | 1215353 | 2021-05-30 | 2023-07-03
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003030/WC/22012034658667 — नवीन तालाब निर्माण कार्य कछपुरा के पास जतावर | Deleted | 0 | 0 | 2021-04-05
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003030/WC/22012035026884 — गली प्लग निर्माण कार्य शांतिधाम एवं पुराने गाॅव के नीचे, जतावर | Completed | 947315.38 | 778056 | 2023-05-06 | 2023-07-12
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003030/WC/22012035033059 — गली प्लग निर्माण कार्य शांतिधाम एवं पुराने गांव के नीचे | Deleted | 0 | 0 | 2022-10-02
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003030/WC/22012035048466 — गली प्लग निर्माण कार्य हनुमान मंदिर पुराना गांव के पास जतावर | Closed | 0 | 0 | 2023-01-24
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701003030/WC/22012035065671 — गली प्लग निर्माण कार्य - हनुमान मन्दिर पुराना गांव के पास जतावर | Completed | 1054104.62 | 749134 | 2023-06-20 | 2024-10-29
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003030/WC/22012035070313 — नवीन परकुलेशन तालाब सुरेश बघेल के पास बेहड मे जतावर | Completed | 1461057.07 | 1395700.25 | 2023-08-18 | 2024-10-29
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003030/WC/22012035070316 — नवीन परकुलेशन तालाब निर्माण कार्य कुशवाह आशाराम एवं बघेल वाले बेहड मे | Completed | 1491199.49 | 1315411.82 | 2023-08-25 | 2024-10-29
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003030/WC/22012035092401 — एनीकट निर्माण कार्य मल्लापुरा के नीचे जतावर | Completed | 1495378.51 | 1459571.8 | 2023-07-27 | 2024-10-29
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003030/WC/22012035092402 — एनीकट निर्माण कार्य पुराना गांव के नीचे जतावर | Completed | 1484691.42 | 1389510.8 | 2023-07-27 | 2025-12-18
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003030/WC/22012035145337 — एनिकट निर्माण कार्य माता वाला बेहड के पास | Closed | 0 | 0 | 2023-10-02
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003030/WC/22012035145340 — एनिकट निर्माण कार्य हनुमान मंदिर के पास | Closed | 0 | 0 | 2023-10-02
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035216045 — परकोलेशन तालाब निर्माण कार्य बडे खार के पास, जतावर | Ongoing | 1478869.76 | 1309662.14 | 2024-08-01
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035216046 — परकोलेशन तालाब निर्माण कार्य लक्ष्मण कुशवाह के बेहड के पास, जतावर | Physically Completed | 1449228.09 | 1348465.38 | 2024-08-01 | 2026-04-27
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035216049 — परकोलेशन तालाब निर्माण कार्य सोनेराम कुशवाह के बेहड के पास, जतावर | Physically Completed | 1458888.52 | 1317719.21 | 2024-07-25 | 2026-04-27
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035216050 — परकोलेशन तालाब निर्माण कार्य सिद्ध बाबा के नीचे, जतावर | Physically Completed | 1459367.22 | 1364368.08 | 2024-07-25 | 2026-04-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035317403 — Talab nirmaan karya jay singh Baghel ke behad ke pass | Ongoing | 1462196.92 | 1285357.28 | 2025-08-22
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035317404 — Talab nirmaan karya Neev wale baba ke pass | Ongoing | 1459398.41 | 1312251.24 | 2025-08-22
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035317406 — Talab nirmaan karya Pana pandit ke behad ke pass | Ongoing | 1478714.59 | 1268103.52 | 2026-01-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035317407 — Talab nirmaan karya Gyasiram Baghel ke behad ke pass | Ongoing | 1480269.83 | 1299380.46 | 2026-01-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035317408 — Talab nirmaan karya Chatri wale behad me | Ongoing | 1475028.62 | 1326704.86 | 2025-08-22
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003030/WC/22012035317679 — Talab nirmaan karya Bharoshilal ke behad ke pass | Ongoing | 1482447.43 | 305250.98 | 2025-08-22
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003030/WH/22012034452075 — पोखर जीर्णोद्धार पुराने गांव के पास जतावर | Closed | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003030/WH/22012034920039 — तालाब जीर्णोद्धार शांतिधाम के पास | Closed | 73000 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003030/WH/22012034920040 — पोखर जीर्णोद्धार पुराने गांव के पास | Completed | 147066 | 130857 | 2022-03-11 | 2022-05-24
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of Canal, Distributary and Minor / Construction of distributary Canal for Community | Construction of Canal | 1701003/IC/9993638068 — वाटर कोर्स फील्ड चैनल निर्माण-अम्बाह शाखा नहर की आरडी/63510/आर/एस संथा 2007 सिकरौदा | Completed | 2168000 | 609470.68 | 2017-07-20 | 2018-01-17