## Work List
Exported on: 2026-10-12 11:29:59
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: HINGONAKALAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003031/AV/22012034468480 — शांतिधाम निर्माण कार्य - गुट्टी का पुरा, हिंगोनाकलां | Closed | 0 | 0 | 2019-08-15
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701003031/AV/22012034503544 — आंगनबाडी भवन निर्माण कार्य - गुट्टी का पुरा,हिंगोनाकलां | Completed | 180000 | 178578 | 2019-11-16 | 2022-02-14
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701003031/AV/22012034503546 — आंगनबाडी भवन निर्माण कार्य - कच्छपुरा पुनीत का पुरा, हिंगोनाकलां | Completed | 180000 | 178976 | 2019-11-16 | 2022-02-14
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003031/AV/22012034632202 — शांतिधाम निर्माण कार्य गुट्टी का पुरा हिंगोनाकलां | Completed | 336401.16 | 297674.71 | 2023-07-12 | 2024-01-30
MORENA / MORENA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003031/AV/22012034665998 — शांतिधाम निर्माण कार्य पुनीत का पुरा हिंगोनाकला | Ongoing | 347299.82 | 271819.57 | 2025-06-12
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003031/DP/02 — व़क्षारोपण पुरानागॉव हिंगौनाकलॉ | Completed | 272534 | 4505 | 2008-09-08 | 2008-04-14
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003031/DP/03 — व़क्षारोपण कार्य मंदिर के पास पहाडी पर पुराना गांव हिंगोना कलां | Completed | 272534 | 3400 | 2008-09-24 | 2008-07-01
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003031/DP/153 — व्रक्षा रोपण कार्य हिगोना कला से गुटटी पुरा रोड किनारे | Deleted | 0 | 400 | 2008-10-05
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003031/DP/22012034328715 — वृक्षारोपण कार्य | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003031/DP/22012034542566 — मां की बगिया प्रा. शा. विधालय नवीन कच्छा हिगोना कलां | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701003031/DP/22012034542567 — मां की बगिया प्रा. शा. विधालय नवीन कच्छा हिगोना कलां | Completed | 21445.35 | 9396 | 2022-08-18 | 2022-09-09
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701003031/DP/22012034602755 — व्रक्षारोपण कार्य आगनवाड़ी भवन गुट्टी का पुरा पर हिंगोनाकलां मेरी माटी मेरा देश | Closed | 55847.4 | 0 | 2023-04-14
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003031/DP/249 — निर्मल वाटिका | Completed | 0 | 33695 | 2010-08-13 | 2013-12-19
MORENA / MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003031/DP/355 — शांती धाम हिगोनाकलॉ | Completed | 227000 | 121466 | 2012-02-01 | 2012-08-04
MORENA / MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Bio Drainage / Block Plantation of Biodrainage Trees in fields for Community | Works for Flood Control and Protection | 1701003031/FP/18 — पत्‍थर खरंजा एवं नाली न‍िर्माण कमलेश के घर से महेन | Completed | 378000 | 248138 | 2011-09-24 | 2014-09-09
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003031/FP/22012034203095 — नाली निर्माण कार्य - सीताराम के मकान से कप्तान के मकान तक पुनीत का पुरा | Completed | 233000 | 225295 | 2015-12-08 | 2016-12-12
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003031/FP/22012034203638 — नाली निर्माण - कृष्णा के मकान से पूर्ण के मकान तक पुनीत का पूरा | Completed | 133000 | 114259 | 2017-01-12 | 2017-05-30
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Storm Water Drains / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003031/FP/22012034203917 — नाली निर्माण कार्य -चौराह से नरुआ तक | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034362887 — पत्थर नाला निर्माण कार्य भागीरथ के घर से रामहेत के घर तक कछपुरा | Completed | 1472000 | 1237668.39 | 2019-03-08 | 2020-07-20
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034624367 — नाला निर्माण कार्य शिवलाल के घर से मुख्य नाले तक एवं द्वारिका के घर से मुख्य नाले तक | Completed | 1490725.34 | 1247141.59 | 2021-05-19 | 2023-08-22
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034629843 — पत्थर नाला निर्माण कार्य बंटी के घर से मुख्य नाले तक | Completed | 1280476.81 | 1192420.25 | 2022-10-28 | 2024-01-05
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034629844 — पत्थर नाला निर्माण कार्य पंचायत भवन से चौराहा तक | Completed | 1248985 | 1186409.87 | 2022-10-28 | 2023-08-16
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034632299 — पत्थर नाला निर्माण कार्य मुख्य नाले से हनुमान मन्दिर तक हिंगोनाकलां | Closed | 0 | 0 | 2023-01-26
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034632300 — पत्थर नाला निर्माण कार्य मुकेश के घर से तालाब तक, गुट्टी का पुरा हिंगोनाकला | Completed | 1312929.75 | 1207973.32 | 2023-05-11 | 2024-01-25
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034633607 — पत्थर नाला निर्माण कार्य संजय के घर से आंगनबाडी की ओर गुुट्टी का पुरा हिंगोनाकलां | Completed | 1485302.97 | 1353934.06 | 2023-06-27 | 2024-12-24
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034634132 — पत्थर नाला निर्माण कार्य नरूआ से चिमनी की ओर हिंगोनाकलां | Completed | 1489867.8 | 1333932.4 | 2023-07-21 | 2024-10-28
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034634636 — पत्थर नाला निर्माण कार्य चिमनी से मुख्य नाले तक हिंगोनाकलां | Completed | 1487132.47 | 1372061.78 | 2023-09-22 | 2025-12-11
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034634637 — पत्थर नाला निर्माण कार्य पुनीत का पुरा चैराहे से नदी की ओर हिंगोनाकलां | Completed | 1417312.67 | 1283873.28 | 2023-09-20 | 2024-12-06
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003031/FP/22012034636059 — पत्थर नाला निर्माण कार्य सीसी रोड से तालाब की ओर नवीन कछा | Completed | 1410990.41 | 1356325.08 | 2023-10-06 | 2024-12-24
MORENA / MORENA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cross Bund / Construction of Earthen graded Bund for Community | Works for Flood Control and Protection | 1701003031/FP/9977522460 — नाली निर्माण - ग्यासी के घर से सिददार के घर तक पुन | Completed | 463582 | 381569 | 2014-03-04 | 2015-07-30
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039756 — पश शैड निर्माण - श्रीरानम /रामविलास | Completed | 80000 | 72182 | 2013-09-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039765 — पशु शेड निर्माण - बनबारी/देवीराम | Completed | 80000 | 57777 | 2013-09-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039774 — पशु शेड निर्माण-रामरतन/देवीरानम् | Completed | 80000 | 56472 | 2013-09-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039787 — पुश शेड निर्माण-दर्श् न/निहाल् | Completed | 80000 | 75211 | 2013-09-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039790 — पशु शेड निर्माण-गोरेलाल/देवीराम | Completed | 80000 | 57367 | 2013-09-29 | 2014-09-12
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039800 — पशु शेड निर्माण-केदार/देवीराम् | Completed | 80000 | 67201 | 2013-09-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000039846 — पशु शेड निर्माण-देवन्द्र/मावसिया | Completed | 80000 | 62504 | 2013-09-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042122 — पशु शेड कार्य निर्माण-सिन्नाम/पहाड् सिह | Completed | 80000 | 67676 | 2014-01-29 | 2015-06-26
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042132 — पशु शेड कार्य निर्माण-नत्थीलाल/कोकसिह् | Completed | 80000 | 72999 | 2014-01-12 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042138 — पशु शेड कार्य निर्माण-संजीव/वेजनाथ | Completed | 80000 | 37859 | 2014-01-29 | 2017-01-11
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042145 — पशु शेड कार्य निर्माण-मोहनसिह्/कोकसिह् | Completed | 80000 | 73469 | 2013-12-30 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042154 — पशु शेड कार्य निर्माण-मोहरसिह/रामदीन् | Deleted | 80000 | 0 | 2013-08-15
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042159 — पशु शेड कार्य निर्माण-अभिशेक/लालसिह् | Deleted | 80000 | 0 | 2013-08-15
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042164 — पशु शेड कार्य निर्माण-रामकिशन/कोकसिह् | Completed | 80000 | 70935 | 2014-01-29 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042169 — पशु शेड कार्य निर्माण-नरेश/मोहन | Completed | 80000 | 71065 | 2014-02-19 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042175 — पशु शेड कार्य मिर्मान-क्र्श्ण/रतनू | Completed | 80000 | 70591 | 2014-02-09 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042180 — प्शु शेड कार्य निर्माण-गिर्राज/मोवसिया | Deleted | 80000 | 0 | 2014-03-05
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/1000042190 — पशु शेड कार्य निर्माण-जंडेल/गादीपाल् | Completed | 80000 | 74997 | 2013-12-30 | 2015-06-25
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003031/IF/22012034343141 — व़क्षाराेपण निर्माण कार्य पुनीत का पुरा से कछा तक रोड के किनारे | Completed | 335000 | 66254 | 2017-06-03 | 2019-11-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003031/IF/22012034357922 — व़क्षाराेपण निर्माण कार्य - डम्बर रोड से नहर तक हिंगोनाकलां | Deleted | 0 | 0 | 2017-06-08
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003031/IF/22012034357932 — व़क्षाराेपण निर्माण कार्य - डम्बर रोड से नहर तक हिंगोनाकलां | Completed | 335000 | 22342 | 2017-06-30 | 2018-07-18
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034805043 — नाडेप निर्माण कार्य मोहरसिंह | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034805047 — नाडेप निर्माण कार्य हेमराज | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034805053 — नाडेप निर्माण कार्य जनक सिंह | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034805057 — नाडेप निर्माण कार्य बृंदावन | Completed | 18552.12 | 16455 | 2021-06-19 | 2022-03-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034805065 — नाडेप निर्माण कार्य मूला | Completed | 18552.12 | 16455 | 2021-06-19 | 2022-03-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034825230 — नाडेप निर्माण कार्य मनोज कुमार | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827756 — नाडेप निर्माण कार्य गम्भीरा / अकलू | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827763 — नाडेप निर्माण कार्य रामेस्वर /केदार | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827768 — नाडेप निर्माण कार्य राकेश /केदार | Completed | 18552.12 | 16455 | 2021-09-09 | 2022-03-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827773 — नाडेप निर्माण कार्य वीरेंद्र /मौजीलाल | Completed | 18552.12 | 16455 | 2021-09-09 | 2022-03-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827778 — नाडेप निर्माण कार्य रघुराज /मौजीलाल | Completed | 18552.12 | 16455 | 2021-09-09 | 2022-03-15
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827780 — नाडेप निर्माण कार्य कुलदीप /हरीमोहन | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827785 — नाडेप निर्माण कार्य उमाशंकर /रामहेत | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701003031/IF/22012034827787 — नाडेप निर्माण कार्य बीरबल /ग़फ़ले | Closed | 18552.12 | 0 | 2021-04-14
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701003031/IF/22012035501501 — Khet Talab Nirmaan Karya Man Singh ke khet me | Completed | 147621.16 | 104660.64 | 2025-05-12 | 2025-12-11
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003031/IF/22012035659122 — Ek Bagiya Maa Ke Naam Seeta/Suresh 157303490 | Ongoing | 283818.64 | 1827 | 2026-01-25
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003031/IF/22012035659138 — Ek Bagiya Maa Ke Naam Vimla/Ramesh 143780772 | Ongoing | 283818.64 | 1827 | 2026-01-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926709934 — rakesh / kedar | Deleted | 80000 | 0 | 2014-03-05
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710422 — पशुशैड निमार्ण - मौहकम/भरोषी | Completed | 80000 | 69165 | 2014-03-04 | 2017-01-11
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710437 — पशु शेड् निर्माड -बुद्दी/सुन्दर् | Completed | 80000 | 71293 | 2014-03-04 | 2015-06-25
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710473 — पशु शेड कार्य निर्माड-पीतम/छत्रपाल् | Deleted | 0 | 0 | 2014-01-26
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710521 — cattel shed nirmad kary -bharoshi/vijaram | Completed | 80000 | 77170 | 2014-03-04 | 2016-08-22
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710564 — cettel setd work-mahesh/sugharsingh | Completed | 80000 | 68091 | 2014-03-04 | 2016-09-26
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710569 — cattel setd work -pohapsingh/rambhajan | Completed | 80000 | 71301 | 2014-03-04 | 2016-09-26
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710575 — cattel shed work-pratap/maharasingh | Deleted | 80000 | 0 | 2014-03-05
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710585 — cattel shed work-hukamsingh/bhagawan | Completed | 86021 | 73199 | 2014-03-04 | 2016-06-20
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003031/IF/9926710590 — cattel shed work-peetam/chhatrapal | Deleted | 80000 | 0 | 2014-03-05
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/1889653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4900223 | Completed | 15660 | 15558 | 2018-08-24 | 2019-08-05
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/1889901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5461919 | Completed | 15660 | 15510 | 2018-08-24 | 2019-07-22
MORENA / MORENA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/3230619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3709651 | Completed | 17370 | 16212 | 2021-09-09 | 2022-03-15
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/42745 — Construction of IAY House -IAY REG. NO. MP-01-003-031-001/44 | Approved | 23490 | 0 | 2015-08-19
MORENA / MORENA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/4329116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120783898 | Completed | 18360 | 16218 | 2022-09-08 | 2023-08-18
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/48896 — Construction of IAY House -IAY REG. NO. MP-01-003-031-001/2 | Completed | 14310 | 13861 | 2016-10-11 | 2017-08-22
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/48897 — Construction of IAY House -IAY REG. NO. MP-01-003-031-001/33 | Completed | 14310 | 13026 | 2016-10-11 | 2017-08-22
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/48898 — Construction of IAY House -IAY REG. NO. MP-01-003-031-001/42 | Completed | 14310 | 13861 | 2016-10-11 | 2017-08-22
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/48899 — Construction of IAY House -IAY REG. NO. MP-01-003-031-001/45 | Approved | 23490 | 0 | 2015-08-19
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/48900 — Construction of IAY House -IAY REG. NO. MP-01-003-031-001/54 | Completed | 14310 | 13861 | 2016-10-11 | 2017-08-22
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/494698 — Construction of IAY House -IAY REG. NO. MP2189101 | Completed | 15030 | 15223 | 2017-01-31 | 2018-01-18
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/518281 — Construction of IAY House -IAY REG. NO. MP2514701 | Completed | 15030 | 15375 | 2017-01-31 | 2018-05-05
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/518895 — Construction of IAY House -IAY REG. NO. MP2527193 | Completed | 15030 | 15360 | 2017-01-31 | 2017-11-22
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/520762 — Construction of IAY House -IAY REG. NO. MP2572697 | Completed | 15030 | 15420 | 2017-01-31 | 2018-01-18
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/551037 — Construction of IAY House -IAY REG. NO. MP3391102 | Completed | 15030 | 15450 | 2017-01-31 | 2018-01-18
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/551271 — Construction of IAY House -IAY REG. NO. MP3398479 | Completed | 15030 | 15450 | 2017-01-31 | 2018-01-18
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/551345 — Construction of IAY House -IAY REG. NO. MP3400884 | Completed | 15030 | 14782 | 2017-03-01 | 2018-05-05
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/570764 — Construction of IAY House -IAY REG. NO. MP5015158 | Deleted | 15030 | 0 | 2017-01-31
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/740630 — Construction of IAY House -IAY REG. NO. MP2245328 | Completed | 15030 | 15480 | 2017-04-28 | 2018-02-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/749039 — Construction of IAY House -IAY REG. NO. MP2504824 | Completed | 15030 | 15308 | 2017-04-28 | 2018-02-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/749620 — Construction of IAY House -IAY REG. NO. MP2524701 | Completed | 15030 | 15480 | 2017-09-30 | 2018-02-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/749640 — Construction of IAY House -IAY REG. NO. MP2525268 | Completed | 15030 | 15480 | 2017-09-30 | 2018-02-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/749656 — Construction of IAY House -IAY REG. NO. MP2525827 | Completed | 15030 | 15136 | 2017-04-28 | 2018-01-18
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/750210 — Construction of IAY House -IAY REG. NO. MP2547854 | Completed | 15030 | 15480 | 2017-09-30 | 2018-01-18
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/768850 — Construction of IAY House -IAY REG. NO. MP3377087 | Completed | 15030 | 14792 | 2017-04-28 | 2018-05-05
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/770737 — Construction of IAY House -IAY REG. NO. MP3469560 | Completed | 15030 | 15136 | 2017-04-28 | 2018-01-18
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/775050 — Construction of IAY House -IAY REG. NO. MP3675557 | Completed | 15030 | 15480 | 2017-04-28 | 2018-02-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/776606 — Construction of IAY House -IAY REG. NO. MP3771717 | Completed | 15030 | 15480 | 2017-04-28 | 2018-04-07
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003031/IF/IAY/795241 — Construction of IAY House -IAY REG. NO. MP2188990 | Completed | 15480 | 14620 | 2017-09-30 | 2018-05-05
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/1170 — मेड वन्‍धान कार्य केदार गोरेलाल वनवारी पुञ देवीराम | Completed | 0 | 19100 | 2010-08-12 | 2010-04-01
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/1360 — मेड वन्‍धान कार्य रामरतन पुञ देवीराम | Deleted | 0 | 0 | 2010-09-09
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387571 — मेढ बंधान देवेन्‍द्र/मावसिया | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387572 — मेढ बंधान गोरेलाल, बनवारी/देवीराम | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387573 — मेढ बंधान रतीराम/चुन्‍नी | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387574 — मेढ बंधान हरिकिशन/आशा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387575 — मेढ बंधान लालसिंह/कोकसिंह | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387576 — मेढ बंधान रमेश/पोहप सिंह | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387577 — मेढ बंधान दाताराम/फैली | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387578 — मेढ बंधान भागीरथ/भंता | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387579 — मेढ बंधान रामकिशन/कोकसिंह | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003031/LD/3799387580 — मेढ बंधान मोहन/कोकसिंह | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/01 — मिटटी मुरम रोड पुनीत का पुरा से कच्‍छा तक | Completed | 213000 | 405128 | 2008-06-01 | 2010-08-12
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003031/RC/02 — सीसीरोड निर्माण हरिजन बस्‍ती | Completed | 300000 | 136670 | 2008-10-11 | 2009-04-01
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/1092 — सी.सी.ख्‍रन्‍जा एंव नाली निर्माण कार्य सोनू के मका | Completed | 282000 | 188176 | 2012-02-21 | 2012-08-24
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/1179 — सी सी खरंजा नालीसहित पुनीत का पुरा | Completed | 423000 | 385824 | 2012-08-04 | 2013-03-28
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034157909 — सी सी खरंजा नालीसहित पुनीत का पुरा | Deleted | 0 | 0 | 2011-12-30
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034161867 — सीसी खरंजा एवं नाली निर्माण गुटटी का पुरा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034161868 — सीसी खरंजा एवं नाली निर्माण माता मंदिर से पुनीत का पुरा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034161869 — सीसी खंरजा एवं नाली निर्माण पुनीत का पुरा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034161870 — सीसी खरंजा एवं नाली निर्माण चौराहे से नरूआ तक गुटटी पुरा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034161903 — पत्‍थर खरंजा निर्माण गुटटी का पुरा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034161904 — पत्‍थर खरंजा निर्माण मुख्‍य रोड से दर्शना के घर तक रामदीन का पुरा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034161905 — पत्‍थर खरंजा निर्माण देवीराम के घर से दयाराम के घर तक कछा | Deleted | 0 | 0 | 2013-01-26
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034187269 — सी सी खरंजा एवं नाली निर्माण कार्य - मुख्‍य मार्ग | Completed | 218508 | 211812 | 2013-10-01 | 2014-09-12
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034284713 — पत्थर खरंजा निर्माण - स्कूल से नरुआ तक, गुट्टी का पूरा | Completed | 312000 | 272859 | 2015-10-08 | 2016-08-22
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034289846 — सी. सी. खरंजा निर्माण एंव नाली कृष्ण के मकान से स्कुल तक पुनीत का पूरा | Completed | 35000 | 19875 | 2015-12-07 | 2016-08-22
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034299511 — मिट्टी बजरी रोड निर्माणब कार्य -मिडिल स्कुल से पुनीत का पूरा रोड तक | Deleted | 795000 | 0 | 2015-11-01
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034305821 — सी. सी. खरंजा निर्माण - प्रकाश के घर से गदीपाल के घर तक | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034305830 — मिट्टी बजरी रोड -नहर से धनीराम के खेत तक | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034305832 — मिट्टी बजरी रोड -भन्ताराम के खेत से गौरीशंकर के खेत तक | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034324124 — सुदूर ग्राम सम्पर्क सड़क निर्माण - गुटटी के पूरा से जतावर की ओर | Completed | 576000 | 432083.22 | 2017-02-02 | 2018-12-05
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034326478 — सी. सी. खरंजा निर्माण कार्य - रामज्ञान के घर से रामनिवास के घर तक पुनीत का पूरा | Deleted | 0 | 0 | 2016-10-02
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034326514 — सी. सी. खरंजा निर्माण - रामज्ञान के घर से रामनिवास के घर तक | Completed | 21600 | 20374 | 2017-03-03 | 2017-09-29
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034327188 — सी. सी खरंजा कार्य निर्माण - डम्बर रोड से मेगराज के घर तक गुट्टी का पूरा | Completed | 21600 | 23908 | 2017-04-05 | 2017-09-29
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034330317 — सी. सी. रोड एंव नाली निर्माण कार्य - गिर्राज के मकान से प्रकाश के मकान तक पुनीत का पूरा | Completed | 50400 | 53664 | 2017-04-05 | 2017-06-20
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034367249 — सी सी खरंजा एंव नाली निर्माण कार्य - दर्शन के घर सेशिवराज के घर तक एंव कप्तान के मकान से पंचम के घर | Completed | 50287 | 49708 | 2017-12-04 | 2018-07-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034367253 — सी सी खरणजेबव नाली निर्माण कार्य -रामनरेश के घर से डी. पी. एंव हैडपम्प तक एंव मोहन से मुख्य मार्ग की | Completed | 103500 | 101478 | 2018-02-06 | 2018-11-19
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034372962 — सी सी खरंजा एंव नाली निर्माण कार्य- श्रीनिवास के मकान से मुख्य मार्ग की ओर | Completed | 24075 | 20760 | 2018-02-21 | 2018-07-27
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034373016 — सी सी खरंजा एंव नाली निर्माण कार्य - सोबरन के मकान से चौराहे तक गुटी का पूरा | Completed | 24075 | 23908 | 2018-02-21 | 2018-07-18
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034373025 — सी सी खरंजा एंव नाली निर्माण कार्य - चित्र के मकान से पत्थर खरंजा एंव सीताराम से रतीराम तक | Completed | 48150 | 9396 | 2018-06-28 | 2019-01-13
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034390894 — सी सी खरंजा नाली निर्माण कार्य बीरवाल मास्टर के घर से रमविलाश के घर तक | Completed | 67833 | 55506 | 2018-08-17 | 2018-12-26
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034390918 — सीसी. खरंजा एवं नाली निर्माण कार्य - रोड से राजू एवं परमहंस के द्वारा तक पुनीतका पुरा, हिंगोनाकलां | Completed | 99750 | 96792 | 2018-08-17 | 2019-06-18
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034390926 — सीसी. खरंजा एवं नाली निर्माण कार्य - भरोसी के घर से सुघर तक, पुनीतपुरा, हिंगोनाकलां | Completed | 13350 | 13224 | 2018-08-17 | 2019-01-13
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034434084 — सी सी रोड एवं नाली निर्माण चोराहे इ कप्तान के घर तक गुट्टी का पुरा | Completed | 73440 | 72508 | 2019-03-08 | 2019-10-10
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034436052 — सी.सी.खरंजा एवं नाली निर्माण कार्य - आशाराम के मकान से जगन्नाथ के मकान तक कच्छपुरा, हिंगोनाकलां | Completed | 79800 | 89022 | 2019-01-21 | 2019-06-18
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034449691 — सी.सी. खरंजा एवं नाली निर्माण कार्य - स्कूल से प्रकाश तक एवं पूरन के मकान से नत्थी चैकीदार के घर तक | Completed | 24585 | 23416 | 2019-03-08 | 2019-09-18
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034449698 — सी.सी. खरंजा एवं नाली निर्माण कार्य - रामरतन के घर से गोरे के घर तक, कच्छपुरा | Completed | 13410 | 12528 | 2019-03-08 | 2019-06-18
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034449708 — सी.सी. खरंजा एवं नाली निर्माण कार्य - विशाल के मान से केदार एवं कन्हैया माहौर के पास माधौ कुशवाह के | Completed | 44700 | 43296 | 2019-08-03 | 2019-10-10
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034473058 — सी.सी.रोड नाली निर्माण कार्य दयाराम के घर से रामनरेश के घर तक कछपुरा +१४ वित्त | Completed | 59850 | 59460 | 2019-12-19 | 2020-12-17
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034473060 — सी.सी.रोड नाली निर्माण कार्य मुकेश के घर से दाताराम के घर तक कछपुरा +१४ वित्त | Completed | 63840 | 60720 | 2019-12-19 | 2020-12-17
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034473061 — सी.सी.रोड नाली निर्माण कार्य दयाराम के घर से आंगनवाड़ी तक कछपुरा +१४ वित्त | Completed | 82305 | 82556 | 2019-11-07 | 2021-01-10
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034523528 — सुदूर ग्राम सम्पर्क सड़क निर्माण कार्य - हिंगोनाकलाँ से प्राथमिक शाला भवन तक | Deleted | 0 | 0 | 2020-01-26
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034524415 — एप्रोच रोड निर्माण कार्य नवीन कछाह (हिगोनक्ला )से माध्यमिक शाला भवन तक | Completed | 1426487.75 | 1369440.26 | 2020-06-13 | 2022-09-25
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/22012034525401 — सी॰सी॰ खरंजा एवं नाली निर्माण कार्य - रामसेवक के घर से श्यामू डंडौतिया के घर तक, बहादुर का पुरा | Completed | 71820 | 69350 | 2020-07-27 | 2020-12-17
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003031/RC/22012034533898 — सुदूर ग्राम /खेत सड़क प्राथमिक शाला भवन से बड़ी नहर तक | Completed | 1474659.75 | 1277910.58 | 2020-08-24 | 2022-09-25
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003031/RC/31 — सी सी रोड निर्माण कार्य कुशवाह मो0 हिगोनाकला | Completed | 148000 | 107461 | 2008-12-15 | 2009-08-17
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/rc/32 — मिटटी बजरी रोड प्रा शा भवन डम्‍वर रोड से नहर की प | Completed | 690000 | 499011 | 2009-03-01 | 2015-06-26
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/367 — मिटटी वजरी रोड ल्‍होरे को पूरा मोहन का पुरा | Completed | 0 | 79700 | 2008-06-01 | 2010-08-30
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/368 — मिटटी वजरी रोड गुटटी पुरा से मदिर तक | Completed | 0 | 9644 | 2009-01-24 | 2013-12-19
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/588 — मिट्र्टी मुरम रोड कछा रोड से शांतीधाम हिगोनाकलॉ | Completed | 139000 | 102536 | 2011-01-05 | 2011-09-05
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003031/RC/589 — मिट्र्टी बजरी रोड गुट्र्टी का पुरा से मन्दिर तक हिगोनाकलॉं | Completed | 0 | 101384 | 2010-05-05 | 2011-09-26
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1701003031/RS/22012034602400 — कचरा भंडार केंद्र (सेग्रीगेशन शेड ) ग्राम पंचायत हिगोनकला | Completed | 628297.23 | 502272.87 | 2021-11-15 | 2022-08-16
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003031/RS/22012034680887 — सामुदायिक स्वच्छता परिसर निर्माण कार्य- पंचायत भवन के पास, हिंगोनाकलां | Completed | 69000 | 60996 | 2023-05-25 | 2023-07-07
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003031/WC/01 — सोख्‍ता गड्रडा पुनीत का पुरा | Completed | 11200 | 13280 | 2008-05-25 | 2010-05-31
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701003031/WC/02 — सोख्‍ता गड्रडा देवीराम का पुरा | Completed | 11200 | 13635 | 2008-05-27 | 2010-05-31
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034386236 — नवीन तालाब निर्माण कार्य हिंगोना कला | Completed | 726000 | 678115.26 | 2018-02-21 | 2024-07-23
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034432258 — नवीन तालाब निर्माण कार्य - | Deleted | 0 | 0 | 2019-01-26
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003031/WC/22012034616364 — सोकता गडडा शा.प्रा.वि. नवीन कछछ (एस.एल.डब्ल्यू.एम.) | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003031/WC/22012034616366 — सोकता गडडा विशम्भर के हैण्पम्प के पास (एस.एल.डब्ल्यू.एम.) | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003031/WC/22012034616369 — सोकता गडडा मुन्ना के हैण्पम्प के पास (एस.एल.डब्ल्यू.एम.) | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003031/WC/22012034616373 — सोकता गडडा पोपसिंह के हैण्पम्प के पास (एस.एल.डब्ल्यू.एम.) | Completed | 18382.8 | 10338 | 2021-06-19 | 2023-08-18
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003031/WC/22012034616375 — सोकता गडडा पंचायत भवन के पास (एस.एल.डब्ल्यू.एम.) | Closed | 18382.8 | 0 | 2021-01-21
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012034768257 — रूफ वाटर हार्वेस्टिंग पंचायत भवन हिगोनाकला | Closed | 22823.53 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012034768260 — रूफ वाटर हार्वेस्टिंग प्राथमिक शाला भवन हिगोनाकला | Deleted | 0 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003031/WC/22012034775123 — नवीन तालाब निर्माण वीरेंद्र के खेत के पास | Completed | 1459809.99 | 1165166.55 | 2021-09-13 | 2023-10-14
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003031/WC/22012034775128 — नवीन तालाब निर्माण राकेश के खेत के पास | Completed | 1264167.61 | 1115852.55 | 2021-08-13 | 2023-10-14
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003031/WC/22012034971587 — नवीन तालाब निर्माण कार्य मौजीलाल के खेत के पास | Closed | 0 | 0 | 2022-04-14
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980777 — nws earthan bund pop singh ke khet ke pass | Deleted | 0 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980779 — nws earthan bund shyamu ke khet ke pass | Closed | 972892.05 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980781 — nws earthan bund bhura ke khet ke pass | Closed | 943667.14 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980784 — nws talab nirman kary pop singh khet ke pass | Deleted | 0 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980789 — nws talab nirman kary pop singh khet ke pass | Closed | 1491716.74 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980792 — nws talab nirman kary gore khet ke pass | Closed | 1497245.83 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980796 — nws talab nirman kary veero khet ke pass | Closed | 1472722.06 | 0 | 2022-05-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012034980802 — nws talab nirman kary raghuraaj khet ke pass | Closed | 1485261.94 | 0 | 2022-05-20
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701003031/WC/22012035049896 — गली प्लग निर्माण कार्य तालाब के नीचे गुट्टी का पुरा हिंगोनाकलां | Physically Completed | 889657.12 | 606832.8 | 2024-02-27 | 2026-04-16
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012035085112 — रपटा निर्माण कार्य पुनीत का पुरा तिराहे पर, हिंगोनाकलां | Completed | 1447225.22 | 1353540.4 | 2023-07-04 | 2025-12-11
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003031/WC/22012035128391 — रपटा निर्माण कार्य हनुमान मंदिर के पास पुराना गांव कछा | Completed | 1391389.91 | 1310185 | 2023-10-06 | 2024-10-28
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701003031/WC/22012035158373 — नवीन रपटा निर्माण कार्य आंगनबाडी भवन के पास गुट्टी का पुरा | Completed | 1480742.36 | 1322711.47 | 2024-02-14 | 2024-10-28
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701003031/WC/22012035158378 — नवीन रपटा निर्माण कार्य पंचायत भवन के पास नरूआ के सामने | Completed | 1490966.23 | 1369138.88 | 2024-02-14 | 2024-11-11
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003031/WC/22012035185955 — रपटा निर्माण कार्य गुट्टी का पुरा नरूआ के पास तिराहे पर | Completed | 1485287.81 | 1389652.7 | 2024-03-09 | 2024-11-11
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035221236 — परकुलेशन टैंक निर्माण कार्य भरोसी के खेत के पास बेहड मे, हिंगोनाकलां | Deleted | 0 | 0 | 2024-08-16
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035221237 — परकुलेशन टैंक निर्माण कार्य पुनीत का पुरा हनुमान मंदिर के पास, हिंगोनाकलां | Deleted | 0 | 0 | 2024-08-16
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035221581 — तालाब निर्माण कार्य भरोसी के खेत के पास बेहड़ मे, हिंगोनाकलाँ | Physically Completed | 1454429.75 | 1398169.12 | 2024-11-11 | 2026-04-16
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035221582 — तालाब निर्माण कार्य पुनीत का पुरा हनुमान मंदिर के पास, हिंगोनाकलाँ | Physically Completed | 1476366.56 | 1387746.33 | 2024-11-11 | 2026-04-16
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003031/WC/22012035302928 — Dugwell Richarge Pit Nirmaan Karya Panchayat Bhawan ke paas wala kua | Completed | 25899.46 | 14616 | 2025-05-24 | 2025-12-11
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035317531 — तालाब निर्माण कार्य पंजाब के बेहड के पास | Ongoing | 1486282.85 | 1007515.12 | 2026-02-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035317532 — तालाब निर्माण कार्य गोरे के बेहड मे | Ongoing | 1487614.4 | 974244.31 | 2026-02-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035317533 — तालाब निर्माण कार्य विजय के बेहड मे | Ongoing | 1487086.37 | 992851.5 | 2026-01-29
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035317534 — तालाब निर्माण कार्य पूरन के बेहड के पास | Ongoing | 1486344.72 | 1022351.63 | 2026-02-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035317535 — तालाब निर्माण कार्य नत्थीलाल के बेहड मे | Ongoing | 1488071.4 | 965196.07 | 2026-02-27
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701003031/WC/22012035317536 — तालाब निर्माण कार्य भारत के बेहड के पास | Approved | 1485254.29 | 0 | 2025-04-14
MORENA / MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001438 — नन्‍दन फलो उधान कार्य जगमन पुञ चन्‍नीराम | Completed | 156000 | 30370.8 | 2012-07-27 | 2015-07-27
MORENA / MORENA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701/IF/1000001568 — वक्षारोपड कार्य शोभाराम पुञ चुन्‍नी | Completed | 153000 | 26799.4 | 2012-08-15 | 2015-08-16