## Work List
Exported on: 2026-10-09 21:04:16
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: CHHICHHAWALI
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / MORENA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003046/DP/145 — व़क्षा रोपड कार्य सुरली मनोहर रामजानकी मदिर वाग छिछावली | Completed | 0 | 10217.54 | 2009-09-14 | 2009-04-01
MORENA / MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003046/DP/336 — शान्‍ती धाम चवूतरा, खरंजा निमार्ण कार्य छिछावली , | Completed | 0 | 241926 | 2011-11-22 | 2012-02-12
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003046/DP/367 — नन्‍द्रन फलोध्‍यान | Completed | 328000 | 116733 | 2012-07-25 | 2016-03-04
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003046/DP/368 — व्रक्षारोपड | Completed | 137000 | 27475 | 2012-07-25 | 2016-03-04
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701003046/DP/383 — नन्‍दन फलोध्‍यान मूलचन्‍द | Completed | 156121 | 77424 | 2012-09-05 | 2016-03-04
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003046/DP/9926688906 — शान्‍तीधामबाउड्री वॉंल निर्माण कार्य छिछावली | Completed | 0 | 470313.99 | 2011-01-30 | 2011-11-20
MORENA / MORENA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003046/FP/22012034635903 — पत्थर नाला निर्माण कार्य शिवराज कुशवाह के घर से शमसान घाट की ओर। | Completed | 934420.28 | 816783.13 | 2024-05-23 | 2025-03-31
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1701003046/FP/26 — नालीनिर्माण कार्य | Completed | 0 | 101695.86 | 2012-07-10 | 2012-07-23
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701003046/FP/9977522033 — नाला निर्माण कार्य - माता से ताल की ओर | Completed | 142766 | 105536.93 | 2013-09-18 | 2015-05-20
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000059473 — cattle shed nirmad karya ramnaresh/phool singh | Completed | 80000 | 72928.81 | 2014-01-01 | 2014-09-14
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000059476 — cattle shed nirmard karya tilak singh /panchilal | Completed | 80000 | 73183.88 | 2013-12-31 | 2014-09-14
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000063117 — पशुशैड निर्माण - रामप्रकाश/रामभरोसी | Completed | 80000 | 70727.88 | 2014-01-14 | 2014-09-14
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000063123 — पशुशैड निर्माण - पूरन/मातादीन तोमर | Completed | 80000 | 72592.47 | 2014-01-14 | 2014-09-14
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000065733 — पशुशैड निर्माण -विजय/रामदनी | Completed | 80000 | 71717.93 | 2014-01-24 | 2015-05-20
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000068071 — पशुशेड निर्माण कार्य भीकम पुत्र बाबू तोमर | Completed | 80000 | 87411.84 | 2014-01-31 | 2015-05-20
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/1000068085 — पशुशेड निर्माण कार्य भारत पुत्र पाल सिंह तोमर | Completed | 80000 | 72122.68 | 2014-02-07 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650937 — पशुशेड निर्माण कार्य- विश्वनाथ/ फूल सिंह | Completed | 90000 | 82725.51 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650944 — पशु शेड निर्माण कार्य- दिनेश/ गंगाराम | Completed | 90000 | 80511.96 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650946 — पशु शेड निर्माण कार्य- गंगा/ बंशी | Completed | 90000 | 79849.72 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650948 — पशु शेड निर्माण कार्य -राकेश /शिवराज | Completed | 90000 | 74959.81 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650951 — पशु शेड निर्माण कार्य -राम कारन /गंगाराम | Completed | 90000 | 77959.87 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650972 — पशु शेड निर्माण कार्य -सुरेन्द्र /धर्म सिंह | Completed | 90000 | 78150.75 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650975 — पशु शेड निर्माण कार्य -दलीप /पंचम | Completed | 90000 | 76215.85 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650977 — पशु शेड निर्माण कार्य -रवि/बल्लो | Completed | 90000 | 84107.78 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650980 — पशु शेड निर्माण कार्य- अगनू /शिव लाल | Completed | 90000 | 37903.65 | 2014-08-23 | 2018-10-30
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993650982 — पशु शेड निर्माण कार्य- सुनील /भारत | Completed | 90000 | 82719.94 | 2014-08-23 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652833 — पशु शैड निर्माण कार्य - तलफा / दर्शन | Completed | 90000 | 80257.89 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652836 — पशु शैड निर्माण -सोमवती / बनवारी | Completed | 90000 | 78570.93 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652837 — पशु शैड निर्माण - हरिज्ञान / रामसिह | Completed | 80000 | 74503.85 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652838 — पशु शैड निर्माण - धर्मसिह भोगीराम | Completed | 80000 | 74189.85 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652842 — पशु शैड निर्माण -अविलाख / गंगा | Completed | 90000 | 77146.64 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652843 — पशु शैड निर्माण - रामवरन /रामदीन | Completed | 90000 | 78520.86 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652844 — पशु शैड निर्माण - ब्रजराज / गिर्राज | Completed | 90000 | 82495.74 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652845 — पशु शैड निर्माण -हरिओम / दामोदर | Completed | 80000 | 81396.73 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652846 — पशु शैड निर्माण -चतुरसिह / धर्मसिह | Completed | 80000 | 76078.87 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652847 — पशु शैड निर्माण -सुरज / रामस्वरुप | Completed | 80000 | 72136.75 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652848 — पशु शैड निर्माण - किशन / ब्रजभुषण | Completed | 90000 | 75742.88 | 2014-09-06 | 2015-07-10
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652849 — पशु शैड निर्माण -विनोद /सरमन | Completed | 90000 | 76372.9 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003046/IF/9993652850 — पशु शैड निर्माण -सुघरसिह / चतुरीसिह | Completed | 90000 | 78256.66 | 2014-09-06 | 2015-05-20
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/1170859 — Construction of IAY House -IAY REG. NO. MP3048723 | Completed | 15480 | 15054 | 2018-06-20 | 2021-10-01
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/1901298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4258316 | Completed | 15660 | 14760 | 2019-01-14 | 2020-01-01
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/1902261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4609706 | Completed | 15660 | 12672 | 2019-01-14 | 2019-10-21
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/1902467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5107540 | Completed | 15660 | 14760 | 2019-01-14 | 2019-10-21
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/524732 — Construction of IAY House -IAY REG. NO. MP2662570 | Completed | 15030 | 14936 | 2017-01-31 | 2019-08-28
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/536468 — Construction of IAY House -IAY REG. NO. MP2969885 | Completed | 15030 | 14652 | 2017-02-20 | 2019-09-04
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/556960 — Construction of IAY House -IAY REG. NO. MP3559132 | Completed | 15030 | 14616 | 2017-02-20 | 2019-04-23
MORENA / MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/722403 — Construction of IAY House -IAY REG. NO. MP1760259 | Completed | 17100 | 15960 | 2020-12-25 | 2021-03-10
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/723488 — Construction of IAY House -IAY REG. NO. MP1785366 | Completed | 15030 | 14628 | 2018-06-20 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/726665 — Construction of IAY House -IAY REG. NO. MP1871409 | Completed | 15030 | 14640 | 2018-06-20 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/758729 — Construction of IAY House -IAY REG. NO. MP2900503 | Completed | 15030 | 15210 | 2019-03-03 | 2019-08-28
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/762263 — Construction of IAY House -IAY REG. NO. MP3066198 | Completed | 15030 | 14676 | 2018-08-29 | 2019-10-05
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/772456 — Construction of IAY House -IAY REG. NO. MP3546111 | Completed | 15030 | 14628 | 2018-06-20 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/803335 — Construction of IAY House -IAY REG. NO. MP3099519 | Completed | 15480 | 15408 | 2019-03-03 | 2019-09-04
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/814668 — Construction of IAY House -IAY REG. NO. MP1757160 | Completed | 15480 | 14640 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/815580 — Construction of IAY House -IAY REG. NO. MP1832356 | Completed | 15480 | 14736 | 2019-03-07 | 2019-09-17
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/815813 — Construction of IAY House -IAY REG. NO. MP1850480 | Completed | 15480 | 15684 | 2018-06-20 | 2019-08-28
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/816048 — Construction of IAY House -IAY REG. NO. MP1871378 | Completed | 15480 | 14466 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/816382 — Construction of IAY House -IAY REG. NO. MP1900453 | Completed | 15480 | 14652 | 2018-06-20 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/816739 — Construction of IAY House -IAY REG. NO. MP1929921 | Completed | 15480 | 14574 | 2019-03-03 | 2019-10-21
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/817135 — Construction of IAY House -IAY REG. NO. MP1968631 | Completed | 15480 | 14628 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/818093 — Construction of IAY House -IAY REG. NO. MP2046758 | Completed | 15480 | 14628 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/819658 — Construction of IAY House -IAY REG. NO. MP2190712 | Completed | 15480 | 14628 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/824987 — Construction of IAY House -IAY REG. NO. MP2907851 | Completed | 15480 | 15054 | 2017-04-30 | 2021-10-15
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/825968 — Construction of IAY House -IAY REG. NO. MP3098106 | Completed | 15480 | 14640 | 2017-04-30 | 2019-09-17
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/825972 — Construction of IAY House -IAY REG. NO. MP3098447 | Completed | 15480 | 14628 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/826094 — Construction of IAY House -IAY REG. NO. MP3113534 | Completed | 15480 | 14640 | 2017-04-30 | 2019-09-04
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/828269 — Construction of IAY House -IAY REG. NO. MP3563729 | Completed | 15480 | 14760 | 2019-02-26 | 2019-09-17
MORENA / MORENA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003046/IF/IAY/828679 — Construction of IAY House -IAY REG. NO. MP3664803 | Completed | 15480 | 14760 | 2019-02-26 | 2019-06-20
MORENA / MORENA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003046/LD/1420 — खेलमेदान निर्माण कार्य छिछावली मजरा दम्‍पतिकापुरा | Completed | 454000 | 317964 | 2012-01-06 | 2012-03-18
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003046/LD/1434 — खेल मेदान निर्माण कार्य रामजानकी मंदिर बाग | Completed | 868500 | 777172.64 | 2012-05-24 | 2013-03-09
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003046/RC/1002 — मिटटी मुरम बजरी रोड निर्माण कार्य चीकी से रामगोपाल | Completed | 497000 | 367626.8 | 2011-06-20 | 2014-09-05
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/1160 — पत्‍थर खरंजा कार्य | Completed | 0 | 77326.41 | 2012-06-24 | 2016-03-04
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/1188 — पत्‍थर खरंजा | Completed | 474000 | 347884.8 | 2012-08-25 | 2013-02-02
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/1227 — सी सी खरंजा एवं नाली निर्माण मेनरोड से स्‍कूल एवं | Completed | 212375 | 223159.18 | 2012-11-16 | 2013-04-02
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034164583 — सी सी खरंजा एवं नाली निर्माण कार्य रामनिवास तोमर के द्वार से रूस्‍तम सिंह के द्वार की ओर | Completed | 18757.4 | 12118 | 2013-05-03 | 2014-09-09
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003046/RC/22012034198557 — पत्थर खरंजा निर्माण - मैन खरंजे से कुआ एंव रामनरे | Completed | 354000 | 289170.63 | 2014-01-22 | 2015-05-20
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003046/RC/22012034200451 — खेत सड्क मिटटी बजरी रोड निर्माण -पंचायत भवन से दंप | Completed | 1066000 | 516955.9 | 2014-02-01 | 2016-09-19
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034208254 — सी सी खरंजा एव नलीनिर्माण कार्य -मजरा दम्पति का पु | Completed | 189814 | 177744 | 2014-02-26 | 2014-09-05
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003046/RC/22012034211034 — खेत सडक योजना मिट्टी बजरी रोड निर्माण - सुदूर ग्रा | Completed | 1382500 | 482401.6 | 2014-03-04 | 2016-08-10
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003046/RC/22012034211798 — खेत सडक मिटटी बजरी रोड निर्माण - खूबत से दतहरा की | Completed | 1010783 | 422699.8 | 2014-03-06 | 2016-09-19
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034329294 — सी सी खरंजा निर्माण कार्य पंचम के मकान से गंगादीन के मकान तक रढूआवारी छिछावली | Completed | 28856.25 | 28724 | 2017-07-29 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034382969 — सी सी रोड गिरधारी के कुआ से गोपाल जाटव् के घर तक | Completed | 62725 | 61920 | 2018-02-03 | 2020-12-15
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034382973 — सी सी रोड रामकरण के घर से सरनाम सिंह जाटव के घर तक | Completed | 39108 | 30276 | 2018-03-14 | 2019-10-21
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034382977 — सी सी रोड रामेश्वर जाटव के घर से घनश्याम के घर तक | Completed | 17776 | 14790 | 2018-07-21 | 2019-10-21
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034382980 — सी सी रोड विजय सिंह कढेरे के घर से चन्दन सिंह सिकरवार के घर तक | Completed | 25395 | 15660 | 2018-07-09 | 2020-08-20
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034382981 — सी सी रोड कन्या शाला से हरी सिंह तोमर हाई स्कूल से गिरधारी तोमर के घर तक | Completed | 25395 | 23838 | 2018-08-07 | 2019-10-21
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034441615 — सी.सी. खरंजा एवं नाली निर्माण कार्य - पंचम के घर से तुलसी एवं भजनलाल के घर तक, ररूआ बाई का पुरा छिछा | Completed | 54978 | 41928 | 2019-02-18 | 2019-10-10
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034441621 — सी.सी. खरंजा एवं नाली निर्माण कार्य - आंगनबाडी से जगदीश कुशवाह के घर तक, छिछावली | Completed | 55080 | 54904 | 2019-02-18 | 2019-06-29
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034441626 — सी.सी. खरंजा एवं नाली निर्माण कार्य - पूरन जाटव के घर से केदार जोशी के घर तक, छिछावली | Completed | 13311 | 12144 | 2019-03-03 | 2019-10-21
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034463158 — सीमेंट कंक्रीट खरंजा निर्माण राजकुमार के घर से बालकिशन जोशी के घर तक | Completed | 13311 | 11792 | 2019-06-20 | 2019-10-21
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034463161 — सीमेंट कंक्रीट खरंजा निर्माण लोडू के घर से बनवारी के घर तक | Completed | 42120 | 30624 | 2019-06-20 | 2019-10-21
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034463163 — सीमेंट कंक्रीट खरंजा निर्माण शिवराम परमार के घर से मुरारी पुजारी के घर तक | Completed | 41121 | 41008 | 2019-06-20 | 2019-10-21
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034477523 — सी.सी. खरंजा एवं नाली निर्माण कार्य - सरमन राजावत के घर से धर्मेन्द्र चैकीदार के घर तक, छिछावली | Completed | 13311 | 12672 | 2019-09-23 | 2020-12-15
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034477573 — सी.सी. खरंजा एवं नाली निर्माण कार्य - छोटे सिंह परमार के घर से मोहर सिंह परमार के घर तक | Completed | 9983 | 9680 | 2019-09-23 | 2020-12-15
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034477574 — सी.सी. खरंजा एवं नाली निर्माण कार्य - शैलेन्द्र भदौरिया के घर से पंचायत भवन तक | Completed | 14202 | 12672 | 2019-09-23 | 2020-12-15
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034506375 — सी.सी. खरंजा एवं नाली निर्माण कार्य - मुख्य मार्ग से जयनारायण के मकान तक, छिछावली | Completed | 34627 | 18656 | 2019-12-13 | 2020-12-09
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034506377 — सी.सी. खरंजा एवं नाली निर्माण कार्य - रोड से शांतिधाम टीन शेड तक | Completed | 91800 | 40142 | 2020-01-03 | 2020-12-09
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034524880 — सी. सी. खरंजा एवं नाली निर्माण कार्य पुजारी के घर से आसाराम कुशवाह के घर तक छिछावली | Completed | 48127 | 44080 | 2020-06-16 | 2020-12-09
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034524883 — सी. सी. खरंजा एवं नाली निर्माण मैंन रोड से रामभजन परमार के घर तक | Completed | 38250 | 38000 | 2020-06-16 | 2020-12-09
MORENA / MORENA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003046/RC/22012034533597 — सुदूर ग्राम /खेत सड़क चौकियाई रोड से दंपती का पुरा | Completed | 1497116.76 | 1408307.09 | 2020-08-18 | 2026-08-18
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003046/RC/22012034541722 — सुदूर सम्पर्क/खेत सडक शमशान घाट से बम्बा तक | Completed | 1325599.9 | 1204547.01 | 2021-04-03 | 2026-08-18
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003046/RC/22012034590620 — सी. सी. खरंजा मैन रोड से शान्तिधाम की और छिछावली | Completed | 65625 | 59723 | 2021-11-22 | 2023-07-04
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/294 — पत्‍थर खरजा निर्माण कार्य राधेश्‍याम के दार से महादेव तक | Completed | 0 | 40236 | 2009-07-30 | 2010-02-10
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/335 — पत्‍थर खरजा निर्माण कार्य मुन्‍शी का पुरा | Completed | 0 | 34328 | 2009-09-05 | 2010-02-10
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003046/RC/444 — पत्‍थर खरजा निर्माण कार्य मेन रोड नरपति के द्वार से समसान व तालाव की ओर छिछावली | Completed | 0 | 44398 | 2009-12-18 | 2010-02-08
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003046/RC/574 — मिटृटी मुरम रोड बाबा की खुटी से रडुआवारी की ओर | Completed | 0 | 479783 | 2010-07-15 | 2012-07-25
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/578 — पत्‍थर खरजा निमार्ण कार्य मेन रोड से कदम सिह जाटव के दार की ओर | Completed | 0 | 32500 | 2010-11-08 | 2010-11-21
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/579 — पत्‍थर खरजा निमार्ण कार्य वल्‍ला माहोर के दार | Completed | 0 | 30271 | 2010-11-12 | 2011-03-17
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003046/RC/580 — पत्‍थर खरजा निमार्ण कार्य गगासिह कुशवाह खरजा | Completed | 0 | 22600 | 2010-12-20 | 2016-05-10
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003046/RC/71 — पत्‍थर खरंजा निर्माण कार्य | Completed | 392000 | 200077.57 | 2009-02-24 | 2010-01-28
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003046/RC/72 — सी.सी. खरंजा निर्माण कार्य | Completed | 103000 | 50334.79 | 2009-02-03 | 2009-09-10
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232418 — शोचालय निर्माण कार्य विजय /रामदीन | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232611 — शौचालय निर्माण कार्य बारेलाल /बेदराम | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232614 — शौचालय निर्माण कार्य रामरूप /गन्दर्भ सिह | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232619 — शौचालय निर्माण कार्य सुघरसिह /चतुरी बरेठा | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232640 — शौचालय निर्माण कार्य पंचम /बिहारी | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232641 — शौचालय निर्माण कार्य हरिज्ञान /श्यामसिंह | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232642 — शौचालय निर्माण कार्य सुनील/सुल्तान | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034232643 — शौचालय निर्माण कार्य मुन्ना /हिमाचल | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260872 — शौचालय निर्माण कार्य विनोद /सरमन | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260896 — शौचालय निर्माण कार्य रामनरेश /फूलसिंह | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260903 — शौचालय निर्माण कार्य विजय /सुरेश | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260906 — शौचालय निर्माण कार्य उदयसिंह/पंचमसिंह | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260911 — शौचालय निर्माण कार्य भारत /पालसिंह तोमर | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260916 — शौचालय निर्माण कार्य गिर्राज /गोपाल | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260926 — शौचालय निर्माण कार्य किशन /ब्रजभूषण शर्मा | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701003046/RS/22012034260930 — शौचालय निर्माण कार्य ब्रजराज/गिर्राजशर्मा | Completed | 5400 | 5300 | 2014-08-19 | 2015-05-20
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701003046/RS/22012034617552 — सामुदायिक स्वछता परिसर छिछावली | Completed | 43000 | 41688 | 2021-11-22 | 2023-07-04
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003046/WC/22012035302290 — Dugwell Richarge Pit Nirmaan Karya Rajveer Kushwah ke ghar ke samne wala kua | Completed | 25899.46 | 15660 | 2025-06-05 | 2026-07-31
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701003046/WC/22012035302292 — Dugwell Richarge Pit Nirmaan Karya Shaskiya School ke samne wala kua | Completed | 25899.46 | 15660 | 2025-07-24 | 2026-07-31
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003046/WC/50 — निर्मल नीर योजना सोक पिट | Completed | 11500 | 5337.21 | 2009-02-18 | 2008-01-26
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003046/WH/22012034921249 — तालाब जीर्णोद्धार दमपती का पुरा | Completed | 364297 | 285345 | 2022-04-29 | 2024-03-16