## Work List
Exported on: 2026-10-14 08:04:46
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BAMURBASAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / MORENA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1701003067/AV/22012034512809 — गोशाला निर्माण कार्य बमूरबसई | Deleted | 3784582.21 | 0 | 2020-04-14
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003067/AV/22012034618866 — शान्तिधाम उन्नयन कार्य बमूरबसई | Deleted | 0 | 0 | 2022-04-14
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003067/AV/22012034619776 — शांतिधाम उन्नयन कार्य बमूरबसई | Closed | 289458.68 | 0 | 2022-04-14
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701003067/AV/22012034619777 — शांतिधाम उन्नयन कार्य बमूरबसई | Deleted | 0 | 0 | 2022-04-14
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003067/DP/125 — व़क्षारोपण कार्य काजी बसई | Completed | 495000 | 9169 | 2008-12-05 | 2008-07-01
MORENA / MORENA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003067/DP/126 — निर्माण कार्य व़क्षारोपण झरोके कार्य | Completed | 495000 | 6264 | 2008-11-08 | 2008-07-01
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov bldng premises Blck Plntation-Forestry-Comunty / Block Plantation of Forestry Trees in Government building premises for Community | Plantation | 1701003067/DP/22012034542220 — माँ की बगिया शा. माँ. वि .शेरपुर | Closed | 17471.6 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov bldng premises Blck Plntation-Forestry-Comunty / Block Plantation of Forestry Trees in Government building premises for Community | Plantation | 1701003067/DP/22012034542228 — माँ की बगिया शा.प्रा. वि जद्दे का पुरा | Closed | 20950.17 | 0 | 2021-10-02
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701003067/DP/266 — निर्मल वाटिका शैरपुर बमूर बसई | Completed | 0 | 19465 | 2010-08-18 | 2013-03-05
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/DP/298 — शाती धाम | Completed | 0 | 418793.63 | 2011-01-11 | 2012-03-07
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Storm Water Drains / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701003067/FP/22012034314149 — नाली निर्माण कार्य सामलिया के घर से भरतदास मंदिर की ओर बमूरबसई | Completed | 1499000 | 1442300.48 | 2017-02-02 | 2018-05-16
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701003067/FP/22012034314805 — नाला निर्माण कार्य - खिरकन के थान से पुलिया की ओर एवं गजराज के मकान से तालाब की ओर | Completed | 1499000 | 254374.13 | 2017-08-21 | 2019-01-10
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003067/FP/22012034630626 — नाला निर्माण कार्य टिंकू के मकान से पुलिया एवं प्राथमिक स्कूल तक जद्दे का पूरा | Deleted | 0 | 0 | 2022-08-20
MORENA / MORENA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003067/FP/22012034630627 — नाला निर्माण कार्य विशाल के घर से भूमिया बाले नरे तक | Deleted | 0 | 0 | 2022-08-20
MORENA / MORENA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701003067/FP/22012034639406 — नवीन नाला निर्माण कार्य पीएम रोड से जय सिंह गुर्जर के घर | Completed | 1422956.06 | 1354731.04 | 2024-03-16 | 2025-07-15
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003067/FR/22012034322967 — Talab nirmaan karya gram jardan ke pura me khubat ke pass | Ongoing | 1477749.28 | 1412203.72 | 2025-04-18
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1701003067/FR/22012034322968 — Talab nirmaan karya gram jardan ke pura me chopla ke nare me | Ongoing | 1462418.59 | 1399280.46 | 2025-04-18
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/1000040200 — पशुशेण निर्माण कार्य जशरथ / रामप्रकाश | Completed | 80000 | 70489.44 | 2013-09-28 | 2015-07-07
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/1000040215 — पशु शेड निर्माण कार्य लोट्न /विजय सिह | Completed | 80000 | 68215.9 | 2013-09-28 | 2015-07-09
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/1000040246 — पशु शेड निर्माण कार्य महाबीर /सरनाम सिह् | Completed | 80000 | 69061.4 | 2013-09-28 | 2015-07-07
MORENA / MORENA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/1000040252 — पशु शेड निर्माण कार्य बाद्शाह /सरनाम | Completed | 80000 | 67679.98 | 2013-09-28 | 2015-07-07
MORENA / MORENA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003067/IF/124 — मेड बन्‍धान कार्य सरनाम पुञ जगदीश | Completed | 0 | 8250 | 2010-09-30 | 2010-10-06
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003067/IF/22012034342889 — शार्वजनिक परिषर मे व्रक्षारोपण निर्माण कार्य | Completed | 335000 | 11270 | 2017-06-22 | 2020-09-08
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003067/IF/22012035496170 — Dugwell Richarge Pit Nirmaan Karya Gadipal ke kua ke pass | Ongoing | 25899.46 | 1827 | 2025-05-12
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003067/IF/22012035496178 — Dugwell Richarge Pit Nirmaan Karya Malkhan ke kua ke pass | Ongoing | 25899.46 | 261 | 2025-05-12
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003067/IF/22012035496183 — Dugwell Richarge Pit Nirmaan Karya Saligram ke kua ke pass | Ongoing | 25899.46 | 261 | 2025-05-12
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003067/IF/22012035496189 — Dugwell Richarge Pit Nirmaan Karya Jai Singh ke kua ke pass | Ongoing | 25899.46 | 261 | 2025-05-12
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1701003067/IF/22012035496192 — Dugwell Richarge Pit Nirmaan Karya Banti ke kua ke pass | Ongoing | 25899.46 | 3393 | 2025-05-12
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1701003067/IF/22012035496709 — JGSA DUGwell Gadhipal/soneram | Deleted | 25899.46 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1701003067/IF/22012035496727 — JGSA DUGWELL malkhan/bajilal | Deleted | 25899.46 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701003067/IF/22012035496756 — Khet Talab Nirman karya Rumali/shiv singh | Approved | 0 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003067/IF/22012035601865 — Ek Bagiya Maa Ke Naam BHURI 159903356 | Ongoing | 284160.73 | 1566 | 2025-09-16
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003067/IF/22012035601873 — Ek Bagiya Maa Ke Naam LALO 156980080 | Ongoing | 283818.64 | 0 | 2026-01-18
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003067/IF/22012035601888 — Ek Bagiya Maa Ke Naam SUNDARIYA 182164389 | Ongoing | 283876.09 | 1566 | 2025-09-16
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003067/IF/22012035601895 — Ek Bagiya Maa Ke Naam RAJENDRADEVI 159736164 | Ongoing | 283810.7 | 1566 | 2025-09-16
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003067/IF/22012035631163 — Ek Bagiya Maa Ke Naam BARFI DEVI BAGHEL 159898123 | Deleted | 266578.64 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701003067/IF/22012035631166 — Ek Bagiya Maa Ke Naam SUKHIBAI 159859220 | Deleted | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003067/IF/22012035651526 — Ek Bagiya Maa Ke Naam BARFI DEVI BAGHEL 159898123 | Ongoing | 283818.64 | 0 | 2025-12-29
MORENA / MORENA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701003067/IF/22012035651527 — Ek Bagiya Maa Ke Naam SUKHIBAI 159859220 | Ongoing | 283818.64 | 0 | 2025-12-29
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993691667 — पशु-सेड निर्माण कार्य -हर्वेद पुत्र लक्ष्मण | Completed | 90000 | 80864.8 | 2015-12-05 | 2016-06-16
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993691674 — पशु-शेड निर्माण कार्य -रामविलाश पुत्र लक्ष्मण सिंह | Completed | 90000 | 79729.95 | 2015-12-05 | 2016-06-16
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993696120 — पशु शेड निर्माण कार्य लाखन /लक्ष्मण सिह | Completed | 90000 | 80264.95 | 2015-12-17 | 2016-06-16
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993696128 — पशु शेड निर्माण कार्य रामविलाश /उम्मेद सिह | Completed | 90000 | 79729.95 | 2015-12-17 | 2016-06-16
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993696138 — पशु शेड निर्माण कार्य सिरमिती /उम्मेद सिह | Completed | 90000 | 80264.95 | 2015-12-17 | 2016-06-16
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993726110 — पशुशेड निर्माण कार्य दिनेश /परषोतम | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993728213 — पशु शेड निर्माण कार्य जीतेंद्र /केदार | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993728218 — पशु शेड निर्माण कार्य नरेन्द्र /अम्रतलाल | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993728223 — पशु शेड निर्माण कार्य बकील सिह /टीकाराम | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993728235 — पशु शेड निर्माण कार्य प्रताप /बाबू | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701003067/IF/9993728238 — पशु शेड निर्माण कार्य निहाल सिह /पातीराम | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1701003067/IF/IAY/34791 — Construction of IAY House -IAY REG. NO. MP-01-003-067-001/17 | Approved | 27000 | 0 | 2015-09-07
MORENA / MORENA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1701003067/IF/IAY/34792 — Construction of IAY House -IAY REG. NO. MP-01-003-067-001/16 | Approved | 27000 | 0 | 2015-09-07
MORENA / MORENA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/4325962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123524056 | Completed | 18360 | 15912 | 2023-04-29 | 2024-02-17
MORENA / MORENA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/4335293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123529386 | Completed | 18360 | 15912 | 2023-05-13 | 2024-02-17
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/446350 — Construction of IAY House -IAY REG. NO. MP1522487 | Completed | 15030 | 14364 | 2017-02-16 | 2018-08-25
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/529435 — Construction of IAY House -IAY REG. NO. MP2782904 | Completed | 15030 | 14364 | 2017-02-16 | 2018-08-25
MORENA / MORENA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/530185 — Construction of IAY House -IAY REG. NO. MP2801404 | Completed | 15030 | 14886 | 2017-02-16 | 2018-10-18
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/705368 — Construction of IAY House -IAY REG. NO. MP1505545 | Completed | 15030 | 15136 | 2017-04-27 | 2018-10-18
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/757036 — Construction of IAY House -IAY REG. NO. MP2822894 | Completed | 15030 | 13744 | 2017-04-27 | 2018-10-26
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701003067/IF/IAY/757106 — Construction of IAY House -IAY REG. NO. MP2826206 | Completed | 15030 | 172 | 2017-04-27 | 2018-07-02
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/1250 — मेडवन्‍धान कार्य मेहताव पुञ रामप्रसाद | Completed | 0 | 13800 | 2010-08-04 | 2010-09-07
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/1340 — मेड वन्‍धान कार्य राजाराम पुञ नवल सिह | Completed | 0 | 8100 | 2010-08-04 | 2010-09-30
MORENA / MORENA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/1341 — मेड वन्‍धान कार्य सभाराम पुञ रामसिह | Completed | 0 | 15750 | 2010-09-23 | 2010-09-29
MORENA / MORENA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/1435 — खेलमेदान कार्य | Completed | 454000 | 423787.97 | 2012-06-06 | 2015-07-09
MORENA / MORENA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/22012034233703 — शांतिधाम निर्माण कार्य ग्राम बमूर बसई | Completed | 496000 | 487416.45 | 2015-11-16 | 2016-11-19
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/22012034315131 — ग्राम बमूर बसई सी.सी खरंजा के दोनो साईड पटटी भराई ग्राम से डाडे वाली माता | Completed | 102164 | 100104 | 2017-06-05 | 2017-10-12
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701003067/LD/22012034316750 — बाउण्‍डरीबाल निर्माण कार्य - हनुमान मंदिर बमूरबसई | Completed | 477000 | 317721.44 | 2017-08-21 | 2018-05-16
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947494 — Peripheral stone bund nirmaan karya panjab ke khet ke pass | Physically Completed | 830912.15 | 813665.82 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947495 — Peripheral stone bund nirmaan karya jodharam ke khet ke pass | Physically Completed | 838373.56 | 812935.8 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947496 — Peripheral stone bund nirmaan karya jardan ke pura ke pass | Physically Completed | 806898.47 | 794454.81 | 2025-04-11 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947497 — Peripheral stone bund nirmaan karya jagdish ke khet ke pass | Physically Completed | 845767.79 | 822071.81 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947498 — Peripheral stone bund nirmaan karya Shree ram ke khet ke pass | Physically Completed | 859358.88 | 842900.79 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947499 — Peripheral stone bund nirmaan karya Chatrapal ke khet ke pass | Physically Completed | 862808.88 | 843892.8 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947500 — Peripheral stone bund nirmaan karya jardan ke pura ke upar | Physically Completed | 849948.5 | 837992.81 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947501 — Peripheral stone bund nirmaan karya sherpur ki taraf | Physically Completed | 873199.16 | 846346.79 | 2025-04-25 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947502 — Peripheral stone bund nirmaan karya vinod ke khet ke pass | Ongoing | 875622.24 | 803908.78 | 2025-05-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034947503 — Peripheral stone bund nirmaan karya talab ke pass | Physically Completed | 871772.01 | 844258.79 | 2025-04-11 | 2026-05-19
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960526 — Peripheral stone bund nirmaan karya mayaram ke khet ki or | New | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960527 — Peripheral stone bund nirmaan karya mayaram ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960529 — Peripheral stone bund nirmaan karya nirpati ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960533 — Peripheral stone bund nirmaan karya ratiram ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960536 — Peripheral stone bund nirmaan karya Omprakash ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960538 — Peripheral stone bund nirmaan karya tehsildar ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960539 — Peripheral stone bund nirmaan karya vishwjeet ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960540 — Peripheral stone bund nirmaan karya hakim ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960542 — Peripheral stone bund nirmaan karya bahadur ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960543 — Peripheral stone bund nirmaan karya maharaj singh ke khet ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960544 — Peripheral stone bund nirmaan karya heera bhumiya ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960545 — Peripheral stone bund nirmaan karya pahad ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960546 — Peripheral stone bund nirmaan karya jardan ke pura ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960547 — Peripheral stone bund nirmaan karya sherpur ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960548 — Peripheral stone bund nirmaan karya bamurbasai ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/LD/22012034960549 — Peripheral stone bund nirmaan karya nare ki or | Approved | 0 | 0 | 2025-10-02
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003067/PG/22012034352345 — खेल मैदान निर्माण -बमूर बसई | Completed | 186500 | 170229.6 | 2017-08-22 | 2018-05-16
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701003067/PG/9425889104 — खैल मैदान कार्य - शेरपुर | Completed | 531000 | 518795.76 | 2016-11-05 | 2017-04-14
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/01 — राम बिलास के घर से आशाराम के मकान तक | Deleted | 0 | 0 | 2008-10-18
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003067/RC/02 — सीसी खरंजा जददे का पुरा बमूरबसई | Completed | 400000 | 288991.54 | 2008-08-12 | 2012-02-25
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003067/RC/1051 — पत्‍थर खरंजा न‍िर्माण कार्य | Completed | 373000 | 365278.25 | 2011-12-24 | 2013-01-22
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003067/RC/106 — सीसी खरंजा निमार्ग्‍ण मंदिर तक | Completed | 252000 | 40599.65 | 2009-02-28 | 2009-05-29
MORENA / MORENA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003067/RC/1075 — सी सी खरंजा निर्माण कार्य | Completed | 0 | 100601 | 2012-02-24 | 2012-03-15
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003067/RC/123 — पत्‍थर खंरजा निर्माण कार्य | Completed | 495000 | 131820 | 2009-01-01 | 2011-10-05
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003067/RC/129 — पत्‍थर खंरजा निर्माण कार्य सूवलाल का पुरा काजीबसई | Completed | 495000 | 0 | 2009-02-21 | 2008-07-01
MORENA / MORENA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034163092 — सी सी खरजा निमा्र्ण कार्य | Completed | 128000 | 125869.98 | 2012-12-03 | 2012-12-30
MORENA / MORENA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034209072 — पत्थर खरंजा निर्माण -स्कूल से पतिराम के पूरा एवंगो | Completed | 886000 | 479501.46 | 2014-02-28 | 2016-06-16
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034267619 — पत्थर खरंजा निर्माण कार्य पी .एम. रोड नारायण के मकान से सियाराम के मकान की और | Deleted | 0 | 0 | 2015-07-20
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034267657 — पत्थर खरंजा निर्माण कार्य प्रधानमन्त्री रोड़ नारायण के मकान से सियाराम के मकान की ओर | Completed | 231000 | 172925.98 | 2015-07-23 | 2016-06-16
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034283420 — पत्थर खरंजा निर्माण कार्य -बकीला के मकान से होते हुए बमूर बसई गांव की ओर | Completed | 693000 | 653999.62 | 2015-08-23 | 2016-06-16
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034284533 — पत्थर खरंजा निर्माण कार्य प्रधानमंत्री रोड भरत दास के मन्दिर से सैयत बाबा के थान तक बमूर बसई | Completed | 655000 | 413645.77 | 2015-09-14 | 2016-11-08
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034292862 — पत्थर खरंजा निर्माण कार्य प्रधानमंत्री रोड प्यारे के पुरा से हनुमान मंदिर की ओर | Completed | 353000 | 20988 | 2016-01-16 | 2017-09-10
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034295201 — सी.सी .खरंजा निर्माण कार्य पी .एम .रोड से प्यारे के पूरा की ओर | Completed | 105379 | 104964 | 2016-01-15 | 2016-06-16
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034298955 — सी .सी. खरंजा एवं नाली निर्माण कार्य बमूर बसई ग्राम से डाडे वाली माता की घटिया के ऊपर तक | Deleted | 0 | 0 | 2015-12-20
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034298956 — सी .सी .खरंजा एवं नाली निर्माण कार्य बमूर बसई ग्राम से डाडे वाली माँ की घटिया के ऊपर तक | Deleted | 272936 | 0 | 2015-12-27
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034305902 — सी सी खरंजा एवं नाली निर्माण कार्य - बमूरबसई गांव से डांडेबाली मां की घटिया के उपर तक ग्राम बमूरबसई | Deleted | 272937 | 0 | 2016-03-22
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034307888 — पत्थर खरंजा महावीर के कुआ से सुघरा के पूरा की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034307935 — पत्थर खरंजा निर्माण कार्य सी.सी. रोड से डंडे वाली माता की और | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034307940 — पत्थर खरंजा निर्माण कार्य जदे के पूरा स्कूल से सुमावली रोड तक | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034307944 — पत्थर खरंजा निर्माण कार्य भगत के मकान से प्यारे के पुरा की ओर | Deleted | 0 | 0 | 2016-01-26
MORENA / MORENA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034324860 — सीमेंट कंक्रीट खरजा एवं नाली निर्माण कार्य प्यारे के पूरा की पुलिया से पूरा तक | Completed | 90000 | 89846 | 2017-02-02 | 2018-04-04
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003067/RC/22012034336755 — सुदूर ग्राम सम्पर्क रोड निर्माण -जददे का पुरा से सुमावली रोड तक | Completed | 1114000 | 1100562.07 | 2017-05-02 | 2017-10-12
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034361103 — cc road -ramvaram ke ghar se pandit mohalla gajaraj ke makan se suresh ke ghar tak | Completed | 84450 | 72240 | 2017-09-25 | 2017-10-17
MORENA / MORENA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034361104 — CC ROAD - PM ROAD SE SEETARAM,PATEL,JODHA BAB EVAM JAGANNATH KE GHAR TAK | Completed | 73800 | 72240 | 2017-09-25 | 2017-10-16
MORENA / MORENA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034434944 — सी सी रोड एवं नाली निर्माण भूप सिंह के मकान से महताब के मकान तक शेरपुर | Completed | 92250 | 90306 | 2019-01-19 | 2019-07-22
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034447708 — सी.सी. खरंजा निर्माण कार्य - काल्ली के मकान से हैण्डपम्प तक, पी.एम. रोड से डोलू के मकान तक | Completed | 54300 | 53856 | 2019-05-29 | 2019-09-11
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034475334 — सी.सी. खरंजा एवं नाली निर्माण कार्य - केदार कंषाना के मौहल्ला एवं लोटन, चतुर सिंह ग्यासीराम | Closed | 57300 | 0 | 2019-04-14
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034475336 — सी.सी. खरंजा एवं नाली निर्माण कार्य - तोगर मौहल्ला | Closed | 38250 | 0 | 2019-04-14
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034475337 — सी.सी. खरंजा एवं नाली निर्माण कार्य - रामदीन के मौहल्ला एवं कोक सिंह के मकान तक | Closed | 59400 | 0 | 2019-04-14
MORENA / MORENA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034475381 — सी.सी. खरंजा एवं नाली निर्माण कार्य - पी.एम. रोड से रामेश्वर सरंपच के मकान तक। | Closed | 55800 | 0 | 2019-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034578922 — सी. सी. रोड निर्माण गोपाल के घर से महेंद्र के घर तक | Closed | 26850 | 0 | 2021-04-14
MORENA / MORENA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701003067/RC/22012034578926 — सी. सी. रोड निर्माण रामविलाश के घर से घटिया तक | Closed | 31500 | 0 | 2021-04-14
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003067/RC/245 — पत्‍थर खरंजा निमा्रण कार्य बमूर बसई | Completed | 54500 | 122047 | 2008-08-28 | 2011-10-05
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701003067/RC/305 — पत्‍थर खरजा निर्माण उम्‍मेद के गोत से आशाराम के घर की ओर | Completed | 0 | 175995 | 2009-07-20 | 2011-10-05
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003067/RC/390 — सी सी खरंजा निमार्ण वमूर बसई | Completed | 0 | 52150 | 2009-02-28 | 2012-02-25
MORENA / MORENA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003067/RC/446 — पत्‍थर खरजा निर्माण कार्य | Completed | 0 | 65779 | 2010-01-21 | 2010-04-20
MORENA / MORENA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701003067/RC/517 — पत्‍थर खरजा निर्माण कार्य | Completed | 0 | 162473 | 2010-04-20 | 2010-04-01
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701003067/SK/9993648054 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BAMURBASAI | Deleted | 1417000 | 0 | 2015-10-08
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034330340 — तालाव जीणोद्धार (पार)शेरपुर शांतीधाम के पास | Completed | 156000 | 153768 | 2017-06-28 | 2017-10-12
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034330590 — तालाब जीर्णोद्वार (पार) जददें का पुरा | Completed | 211000 | 1032 | 2017-06-28 | 2018-09-20
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701003067/WC/22012034330980 — तालाब जीर्णोद्वार(पार)शेरपुर मेढुकी तालाब | Completed | 176000 | 173048 | 2017-07-19 | 2017-10-10
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003067/WC/22012034380228 — TALAB GARIKAAN | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034380864 — MWC CHECK DAM | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034380865 — MWC EARTHEN DAM | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034380866 — MWC EARTHEN DAM 2 | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701003067/WC/22012034380867 — MWC FARM POND | Deleted | 0 | 0 | 2017-10-02
MORENA / MORENA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034386809 — MWC नवीन तालाब निर्माण कार्य - बमूर बसई | Suspended | 1372500 | 0 | 2018-03-02
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034388369 — MWC NAVEEN TALAB | Completed | 2077500 | 1848940 | 2018-04-24 | 2018-09-12
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/WC/22012034422887 — nws earthen bund | Completed | 421936 | 418851.77 | 2018-10-01 | 2018-12-10
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034431477 — nws earthen dam | Completed | 1497900 | 1492344.8 | 2019-01-12 | 2019-06-27
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034432229 — नवीन तालाब निर्माण कार्य - | Deleted | 0 | 0 | 2019-01-26
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034440085 — check dam | Completed | 1496009 | 1491704.81 | 2019-02-20 | 2019-06-27
MORENA / MORENA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034441061 — नवीन तालाब निर्माण कार्य - खेल मैदान के पास | Completed | 1473000 | 1465241.78 | 2019-02-27 | 2019-06-29
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034467324 — check dam | Completed | 1481811.51 | 1471375.72 | 2019-06-19 | 2020-05-05
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034467325 — earthen dam | Completed | 1484478.25 | 1472149.44 | 2019-06-19 | 2020-05-05
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034478072 — Nws earthen dam bamu. Nale ke pass | Completed | 1478153.12 | 1422554 | 2019-08-09 | 2020-06-16
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034478073 — Nws check dam bamu. Pahadi ke pass | Completed | 1484054.48 | 1483512 | 2019-08-09 | 2020-05-05
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034509296 — एन.डब्ल्यू.एस. अद्र्वनडेम बेहड में पहाड़ी के नीचे | Deleted | 0 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034511664 — n.w.s. ardhan dam bamoorbasaidurga ke khet ke pass | Deleted | 0 | 0 | 2019-10-02
MORENA / MORENA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034511667 — n.w.s. ardhan dam bamoorbasaidurga ke khet ke pass | Completed | 1431623.33 | 1405752 | 2020-02-14 | 2020-12-02
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034544131 — Nws Earthen dam jaddekapura bamu. | Completed | 1493053.6 | 1450020 | 2020-05-25 | 2021-01-27
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034544132 — Nws check dam jagnaath ke khet ke pas bamu. | Completed | 1494228.5 | 1448974 | 2020-05-27 | 2021-01-27
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034544133 — Nws check dam sher pur bamu. | Completed | 1498932.65 | 1464426 | 2020-06-29 | 2021-01-27
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034573182 — Nws check dam pratap ke khet ke pass bamur | Completed | 1476568.45 | 1442460 | 2020-08-18 | 2021-01-13
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034573183 — Nws Earthen dam prakash ke khet ke pass bamur | Completed | 1452426.24 | 1444667 | 2020-08-18 | 2024-01-05
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034576124 — Nws check dam sherpur bamurbasai | Completed | 1462383.78 | 1443198 | 2021-01-06 | 2021-04-24
MORENA / MORENA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034599162 — nws check dam nare main bamurabasai | Completed | 1478059.55 | 1457923 | 2021-02-12 | 2022-09-24
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034659945 — nws check dam mansha raam ke khet ke pas bamorbsai | Completed | 1499211.91 | 1393526 | 2021-06-09 | 2022-12-28
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034659963 — nws check dam nirman jagdish ke khet ke pass sherpur | Completed | 1494189.18 | 1278364 | 2021-04-25 | 2022-01-10
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034659978 — nws talab nirman khai nare ke ke pass sherpur | Ongoing | 1496793.39 | 1429931.98 | 2025-06-30
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034659989 — nws talab nirman dadhiram ke lhet ke pass sherpur | Completed | 1496749.23 | 1462075 | 2021-05-19 | 2022-11-24
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034699084 — nws check dam nare me sherpur | Completed | 1497178.79 | 1462470 | 2021-05-19 | 2021-11-03
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034860721 — ctr/nws talav nirman karya rakheko | Deleted | 0 | 0 | 2021-10-28
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034944177 — Amrat sarovar talab nirman kary serpur raod ke pass | Closed | 1972501.1 | 0 | 2022-04-09
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034956393 — nws talan nirman kary tehsildar kde khet ke pass | Deleted | 0 | 0 | 2022-04-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034956399 — nws khet talab dinesh ke khet ke pass | Deleted | 0 | 0 | 2022-04-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034956402 — nws khet talab nirman karya dinesh ke khet ke pass | Completed | 475963.81 | 434446.85 | 2022-05-06 | 2024-01-05
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034963146 — nws talab nirman kary tehsildar ke khet ke pass | Closed | 1489561 | 0 | 2022-04-28
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034977107 — nws earthan bund rinku ke khet ke pass | Completed | 704823.39 | 705164 | 2022-05-24 | 2022-09-24
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034977111 — nws earthan bund bedia ke khet ke pass | Completed | 872201.2 | 860780 | 2022-05-24 | 2022-09-24
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012034977112 — nws earthan bund bedia ke khet ke pass | Deleted | 0 | 0 | 2022-05-18
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006021 — nws talav nirman kary mandir ke pass | Completed | 1485323.83 | 1417572 | 2023-10-09 | 2024-10-09
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006024 — talav nirman kary nyi tor | Deleted | 0 | 0 | 2022-08-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701003067/WC/22012035006025 — nws talav nirman kary nayi tor | Completed | 1495825.39 | 1430883.88 | 2022-11-04 | 2024-01-05
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006028 — nws talav nirman kary longthiyai ke pass | Completed | 1452531.37 | 1371698.52 | 2022-11-04 | 2024-01-12
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006037 — nws talav nirman kary bhumiya waale nare me | Physically Completed | 1482945.68 | 1419274.7 | 2023-10-09 | 2026-08-21
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006039 — nws talav nirman kary chhokar ke pass | Completed | 1490985.43 | 1410320.6 | 2022-11-04 | 2024-02-17
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035006687 — nws talav nirman kary nayi tor | Deleted | 0 | 0 | 2022-10-07
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035007578 — amrat sarovar talav nirman kary chauk waale daade par | Physically Completed | 1992921.74 | 1917751.64 | 2025-07-16 | 2026-08-21
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012035034050 — new talav nirmad kary khirkai ke pas | Deleted | 0 | 0 | 2022-11-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012035034052 — new talav nirmad kary khirkai ke pas | Deleted | 0 | 0 | 2022-11-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012035034054 — new talav nirmad kary khirkai ke pas | Deleted | 0 | 0 | 2022-11-20
MORENA / MORENA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012035034060 — New talav nirmad kary gujja ke vjara me | Deleted | 0 | 0 | 2022-12-20
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035065025 — NWS talab nirman kary atar singh ke khet ke pass | Completed | 1477791.6 | 1425443.88 | 2023-08-30 | 2024-10-23
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035065028 — NWS talab nirman kary peepal waale nare me | Completed | 1480820.24 | 1422534 | 2023-07-19 | 2024-10-09
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035065033 — anicut nirman kary atar singh ke khet ke pass naale par | Completed | 1478539.69 | 1371906 | 2023-07-20 | 2024-02-17
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035065034 — anicut nirman kary prakash ki nayi tor me | Completed | 1487833.98 | 1457639 | 2023-07-20 | 2024-01-05
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035152781 — nws anicut nirman kary ghanshyam baghel ke khet ke pass | Completed | 1460959.98 | 1434954 | 2024-02-12 | 2024-10-09
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035152782 — nws anicut nirman kary gajendra singh gurjar ke khet ke pass | Completed | 1467427.63 | 1440959 | 2024-02-12 | 2024-10-09
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012035170546 — Chekdem nirman karya jaswant gurjar ke khet ke pass | Deleted | 0 | 0 | 2023-08-15
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701003067/WC/22012035170548 — Chekdem nirman karya Otar ke khet ke pass | Deleted | 0 | 0 | 2023-08-15
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035186283 — नवीन रपटा निर्माण कार्य शांतिधाम के पास | Completed | 1313251.9 | 1291743.75 | 2024-03-15 | 2024-11-03
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035186285 — नवीन रपटा निर्माण कार्य विद्याराम सिंह का पुरा | Completed | 1415569.87 | 1398317.64 | 2024-05-01 | 2025-07-15
MORENA / MORENA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701003067/WC/22012035186289 — नवीन रपटा निर्माण कार्य मायाराम सिंह के खेत के पास | Completed | 1324663.63 | 1301373.01 | 2024-05-01 | 2024-11-03
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701003067/WC/22012035186370 — लूज बोल्डर निर्माण कार्य गाजीताल के खेत के पास | Ongoing | 807089.77 | 701152 | 2024-03-14
MORENA / MORENA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1701003067/WC/22012035186376 — लूज बोल्डर निर्माण कार्य औतार के खेत के पास | Ongoing | 796880.3 | 740408 | 2024-03-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003067/WC/22012035302066 — Dugwell Richarge Pit Nirmaan Karya Gadipal ke kua ke pass | Deleted | 0 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003067/WC/22012035302067 — Dugwell Richarge Pit Nirmaan Karya Malkhan ke kua ke pass | Deleted | 0 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003067/WC/22012035302068 — Dugwell Richarge Pit Nirmaan Karya Saligram ke kua ke pass | Deleted | 0 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003067/WC/22012035302070 — Dugwell Richarge Pit Nirmaan Karya Jai Singh ke kua ke pass | Deleted | 0 | 0 | 2025-04-14
MORENA / MORENA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701003067/WC/22012035302071 — Dugwell Richarge Pit Nirmaan Karya Banti ke kua ke pass | Deleted | 0 | 0 | 2025-04-14
MORENA / MORENA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701003067/wC/68 — सोक्‍ता गडडा सूवालाल कापुरा | Completed | 495000 | 0 | 2008-11-20 | 2008-07-01
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003067/WH/22012034451803 — तालाब जीर्णोद्धार कार्य जद्देका पुरा बमूरबसई | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003067/WH/22012034451805 — तालाब जीर्णोद्धार कार्य मेडुकी | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701003067/WH/22012034451809 — तालाब जीर्णोद्धार कार्य शेरपुर गोपाल ताल | Deleted | 0 | 0 | 2021-10-02
MORENA / MORENA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701003068/RC/22012034267662 — पत्थर खरंजा निर्माण कार्य प्रधानमंत्री रोड से सिरनाम के पुरा से रामदीन के घर तक | Deleted | 0 | 0 | 2015-07-05