## Work List
Exported on: 2026-10-13 18:39:56
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KHITORA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701004019/RC/22012034185124 — C.C. Road nali Laxminarayan Sharma ke makan se B | Deleted | 60667 | 0 | 2012-10-02
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/18 — व़क्षारोपण क्‍वारीपुल से मिडिल स्‍कूल तक | Deleted | 468000 | 0 | 2008-08-05
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/19 — व़क्षारोपण मिडिल स्‍कूल से महावन रोड तक | Deleted | 468000 | 0 | 2008-08-12
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/20 — व़क्षारोपण महावन रोड से बलधारी के पुरा तक | Deleted | 468000 | 0 | 2008-08-19
MORENA / PAHADGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701004021/DP/22012034236839 — shanti dham nirman kary | Completed | 245000 | 176657.34 | 2016-12-24 | 2018-07-31
MORENA / PAHADGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701004021/DP/22012034238669 — SHANTI DHAM NIRMAN KARY MAHABAN GRAM PANCHAYAT KHITORA | Deleted | 18000000000 | 0 | 2017-03-10
MORENA / PAHADGARH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/22012034244925 — bracharopad pul se gam ki or | Deleted | 0 | 0 | 2017-04-27
MORENA / PAHADGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701004021/DP/22012034246550 — SHANTI DHAM MAHABAN KHITORA | Completed | 180000 | 162835.36 | 2017-08-12 | 2018-07-31
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701004021/DP/22012034542054 — माँ की बगिया m/s स्कूल khitora | Deleted | 12186.92 | 0 | 2021-04-14
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701004021/DP/22012034543208 — माँ की बगिया धर्मसिंह का पुरा | Completed | 12186.92 | 12516 | 2022-03-10 | 2023-07-05
MORENA / PAHADGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701004021/DP/22012034544753 — पत्थर नाला निर्माण कार्य कमलसिंह के मकान से नदी की ओर महावन | Deleted | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1701004021/DP/22012034552973 — NAVEEN TALAB NIRMAN KARY MAHABAN K BEHAD ME | Deleted | 0 | 0 | 2022-04-01
MORENA / PAHADGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701004021/DP/22012034571314 — patthar nala nirman kary lal singh ke ghar se khar nala ki or, MADHO SINGH KA PURA | Completed | 965919.63 | 769618.6 | 2023-10-06 | 2025-12-31
MORENA / PAHADGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701004021/DP/22012034571315 — patthar nala nirman kary ramswarup pandit ke ghar se nadi ki or, khitora | Completed | 963919.63 | 883949.02 | 2022-11-22 | 2024-12-28
MORENA / PAHADGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701004021/DP/22012034571316 — patthar nala nirman kary siddhar ghat se pandit ke makaan ki or khitora | Closed | 966919.63 | 0 | 2022-08-16
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1701004021/DP/22012034604164 — मेरी माटी मेरा देश वृक्षारोपण कार्य ग्राम पंचायत खिटौरा | Closed | 0 | 0 | 2023-06-05
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1701004021/DP/22012034614073 — CTR-पत्थर नाला निर्माण कार्य दशरथ के मकान से नदी की ओर कल्लू के मकान से नदी की ओर निर्माण खितोरा | Closed | 0 | 0 | 2024-01-25
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Lining of water courses Canal for Community / Lining of water courses Canal for Community | Lining of Canal | 1701004021/DP/22012034615593 — पत्थर नाला निर्माण कार्य दशरथ के मकान से नदी की और कल्लू के मकान से नदी की और कार्य खिटोरा | Ongoing | 1499619.04 | 1337632.5 | 2024-03-16
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701004021/DP/22012034620737 — Vruksharopan Kary Kansh Baba ke mandir ke pass mahavan khitora | New | 0 | 0 | 2024-06-08
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1701004021/DP/22012034620797 — Vruksharopan Kary Kansh Baba ke mandir ke pass mahavan khitora | Approved | 0 | 0 | 2024-06-08
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1701004021/DP/22012034624805 — विराचारोपण कार्य कांश बाबा के मंदिर के पास महावन खिटोरा | Approved | 0 | 0 | 2024-06-08
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1701004021/DP/22012034624807 — viracharopan kary kansh baba ke mandir lke pass mahaban khitora | Ongoing | 306992.38 | 5832 | 2024-07-31
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/33 — वृक्षारोपण महावन रोड से बलधारी पुरा तक | Completed | 0 | 1785 | 2008-08-19 | 2008-01-01
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/34 — वृक्षारोपण क्‍वारी पुल से मिडिल स्‍कूल तक | Completed | 458676 | 5910 | 2008-08-05 | 2008-01-01
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/35 — वृक्षारोपण मिडिल स्‍कूल से महावन रोड तक | Completed | 0 | 3230 | 2008-09-02 | 2008-04-01
MORENA / PAHADGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/DP/86 — नन्‍दन फलोद्यानकार्य बारेलाल पुञ तेजसिंह खिटोरा | Completed | 220500 | 22142 | 2011-11-12 | 2014-07-08
MORENA / PAHADGARH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/DP/9926695609 — शांतीधाम निर्माण कार्य महावन | Deleted | 0 | 0 | 2013-01-26
MORENA / PAHADGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701004021/FP/22012034202721 — NALA NIRMAN Ramesh Pandit ke makan se nadi ki oar. | Completed | 1412600 | 480236.83 | 2015-08-22 | 2020-05-06
MORENA / PAHADGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701004021/FP/22012034202722 — NALA NIRMAN Kallu Khateek ke makan se nadi ki oar. | Completed | 1291000 | 504554.1 | 2015-08-22 | 2017-08-30
MORENA / PAHADGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Diversion weir / Construction of Masonry/CC Check Dam for Community | Works for Flood Control and Protection | 1701004021/FP/22012034203451 — nala nirman kary baranj mandir se puliya ki or | Completed | 1491000 | 316574.5 | 2016-01-16 | 2017-08-30
MORENA / PAHADGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701004021/FP/22012034362398 — नाला निर्माण कार्य खिटोरा | Closed | 0 | 0 | 2018-10-02
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701004021/FP/22012034366080 — kachcha nala nirman kary baldhari pura se mandir ki or | Completed | 1051109 | 754851 | 2020-09-23 | 2021-07-16
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701004021/FP/22012034366081 — patthar nala nirman kary ramdash ke makan se mandir ki or | Deleted | 0 | 0 | 2020-04-14
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701004021/FP/22012034367398 — Patthar nala nirman kary ramdas ke makan se mandir ki or | Completed | 1430745.99 | 1307962.09 | 2020-10-10 | 2023-07-12
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701004021/FP/22012034369473 — Patthar nala nirman kary jaysingh ke makan se khar ki or | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701004021/FP/22012034369675 — nala nirman kary rambhajan ke makan se siddhar ke makan se shantidham tak | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701004021/FP/22012034369676 — nala nirman kary ekbal khan ke makan se purane nale tak v bheem sen ke makan se nadi ki or | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1701004021/FP/22012034369680 — kachcha nala nirman kary dharmsingh ke pura se mahavan ki or | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701004021/FP/22012034626986 — patthar nala nirman kary mahavan upar pura par | Completed | 1003770.16 | 912311.39 | 2021-12-04 | 2024-12-28
MORENA / PAHADGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701004021/FP/22012034627455 — CTS NAVEEN PATTHAR NALLAH NIRMAN KARY PATEL KE GHAR SE NADI KI OR MAHAVAN | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701004021/FP/22012034627850 — पत्थर नाला निर्माण कार्य कमलसिंह के मकान से नदी की ओर महावन | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701004021/FP/22012034628994 — Patthar nala nirman kary kamal singh ke makan se nadi ki or | Completed | 960919.63 | 894649.47 | 2022-05-23 | 2023-07-05
MORENA / PAHADGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701004021/FP/22012034631304 — पत्थर नाला निर्माण कार्य खेमा के मकान से खार तक | Completed | 1476766.12 | 1337402.73 | 2023-07-25 | 2024-12-28
MORENA / PAHADGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/1936 — मेढ वन्‍धान कार्य वाहिद पुञ नत्‍थू | Completed | 0 | 36478 | 2011-10-05 | 2011-10-18
MORENA / PAHADGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/1937 — मेढ वन्‍धान कार्य केदार पुञ माधो | Completed | 0 | 26962 | 2011-10-05 | 2011-10-18
MORENA / PAHADGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/1938 — मेढ वन्‍धान कार्य परसूराम पुञ गोकुल | Completed | 0 | 30744 | 2011-10-25 | 2011-11-07
MORENA / PAHADGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/1996 — मैडवन्‍धान कार्य धर्मसिंह पुञ हरिकि‍शुन | Completed | 0 | 21838 | 2011-10-25 | 2011-11-07
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2141 — मैडवन्‍धान कार्य मेहरवान पुत्र मुन्‍शी | Completed | 0 | 38808 | 2012-04-18 | 2012-05-01
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2142 — मैडवन्‍धान कार्य मातादीन पुत्र नेहने | Completed | 0 | 38808 | 2012-04-18 | 2012-05-01
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2179 — मैडवन्‍धान निर्माण कार्य महेन्‍द्र पुत्र मुंशी | Completed | 0 | 33924 | 2012-05-01 | 2012-05-14
MORENA / PAHADGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701004021/IF/22012034370893 — वृक्षारोपण कार्य शांति धाम खिटोरा | Completed | 335000 | 11277.08 | 2017-07-19 | 2022-02-15
MORENA / PAHADGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701004021/IF/22012034390829 — veracharopan | Completed | 335000 | 10446.8 | 2017-07-19 | 2022-02-15
MORENA / PAHADGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701004021/IF/22012034390830 — veracharopan | Completed | 335000 | 10446.8 | 2017-07-19 | 2022-02-15
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701004021/IF/22012035248410 — विराचारोपण कार्य कांश बाबा के मंदिर के पास महावन खिटोरा | New | 0 | 0 | 2024-06-08
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035393304 — khet talab nirman kary nirpal | Completed | 147166.45 | 107532 | 2025-04-30 | 2025-06-26
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035393325 — khet talab nirman kary gajraj | Completed | 146913.82 | 104400 | 2025-04-30 | 2025-12-14
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035393337 — khet talab nirman kary vinod | Completed | 146408.58 | 110664 | 2025-04-30 | 2025-06-26
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035393355 — khet talab nirman kary sahabsingh | Physically Completed | 147419.07 | 107532 | 2025-04-30 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421181 — khet talab nirman kary suresh | Approved | 0 | 0 | 2025-04-16
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421212 — khet talab nirman kary jandel | Physically Completed | 147621.16 | 62901 | 2025-05-15 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421248 — khet talab nirman kary ranveer | Completed | 147621.16 | 56376 | 2025-05-15 | 2026-02-11
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421270 — khet talab nirman kary satish | Completed | 147621.16 | 102051 | 2025-05-15 | 2025-12-16
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421301 — khet talab nirman kary prakash | Physically Completed | 144134.97 | 58203 | 2025-05-08 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421340 — khet talab nirman kary netram | Completed | 146913.82 | 50373 | 2025-05-08 | 2025-12-14
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421358 — khet talab nirman kary balveer | Completed | 146661.2 | 111447 | 2025-05-08 | 2025-06-26
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421375 — khet talab nirman kary mohit | Completed | 146408.58 | 106749 | 2025-05-08 | 2025-06-26
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421397 — khet talab nirman kary malkhan | Completed | 146155.96 | 69165 | 2025-05-08 | 2025-06-26
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421423 — khet talab nirman kary basdeb | Completed | 145903.33 | 78561 | 2025-05-08 | 2025-06-26
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421449 — khet talab nirman kary nathu singh | Completed | 145650.71 | 75429 | 2025-05-08 | 2025-12-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421482 — khet talab nirman kary pansingh | Completed | 145398.09 | 31581 | 2025-05-08 | 2025-12-15
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421524 — khet talab nirman kary mahesh | Completed | 145145.46 | 87957 | 2025-05-08 | 2025-12-16
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421553 — khet talab nirman kary lakhan | Completed | 144892.84 | 91089 | 2025-05-08 | 2025-12-15
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421569 — khet talab nirman kary sonu | Physically Completed | 144640.22 | 69165 | 2025-05-08 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035421597 — khet talab nirman kary gajraj | Physically Completed | 144387.59 | 94221 | 2025-05-08 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035495326 — Khet talab nirman kary ranveer | Completed | 147621.16 | 50373 | 2025-05-15 | 2025-12-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035495339 — Khet talab nirman kary prakash | Completed | 147621.16 | 76995 | 2025-05-15 | 2026-02-11
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035495350 — Khet talab nirman kary vasdev | Completed | 147621.16 | 76995 | 2025-05-15 | 2026-02-11
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/22012035495361 — Khet talab nirman kary vasdev | Completed | 147621.16 | 76995 | 2025-05-15 | 2026-02-11
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701004021/IF/22012035498177 — Dugwell recharge nirman vinod | Physically Completed | 25899.46 | 9343.8 | 2025-05-15 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701004021/IF/22012035498207 — Dugwell recharge nirman lakhan | Physically Completed | 25899.46 | 10857.6 | 2025-05-15 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701004021/IF/22012035498221 — Dugwell recharge nirman rambaran | Physically Completed | 25899.46 | 13885.2 | 2025-05-15 | 2026-02-25
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701004021/IF/22012035498230 — Dugwell recharge nirman Rajendra | Completed | 25899.46 | 15399 | 2025-05-15 | 2025-07-06
MORENA / PAHADGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701004021/IF/22012035498244 — Dugwell recharge nirman hakim | Completed | 25899.46 | 15399 | 2025-05-15 | 2025-07-06
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2233 — मैडवन्‍धान निर्माण कार्य भवर पुत्र नरेन्‍द्र | Completed | 0 | 32076 | 2012-05-15 | 2012-05-28
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2242 — मैडवन्‍धान निर्माण कार्य रामस्‍वरूप पुत्र किशनलाल | Completed | 0 | 38808 | 2012-05-15 | 2012-05-28
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2243 — मैडवन्‍धान निर्माण कार्य देवीराम पुत्र चिम्‍मन | Completed | 0 | 40920 | 2012-05-01 | 2012-05-14
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2331 — मैडवन्‍धान निर्माण कार्य मुन्‍शी पुत्र दुर्गसिंह | Completed | 0 | 31680 | 2012-06-29 | 2012-07-12
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2332 — मैडवन्‍धान निर्माण कार्य बाबू पुत्र रतना | Completed | 0 | 31680 | 2012-06-14 | 2012-06-27
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2340 — मैडवन्‍धान निर्माण कार्य रामजीलाल पुत्र गोधना | Completed | 0 | 31680 | 2012-06-29 | 2012-07-12
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2445 — मैडवन्‍धान निर्माण कार्य प्रकाश पुत्र चौखरिया | Completed | 31086 | 29304 | 2012-07-13 | 2012-07-30
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2446 — मैडवन्‍धान निर्माण कार्य सुन्‍दरवाई बेबा/गोधना | Completed | 36700 | 34848 | 2012-07-13 | 2012-07-26
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2447 — मैडवन्‍धान निर्माण कार्य गोटेराम पुत्र चौखरिया | Completed | 31086 | 29304 | 2012-07-20 | 2012-08-02
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2448 — मैडवन्‍धान निर्माण कार्य भीमसेन पुत्र करनसिंह | Completed | 36700 | 34848 | 2012-07-27 | 2012-08-09
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2449 — मैडवन्‍धान निर्माण कार्य बनवारी पुत्र फोसू | Completed | 36700 | 34848 | 2012-08-03 | 2012-08-14
MORENA / PAHADGARH | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/IF/2450 — मैडवन्‍धान निर्माण कार्य राजेश पुत्र चोखरिया | Completed | 31086 | 29304 | 2012-07-27 | 2012-08-09
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701004021/IF/9926721712 — पशु शेड निर्माण कार्य पूरन / भजनलाल | Completed | 80000 | 74576 | 2014-04-05 | 2015-07-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701004021/IF/9926721715 — पशु शेड निर्माण कार्य बन्‍टी/ बनवारी | Completed | 80000 | 74538 | 2014-04-12 | 2015-06-14
MORENA / PAHADGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1701004021/IF/9926721717 — पशु शेड निर्माण कार्य सत्‍यराम / केदार | Deleted | 80000 | 0 | 2013-04-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926731827 — पशु शेड निर्माण हबीब खाॅ / काले खॉ | Completed | 80000 | 74039.47 | 2014-07-05 | 2015-07-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926731828 — पशु शेड निर्माण मसूर / काले खॉ | Completed | 80000 | 48168.71 | 2014-07-05 | 2016-08-11
MORENA / PAHADGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745605 — पशु शेड निर्माण कार्य महेन्‍द्र / मुन्‍शी सिह | Deleted | 53000 | 0 | 2013-04-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745606 — पशु शेड निर्माण कार्य रधुवीर / श्री गोधना | Completed | 53000 | 51175.75 | 2014-07-19 | 2015-06-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745607 — पशु शेड निर्माण कार्य मातादीन / गोविन्‍द्र | Completed | 80000 | 74826.25 | 2014-07-19 | 2015-07-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745608 — पशु शेड निर्माण कार्य शिवकुमार / जाहर सिह | Completed | 80000 | 74293 | 2014-08-02 | 2015-06-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745697 — पशूु शेड निर्माण कार्य भीमसेन / श्री करन सिह | Completed | 80000 | 69223.7 | 2014-07-19 | 2015-06-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745698 — पशूु शेड निर्माण कार्य महेश / श्री किसुन सिह | Completed | 80000 | 76767 | 2014-07-19 | 2015-06-14
MORENA / PAHADGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9926745702 — पशूु शेड निर्माण कार्य रामस्‍वरूप / होतम सिह | Completed | 80000 | 76776 | 2014-07-19 | 2015-07-14
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681903 — pashu shed nirman kary sikandar / ikbal | Completed | 80000 | 66837.82 | 2015-10-17 | 2016-08-11
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681906 — pashu shed nirman kary jahagir / rajjan | Completed | 80000 | 64997.32 | 2015-10-24 | 2016-08-11
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681907 — pashu shed nirman kary shakura / babu khan | Completed | 80000 | 69142.5 | 2015-10-24 | 2016-08-11
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681908 — pashu shed nirman kary gote / chokhariya | Completed | 80000 | 71607.82 | 2015-10-24 | 2016-08-11
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681910 — pashu shed nirman kary jayprakash/ rambeer | Completed | 80000 | 72665.25 | 2015-10-17 | 2016-08-11
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681913 — pashu shed nirman kary ramswarup/ bhajanlal | Completed | 80000 | 69303.3 | 2015-10-17 | 2016-08-11
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701004021/IF/9993681914 — pashu shed nirman kary bhookan / ramswarup | Completed | 80000 | 71210.4 | 2015-10-17 | 2016-08-11
MORENA / PAHADGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701004021/IF/IAY/1883746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5313160 | Completed | 15660 | 15973.2 | 2018-07-24 | 2018-12-06
MORENA / PAHADGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701004021/IF/IAY/1903891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4693802 | Completed | 15660 | 15660 | 2018-07-24 | 2019-01-05
MORENA / PAHADGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701004021/IF/IAY/210624 — Construction of IAY House -IAY REG. NO. MP1075315 | Completed | 15030 | 12270 | 2017-02-17 | 2018-11-22
MORENA / PAHADGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701004021/IF/IAY/2313171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3202834 | Completed | 17100 | 17560 | 2020-02-04 | 2021-12-30
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701004021/IF/IAY/36953 — Construction of IAY House -IAY REG. NO. MP-01-004-021-002/61TH | Approved | 23490 | 0 | 2015-11-09
MORENA / PAHADGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701004021/IF/IAY/36984 — Construction of IAY House -IAY REG. NO. MP-01-004-021-002/02 | Approved | 23490 | 0 | 2015-11-09
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957575 — peripheral stone band nirman kary shantidham ke pass | Ongoing | 1393507.89 | 1102273.68 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957576 — peripheral stone band nirman kary pra school ke pass | Ongoing | 1481749.29 | 1159234.7 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957577 — peripheral stone band nirman kary vinod ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957578 — peripheral stone band nirman kary mandir ke pass | Ongoing | 1363196.6 | 1168775.68 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957581 — peripheral stone band nirman kary harisingh ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957583 — peripheral stone band nirman kary mahavan | Ongoing | 1337236.89 | 1054245.7 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957585 — peripheral stone band nirman kary shahabsingh ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957586 — peripheral stone band nirman kary karas baba mandir | Ongoing | 1324159.54 | 1058420.69 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957587 — peripheral stone band nirman kary dharmsingh ka pura | Ongoing | 1336292.78 | 1007264.69 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957588 — peripheral stone band nirman kary school madhosingh ka pura | Ongoing | 1355918.82 | 1134637.68 | 2026-01-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957589 — peripheral stone band nirman kary shivsingh ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957590 — peripheral stone band nirman kary gajraj ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957591 — peripheral stone band nirman kary satish ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/LD/22012034957592 — peripheral stone band nirman kary satendra ke khet ke pass | Approved | 0 | 0 | 2025-04-15
MORENA / PAHADGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/LD/3044 — मैडवन्‍धान कार्य महेश पुञ व्रन्‍दावन | Completed | 0 | 21000 | 2010-09-28 | 2010-10-12
MORENA / PAHADGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/LD/3045 — मैडवन्‍धान कार्य सत्‍यराम पुञ केदार | Completed | 0 | 21200 | 2010-09-29 | 2010-10-19
MORENA / PAHADGARH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/LD/3799387114 — Habib Kha s/o Kale Kha | Deleted | 0 | 0 | 2013-01-26
MORENA / PAHADGARH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/LD/94 — भू समतलीकरण एवं मेढ बंधान कार्य | Completed | 0 | 111111 | 2009-06-26 | 2009-10-14
MORENA / PAHADGARH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/LD/95 — भूमि समतलीकरण एवं मेढ बंधान निर्माण कार्य | Completed | 0 | 106015 | 2009-08-07 | 2009-10-14
MORENA / PAHADGARH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701004021/LD/96 — भूमि समतलीकरण एवं मेढ बंधान कार्य बारेलाल तेजसिंह | Completed | 0 | 35217 | 2009-08-01 | 2009-08-30
MORENA / PAHADGARH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701004021/RC/172 — सी सी खरंजा निर्माण कार्य | Completed | 0 | 14785 | 2009-04-01 | 2009-04-13
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701004021/RC/22012034160983 — C.C. Kharanja | Deleted | 0 | 0 | 2013-01-26
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034160989 — Pathar Kharanja | Deleted | 0 | 0 | 2013-01-26
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034160990 — Pathar Kharanja | Deleted | 0 | 0 | 2013-01-26
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034160991 — Mitti/Graval Road | Deleted | 0 | 0 | 2013-01-26
MORENA / PAHADGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034184424 — Patthar Kharaja PMGSY Road se Rahim Khan ke makan | Completed | 190000 | 164960.79 | 2013-09-28 | 2014-09-05
MORENA / PAHADGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701004021/RC/22012034185135 — C.C. Road nali Laxminarayan Sharma ke makan se B | Completed | 60667 | 48164 | 2013-09-28 | 2013-12-02
MORENA / PAHADGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034191126 — पत्‍थर खरंजा निर्माण देवीराम के मकान से भगवान सिंह | Completed | 170000 | 139912.84 | 2014-03-02 | 2015-06-17
MORENA / PAHADGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034191127 — पत्‍थर खरंजा निर्माण पीएमजीएसवाय रोड से वावू मेहन् | Completed | 94000 | 87060.15 | 2014-02-17 | 2014-09-05
MORENA / PAHADGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034191129 — पत्‍थर खरंजा निर्माण धर्मसिंह के मकान से रामचरन प | Completed | 170000 | 161725.44 | 2014-03-02 | 2015-07-17
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034197405 — patter Kharanja Nirmad karya pMGSY Road se rahim K | Deleted | 190000 | 0 | 2013-01-26
MORENA / PAHADGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034210491 — Sudur Gram Sampark PMGSY road se Mahavan road tak | Completed | 805957 | 308238 | 2014-03-02 | 2016-08-23
MORENA / PAHADGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034283363 — PATTHAR KHARANJA Gyan Singh ke makan se nadi ki oar Aanganbadi se nadi ki oar. | Completed | 1465000 | 400328.1 | 2015-08-22 | 2016-09-11
MORENA / PAHADGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034296462 — patthar kharanja nirman matadin ke makan se road tak ramdas ke mkan se school tak jagdish ke makan s | Completed | 1303000 | 135000.07 | 2016-01-16 | 2016-09-11
MORENA / PAHADGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034300331 — patthar kharnja nirmad karya hameer to banvari baretha tak | Completed | 1054000 | 5724 | 2016-03-19 | 2016-08-23
MORENA / PAHADGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034301734 — patthar kharanja nirmad karya mahavan ka pura,madhosingh ka pura,dharmsingh ka pura | Completed | 1178000 | 9540 | 2016-03-19 | 2016-08-23
MORENA / PAHADGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034328537 — Sudoor gram sampark road | Closed | 0 | 0 | 2017-01-26
MORENA / PAHADGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034330508 — SUDUR GRAM SAMPARK SADAK NIRMAN KARY MAHAWAN SE KHARIKA KI OR | Completed | 1200000 | 539642.8 | 2017-03-17 | 2020-02-09
MORENA / PAHADGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701004021/RC/22012034331331 — C C KHARANJA NIRMAN KARY KANYA SHALA SE GOTE HARIJAN KE MAKAN TAK | Completed | 11062500000 | 95116 | 2017-03-17 | 2018-07-30
MORENA / PAHADGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701004021/RC/22012034348806 — सी सी खरंजा एवं नाली निर्माण कार्य छत्रपाल बघेल के मकान से रामचरन पटेल के मकान की ओर महावन | Completed | 7500000000 | 74304 | 2017-08-12 | 2017-10-30
MORENA / PAHADGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701004021/RC/22012034360805 — सी सी खरंजा निर्माण कार्य माधो सिंह का पुरा | Deleted | 6630000000 | 0 | 2017-08-15
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034526251 — sudar road nirman kary pmgsy road se rambhajan ke khet tak | Deleted | 0 | 0 | 2020-04-14
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034539024 — Sudar road nirman kary pmgsy road se rambhajan ke khet tak | Completed | 3442575.16 | 3040872.51 | 2020-09-23 | 2023-07-05
MORENA / PAHADGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034539805 — sudar road nirman kary dharmsingh ka pura se narua ki or | Completed | 3463902.45 | 1914555.94 | 2020-12-21 | 2023-07-05
MORENA / PAHADGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701004021/RC/22012034647336 — सुदूर ग्राम सम्पर्क मिट्टी ग्रेवल रोड माधोसिंह के पुरा से बमनपुरा की ओर | Completed | 2490465.68 | 1726402 | 2023-10-05 | 2025-12-24
MORENA / PAHADGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701004021/RC/2815 — पत्‍थर खरन्‍जा निर्माण कार्य खिटोरा | Completed | 0 | 202090 | 2010-06-01 | 2010-08-16
MORENA / PAHADGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701004021/RC/2884 — पत्‍थर खरंजा निमार्ण कार्य प्रधान मञी सी.सी. खरंजा से रामभजन के मकान तक . | Completed | 0 | 114212 | 2011-09-20 | 2011-10-03
MORENA / PAHADGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/2895 — पत्‍थर खरन्‍जा निर्माण कार्य सरदार के घर से भीकम के घर तक | Completed | 145700 | 137082 | 2011-12-01 | 2011-12-22
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701004021/RC/3001 — सीमेन्‍ट कंक्रीट खरंजा रामभजन शर्मा के मकान से सरदार के मकान तक | Completed | 0 | 71051 | 2012-10-22 | 2012-11-03
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701004021/RC/3007 — सी सी खरंजा निर्माण कार्य व्रन्‍दावन त्‍यागी के मकान से श्‍यामदेव वावा की ओर | Completed | 0 | 60700 | 2012-12-24 | 2013-01-04
MORENA / PAHADGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701004021/RC/3059 — पत्‍थर खरंजा निर्माण कार्य गोटेराम जाटव के घर से प्रा0 कन्‍या शाला तम | Completed | 195212 | 179372 | 2013-02-01 | 2013-03-11
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701004021/WC/15 — सोख्‍ता गड्रडा पंचायत भवन के पास खिटोरा | Completed | 4480 | 1020 | 2008-05-25 | 2013-02-15
MORENA / PAHADGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/WC/196 — सोक पिट माधै सिंह का पुरा | Completed | 0 | 10985 | 2008-05-25 | 2009-12-03
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701004021/WC/197 — सोक पिट पंचायत भवन के पास | Completed | 0 | 10985 | 2008-05-11 | 2009-11-26
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701004021/WC/198 — सोक पिट गढढा गोकुला के मकान के पास | Completed | 0 | 10705 | 2008-05-18 | 2009-11-25
MORENA / PAHADGARH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701004021/WC/22012034380318 — TALAV NIRMAD | Closed | 0 | 0 | 2017-04-14
MORENA / PAHADGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701004021/WC/22012034390453 — Talav naveen baldharipura khitora | Completed | 1430000 | 819591.83 | 2019-01-10 | 2021-03-21
MORENA / PAHADGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701004021/WC/22012034525821 — CHEK DEM BABU KHET KE PASS KHITORA | Closed | 0 | 0 | 2020-01-26
MORENA / PAHADGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701004021/WC/22012034525822 — CHEK DEM KARDEN EISTHAN KE PASS MAHAVAN KHITORA | Completed | 1430493.68 | 1353751.6 | 2020-03-19 | 2021-07-16
MORENA / PAHADGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701004021/WC/22012034525823 — CHEK DEM JAI SINGH KHET KE PASS KHITORA | Closed | 0 | 0 | 2020-01-26
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1701004021/WC/22012034529953 — Gali plug nirman kary behad me khitora | Completed | 1396688.9 | 1178760 | 2020-07-26 | 2021-07-16
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble contour Bund for Community / Construction of Pebble contour Bund for Community | Construction of Bund | 1701004021/WC/22012034529954 — Gali plug nirman kary behad me dharmsingh ka pura | Completed | 1437848.95 | 1106940 | 2020-07-26 | 2021-07-16
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701004021/WC/22012034545848 — chek dem nirman kary khitora ke khar me | Completed | 1495723.36 | 1359845.26 | 2020-05-20 | 2021-07-16
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034545849 — chek dem nirman kary babu ke khet ke pass | Completed | 1493988.46 | 1417763.62 | 2020-05-20 | 2021-07-16
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034545850 — chek dem nirman kary kedar ke khet ke pass | Completed | 1495289.66 | 1401252.7 | 2020-05-20 | 2021-07-16
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701004021/WC/22012034576315 — Navin talab nirman khitora ke behad me | Completed | 1349030.18 | 1234466.37 | 2020-09-23 | 2022-01-01
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701004021/WC/22012034584796 — rapta nirman kary shantidham wale raste par | Closed | 0 | 0 | 2020-04-14
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034619835 — Rapta nirman kary shanti dham wale raste par | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1701004021/WC/22012034619836 — Rapta nirman kary baldhari pura ke raste par | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701004021/WC/22012034619837 — Rapta nirman kary mahavan ke raste par | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034619838 — Chek dem nirman kary khitora ke behad me | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1701004021/WC/22012034622758 — rapta nirman kary shantidham ke pass nadi par | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034622760 — chek dem nirman kary rambhajan sharma ke khar par | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034622780 — gali plug nirman kary rambhajan ke behad me | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Along the coast Line Plantation of Coastal Shelter Belt Trees for Community | Plantation | 1701004021/WC/22012034622785 — gali plug nirman kary mahendra ke khet ke pass | Closed | 0 | 0 | 2021-01-25
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701004021/WC/22012034722371 — Nabin talab Nirmal Mukesh ke khet ke pass | Completed | 987611.37 | 925036.4 | 2021-11-25 | 2024-10-16
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701004021/WC/22012034722387 — Chek dem Kary puttu ke khet ke pass | Completed | 989904.8 | 946804.62 | 2021-06-18 | 2023-07-05
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1701004021/WC/22012034722408 — Chek dem Kary naresh ke behavior me khitora ke pass | Completed | 999840.12 | 988061.38 | 2021-07-06 | 2023-07-05
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701004021/WC/22012034722434 — Falling plag Mukesh pandit ke khet ke pass | Closed | 0 | 0 | 2021-04-14
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701004021/WC/22012034722452 — Falling plag ramveer ke began me | Closed | 0 | 0 | 2021-04-14
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701004021/WC/22012034791498 — Chek dem Kary Rajendra ke khar me | Closed | 0 | 0 | 2021-04-14
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701004021/WC/22012034791506 — Chek dem Kary pappy ke khet ke pass khar me | Closed | 0 | 0 | 2021-04-14
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1701004021/WC/22012034791512 — Chek dem Kary khitora ke Behad me | Closed | 0 | 0 | 2021-04-14
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034847945 — गली प्लग रामू के खेत के पास | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1701004021/WC/22012034848054 — gali plug shyam singh ke khet ke pass | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034848062 — gali plug balveer ke khet ke pass | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034848068 — gali plug veer bahadur ke khet ke pass | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701004021/WC/22012034848072 — gali plug ramsevak master ke khet ke pass | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034854098 — navin talab nirman kary arvind ke khet ke pass | Completed | 1002619.06 | 963437.54 | 2021-11-25 | 2023-07-05
MORENA / PAHADGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034854099 — navin talab nirman kary veerbahadur ke khet ke pass | Closed | 0 | 0 | 2021-10-02
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034938098 — NAVEEN TALAB NIRMAN KARY MAHABAN K BEHAD ME | Ongoing | 988030.24 | 762556.74 | 2022-05-23
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034938103 — NAVEEN TALAB NIRMAN KARY PARSHOTTAM K KHET K PASS | Closed | 983860.14 | 0 | 2022-04-01
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012034938110 — NAVEEN TALAB NIRMAN KARY BALVEER K KHET K PASS | Ongoing | 982169.33 | 851912.26 | 2022-05-23
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701004021/WC/22012034938115 — GALI PLUG NIRMAN KARY VIRENDRA K KHET K PASS | Ongoing | 485878.12 | 218052 | 2022-05-23
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1701004021/WC/22012034970236 — गली प्लग निर्माण कार्य रामू के खेत के पास | Ongoing | 489768.15 | 371592 | 2022-05-23
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1701004021/WC/22012034970596 — Gali plug nirman kary Shyam singh ke khet ke pass | Completed | 485878.12 | 420444 | 2022-05-23 | 2023-07-05
MORENA / PAHADGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701004021/WC/22012034970608 — Navin talab nirman kary parsottam ke khet ke pass | Completed | 988030.24 | 939056.6 | 2022-05-23 | 2023-07-05
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701004021/WC/22012035009794 — TALAB NIRMAN KARY KANSH BABA MANDIR KE PASS MAHAVAN | Completed | 1261794.72 | 1173890.97 | 2023-09-12 | 2024-12-28
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1701004021/WC/22012035025801 — गली प्लग देवीराम के खेत पास | Ongoing | 492768.15 | 389899 | 2023-08-01
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/WC/22012035087265 — तालाब निर्माण कार्य महेश के खेत के पास | Closed | 0 | 0 | 2023-04-14
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/WC/22012035087268 — रपटा निर्माण कार्य माधोसिंह के पुरा के पास | Completed | 1496938.16 | 1390861.9 | 2023-08-01 | 2025-12-31
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701004021/WC/22012035087269 — रपटा निर्माण कार्य पानसिंह खेत के पास | Physically Completed | 1482955.88 | 1258388.07 | 2023-08-01 | 2026-05-12
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1701004021/WC/22012035166932 — CTR-चेकडेम निर्माण पूरन के खेत के पास खिटोरा | Closed | 0 | 0 | 2023-08-16
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1701004021/WC/22012035166939 — CTR-चेकडेम निर्माण रामसेवक मास्टर के खेत के पास खिटोरा | Closed | 0 | 0 | 2023-08-16
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1701004021/WC/22012035166945 — CTR-चेकडेम निर्माण बासुदेव के खार के खेत के पास महावन खिटोरा | Closed | 0 | 0 | 2023-08-16
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1701004021/WC/22012035166950 — CTR- | Closed | 0 | 0 | 2023-08-16
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701004021/WC/22012035170317 — CTR-रपटा निर्माण कार्य राम सिंह के पास महावन खितोरा | Closed | 0 | 0 | 2024-01-25
MORENA / PAHADGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701004021/WC/22012035186236 — रपटा निर्माण कार्य रामसिंह के खेत के पास खिटोरा | Physically Completed | 1488241.54 | 1273866.23 | 2024-03-16 | 2026-05-12
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1701004021/WC/22012035214597 — बृक्षारोपड़ कार्य कांस बाबा मंदिर के पास महावन खिटोरा | New | 0 | 0 | 2024-06-08
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220722 — navin talab nirman kary vakil ke khet ke pass | Physically Completed | 1490416.69 | 1337439.98 | 2025-05-26 | 2026-05-12
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220724 — navin talab nirman kary babu baba mandir ke pass | Ongoing | 1477280.69 | 579331.39 | 2025-05-26
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220725 — navin talab nirman kary mahesh ke khet ke pass | Approved | 0 | 0 | 2024-08-16
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220726 — navin talab nirman kary men road ke pass | Physically Completed | 1489865.68 | 725534.82 | 2025-05-26 | 2026-05-12
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220727 — navin talab nirman kary raghuraj ke khet ke pass | Approved | 0 | 0 | 2024-08-16
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220728 — navin talab nirman kary keshav ke khet ke pass | Approved | 0 | 0 | 2024-08-16
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220729 — navin talab nirman kary kwari nadi ke pass | Ongoing | 1483929.66 | 587594.14 | 2025-05-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220731 — navin talab nirman kary chhote khar me | Physically Completed | 1477543.77 | 723247.63 | 2025-05-26 | 2026-05-12
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220732 — navin talab nirman kary bade tapun ke pass | Ongoing | 1474355.47 | 849276.84 | 2025-05-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220733 — navin talab nirman kary bhadbhada nare par | Ongoing | 1484404.62 | 762846.42 | 2025-05-26
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220734 — navin talab nirman kary sukha khor me | Physically Completed | 1459033.46 | 1359331.82 | 2024-12-20 | 2026-04-23
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220735 — navin talab nirman kary peeli mati wale khor me | Ongoing | 1441821.69 | 598830.04 | 2025-05-26
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220736 — navin talab nirman kary vasdev ke khet ke pass | Approved | 0 | 0 | 2024-08-16
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220737 — navin talab nirman kary nirpal ke khet ke pass | Approved | 0 | 0 | 2024-08-16
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035220738 — navin talab nirman kary remja wale khar me | Ongoing | 1465193.99 | 1016943.35 | 2024-12-20
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224338 — percolation tank nirman kary kimliya wali nari me | Ongoing | 1483716.04 | 686691.98 | 2025-05-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224339 — percolation tank nirman kary peepal wale nare ke pass | Ongoing | 1485770.18 | 1227035.01 | 2025-05-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224342 — percolation tank nirman kary parsottam ke khet ke pass | Physically Completed | 1483909.04 | 1296564.17 | 2025-05-26 | 2026-05-12
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224343 — percolation tank nirman kary satendra ke khet ke pass | Ongoing | 1473476.33 | 976102.41 | 2024-12-20
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224345 — percolation tank nirman kary bade bamu ke pass | Ongoing | 1468875.03 | 1240463.89 | 2024-12-20
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224346 — percolation tank nirman kary kedar ke khet ke pass | Ongoing | 1490148.03 | 1233618.54 | 2025-05-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224348 — percolation tank nirman kary umar wale nare ke pass | Ongoing | 1466231.37 | 606864.14 | 2025-10-29
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224349 — percolation tank nirman kary khadar ke pass | Ongoing | 1488371.93 | 859353.87 | 2025-09-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224350 — percolation tank nirman kary amarsingh ke khet ke pass | Ongoing | 1486045.67 | 915135.68 | 2025-09-26
MORENA / PAHADGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035224352 — percolation tank nirman kary chhokar wale behad me | Ongoing | 1488806.45 | 1101913.7 | 2025-09-19
MORENA / PAHADGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701004021/WC/22012035240456 — navin talab nirman kary bharoshi ke khet ke pass | Approved | 0 | 0 | 2024-10-09
MORENA / PAHADGARH | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701004021/WC/323 — सोखता गडडा निर्माण कार्य धर्म सिंह का पुरा | Completed | 0 | 10820 | 2009-11-26 | 2010-03-12
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701004021/WC/34 — सोख्‍ता गड्रडा गोकुला के पास खिटोरा | Completed | 4480 | 0 | 2008-05-18 | 2013-02-15
MORENA / PAHADGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701004021/WC/35 — सोख्‍ता गड्रडा पी.एस. शाला के पास महाबन खिटोरा | Completed | 4480 | 1020 | 2008-05-11 | 2008-04-01
MORENA / PAHADGARH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701004021/WC/9993632081 — नवीन तालाव निमार्ण | Deleted | 0 | 0 | 2013-01-26