## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005013/AV/22012034375921 — शांति धाम निर्माण कार्य बिलैया पूरा इमलिया | Completed | 245000 | 166576.66 | 2019-11-15 - 2022-07-10
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005013/AV/22012034393595 — पंचायत भवन निर्माण कार्य,इमलिया | Completed | 579200 | 552349 | 2019-03-09 - 2023-07-20
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005013/AV/22012034393608 — शांतीध्‍ााम निर्माण कार्य इमलिया | Closed | 245000 | 0 | 2018-01-26 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005013/AV/7191 — आँगनबाड़ी भवन निर्माण कार्य एवम बाउंड्रीवाल (इमलिया द्वितीय) | Completed | 180000 | 172978 | 2017-01-30 - 2020-06-02
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005013/AV/7192 — आँगनबाड़ी भवन निर्माण कार्य एवम बाउंड्रीवाल प्रथम ,इमलिया | Completed | 180000 | 174167 | 2017-01-30 - 2020-06-02
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005013/AV/7193 — आँगनबाड़ी भवन निर्माण कार्य एवम बाउंड्रीवाल (बिलैयापुरा) | Completed | 180000 | 174758 | 2017-01-30 - 2020-06-02
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005013/DP/122 — निर्मल वाटिका इमलिया | Completed | 0 | 27000 | 2010-09-08 - 2016-06-28
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/DP/22012034228033 — पत्थर नाली निर्माण कार्य दामोदर लुहार के घर से गब्बर बघेल के घर तक देवीसिंघ के पूरा से गब्बर के घर त | Deleted | 1300975 | 0 | 2015-12-09 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & Maint of Community infrastructure | 1701005013/DP/22012034244173 — शान्तिधाम निर्माण इमलिया | Completed | 245000 | 160214.7 | 2017-06-12 - 2020-06-02
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005013/DP/22012034244175 — शान्तिधाम निर्माण विलैया का पुरा इमलिया | Deleted | 245000 | 0 | 2017-06-10 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005013/DP/22012034601151 — Vasudha vandan amarat vatika Imaliya | Closed | 0 | 0 | 2023-08-07 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005013/DP/42 — व़क्षारोपण कार्य ककरदा मोपा से पुलिया की ओर | Completed | 0 | 9775 | 2008-08-14 - 2016-06-28
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005013/DP/78 — वूक्षारोपण कब्रस्‍तान पर | Completed | 0 | 5642 | 2009-08-28 - 2016-06-28
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1701005013/FP/18 — पत्‍थर नाली निर्माण कार्य सुरेश के मकान से | Completed | 416761 | 411483.72 | 2011-10-01 - 2012-04-20
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034203006 — पत्थर नाली निर्माण हनुमान मंदिर से पी एस तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005013/FP/22012034203007 — पत्थर नाली निर्माण हनुमान मंदिर से पी एस | Completed | 1300971 | 581036.33 | 2015-11-16 - 2017-07-04
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005013/FP/22012034204294 — पत्थर नाला निर्माण प्रायमरी स्कूल से हनुमान मन्दिर तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Diversion Channel / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034204295 — पत्थर नाली निमाण pm sadak से सोनेराम के कुआ तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034360154 — नाला निर्माण प्र शा वि से पुराण गांव की ओर | Completed | 1264000 | 1129105.44 | 2017-11-06 - 2020-06-10
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034362320 — पत्थर नाला निर्माण कार्य ईमलिया | Closed | 0 | 0 | 2018-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034364418 — नाला निर्माण बघेलों के मोहल्ला से पुराना गाँव इमिलिया तक | Closed | 0 | 0 | 2019-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034364448 — पत्थर नाला निर्माण बघेलों के मोहल्ला से पुराना गाँव इमिलिया तक | Completed | 1499447.19 | 1444396 | 2020-02-01 - 2025-02-10
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034364644 — पत्थर नाला लाखन प्रजापति के खेत से शांति धाम की ओर | Completed | 1454456.93 | 1430579 | 2020-03-08 - 2021-08-23
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034366272 — pathar nala purv nala evam aaganvadi bhavan se lalaram ke pura tak | Completed | 1498434.38 | 1477075 | 2020-06-28 - 2021-09-05
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034366705 — pathar nala lalaram ke pura se biliyapura ki or | Completed | 1468218.56 | 1301832 | 2020-08-01 - 2025-07-08
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034367376 — Pathar Nala parsram ke makan se kacchi road tak imiliya | Completed | 1489636.66 | 1199347.3 | 2020-09-11 - 2025-07-08
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034367377 — Pathar Nala masjid se arjun singh ka pura imiliya | Completed | 1492709.1 | 1464025 | 2020-09-11 - 2022-08-12
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034624289 — Patthar nala nirman kary lalaram ke pura se pmgsy road tak | Closed | 0 | 0 | 2021-04-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034624290 — Patthar nala nirman kary koksingh ke pura se nadi ki or | Closed | 0 | 0 | 2021-04-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034624865 — पत्थर नाला निर्माण कार्य कोकसिंह के पुरा से नदी की ओर | Completed | 996998.43 | 864115.08 | 2022-10-16 - 2025-02-25
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005013/FP/22012034624866 — पत्थर नाला नि र्माण कार्य कोकसिंह के पुरा से कब्रिस्तान की ओर | Completed | 989933.51 | 480869.4 | 2022-10-16 - 2025-09-27
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034629661 — Patthar nallah nirman lalaram ka pura | Completed | 1368722.36 | 1255480 | 2022-09-24 - 2025-07-08
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034629662 — Patthar nallah nirman ramdayal ke makan se kachchi road ki or | Completed | 1371267.64 | 874160 | 2022-09-24 - 2025-09-27
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034629663 — Kachcha Nala nirman imliya | Completed | 898061.8 | 470424 | 2022-09-24 - 2025-09-27
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005013/FP/22012034630368 — Patthar Nala nirman imliya | Completed | 1457117 | 819900 | 2022-11-15 - 2026-03-06
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005013/FP/22012034630369 — Patthar nallah nirman imliya se chhera ki or | Physically Completed | 1454595.21 | 1356946 | 2022-11-15 - 2026-05-18
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005013/FP/22012034630370 — Patthar nallah nirman Devi singh ka pura avm jatav mohalla imliya | Physically Completed | 1451258.63 | 1335334 | 2022-11-15 - 2026-05-18
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005013/FP/22012034630371 — Kachcha Nala nirman imliya se chimni ki or | Ongoing | 701881.2 | 118728 | 2022-11-15 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005013/FP/22012034630372 — Kachcha Nala nirman imliya se nadi ki or | Ongoing | 736875.26 | 22032 | 2022-11-15 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034634387 — pathar nala nirman karya harijan basti imliya | Closed | 0 | 0 | 2023-07-01 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034634388 — pathar nala nirman karya Kushwah Mohalla Imliya | Closed | 0 | 0 | 2023-07-01 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034634421 — Patthar nallah nirman Prabhu kushwah ke makan se layak kushwah ke makaan ki or | Physically Completed | 1473962.06 | 1350632.04 | 2023-08-28 - 2026-05-18
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005013/FP/22012034634422 — Patthar nallah nirman shrilal jatav ke makaan se chhatri ki or | Ongoing | 1469742.65 | 992526.94 | 2023-08-28 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1701005013/FP/34 — पत्थर नाला निर्माण इमाम खां के मकान से मस्जिद तक | Completed | 399639 | 333839.16 | 2012-06-01 - 2018-12-07
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005013/FP/9977521694 — पत्थर नाला स्कूल से लेकर आसन नदी तक | Deleted | 0 | 0 | 2013-01-26 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005013/FP/9977522045 — नाली निर्माण स्‍कूल से आसन नदी की ओर | Completed | 499200 | 268197.99 | 2013-09-16 - 2016-09-17
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005013/IF/1000042144 — पशु आश्रय केंद्र शंकर / हरी कंठ | Completed | 80000 | 33023.33 | 2013-10-01 - 2016-10-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005013/IF/1000042190 — पशु आश्रय केंद्र राजेंद्र / हरिकंठ | Completed | 80000 | 50305.6 | 2013-10-01 - 2016-10-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005013/IF/1000042194 — पशु आश्रय केंद्र रामस्वरूप / भगवान | Completed | 80000 | 13140 | 2013-10-01 - 2016-10-18
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005013/IF/1000042196 — पशु आश्रय केंद्र ओतार / बीघाराम | Completed | 80000 | 51034.88 | 2013-10-01 - 2017-01-01
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005013/IF/1000042199 — पशु आश्रय केंद्र सुरेश / हरी कंठ | Completed | 80000 | 58401.58 | 2013-10-01 - 2016-10-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005013/IF/1000042207 — पशु आश्रय केंद्र गंगाराम / श्रीपति | Completed | 80000 | 52411.04 | 2013-10-01 - 2016-10-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005013/IF/114 — मैढ बंधान दिलीप / लालपति | Completed | 35000 | 25132 | 2012-04-01 - 2012-08-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005013/IF/22012034349681 — सार्वजनिक परिषर वृक्षारोपण कार्य बिलैयापुरा स्कूल के चारो तरफ शांति धाम के चारो तरफ | Completed | 335000 | 4016 | 2017-06-12 - 2019-07-20
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005013/IF/22012034349684 — सार्वजनिक परिषर वृक्षारोपण कार्य पुराने गांवों व आंगनबाड़ी के पीछे खेल मैदान के चारो ओर | Completed | 335000 | 4188 | 2017-06-12 - 2019-07-20
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005013/IF/82 — मेड बधान कार्य गगाराम / श्रीपति | Completed | 0 | 46116 | 2011-09-08 - 2011-09-28
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005013/IF/83 — मेड बधान कार्य ग्‍यासी / नहने प्रजापति | Completed | 0 | 35868 | 2011-09-02 - 2011-09-28
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/1177069 — Construction of IAY House -IAY REG. NO. MP1004601 | Completed | 15480 | 15660 | 2017-10-31 - 2018-09-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/1533152 — Construction of IAY House -IAY REG. NO. MP2715273 | Completed | 15480 | 14616 | 2018-11-27 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/1903708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4397124 | Completed | 15660 | 15660 | 2018-11-27 - 2018-12-17
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/1910798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4352820 | Completed | 15660 | 14964 | 2018-10-08 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/1911037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4803080 | Completed | 15660 | 14616 | 2018-12-04 - 2018-12-21
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/1915443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4722664 | Completed | 15660 | 14616 | 2018-12-11 - 2018-12-21
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/193283 — Construction of IAY House -IAY REG. NO. MP-01-005-013-001/24 | Completed | 14310 | 14292 | 2019-03-09 - 2019-05-31
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/193284 — Construction of IAY House -IAY REG. NO. MP-01-005-013-001/45 | Completed | 14310 | 14322 | 2017-01-09 - 2018-12-21
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/193285 — Construction of IAY House -IAY REG. NO. MP-01-005-013-001/52 | Completed | 14310 | 14448 | 2017-01-23 - 2018-12-21
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/193286 — Construction of IAY House -IAY REG. NO. MP-01-005-013-001/57 | Completed | 14310 | 14574 | 2017-02-20 - 2018-12-21
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/193287 — Construction of IAY House -IAY REG. NO. MP-01-005-013-001/58 | Completed | 14310 | 14760 | 2019-03-10 - 2019-05-31
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/473641 — Construction of IAY House -IAY REG. NO. MP1880961 | Completed | 15030 | 16086 | 2017-02-13 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/521114 — Construction of IAY House -IAY REG. NO. MP2581776 | Completed | 15030 | 15204 | 2017-02-13 - 2018-10-26
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/531335 — Construction of IAY House -IAY REG. NO. MP2832116 | Completed | 15030 | 14964 | 2017-10-31 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/700836 — Construction of IAY House -IAY REG. NO. MP1439603 | Completed | 15030 | 16006 | 2017-10-31 - 2018-11-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/719343 — Construction of IAY House -IAY REG. NO. MP1692577 | Completed | 15030 | 15312 | 2017-10-31 - 2018-12-09
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/730240 — Construction of IAY House -IAY REG. NO. MP1971254 | Completed | 15030 | 15660 | 2017-10-31 - 2018-09-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/735739 — Construction of IAY House -IAY REG. NO. MP2124233 | Completed | 15030 | 15660 | 2017-10-31 - 2018-09-20
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/735741 — Construction of IAY House -IAY REG. NO. MP2124271 | Completed | 15030 | 15660 | 2017-10-31 - 2018-09-15
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/736310 — Construction of IAY House -IAY REG. NO. MP2136327 | Completed | 15030 | 346 | 2017-05-29 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/741859 — Construction of IAY House -IAY REG. NO. MP2282490 | Completed | 15030 | 15312 | 2017-10-31 - 2018-10-26
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/742055 — Construction of IAY House -IAY REG. NO. MP2287429 | Completed | 15030 | 14964 | 2017-10-31 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/742236 — Construction of IAY House -IAY REG. NO. MP2292869 | Completed | 15030 | 14784 | 2017-05-29 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/747820 — Construction of IAY House -IAY REG. NO. MP2462977 | Completed | 15030 | 16180 | 2017-05-29 - 2018-11-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/760851 — Construction of IAY House -IAY REG. NO. MP2995544 | Completed | 15030 | 15632 | 2017-05-29 - 2018-12-01
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/765718 — Construction of IAY House -IAY REG. NO. MP3223887 | Completed | 15030 | 15834 | 2017-10-31 - 2018-11-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/766188 — Construction of IAY House -IAY REG. NO. MP3244245 | Completed | 15030 | 17394 | 2017-05-29 - 2018-11-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/768913 — Construction of IAY House -IAY REG. NO. MP3381722 | Completed | 15030 | 15656 | 2017-05-29 - 2018-12-01
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/769624 — Construction of IAY House -IAY REG. NO. MP3416994 | Completed | 15030 | 14784 | 2017-05-29 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/775910 — Construction of IAY House -IAY REG. NO. MP3729760 | Completed | 15030 | 16878 | 2017-10-31 - 2018-11-14
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/776497 — Construction of IAY House -IAY REG. NO. MP3764817 | Completed | 15030 | 14964 | 2017-10-31 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/776886 — Construction of IAY House -IAY REG. NO. MP3786265 | Completed | 15030 | 13914 | 2017-05-29 - 2018-12-07
MORENA / JOURA / IMALIYA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005013/IF/IAY/777191 — Construction of IAY House -IAY REG. NO. MP3808440 | Completed | 15030 | 14786 | 2017-05-29 - 2018-12-07
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/156 — खेत समतली करण मेड बंधान केदारसिह के खेत | Completed | 0 | 82400 | 2010-04-28 - 2010-06-15
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/166 — मेड बधान राजैन्‍द्र बगैरा | Completed | 0 | 26900 | 2010-06-30 - 2010-07-13
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/168 — मेड वन्‍धान कार्य होतम पुञ कुदाराम के खेत मे | Completed | 0 | 21300 | 2010-07-07 - 2010-07-20
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/179 — मैढ बंधान कार्य रामलखन / ब्रदी सिंह के खेत में | Completed | 0 | 14000 | 2010-08-02 - 2010-08-08
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/180 — मैढ बंधान कार्य रामस्‍वरूप जाटव के खेत में | Completed | 0 | 24100 | 2010-07-21 - 2010-08-08
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1701005013/LD/22012034591868 — लालाराम के पुर से विलैॅया पुरा की ओर व़क्षा रोपड कार्य | Closed | 0 | 0 | 2023-04-01 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034953186 — Peripheral stone bund nirman karya kabristaan imaliya | Ongoing | 1426565.6 | 1111795.67 | 2025-08-18 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034953188 — Peripheral stone bund nirman karya shantidham imaliya | Ongoing | 1457942.38 | 1213499.54 | 2025-08-18 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034953189 — Peripheral stone bund nirman karya abmedkar park bilaiyapura | Physically Completed | 1048969.72 | 1017430.22 | 2025-07-07 - 2026-05-18
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034959137 — pheripheral stone bund nirman karya bilaiyapura shantidham | Ongoing | 1493460.57 | 95265 | 2026-01-23 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034959328 — pheripheral stone bund nirman karya chhatri baba mandir imliya | Ongoing | 1484320.6 | 26100 | 2026-02-21 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034959329 — pheripheral stone bund nirman karya sidhd baba mandir imliya | Ongoing | 1477768.59 | 47763 | 2026-01-23 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/LD/22012034959330 — pheripheral stone bund nirman karya primary school bilaiyapura | Approved | 1479460.9 | 0 | 2025-04-14 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/222 — मैढ बंधान कार्य वनवारी पुञ भीकाराम | Completed | 0 | 18600 | 2010-10-09 - 2010-10-18
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005013/LD/225 — मैडवन्‍धान कार्य प्रकाश पुञ पंछी | Completed | 0 | 20400 | 2010-09-15 - 2010-09-24
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701005013/PG/22012034312698 — खेलमैदान निर्माण इमलिया | Completed | 320000 | 142720 | 2017-06-12 - 2020-07-10
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/108 — पत्‍थर खरजा निर्माण लालाराम का पुरा | Completed | 0 | 81379 | 2009-04-03 - 2010-08-28
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/110 — मिटटी मुरम रोड प्रधान मंत्री रोड से | Completed | 417000 | 200003 | 2009-07-17 - 2010-07-10
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034164438 — सी.सी. खरंजा एवं नाली निर्माण रामविलास के घर से इम | Deleted | 44940 | 0 | 2014-02-17 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034165955 — पत्थर खरंगा अर्जुन सिंह के पूरा से लेकर आसन नदी तक | Deleted | 0 | 0 | 2013-01-26 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034183176 — पत्‍थर खरंजा निर्माण अर्जुन सिंह के पुरा से आसन नद | Completed | 498800 | 419984.5 | 2013-09-16 - 2016-09-17
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034211608 — मिटटी ग्रेवल रोड गब्बर बघेली के मकान से लालारम के | Completed | 903000 | 893275.3 | 2014-03-04 - 2016-12-22
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034211620 — मिटटी ग्रेवल रोड पुरुषोत्तम के कुँआ से समले कि पुर | Completed | 1053000 | 729389.4 | 2014-03-04 - 2016-12-22
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034289128 — पत्थर खरंजा निर्माण विलैयापुरा से मेन रोड | Completed | 363700 | 245812.9 | 2015-11-16 - 2016-09-17
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034292627 — सी सी खरंजा निर्माण हनुमान मंदिर से रामदयाल का मकान हरिविलास के घर से रामदयाल के घर तक माधो के मकान | Completed | 170698 | 130422 | 2015-12-14 - 2016-09-17
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034308578 — मिट्टी ग्रेवल रोड बासदेव के कुआ से हनुमान मन्दिर तक एवम स्कूल से शांती धाम तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034308580 — मिट्टी ग्रेवल रोड बल्लम के खेत से कब्रिस्तान एवम सूरदास तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034308582 — मिट्टी ग्रेवल रोड लालाराम के पुरा से बिलैया पुरा की ओर | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034308584 — पत्थर खरंजा निर्माण प्रधान्मंत्री सडक से सोनेराम के कुआ तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034308588 — सी सी खरंजा एवम नाली निर्मान पर्शोत्त्म के घर से गब्बर बघेल के घर तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034308589 — सी सी खरंजा एवम नाली निर्मण नेमीचन्द्र के घर से सलीम के घर तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034308590 — सी सी खरंजा एवम नाली pm sadak से नजीरा के घर तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034308591 — सी सी खरंजा एवम नाली गओन की रोड से दुर्जन के घर तक | Deleted | 0 | 0 | 2015-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034341125 — सुदूर सड़क संपर्क सूरदास के नरे से ग्यासी राम के पूरा तक एवम शान्तिधाम एवं कव्रिस्तान तक | Completed | 1100000 | 1058194.28 | 2017-06-19 - 2025-02-10
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034398216 — सी सी खरंजा मय नाली निर्माण कार्य जसराम के घर से आंगनबाड़ी भवन तक ,देवीसिंह का पुरा | Ongoing | 150727.5 | 7344 | 2022-09-21 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034473171 — c c road nirman vijay ke makan se main road tak | Completed | 53212 | 50688 | 2019-09-26 - 2020-06-02
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034473172 — c c road nirman kary soneram savita ke makan se rajpal ke makan take | Completed | 31200 | 30976 | 2019-09-26 - 2020-06-19
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034531184 — सी .सी रोड निर्माण कार्य मुस्ताक के घर मस्जिद तक पुराना गाब | Completed | 80325 | 80180 | 2020-08-22 - 2020-11-20
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/22012034533913 — सी सी खरंजा निर्माण कार्य बैजनाथ के घर से सलीम के घर तक | Completed | 51300 | 38000 | 2020-08-22 - 2023-07-06
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/22012034535420 — सुदूर संपर्क सड़क आंगनवाड़ी भवन से सोभान का पुरा (इमिलिया) | Completed | 1483500.13 | 1429432.95 | 2020-08-29 - 2022-08-12
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/426 — मिटटी ग्रेबल रोड इमाम खा घर से प्रधान मञी रोड तक | Completed | 0 | 94106.96 | 2009-09-03 - 2010-08-25
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005013/RC/465 — मिटृटी ग्रेवल रोड विलेयापुरा से भगवन्‍त | Completed | 0 | 346808.64 | 2010-10-16 - 2016-12-22
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005013/RC/51 — सी.सी. खरंजा अर्जुन सिंह का पुरा | Completed | 0 | 65116 | 2009-02-03 - 2009-07-03
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005013/RC/511 — पत्‍थर खरंजा सुरेश के मकान से लेकर सरकारी कुआ तक | Deleted | 0 | 0 | 2011-04-14 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005013/RC/512 — पत्‍थर खरजा निर्माण कार्य सूरेश के मकान से सरकारी कुआ तक | Completed | 425178 | 400265.88 | 2011-10-09 - 2012-07-07
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005013/RC/626 — सी.सी. खरंजा निर्माण स्‍कूल से सूरदास के मन्दिर तक | Completed | 188600 | 158514 | 2012-12-02 - 2015-04-01
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005013/WC/114 — सोक पिट विलैया पुरा इमलिया | Completed | 0 | 13228.24 | 2009-02-03 - 2016-06-28
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005013/WC/183 — हैण्‍ड पम्‍प सोख्‍ता गडडा देवी सिह | Completed | 0 | 4004 | 2009-03-18 - 2015-07-01
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005013/WC/184 — हैण्‍ड पम्‍प सोक्‍ता गडडा लालाराम का पुरा | Completed | 0 | 6804 | 2009-03-25 - 2015-07-01
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1701005013/WC/22012034296917 — रिंग बन्ड निर्माण कार्य सूरदास के नाले के पास | Deleted | 131975 | 0 | 2016-06-20 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005013/WC/22012034380626 — naveen talab nirman | Closed | 0 | 0 | 2017-10-02 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005013/WC/22012034618092 — सोखता गड्डा कार्य संख्या 08 ग्राम पंचायत इमिलिया | Closed | 0 | 0 | 2021-01-26 -
MORENA / JOURA / IMALIYA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005013/WC/22012034618093 — सोखता गड्डा कार्य संख्या 08 ग्राम पंचायत इमिलिया | Closed | 0 | 0 | 2021-01-26 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Along the coast Line Plantation of Coastal Shelter Belt Trees for Community | Plantation | 1701005013/WC/22012034642831 — Rapta nirman kary khel medan ke pass | Closed | 0 | 0 | 2021-04-02 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701005013/WC/22012034642835 — Chek dem nirman karya shanti dham ke pass | Closed | 0 | 0 | 2021-04-02 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1701005013/WC/22012034642842 — Chek dem nirman karya kali mata mandir ke pass | Closed | 0 | 0 | 2021-04-02 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1701005013/WC/22012034642847 — Rapta nirman karya kok singh ke pura ke rashte par | Closed | 0 | 0 | 2021-04-02 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005013/WC/22012034687200 — चैकडेम निर्माण कार्य कब्रिस्तान के यहां पर | Closed | 998656.59 | 0 | 2021-04-14 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005013/WC/22012034687202 — तालाब निर्माण कार्य शांतिधाम के पास | Physically Completed | 993074.28 | 960262 | 2022-10-16 - 2026-04-16
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005013/WC/22012034744463 — Roop watar Harvesting Pachayat bhavan | Closed | 0 | 0 | 2021-04-14 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005013/WC/22012034744476 — Roop watar Harvesting Anganwadi bhavan | Closed | 0 | 0 | 2021-04-14 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1701005013/WC/22012035096182 — Rapta nirman karya Main road ke bagal se imaliya | Closed | 0 | 0 | 2023-07-01 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005013/WC/22012035096241 — Rapta nirman karya Main road ke bagal se imaliya | Physically Completed | 1338841.36 | 1303999.83 | 2023-09-08 - 2026-05-18
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005013/WC/22012035211039 — Pattar nala nirman karya mata ke mandir ke pas purana gao imaliya | Deleted | 0 | 0 | 2024-04-15 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005013/WC/22012035211042 — Pattar nala nirman karya siddh pura se balaiya pura ki aur imaliya | Deleted | 0 | 0 | 2024-04-15 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005013/WC/22012035322148 — Naveen talab nirman karya middle school ke pass | Ongoing | 1491199.69 | 0 | 2025-11-20 -
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005013/WC/48 — सोख्‍ता गडडा | Completed | 0 | 9105 | 2008-05-16 - 2016-06-28
MORENA / JOURA / IMALIYA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005013/WC/49 — सोखता गडडा निर्माण कार्य | Completed | 0 | 9105 | 2008-08-13 - 2016-06-29