## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005016/AV/22012034390601 — शांतिधाम निर्माण - मानपुर प़थवी | Completed | 245000 | 245377.5 | 2020-01-30 - 2021-04-11
MORENA / JOURA / BISANGPURA | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of Infra for Liquid Biomanure for Grps / Construction of Infrastructure for Liquid Biomanure for Groups | Bio-Fertilizer | 1701005016/AV/22012034470266 — NAVEEN SHANTI DHAM NIRMAN KARY MANPUR PRATHVI | Deleted | 281062.92 | 0 | 2020-02-01 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005016/AV/22012034612847 — मॉ की बगिया कार्य शा0प्रा0वि0 विसंगपुरा | Closed | 0 | 0 | 2021-08-10 -
MORENA / JOURA / BISANGPURA | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005016/AV/22012034616123 — Panchayat Bhawan | Closed | 0 | 0 | 2022-01-26 -
MORENA / JOURA / BISANGPURA | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005016/AV/22012034616126 — Panchayat Bhawan | Closed | 0 | 0 | 2022-01-26 -
MORENA / JOURA / BISANGPURA | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005016/AV/22012034616127 — Panchayat Bhawan | Closed | 0 | 0 | 2022-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005016/AV/22012034619394 — Panchayat Bhavan gp bisangpura | Closed | 0 | 0 | 2022-04-01 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005016/AV/22012034619395 — Panchayat Bhavan gp bisangpura | Completed | 1000000 | 949465 | 2022-06-02 - 2025-12-13
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005016/DP/127 — निर्मल वाटिका | Completed | 0 | 148256 | 2011-04-05 - 2011-12-12
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005016/DP/128 — निर्मल वाटिका | Completed | 0 | 107228 | 2011-04-08 - 2011-12-12
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005016/DP/137 — शान्ति धाम ि‍ नर्माण्‍ा कार्य मानपुर पूथ्‍वी | Completed | 0 | 481820.6 | 2011-08-17 - 2012-02-02
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005016/DP/186 — निर्मल वाटिका विसंगपुर | Completed | 84060 | 32736 | 2012-06-02 - 2016-03-31
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005016/DP/187 — निर्मल वाटिका विसंगपुर 2 | Completed | 84060 | 137403.2 | 2012-05-26 - 2016-03-31
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005016/DP/188 — निर्मल वाटिका विसंगपुर 3 | Completed | 84060 | 86517.6 | 2012-06-23 - 2014-07-10
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005016/DP/22012034236852 — शांति धाम निर्माण कार्य बिसंगपुरा | Deleted | 0 | 0 | 2016-10-02 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701005016/DP/22012034236938 — शांति धाम निर्माण बिसंगपुरा | Completed | 180000 | 144719.95 | 2016-12-31 - 2018-12-06
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1701005016/DP/22012034482538 — शांति धाम निर्माण मानपुर पृथ्वी | Deleted | 0 | 0 | 2019-04-01 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005016/DP/22012034528887 — nandanfaloudhyan lakhan singh/gadipal gram bishanpura | Closed | 0 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1701005016/DP/22012034531996 — नंदन फलोउद्यान कार्य लाखन सिंह/गादीपाल यादव | Deleted | 144900 | 0 | 2021-09-08 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701005016/DP/22012034583175 — नंदन फलोद्यान लाखन सिंह /गादी पाल ग्राम बिसंगपुरा | Closed | 0 | 0 | 2023-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1701005016/DP/22012034603795 — वंसुधा वंधन शा0मा0वि0 विसंगपुरा | Closed | 0 | 0 | 2023-04-01 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005016/DP/22012034613700 — नन्‍दन फलोधान लाखन सिंह के खेत में विसंगपुरा | Closed | 0 | 0 | 2023-08-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1701005016/DP/22012034619654 — ब्रक्षारोपण सती माता मंदिर मानपुर पृथ्वी | Approved | 0 | 0 | 2024-06-20 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1701005016/DP/22012034620020 — ब्रक्षारोपण सती माता मंदिर मानपुर पृथ्वी | Approved | 173308.58 | 0 | 2024-06-20 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005016/DP/22012034627869 — nandan falodyan lakhan singh ke khet me bisangpura | Approved | 0 | 0 | 2024-04-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005016/DP/47 — व़क्षारोपण हरियाली महात्‍सव | Completed | 273600 | 2420 | 2008-09-05 - 2016-03-31
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005016/DP/50 — हरियाली महोत्‍सव विसंगपुरा | Completed | 0 | 3185 | 2008-09-15 - 2016-09-20
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005016/FP/22012034328921 — पत्थर नाला निर्माण लक्छमीनारायण के मकान से सती माता की और | Completed | 894000 | 667432 | 2017-08-19 - 2020-01-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034362007 — PATTHAR NALA Goswami mohalla se pokhar tak | Completed | 1148800 | 1183551.71 | 2019-02-11 - 2020-07-13
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034362297 — पत्थर नाला निर्माण कार्य बिसंगपुरा | Deleted | 0 | 0 | 2018-10-02 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034362800 — Patthar Nala Vinod ki dukan se School hote hue nahar ki oar | Completed | 1436000 | 1397930.65 | 2019-03-05 - 2020-05-11
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034362801 — Patthar Nala Pokhar se Rajendra ke ghar kioar | Completed | 689280 | 665046 | 2019-03-06 - 2020-05-11
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034363614 — नाला निर्माण कार्य - ग्राम विसंगपुरा में भूरा के मकान से पोखर तक। | Deleted | 0 | 0 | 2019-08-15 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034363780 — PATTHAR NALA NIRMAN KARY DATARAM KE MAKAN SE NAHAR KI OR | Deleted | 0 | 0 | 2019-10-02 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034363781 — PATTHAR NALA NIRMAN KARY RAMESH KE MAKAN SE NAHAR KI OR | Deleted | 0 | 0 | 2019-10-02 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034365098 — PATTHAR NALLAH NIRMAN KARY DATARAM KE GHAR SE HARIJAN BASTI KI OR | Completed | 1490731.5 | 1426095 | 2020-06-07 - 2021-02-01
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034365099 — PATTHAR NALLAH NIRMAN KARY RAJENDRA KE GHAR SE POKHAR KI OR BISANGURA | Deleted | 0 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034365196 — PATTHAR NALA NIRMAN KARY RAJENDRA KE GHAR SE POKHAR AIVN MANPUR KI OR | Completed | 1497756.6 | 1416665 | 2020-06-15 - 2021-08-28
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034366989 — नाला निर्माण कार्य राजवीर के मकान से शांतिधाम की ओर एवं जाटव मौहल्ला, मानपुर पृथ्वी | Completed | 1485743.51 | 1441525 | 2020-09-10 - 2021-02-01
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034366990 — नाला निर्माण कार्य जगदीश के मकान से नहर की ओर एवं किरार मौहल्ला | Completed | 1462977.11 | 1427860 | 2020-09-10 - 2021-02-01
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034624811 — पत्थर नाला निर्माण कार्य मानपुर से अरहेला की ओर | Completed | 996263.19 | 988368 | 2021-05-25 - 2022-08-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034624812 — पत्थर नाला निर्माण कार्य मानपुर से कुम्हेरी की ओर | Completed | 998277.24 | 959988 | 2021-05-26 - 2022-08-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625100 — नाला निर्माण कार्य मैनरोड़ से ककराई | Completed | 987711.27 | 977244 | 2021-06-29 - 2022-08-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625101 — नाला निर्माण कार्य विसंगपुरा | Completed | 993240.05 | 942988 | 2021-10-26 - 2022-08-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625102 — नाला निर्माण कार्य मानपुर | Completed | 999945.99 | 995578 | 2021-06-12 - 2022-08-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625103 — कच्चा नाला निर्माण कार्य विसंगपुरा | Completed | 750800.88 | 643848 | 2021-06-29 - 2021-11-01
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625104 — कच्चा नाला निर्माण कार्य मानपुर | Deleted | 0 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625912 — नाला निर्माण कार्य यादव मौहल्ला | Completed | 1479203.62 | 1452924 | 2021-07-13 - 2022-05-23
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034625913 — नाला निर्माण कार्य हरिजन बस्ती | Completed | 1471986.85 | 1395720 | 2021-07-13 - 2023-04-15
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034627692 — पत्थर नाला निर्माण कार्य राजकुमार के घर से सती मंदिर एवं यादव मौहल्ला | Deleted | 1460814.48 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034627693 — पत्थर नाला निर्माण कार्य पप्पू के घर से सी सी खरंजा की ओर | Deleted | 0 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034628062 — कच्चा नाला निर्माण कार्य विसंगपुरा | Completed | 877179.8 | 685110 | 2022-02-14 - 2022-06-30
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034628108 — पत्थर नाला मुलायम के घर से सती मंदिर एवं यादव मौहल्ला विसंगपुरा | Physically Completed | 1432859.88 | 1223293 | 2022-02-22 - 2026-06-23
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034628109 — पत्थर नाला निर्माण पंचायत भवन से मैनरोड़ एवं राजपूत मौहल्ला विसंगपुरा | Completed | 1397595.78 | 623445 | 2022-02-22 - 2022-08-11
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034628203 — पत्थर नाला निर्माण कार्य गोस्वामी मौहल्ला से अरहेला की ओर ग्राम विसंगपुरा | Completed | 1405671.2 | 1320612 | 2022-03-20 - 2023-05-12
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034628204 — पत्थर नाला निर्माण कार्य गोस्वामी मौहल्ला से अरहेला की ओर ग्राम विसंगपुरा | Closed | 0 | 0 | 2022-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034628444 — पत्थर नाला निर्माण कार्य सती मंदिर के पास एवं किरार मौहल्ला, ​विसंगपुरा | Closed | 1391406.26 | 0 | 2022-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629033 — Patthar Nala nirman ramveer ke makaan se daddu baba ki or | Completed | 1474694.55 | 1407824 | 2022-05-23 - 2023-04-15
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629034 — Patthar nallah nirman manpur chauraha se bisangpura ki or | Completed | 1479659.75 | 1196178 | 2022-05-20 - 2023-12-13
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629035 — Patthar nallah nirman school ke paas | Closed | 1483766.31 | 0 | 2022-04-14 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629036 — Patthar nallah nirman hemu ke makaan ke paas | Completed | 1487872.86 | 1355464 | 2022-05-20 - 2023-07-19
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629244 — Kachcha Nala nirman bisangpura | Closed | 936998.92 | 0 | 2022-04-14 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629470 — नाला निर्माण कार्य कैलासी बावा के मकान से हीरामन बाबा की ओर मानपुर | Completed | 1451913.86 | 1160579.52 | 2022-09-24 - 2024-02-27
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629471 — नाला निर्माण कार्य जगदीश के मकान से मेन रोड मानपुर चौराहे की ओर | Physically Completed | 1454396.35 | 1150348.84 | 2025-01-02 - 2026-06-23
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629472 — नाला निर्माण कार्य सुल्‍तान के माकान से जगदीश के मकान की ओर विशंगपुरा | Completed | 1449431.36 | 1220362.02 | 2022-09-16 - 2023-12-15
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629473 — नाला निर्माणकार्य दशरथ के मकान से धारा के मकान की ओर विसंगपुरा | Completed | 1457378.85 | 1267587.52 | 2022-09-16 - 2024-02-27
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034629474 — नाला निर्माण कार्य पंसार के मकान से सिद्ध वावा की ओर विसंगपुरा | Completed | 1431881.07 | 1213279.6 | 2023-08-11 - 2023-12-15
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034631012 — Patthar nala nirman karya Patel ke khet se tau ke bor ki or bisangpura | Completed | 1481512.53 | 1361213 | 2023-05-04 - 2024-04-09
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005016/FP/22012034631013 — NALA NIRMAN KARYA Tau ki tibariya se babu ke bor ki or bisangpura | Completed | 1475756.82 | 1365544 | 2023-06-09 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005016/FP/22012034631014 — NALA NIRMAN KARYA Babu ke bor se kakarai ki or bisangpura | Completed | 1494337.33 | 1350911.5 | 2023-06-16 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034634134 — पत्थर नाला निर्माण कार्य दीपक के घर से उरहेरा नहर की ओर बिसंगपुरा | Completed | 1417716.56 | 1328641 | 2023-08-18 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034634135 — पत्थर नाला निर्माण कार्य सुरेश जाटव के घर नहर से ककरारी की ओर बिसंगपुर | Completed | 1410464.14 | 1321974 | 2023-08-18 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034634136 — पत्थर नाला निर्माण कार्य उदयसिंह के घर से हनुमान मंदिर की ओर बिसंगपुरा | Completed | 1378403.23 | 1295390 | 2023-08-18 - 2024-11-29
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005016/FP/22012034634137 — पत्थर नाला निर्माण कार्य मानपुर यादव मोहल्ला से तालाब की ओर मानपुर | Closed | 0 | 0 | 2023-05-15 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034637584 — pathar nala nirman karya rajveer se chourah ki or | Completed | 1471760.42 | 1167423 | 2024-03-07 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034637608 — Pathar nala nirman karya Fondiram ke kua se talab ki or | Completed | 1470065.4 | 1172231 | 2024-03-07 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034637609 — Pathar nala nirman karya Antram ke khet se kakrai talab ki or | Completed | 1474324.5 | 1246184.5 | 2024-03-07 - 2024-11-29
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034637832 — Pathar nala nirman karya narua se nahar ki or | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034637833 — Pathar nala nirman karya vishal ke khet se talab ki or | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005016/FP/22012034637834 — Pathar nala nirman karya Papu ke Ghar se anganwaadi ki or | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012034343200 — वृक्ष रोपण कार्य शान्तिधाम विसंगपुरा | Completed | 335000 | 5440 | 2017-05-27 - 2020-12-27
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012034343217 — वृक्ष रोपण कार्य शान्तिधाम मानपुरपृथ्वी विसंगपुरा | Completed | 335000 | 7408 | 2017-05-27 - 2020-12-27
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005016/IF/22012034359357 — नरूआ से सतीमाता की ओर मानपुरप़थ्‍वी | Closed | 335000 | 0 | 2017-04-24 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012034359364 — नरूआ से सडक किनारे रोड किनारे विसंगपुरा | Deleted | 335000 | 0 | 2017-08-05 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1701005016/IF/22012035377600 — Khet talab nirman karya Rambaran ke khet me | Approved | 0 | 0 | 2025-04-14 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005016/IF/22012035380619 — खेत तालाब निर्माण कार्य रामबरन के खेतमें बिसंगपुरा | Physically Completed | 450885.64 | 299367 | 2025-05-01 - 2026-05-18
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005016/IF/22012035380640 — खेत तालाब निर्माण कार्य रामचंद के खेतमें बिसंगपुरा | Physically Completed | 450885.64 | 269874 | 2025-05-01 - 2026-05-18
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005016/IF/22012035380856 — Khet talab nirman karya Rambaran ke khet me | New | 0 | 0 | 2025-04-14 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035633490 — EK BAGIYA MAA KE NAAM SHRI MATI MP-01-005-016-001/721-C | Deleted | 0 | 0 | 2025-09-01 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035633491 — EK BAGIYA MAA KE NAAM SHRI MATI MP-01-005-016-001/721-C | Ongoing | 282818.64 | 261 | 2026-02-02 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035633497 — EK BAGIYA MAA KE NAAM RAJANI MP-01-005-016-001/721-D | Ongoing | 282818.64 | 0 | 2025-12-29 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035650161 — EK BAGIYA MAA KE NAAM MITHALESH MP-01-005-016-001/721-B | Ongoing | 266578.64 | 0 | 2026-02-02 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035650162 — EK BAGIYA MAA KE NAAM ANNDI MP-01-005-016-001/721-A | Deleted | 0 | 0 | 2025-10-02 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035659363 — EK BAGIYA MAA KE NAAM REKHA BAI MP-01-005-016-001/780 | Ongoing | 266578.64 | 0 | 2026-02-02 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005016/IF/22012035660263 — EK BAGIYA MAA KE NAAM REKHA JATAV MP-01-005-016- 001/780 | Deleted | 0 | 0 | 2025-12-15 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005016/IF/52 — मेढ वन्‍धान भोगीराम / रामरतन | Completed | 0 | 11590 | 2011-05-11 - 2011-12-12
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9926714054 — pashu शेड निर्माण सुधीर / लक्मी नारायण | Completed | 80000 | 50865.62 | 2014-03-05 - 2016-09-22
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9926714057 — pashu शेड निर्माण अनेक सिंह / माधो सिंह | Completed | 80000 | 45702.62 | 2014-03-05 - 2016-09-22
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9926714060 — pashu शेड निर्माण राजकुमार / गयाप्रसाद | Completed | 80000 | 44730.59 | 2014-03-05 - 2016-09-22
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9926714062 — pashu शेड निर्माण murari लाल / maharaj सिंह | Completed | 80000 | 45756.62 | 2014-03-05 - 2016-09-22
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1701005016/IF/9993725279 — pashu sedherajkumae gyaprashd | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9993726072 — पसु शेड निर्माण कार्य रामेस्वर / जगनाथ | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9993727158 — पशु सेट उदयसिंह /सुआलाल | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9993727549 — Pasused bhagwanlal/santosilal | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9993727831 — Ragvendra/rajkumar | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005016/IF/9993727834 — Diwan/sowaran | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1701005016/IF/9993727837 — Veerendra/shivsingh | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005016/IF/IAY/116586 — Construction of IAY House -IAY REG. NO. MP-01-005-016-001/30 | Completed | 14310 | 14863 | 2016-11-26 - 2018-03-05
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005016/IF/IAY/193288 — Construction of IAY House -IAY REG. NO. MP-01-005-016-002/19 | Completed | 14310 | 11022 | 2016-11-26 - 2018-03-20
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005016/IF/IAY/40758 — Construction of IAY House -IAY REG. NO. MP-01-005-016-002/10 | Completed | 14310 | 14863 | 2016-11-26 - 2018-03-20
MORENA / JOURA / BISANGPURA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005016/IF/IAY/40763 — Construction of IAY House -IAY REG. NO. MP-01-005-016-002/17 | Completed | 14310 | 13026 | 2016-12-31 - 2018-03-20
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1701005016/LD/22012034591848 — व़क्षारोपड कार्य विसंगपुरा लाखन सिंह यादव पुृ श्री गादीपाल | Closed | 0 | 0 | 2023-04-01 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1701005016/LD/22012034592003 — व़क्षारोपड कार्य स्‍कूल से नहर की ओर विसंगपुुरा | Closed | 0 | 0 | 2023-04-01 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701005016/LD/22012034944807 — Talab nirman karya kakrail talab | Approved | 0 | 0 | 2024-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701005016/LD/22012034944809 — Percolation Talab nirman karya Darshan ke khet pas Manpur | Approved | 0 | 0 | 2024-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701005016/LD/22012034944810 — Talab nirman karya Aamuli wala talab | Approved | 0 | 0 | 2024-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701005016/LD/22012034944811 — PerculationTalab nirman karya jatav mohhala wala | Approved | 0 | 0 | 2024-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701005016/LD/22012034944873 — PerculationTalab nirman karya jatav mohhala manpur prathavi | Approved | 0 | 0 | 2024-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034944890 — percolation talab karya Kira bisangpura | Approved | 0 | 0 | 2024-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034944891 — percolation talab karya kakrai bisangpura | Physically Completed | 1425751.11 | 1082343.28 | 2024-11-29 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034944892 — percolation talab jatav mohlla bisangpura | Physically Completed | 1268137.91 | 1041850.42 | 2024-11-22 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034944893 — percolation talab karya aamuli wala bisangpura | Ongoing | 1360940.22 | 632255.69 | 2024-11-29 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034944894 — percolation talab karya jatav mohlla manpur prathi | Physically Completed | 1321974.1 | 962280.57 | 2024-11-29 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034944895 — percolation talab karya vishal ke khet ke pass manpur prathvi | Physically Completed | 1308318.19 | 1002400.34 | 2024-11-22 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034953457 — Peripheral stone Bunds nirmad karya shanti dham bisangpura | Physically Completed | 1460728.04 | 1071745.03 | 2025-06-18 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034953458 — Peripheral stone Bunds nirmad karya shanti dham manpur | Physically Completed | 1471899.75 | 1246977.11 | 2025-06-19 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034953531 — Peripheral stone Bunds nirman kary shanti dham sati mata mandir ke pas manpur | Physically Completed | 1479855.09 | 1097570.93 | 2025-06-19 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034958013 — Peripheral stone bund Nirmad karya Hanuman mandir ke pas sati mata mandir manpur | Ongoing | 1473835.35 | 1081816.91 | 2025-09-09 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034958014 — Peripheral stone bund Nirmad karya sati mata mandir manpur | Ongoing | 1453776.46 | 975613.44 | 2025-11-12 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034958015 — Peripheral stone bund Nirmad karya sati mata mandir samudayik sochalay ke pas manpur | Physically Completed | 1473215.42 | 1259323.9 | 2025-09-09 - 2026-06-23
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005016/LD/22012034958028 — Peripheral stone bund Nirmad karya Siddh sthan bisangpura | Ongoing | 1475981.7 | 997656.73 | 2025-09-09 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034164644 — पंच परमेश्‍ववर सीसी खरंजा नाली निर्माण सिया के घर से हनुमान मंदिर तक | Deleted | 68498 | 0 | 2012-10-02 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034177386 — सी.सी. खरंजा एवं नाली निर्माण कार्य पंडित के मकान | Completed | 68498 | 65488 | 2013-08-03 - 2014-07-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034188812 — पत्‍थर खरंजा निर्माण कार्य गोस्‍वामी मोहल्‍ला से र | Completed | 500000 | 16644 | 2013-10-04 - 2016-09-25
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034290406 — PATHAER KHARNJA RAMLAL KE KHET SE BHANSHI LAL KE KHET TAK | Completed | 765000 | 140278.8 | 2015-12-05 - 2016-09-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034307935 — मिट्टी मुरम रोड शकर के टुबल से फोकर तक बिसंगपुरा | Deleted | 0 | 0 | 2016-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034339255 — सुदूर ग्राम संपंर्क सड़क मानपुर पृथ्वी से कुम्हेरी की ओर विसंगपुर | Completed | 1100000 | 935630.25 | 2017-05-27 - 2020-05-11
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034340864 — सुदूर ग्राम संपर्क सड़क निर्माण हरिजन पुरा से ककराई होते हुए बिसंगपुरा गावं की और | Completed | 1100000 | 1052740.42 | 2017-06-10 - 2020-05-11
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034382642 — CC kharanja avm nali nirman manpur chourahe se jagdish ke makan ki aor | Completed | 66187 | 67080 | 2018-02-03 - 2020-01-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034434553 — C. C kharanja Rajpal ke makan so Sanjay kw man tak | Completed | 38901 | 38976 | 2019-01-09 - 2020-06-12
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034442864 — सी सी खरंजा निर्माण कार्य - अशोक के घर से लाखन के घर तक विसंगपुरा | Completed | 39744 | 39600 | 2019-03-05 - 2019-09-21
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034442865 — सी सी खरंजा निर्माण कार्य - मैनरोड् से स्‍कूल कैम्‍पस तक | Completed | 34425 | 33968 | 2019-03-05 - 2019-09-21
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034442866 — सी सी खरंजा एवं नाली निर्माण - रामेश्‍वर के घर से मौनू के घर तक विसंगपुर | Completed | 36720 | 36432 | 2019-03-05 - 2019-09-25
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034526339 — सुदूर ग्राम संपर्क रोड शांति धाम से कुम्हेरी तक | Completed | 1493639.67 | 1445037.69 | 2020-06-30 - 2021-02-01
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034529311 — c c road nirman bharat gali,ratiram gali,lakhan gali or chouk,bisangpura | Deleted | 0 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/22012034529312 — c c road nirman bharat gali,ratiram gali,lakhan gali or chouk,bisangpura | Closed | 90516 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034535334 — जाटव मौहल्ला से अरहेला मौजा होते हुए डामर रोड़ अरहेला तक मानपुर | Deleted | 0 | 0 | 2020-04-14 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034535662 — सुदूर ग्राम संपर्क सड़क जाटव मौहल्ला से अरहेला मौजा होते हुए डामर रोड़ अरहेला तक मानपुर | Completed | 3346992.65 | 3198823.76 | 2020-09-08 - 2022-08-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/22012034648592 — सुदूर /खेत सड़क निर्माण सुरेश के बोर से चचिहा मौजे की और | Completed | 2499228.51 | 2463980.37 | 2023-09-28 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005016/RC/405 — मिटटी ग्रेबिल रोड कार्य विसगपुरा से मानपुरा तक | Completed | 0 | 340816 | 2009-11-04 - 2011-12-12
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005016/RC/525 — सी सी रोड निर्माण्‍ा कार्य गजेन्‍द्र के मकान से हनुमान मन्दिर कीओर | Completed | 0 | 136912 | 2011-11-16 - 2011-12-30
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005016/RC/584 — पंचपरमेश्‍वर सी.सी. खरंजा अजयपाल के मकान से प्रजापतिमोहल्‍ला | Completed | 62123 | 67128 | 2012-06-17 - 2014-07-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005016/RC/585 — पत्‍थर खरंजा जन्‍दर की तिवरिया से शान्‍तीधाम तक | Completed | 394623 | 391285.48 | 2012-07-04 - 2014-04-01
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005016/RC/606 — पत्‍थर खरंजा मानपुर के हरिजन मोहल्‍ला से | Completed | 394623 | 411875.48 | 2012-09-04 - 2016-09-29
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005016/RC/87 — सी सी खरंजा बाबु के मकान से आमा के | Deleted | 0 | 0 | 2008-04-01 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005016/RC/88 — सी सी खरजा बाबु के मकान से अमदती के मकान | Completed | 0 | 52024 | 2009-02-11 - 2009-09-10
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005016/RC/94 — पत्‍थर खरंजा निर्माण कार्य हरिजन मो0 | Completed | 281000 | 145587 | 2009-02-01 - 2016-03-31
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034269540 — व्यक्तिगत शौचायल ओमप्रकाश / लज्जाराम | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270109 — व्यक्तिगत शौचायल रामवीर / उधोसिंह | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270118 — व्यक्तिगत शौचायल रामवीर / गोपाल | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270135 — व्यक्तिगत शौचायल/भारत/ मिश्रीलाल | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270191 — व्यक्तिगत शौचायल/नरवर/दीनानाथ | Deleted | 5400 | 0 | 2014-07-25 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270194 — व्यक्तिगत शौचायल/ लखन/मिश्रीलाल | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270202 — व्यक्तिगत शौचायल/जेहेन्द्र | Deleted | 5400 | 0 | 2014-07-25 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270435 — व्यक्तिगत शौचायल /ध्रुव सिंह /रामजीलाल | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270841 — व्यक्तिगत शौचायल/ब्रजकिशोर /मातादीन | Deleted | 5400 | 0 | 2014-07-16 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270851 — व्यक्तिगत शौचायल/ नारयण /मायाराम | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270855 — व्यक्तिगत शौचायल/जीतेन्द्र /छत्रपाल | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270858 — व्यक्तिगत शौचायल/ गबदा/दोजीराम | Deleted | 5400 | 0 | 2014-10-11 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270861 — व्यक्तिगत शौचायल/ हाकिम /फेरन | Deleted | 5400 | 0 | 2014-07-16 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270890 — व्यक्तिगत शौचायल/भगीरत /कोकसिंघ | Deleted | 5400 | 0 | 2014-07-16 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270891 — व्यक्तिगत शौचायल/ रतिराम /पतिराम | Deleted | 5400 | 0 | 2014-07-16 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034270892 — व्यक्तिगत शौचायल/ रामनायड /गगनाथ | Deleted | 5400 | 0 | 2014-07-16 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034277325 — व्यक्तिगत शौचायल/बलिराम /पंछिपाल | Deleted | 5400 | 0 | 2014-07-20 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1701005016/RS/22012034277332 — व्यक्तिगत शौचायल/लाछी/रामपाल | Deleted | 5400 | 0 | 2014-07-20 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1701005016/RS/22012034363442 — पत्थर नाला निर्माण लछमीनारायण के माकन से सटी माता की और | Closed | 894000 | 0 | 2017-07-20 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701005016/RS/22012034700289 — पत्थर नाला निर्माण कार्य दीपक के घर से उरहेरा नहर की ओर बिसंगपुरा | Deleted | 0 | 0 | 2023-05-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005016/WC/201 — सोकफिट सरपंच के पास भानपुर | Completed | 0 | 6267 | 2009-03-08 - 2016-03-31
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005016/WC/206 — सोक फिट दारिका वरेटा के पास | Completed | 0 | 1092 | 2009-05-01 - 2015-04-01
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005016/WC/22012034380607 — naveen talab nirman | Deleted | 0 | 0 | 2017-10-02 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1701005016/WC/22012034474175 — तालाब मारबत बिसंगपुरा ककराई | Deleted | 0 | 0 | 2019-07-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1701005016/WC/22012034474176 — तालाब मारबत बिसंगपुरा किरा का तालाब | Deleted | 0 | 0 | 2019-07-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1701005016/WC/22012034493440 — तालाब जीर्णोद्धार कार्य ककराई | Deleted | 0 | 0 | 2019-08-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701005016/WC/22012034550077 — NAVEEN TALAB NIRMAN KARY KAKRAI BISANGPURA | Deleted | 0 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005016/WC/22012034550080 — NAVEEN TALAB NIRMAN KARY AAMALI WALE GADDA BISANGPURA | Deleted | 0 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738344 — sokhta gadd nirmad karya satimata mandir manpur | Completed | 18395.12 | 13163.45 | 2021-10-19 - 2021-11-07
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738353 — sokhata gadd samudhayak manpur bhavan | Completed | 18149.18 | 10422 | 2021-10-19 - 2021-11-07
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738357 — sokhata gadd nirmad karyasati mata mandir manpur | Completed | 18158.64 | 16862.52 | 2021-10-19 - 2021-11-07
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738366 — sokhta gadd nirmad karya aaganbadi bhavan manpur | Completed | 18393.59 | 15923.04 | 2021-10-19 - 2021-11-07
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738372 — sokhata gadda nirmad karya bishanpura | Completed | 18395.12 | 16862.52 | 2021-10-19 - 2021-11-02
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738378 — water havesting karya bishanpura | Closed | 22660.91 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034738383 — water havesting karya manpur | Closed | 22420.37 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005016/WC/22012034740033 — सोक्ता गडडा निर्माण कार्य संख्या 10 विसंगपुरा | Closed | 183817.42 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012034740040 — रूफ वाटर हार्वेस्टिंग शा.प्रा.वि. विसंगपुरा | Deleted | 0 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012034740047 — रूफ वाटर हार्वेस्टिंग पंचायत भवन के पास | Deleted | 0 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1701005016/WC/22012034951310 — Roof Water harvesting aaganbadi manpur | Closed | 0 | 0 | 2022-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1701005016/WC/22012034951313 — Roof Water harvesting aaganbadi manpur | Deleted | 0 | 0 | 2022-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012035093076 — नवीन तालाव निर्माण कार्य जाटव मोहल्ला तालाव बिसंगपुरा | Closed | 0 | 0 | 2023-05-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012035094344 — रपटा निर्माण कार्य सुल्तान के खेत के पास नहर पर बिसंगपुरा | Completed | 1269764.08 | 1231677 | 2023-09-01 - 2024-10-22
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012035094346 — रपटा निर्माण कार्य सुरेश के खेत के पास बिसंगपुरा | Closed | 0 | 0 | 2023-05-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012035094349 — रपटा निर्माण कार्य दस बीघा पर फद्दीराम के खेत के पास | Completed | 1255070.79 | 1120159 | 2023-08-18 - 2024-11-29
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005016/WC/22012035094356 — रपटा निर्माण कार्य ककराई चौराहा शंकर के बोर के पास बिसंगपुरा | Completed | 1293373.62 | 1214279 | 2023-09-01 - 2024-10-22
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005016/WC/22012035153498 — रपटा निर्माण कार्य रुखन ताऊ के खेत के पास | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005016/WC/22012035153503 — Rapta nirman karya bari bale raste ke pas | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005016/WC/22012035153504 — Rapta nirman karay antram ke khet ke pas | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005016/WC/22012035153505 — Rapta nirman karay kakarai talab ke pas | Closed | 0 | 0 | 2023-12-28 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701005016/WC/22012035285993 — Dugwell recharge karya jatav mohhalla kua ke pass | Ongoing | 25899.46 | 14355 | 2025-05-06 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1701005016/WC/22012035286041 — Dugwell recharge karya patel ke kua ke pass | Ongoing | 25899.46 | 12528 | 2025-06-04 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1701005016/WC/22012035302839 — Dugwell recharge karya Bisangpura | Approved | 0 | 0 | 2025-05-10 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005016/WC/85 — सोक पिट विसंगपुरा | Completed | 0 | 1020 | 2008-10-12 - 2015-04-01
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005016/WH/22012034325373 — उदय सिंह के मकान के पास बिसंगपुरा | Deleted | 0 | 0 | 2017-04-24 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034441502 — तालाब जीर्णोद्धार कार्य - ग्राम विसंगपुर कमराई में | Deleted | 0 | 0 | 2019-08-15 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034443789 — TALAB JEERNOUDDHAR KARY KAKRAI BISANGPURA | Deleted | 0 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034443790 — TALAB JEERNOUDDHAR KARY AAMLI WALA GADA BISANGPURA | Deleted | 0 | 0 | 2020-01-26 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034444100 — TALAB JEERNOUDDHAR KARY KAKRAI MAI | Deleted | 0 | 0 | 2020-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034444161 — TALAB JEERNOUDDHAR KARY AAMLI WALE GADA MAI | Deleted | 0 | 0 | 2020-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034444598 — तालाब बिस्तारीकरण कार्य आमुली बाला गढ़ा | Completed | 809551.08 | 525990 | 2020-07-18 - 2023-07-05
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034444599 — तालाब बिस्तारीकरण कार्य ककरारी | Completed | 840237.47 | 761610 | 2020-07-19 - 2021-02-01
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034448097 — तालाब बिस्तारीकरण जाटव मौहल्ला | Completed | 865196.02 | 827744 | 2021-05-24 - 2021-10-08
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034448098 — तालाब बिस्तारीकरण कार्य दोहटा | Completed | 875403.33 | 798565 | 2021-05-10 - 2021-11-01
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034448099 — तालाब बिस्तारीकरण कार्य खदरा | Completed | 971976.81 | 901802 | 2021-05-10 - 2021-09-17
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034448565 — तालाब बिस्तारीकरण कार्य किरा विसंगपुरा | Completed | 875489 | 800320 | 2021-06-04 - 2021-10-03
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034448567 — तालाब बिस्तारीकरण कार्य रूध मानपुर | Completed | 852775.89 | 779898 | 2021-06-12 - 2021-11-01
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034449164 — तालाब बिस्तारीकरण कुम्हेरी रोड़ के पास | Completed | 934907.83 | 866923 | 2021-07-04 - 2022-02-01
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034452334 — तालाब विस्तारीकरण कार्य मानपुर | Deleted | 0 | 0 | 2021-04-14 -
MORENA / JOURA / BISANGPURA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005016/WH/22012034452335 — तालाब विस्तारीकरण कार्य विसंगपुरा | Deleted | 0 | 0 | 2021-04-14 -