## Work List
Exported on: 2026-09-09 04:47:01
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MUNDRAWAJA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701005018/AV/22012034659320 — शान्तिधाम निर्माण कार्य मलखान का पूरा ग्राम पंचायत मुंद्रावाज़ा | Approved | 334906.09 | 0 | 2024-06-10
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1701005018/DP/22012034496657 — नन्दंफलोध्यान/उत्तम /जगन्नाथ | Ongoing | 144900 | 0 | 2021-10-01
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034496750 — nandan falodhyan/ mukesh/naval singh | Ongoing | 144900 | 0 | 2021-10-01
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034496751 — nandan falodhyan/mansingh/gyasiya | Ongoing | 144900 | 0 | 2021-10-01
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034496752 — nadanfalodhyan/trilokpal/keshav | Ongoing | 144900 | 0 | 2021-10-01
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034496753 — nandanfaldhyan/fateh singh/savdhan | Ongoing | 144900 | 0 | 2021-10-01
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523589 — nandan falodhyan /guddi/virendra | Ongoing | 144900 | 0 | 2021-11-02
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523590 — nadanfalodhyan/banbari /harivilash | Ongoing | 144900 | 0 | 2021-11-02
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523591 — nadanfalodhyan/ maniram/bhagwanlal | Ongoing | 144900 | 0 | 2021-11-02
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523592 — nadanfalodhyan/ramnarayan/nandkishor | Ongoing | 144900 | 0 | 2021-11-02
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523593 — nadanfalodhyan/ jaharsingh/bhagwanlal | Ongoing | 144900 | 0 | 2021-11-02
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523594 — nadanfalodhyan/gayaprasad/ganpati | Ongoing | 144900 | 0 | 2021-11-02
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523653 — nadanfalodhyan/kaptan / girwar | Ongoing | 144900 | 0 | 2022-02-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1701005018/DP/22012034523980 — nadanfalodhyan/viddhyaram/feran | Ongoing | 144900 | 0 | 2022-02-16
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034640791 — patthar nala nirman karya Darshan ke ghar se mahendra ke ghar k or | Approved | 997478.81 | 0 | 2024-06-10
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034640792 — patthar nala nirman karya mahendra ke khet se shantidham ki or | Approved | 987540.44 | 0 | 2024-06-10
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034640793 — patthar nala nirman karya passotam ke khet se murari ke khet ki or | Approved | 970455.37 | 0 | 2024-06-10
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034640794 — patthar nala nirman karya barelal ke khet se narua ki or | Approved | 985441.41 | 0 | 2024-06-10
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034641274 — kachha nala nirman karya Dharmveer ke khet se dwarika ke khet ki or | Approved | 0 | 0 | 2024-08-16
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034641275 — kachha nala nirman karya Sultan ke khet se virendra ke khet ki or | Approved | 0 | 0 | 2024-08-16
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005018/FP/22012034641276 — kachha nala nirman karya munna ke khet se gopal ke khet ki or | Approved | 0 | 0 | 2024-08-16
MORENA / JOURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035026893 — nandan falodhyan rambeti /jagdeesh | Ongoing | 124659.37 | 0 | 2024-07-30
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1701005018/IF/22012035027420 — Nandan falodhyan/Dharm singh/beerbal | Ongoing | 124659.37 | 0 | 2024-02-17
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1701005018/IF/22012035027450 — Nandan falodhyan/birbal//mharaj singh | Ongoing | 123659.37 | 0 | 2024-07-30
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1701005018/IF/22012035027451 — Nanadna falodhyan dataram/ jivnalal | Ongoing | 123659.37 | 0 | 2024-02-17
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1701005018/IF/22012035503422 — khet talab nirman karya gp mundrawaja | Ongoing | 147621.16 | 0 | 2025-05-12
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1701005018/IF/22012035647441 — ek bagiya ma ke nam meena kushwah MP010050180018807A | Ongoing | 283818.64 | 0 | 2026-01-06
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035650020 — EK BAGIYA MAA KE NAAM DHANMANTI MP-01-005-018-001/802-D | Ongoing | 280320.64 | 0 | 2026-01-29
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035650102 — EK PED MAA KE NAAM GEETA KUSHAWAH MP-01-005-018-001/1195 | Ongoing | 283818.64 | 0 | 2026-01-06
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035650152 — EK BAGIYA MAA KE NAAM HARIDVARI KUSHWAH MP-01-005-018-001/877-A | Ongoing | 280320.64 | 0 | 2026-01-06
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035659348 — EK BAGIYA MAA KE NAAM PUSHPA KUSHWAH MP-01-005-018-001/816-C | Ongoing | 283818.64 | 0 | 2026-01-29
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035660141 — EK BAGIYA MAA KE NAAM KASTURI MP-01-005-018- 001/875 | New | 0 | 0 | 2025-12-15
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035660144 — EK BAGIYA MAA KE NAAM MAMTA MP-01-005-018- 001/959 | New | 0 | 0 | 2025-12-15
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035660164 — EK BAGIYA MAA KE NAAM RAMRATI MP-01-005-018- 001/50D | Ongoing | 283818.64 | 0 | 2026-02-09
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005018/IF/22012035660166 — EK BAGIYA MAA KE NAAM JANAKSHRI MP-01-005-018- 001/26D | New | 0 | 0 | 2025-12-15
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005018/IF/IAY/1567166 — Construction of IAY House -IAY REG. NO. MP3189777 | Approved | 27000 | 0 | 2018-03-26
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034953518 — Peripheral Stonbund nirman karya shantidham ke pas balla ka pura | Ongoing | 1484293.41 | 0 | 2025-05-06
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034958879 — peripheral stone bund nirman karya middle school ke pas | Closed | 1488251.42 | 0 | 2025-11-19
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034958881 — peripheral stone bund nirman karya ramjanaki mandir ke pas | Ongoing | 1487291.15 | 0 | 2025-11-20
MORENA / JOURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034958882 — peripheral stone bund nirman karya khori wali mata ke pas | Ongoing | 1487384.62 | 0 | 2026-04-22
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034958884 — peripheral stone bund nirman karya hanuman mandir ke charo or balla ka pura | Ongoing | 1487677.77 | 0 | 2025-11-20
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034958885 — peripheral stone bund nirman karya unsar wale talab ke pas | Closed | 1487254.67 | 0 | 2025-11-02
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005018/LD/22012034958886 — peripheral stone bund nirman karya pokhar wale raste ke pas | Ongoing | 1480531.92 | 0 | 2025-12-26
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005018/WC/22012035239750 — Talab nirman remja pura | Ongoing | 1396214.83 | 0 | 2025-02-17
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005018/WC/22012035320906 — Talab nirman karya balla ka pura | Ongoing | 1483182.41 | 23700 | 2026-03-10
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005018/WC/22012035320907 — Talab nirman karya tejpal dada ke ghar ke pas balla ka pura | Approved | 1489141.14 | 0 | 2025-08-18
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005018/WC/22012035320908 — Talab nirman karya susaity ke pas mundrawaja | Ongoing | 1489838.83 | 0 | 2026-03-10
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005018/WC/22012035320909 — Talab nirman karya khori ke pas batai ka pura | Approved | 1489551.26 | 0 | 2025-08-18
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1701005043/IF/22012035660139 — EK BAGIYA MAA KE NAAM JULEE MP-01-005-018- 001/1247 | Approved | 0 | 0 | 2025-12-15