## Work List
Exported on: 2026-09-03 04:03:44
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BIRUNGA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005041/AV/22012034399075 — Shanti Dham Hotam Singh ka pura Birunga | Completed | 215000 | 224671.06 | 2019-03-04 | 2022-03-08
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1701005041/AV/22012034511138 — Boundry wall nirman kary silarpur hanuman mandir ke pas birunga | Completed | 200000 | 200870 | 2020-09-25 | 2026-02-20
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1701005041/AV/22012034551535 — बाउंड्री बॉल निर्माण कार्य माध्यमिक शाला भवन विरुंगा | Completed | 261000 | 260934 | 2021-03-10 | 2022-03-17
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005041/AV/22012034612804 — apani bagiya midilschoolvirunga | Closed | 0 | 0 | 2021-10-04
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005041/AV/22012034612805 — apani bagiya midilschoolvirunga | Closed | 0 | 0 | 2021-10-04
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005041/AV/22012034612862 — maa ki bagiya midil school virunga | Closed | 0 | 0 | 2021-10-04
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005041/AV/22012034661246 — Santhi dham togar ka pura silalapur | Ongoing | 344082.71 | 293139.03 | 2025-03-20
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005041/AV/22012034661354 — Shanti dham prajapati ka pura | Physically Completed | 344082.71 | 290470.73 | 2025-03-20 | 2026-06-23
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005041/AV/22012034661357 — Shanti dham birunga | Physically Completed | 344082.71 | 293041.89 | 2025-03-20 | 2026-06-23
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005041/AV/22012034661358 — Shanti dham silrpur | New | 0 | 0 | 2024-10-02
MORENA / JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1701005041/AV/22012034666147 — Khel maidan kary Hotam singh ka pura Gp Biirunga | Approved | 469349.12 | 0 | 2025-04-14
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/106 — वक्षा रोपड कार्य खिरी खो स्‍थान | Completed | 0 | 16010 | 2009-10-06 | 2009-04-01
MORENA / JOURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/DP/144 — शान्ति धाम निर्माण कार्य विरूगा | Completed | 497200 | 417893.74 | 2011-09-12 | 2013-07-03
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/15 — गुटटी / ओछा नंदन फलोउधान | Completed | 123000 | 1638 | 2009-10-03 | 2013-03-05
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/16 — मुंशी / रामनाथ नंदन फलोउधान | Deleted | 123000 | 0 | 2008-11-04
MORENA / JOURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005041/DP/198 — वृक्षारोपण शांतीधाम विरूंगा | Completed | 177297 | 7788 | 2012-08-16 | 2015-07-08
MORENA / JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/DP/22012034557399 — बृक्षारोपण कार्य अमृत सरोवर तालाब खारी बाला विरूंगा पी.डब्ल्यू.डी | Closed | 0 | 0 | 2022-04-14
MORENA / JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/DP/22012034557400 — बृक्षारोपण कार्य अमृत सरोवर तालाब खिरी खोह के पास विरूंगा | Closed | 0 | 0 | 2022-04-14
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Shelter Belt Trees-Comm / Road Line Plantation of Shelter Belt Trees for Community | Plantation | 1701005041/DP/22012034620088 — ग्राम पंचायत बिरूंगा में वृक्षारोपड़ कार्य हनुमान मंदिर सीलरपुर | Approved | 0 | 0 | 2024-06-20
MORENA / JOURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1701005041/DP/228 — शांतीधाम निर्माण सिलारपुर | Completed | 473000 | 390944 | 2013-02-22 | 2016-05-10
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/DP/28 — मेडबंधान कार्य दशरथ / हीरालाल | Completed | 26732 | 7065 | 2008-12-01 | 2016-11-05
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/DP/29 — दीवान सिंह / शिव सिंह नंदन फलोउधान | Completed | 123000 | 2183 | 2008-04-11 | 2013-03-05
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/30 — व्रक्षा रोपण होतम सिंह का पुरा | Completed | 495000 | 13598 | 2008-08-14 | 2016-11-05
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/31 — हाकिम सिंह / मोहकम सिंह मेड बधान निर्माण कार्य | Deleted | 14250 | 0 | 2008-11-01
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/32 — मेड बधान निर्माण कार्य कल्‍याण पुत्र हटी सिंह | Deleted | 16286 | 0 | 2008-06-01
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/33 — मेड बधान निर्माण कार्य नारायण पुत्र शंकर सिंह | Completed | 13747 | 2605 | 2008-07-13 | 2009-09-27
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/DP/9 — शिव सिंह / नाथू सिंह नंदन फलोउधान | Deleted | 123000 | 0 | 2008-04-11
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034361968 — पत्‍थर नाला निर्माण - हरिजन बस्‍ती से होतम सिंह पुरा बाले रोड की ओर बिरूंगा | Closed | 0 | 0 | 2018-12-25
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034361969 — पत्थर नाला निर्माण - हरिजन बस्ती से होतम सिंह का पुरा बाली रोड़ की ओर बिरूंगा | Completed | 1483000 | 1258240 | 2019-01-28 | 2021-01-04
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034362296 — पत्थर नाला निर्माण कार्य बिरूगा | Closed | 0 | 0 | 2018-10-02
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005041/FP/22012034362797 — Patthar Nala Vakeel Singh ke makan se Hanuman Mandir ki oar | Physically Completed | 1494000 | 198168 | 2019-03-07 | 2021-02-02
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034369368 — patharnala | Closed | 0 | 0 | 2021-01-28
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034625959 — patharnala | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034628466 — Nala nirman hotam Singh ke pura se virunga khar ki our | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034628467 — Nala nirman hiraman se nadi ki or virunga | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034630575 — pathar nala nirman santi dham hotamsinghke pura se nadi ki ore | Completed | 1403455.34 | 1312548 | 2022-12-11 | 2025-07-25
MORENA / JOURA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/22012034630576 — patharnala hotam singh ke pura se nadi ki or virunga | Completed | 1435010.29 | 1348714.84 | 2024-09-13 | 2025-07-25
MORENA / JOURA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1701005041/FP/44 — नाली निर्माण गपुआ जाटव के मकान से जिम्‍मीपाल के खेत तक | Completed | 0 | 75651 | 2012-11-08 | 2015-01-03
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005041/FP/9977522541 — पत्थर नाला निर्माण रामस्वरूप गिरिर के मकान से स्कू | Completed | 222797 | 153404 | 2014-03-05 | 2016-05-19
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/1000068026 — पशु शेड निर्माण परिमल / बाबू सिंह गुर्जर | Completed | 80000 | 66432.34 | 2014-02-20 | 2016-05-19
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/1000068030 — पशु शेड निर्माण पंजाब / जगन्नाथ | Completed | 80000 | 66167.34 | 2014-02-20 | 2017-03-25
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/103 — मेड वन्‍धान कार्य राजवीर पु् जयेन्‍द | Completed | 0 | 16503 | 2011-11-06 | 2012-09-02
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/104 — मेड वन्‍धान कार्य बकील पु प्रितम | Completed | 0 | 20280 | 2011-11-06 | 2012-08-31
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/105 — मेड वन्‍धान कार्य रामवीर पु पीतम | Completed | 0 | 22656 | 2011-10-28 | 2012-08-24
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/108 — मैढ बंधान सुल्‍तान / रामसिंह | Completed | 19806 | 16592 | 2012-02-16 | 2012-05-20
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/109 — मैढ बंधान राजेन्‍द्र / मोहकम सिंह | Completed | 20721 | 17994 | 2012-02-12 | 2012-09-02
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/110 — मैढ बंधान रामवरन/लक्ष्‍मण | Completed | 33535 | 25548 | 2012-02-12 | 2012-09-01
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/14 — मेड बंधान स्‍वरूपा पुत्र भगरी | Completed | 19094 | 7036 | 2008-12-01 | 2010-03-30
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005041/IF/15 — गुटटी / ओछा नंदन फलोउधान | Completed | 123000 | 1785 | 2008-11-04 | 2010-10-03
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005041/IF/16 — मुंशी / रामनाथ नंदन फलोउधान | Completed | 123000 | 2785.34 | 2008-11-04 | 2010-10-03
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/2 — मेड बंधान केशव पुत्र रामनाथ | Deleted | 0 | 0 | 2008-05-23
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005041/IF/22012034345229 — सार्वजनिक वृक्षारोपण पंचायत भवन स्कूल हाट बाजार बिरूंगा | Completed | 335000 | 15996 | 2017-07-12 | 2020-12-22
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005041/IF/22012034359129 — सार्वजनिक व्रक्षारोपण कार्य शांतिधाम सिलारपुर स्‍कूल के पास सार्वजनिक स्‍थल पर | Completed | 335000 | 18060 | 2017-07-28 | 2020-12-22
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/22012035497309 — khet talab nirman kary yogendra /Ramnaresh gp birunga | Physically Completed | 385087.14 | 291011.52 | 2025-05-26 | 2026-06-23
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/22012035504969 — Kheta talab nirmad karya jagadesh | Physically Completed | 257597.95 | 192092.64 | 2025-05-26 | 2026-06-23
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/22012035504999 — Kheta talab nirmad banvaree gp birunga | Physically Completed | 269723.85 | 188939 | 2025-05-15 | 2026-06-23
MORENA / JOURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/22012035505038 — Khet talab nirmad bhupendra gp birunga | Completed | 269723.85 | 184773.12 | 2025-05-16 | 2026-01-07
MORENA / JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/29 — मेढवंधान गपुआ / भगरी | Completed | 0 | 17976 | 2011-01-03 | 2011-06-04
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/3 — मेड बंधान गुडडी पुत्र ओक्षा | Completed | 26432 | 10030 | 2008-05-19 | 2010-10-03
MORENA / JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/30 — मेढवंधान कार्य भरोषी / तुस्‍सीराम | Completed | 0 | 16512 | 2011-01-05 | 2011-06-11
MORENA / JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/31 — मेढ वंधान निर्माण कम्‍मोदी | Completed | 0 | 19340 | 2011-01-05 | 2011-06-18
MORENA / JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/32 — मेढवंधान छविराम / वुध्‍दीराम | Completed | 0 | 10656 | 2011-01-05 | 2011-06-25
MORENA / JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/36 — सोनेराम / बुद्धाराम मैडबंधान निर्माण | Completed | 16604 | 17244 | 2011-01-17 | 2011-04-28
MORENA / JOURA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/37 — मेढबंधान झम्‍मन / भगरी | Completed | 0 | 17144 | 2011-01-05 | 2011-05-28
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/4 — मैंढ बंधान कार्य नारायण पुत्र शंकर सिंह | Deleted | 0 | 0 | 2008-07-13
MORENA / JOURA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/5 — मैंढ बंधान कार्य कल्‍याण सिंह पुत्र हटी सिंह | Deleted | 0 | 0 | 2008-06-01
MORENA / JOURA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1701005041/IF/53 — मेढ वन्‍धान निमार्ण वनवारी / रामप्रसाद | Completed | 0 | 12444 | 2011-06-13 | 2011-06-18
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9926700809 — पशु आश्रय केंद्र अजीत सिंह / बाबूसिंह | Completed | 80000 | 64336.34 | 2014-02-12 | 2017-03-25
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9926700812 — पशु आश्रय केंद्र राजवीर सिंह /दर्शन सिंह | Completed | 80000 | 67717.33 | 2014-02-20 | 2016-05-19
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9926700819 — पशु आश्रय केंद्र रामनरेश / बाबू सिंह | Completed | 80000 | 60846.34 | 2014-02-12 | 2017-03-25
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9926708102 — पशु आश्रय केंद्र जिम्मीपल/ अोछा | Completed | 80000 | 70291.07 | 2014-02-27 | 2016-05-19
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9926713610 — पशु आश्रय केंद्र बनबारी / बदलुआ जाटव | Completed | 80000 | 71086.91 | 2014-03-05 | 2016-05-19
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9926713625 — पशु आश्रय केंद्र मुन्ना सिंह / पुरुसोत्तम सिंह | Completed | 80000 | 1752 | 2014-03-05 | 2020-07-15
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724582 — पशु सेट निर्माण राम प्रिकास /हरी सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724583 — पशु सेट निर्माण राम पाल /नवाव सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724584 — पशु सेट निर्माण गवर सिंह /राम सरूप | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724585 — पशु सेट निर्माण मुरारी /हलुका | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724617 — पशु शेट निर्माण पारथ /जसमन्त सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724618 — पशु शेट निर्माण राजवीर /मातादीन | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724619 — पशु शेट निर्माण रामवरन /रामकिसा | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724620 — पशु शेट निर्माण यानी/रामनरेश | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724622 — पशु शेट निर्माण जण्डेल /श्यामलाल | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993724624 — पशु शेट निर्माण सरनाम /सीताराम | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005041/IF/9993725178 — पशु सेट बकील सिंह /सहव सिंह | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/116599 — Construction of IAY House -IAY REG. NO. MP-01-005-041-001/61J | Completed | 14310 | 14863 | 2016-11-30 | 2017-10-10
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/193311 — Construction of IAY House -IAY REG. NO. MP-01-005-041-001/10 | Completed | 14310 | 13416 | 2017-06-14 | 2017-10-10
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/193313 — Construction of IAY House -IAY REG. NO. MP-01-005-041-001/61N | Completed | 14310 | 13416 | 2017-06-14 | 2017-10-10
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/193343 — Construction of IAY House -IAY REG. NO. MP-01-005-041-002/09 | Completed | 14310 | 14863 | 2016-11-30 | 2017-10-10
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/410339 — Construction of IAY House -IAY REG. NO. MP1264402 | Completed | 15030 | 14728 | 2017-02-08 | 2019-04-01
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/502894 — Construction of IAY House -IAY REG. NO. MP2290020 | Completed | 15030 | 14221 | 2017-03-08 | 2018-06-18
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/52831 — Construction of IAY House -IAY REG. NO. MP-01-005-041-001/61M | Completed | 14310 | 14863 | 2016-11-30 | 2017-10-10
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/52832 — Construction of IAY House -IAY REG. NO. MP-01-005-041-001/9 | Completed | 14310 | 14863 | 2016-11-30 | 2017-10-10
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005041/IF/IAY/760680 — Construction of IAY House -IAY REG. NO. MP2986654 | Completed | 15030 | 15078 | 2018-01-25 | 2019-01-12
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/10 — मैढ बंधान कार्य केशव/रामनाथ | Completed | 0 | 5388 | 2008-06-18 | 2010-10-25
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/14 — मेड बंधान स्‍वरूपा पुत्र भगरी | Completed | 19094 | 11997 | 2009-09-13 | 2010-10-25
MORENA / JOURA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/2 — मैढ बंधान केशव /रामनाथ | Deleted | 0 | 0 | 2007-10-17
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1701005041/LD/22012034591869 — व़क्षारोपड कार्य मलिक पुर से सिलार पुर की ओर रोड के बगल में | Closed | 426720.58 | 0 | 2023-04-01
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034954859 — Periferal ston bund nirman kary Shantidham Hotam singh ka pura Gp Birunga | Physically Completed | 1490283.03 | 1360454.73 | 2025-11-05 | 2026-05-22
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034954860 — Periferal ston bund nirman kary Heeraman mandir Gp Birunga | Physically Completed | 1494235.61 | 1424942.62 | 2025-11-05 | 2026-05-28
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034954861 — peripheral stonband nirman kary Churela bale Hanuman ji Mandir Gp Birunga | Physically Completed | 1490283.03 | 1413696.95 | 2025-11-12 | 2026-05-28
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034954862 — Periferal ston bund nirman kary khere kho Gp Birunga | Ongoing | 1490010.7 | 1255679.19 | 2026-02-08
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034959301 — Periferal ston bund nirman kary Heeraman mandir Silarpur Gp Birunga | Ongoing | 1494672.53 | 923883.04 | 2026-02-07
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034960970 — Periferal ston bund nirman kary Mahadev mandir silarpur Gp Birunga | Physically Completed | 1494672.53 | 1161877.03 | 2026-02-14 | 2026-05-28
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034960971 — Periferal ston bund nirman kary E kakch Silarpur Gp Birunga | Ongoing | 1490010.7 | 873001.59 | 2026-02-21
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034960972 — Periferal ston bund nirman kary Kali mata mandir Silarpur Gp Birunga | Physically Completed | 1494672.53 | 1179708.29 | 2026-02-07 | 2026-05-22
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034961430 — Periferal ston bund nirman kary khere kho Gp Birunga | Approved | 0 | 0 | 2025-10-02
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/LD/22012034961431 — Periferal ston bund nirman kary Mahadev ka mandir Silarpur Gp Birunga | Approved | 0 | 0 | 2025-10-02
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/28 — मैढ बंधान कार्य दशरथ/हीरालाल | Completed | 0 | 19400 | 2009-04-05 | 2010-10-25
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/3 — मेड बंधान गुडडी पुत्र ओक्षा | Completed | 26432 | 8645 | 2009-07-06 | 2010-10-25
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/31 — हाकिम सिंह / मोहकम सिंह मेड बधान निर्माण कार्य | Completed | 14250 | 10951 | 2009-09-13 | 2010-10-25
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/32 — मेड बधान निर्माण कार्य कल्‍याण पुत्र हटी सिंह | Completed | 16286 | 15428 | 2009-07-06 | 2010-10-25
MORENA / JOURA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/33 — मेड बधान निर्माण कार्य नारायण पुत्र शंकर सिंह | Completed | 13747 | 2730 | 2009-09-20 | 2010-10-25
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/7 — मैड बंधान रमेश पुत्र गिरवर | Completed | 20358 | 20330 | 2008-11-11 | 2010-10-25
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/8 — मैड बंधान लालपति पुत्र फैलीराम | Completed | 18322 | 26359 | 2008-11-19 | 2010-10-25
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005041/LD/9 — शिव सिंह / नाथू सिंह नंदन फलोउधान | Completed | 123000 | 2183 | 2008-04-11 | 2008-01-01
MORENA / JOURA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1701005041/PG/9425891885 — खेल मैदान विरूंगा | Completed | 320000 | 167064.8 | 2017-01-04 | 2018-04-06
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034164421 — panch permeswar cc kharnha nali nirman sobran singh ke makan se swaraj bhavan ki or | Deleted | 0 | 0 | 2012-10-02
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034164422 — panch permeswar cc kharnja nali nirman karya sobran ke makan se swaraj bharban ki or | Deleted | 0 | 0 | 2012-10-02
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034164424 — pach perswar cc kharnga nali nirman sobarn ke maka | Deleted | 62600 | 0 | 2012-10-02
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034187945 — सी.सी. खरंजा एवं नाली निर्माण आगनवाडी से शा.प्रा.व | Completed | 24847 | 7190 | 2013-10-02 | 2015-10-03
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034201539 — सी.सी. खरंजा एवं नाली निर्माण कार्य अथाई से जगदीश् | Completed | 52946 | 26778 | 2014-02-04 | 2015-10-03
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005041/RC/22012034206250 — पत्थर खरंजा निर्माण रमुआ धोबी के मकान से रामवरन वघ | Completed | 75000 | 57740.05 | 2014-02-20 | 2015-10-03
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005041/RC/22012034304186 — पत्थर खरंजा निर्माण भूरा सिंह के माकन से उत्तम के माकन की ओर | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1701005041/RC/22012034304703 — पत्थर खरंजा निर्माण भूरा के माकन से उत्तम सिंह के माकन की और | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1701005041/RC/22012034304713 — पत्थर खरंजा निर्माण रामबरन बघेल के मकान से काशीराम की मठिया की और | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1701005041/RC/22012034305302 — पत्थर खरंजा निर्माण शा० मा० वि० बिरंगा से शान्ती धाम तक | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005041/RC/22012034336473 — सुदूर ग्राम संपर्क सड़क अंतर्गत रोड निर्माण शा. मां.विध. बिरूंगा मैन रोड से होतम सिंह के पुरा तक | Completed | 1105600 | 962279.9 | 2017-04-26 | 2018-07-30
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034389154 — C C kharanja v nali nirman kary prajapati mohalla mai main rode se baniyaprajapati ke ghar tak | Completed | 48024 | 44196 | 2018-06-30 | 2020-12-14
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034390597 — सी सी रोड निर्माण कार्य प्रकाश के घर से परिमाल के घर होते हुए बाबू के घर तक | Completed | 92046 | 92046 | 2018-07-13 | 2020-12-14
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034390598 — सीसी रोड निर्माण कार्य जाटव मोहल्‍ला से होतम की रोड की ओर | Completed | 42630 | 32712 | 2018-07-07 | 2018-08-06
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034446594 — सी सी खरंजा व नाली कार्य केशव राठौर के घर से चित्रा के घर तक | Completed | 38280 | 37644 | 2019-03-07 | 2020-12-14
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034446596 — सी.सी खरंजा व.नाली कार्य सोनेराम के घर से कली के घर तक | Completed | 40194 | 40128 | 2019-03-07 | 2020-12-14
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005041/RC/22012034524734 — सुदुर ग्राम सम्पर्क रोड तालपुरा सिलाल पुर से सरपंच का पुरा बिरुंगा रोड की ओर | Closed | 0 | 0 | 2020-04-14
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/22012034571514 — c c karnja nirmad antai se ravinder unkar ke gar ki or virunga | Completed | 61443 | 61374 | 2021-06-06 | 2026-02-20
MORENA / JOURA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005041/RC/459 — मिटटी एंव ग्रेवल रोड बिरूगा से खिरीखोतक | Completed | 0 | 236069.3 | 2010-07-12 | 2012-09-13
MORENA / JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005041/RC/531 — सी सी खंरंजा निर्माण कार्य मेनरोड से जयनन्‍द सिंह कां पुरा | Completed | 0 | 66414 | 2011-12-23 | 2012-02-23
MORENA / JOURA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005041/RC/553 — सी.सी. खरंजा निर्माण मैन रोड से घनश्‍याम के मकानतक | Completed | 48560 | 39142 | 2012-03-21 | 2012-11-15
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005041/RC/672 — सी.सी. खरंजा निर्माण सोवरन सिंह के मकान से स्‍वराज भवन की ओर | Completed | 0 | 38410 | 2013-03-08 | 2013-03-23
MORENA / JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005041/RC/98 — सी.सी. खरंजा निर्माण कार्य बच्‍चू सिंह के मकान से पुजारी महाराज के मकान तक | Completed | 0 | 92553.58 | 2009-02-09 | 2009-06-15
MORENA / JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1701005041/RS/22012034381313 — Shochalay nirman Dangi baba mandir silarpur | Completed | 91000 | 10700 | 2017-10-31 | 2018-10-20
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701005041/RS/22012034520873 — Nadep kary 10 Selapur | Closed | 185521.76 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701005041/RS/22012034520876 — Nadep 05birunga | Closed | 92760.87 | 0 | 2021-04-14
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/145 — तालाब का जीर्णोध्‍दार कार्य सिलालपुर में मद कार्य | Deleted | 1621000 | 0 | 2008-04-01
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/20 — सोख्‍ता गडडा हेडपम्‍प का कार्य बघेल का पुरा | Completed | 417000 | 9439.89 | 2008-06-19 | 2010-04-26
MORENA / JOURA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/21 — सोक पिट शा0 मा0 विद्यालय | Completed | 417000 | 8468 | 2010-04-14 | 2016-09-27
MORENA / JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005041/WC/22012034380606 — naveen talab nirman | Closed | 0 | 0 | 2017-10-02
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1701005041/WC/22012034573507 — नवीन तालाब निर्माण कार्य सिलालपुर | Completed | 1445991.62 | 1405970 | 2020-09-25 | 2021-12-01
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012034573508 — नवीन चेक डैम निर्माण कार्य खीरी खोह के बगल मै बिरूंगा | Closed | 0 | 0 | 2020-05-09
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/WC/22012034573511 — नवीन तालाब कार्य बिरूंगा | Completed | 1463508.35 | 932080 | 2020-09-04 | 2023-08-13
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701005041/WC/22012034581394 — rapta nirman karya khiri kho birunga | Completed | 1492054.32 | 809614 | 2020-09-14 | 2025-12-22
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1701005041/WC/22012034581396 — rapta nirman karya baghel ke khet ke pass nare par birunga | Completed | 1497854.59 | 873472 | 2020-09-14 | 2026-02-20
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005041/WC/22012034738081 — ग्राम स्वराज भवन बिरुंगा | Closed | 22229.14 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005041/WC/22012034738106 — शास्कीय माध्यमिक विद्यालय बिरुंगा | Closed | 22229.14 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005041/WC/22012034738116 — शास्कीय माध्यमिक विद्यालय बिरुंगा | Closed | 22229.14 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005041/WC/22012034738123 — शास्कीय माध्यमिक विद्यालय बिरुंगा | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005041/WC/22012034738182 — शास्कीय माध्यमिक विद्यालय बिरुंगा | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005041/WC/22012034747388 — Z | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005041/WC/22012034784579 — check dem said abm jain mandir ke pas birunga | Completed | 988210.12 | 851971 | 2021-08-12 | 2023-08-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012034784621 — check dem chamar khar ke pas birunga | Completed | 997322.05 | 957119 | 2021-08-12 | 2022-04-20
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012034784623 — check dem chamar khar ke pas birunga | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012034784640 — check dem khiri khoh ke pas birunga | Closed | 988608.82 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012034784653 — check dem hotam singh ke pura ke as birunga | Physically Completed | 987811.42 | 903180 | 2021-08-10 | 2026-04-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1701005041/WC/22012034788859 — khet talab deevANSINGH | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701005041/WC/22012034800523 — khet talab deevANSINGH | Deleted | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701005041/WC/22012034800524 — khet talab deevANSINGH | Deleted | 0 | 0 | 2021-04-14
MORENA / JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/WC/22012034935246 — Talab Nirman khiri khoh ke pass virunga | Completed | 2458280.43 | 1795649.69 | 2022-04-28 | 2025-07-25
MORENA / JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/WC/22012034935253 — Talab Nirman hotam Singh ke pura ke pass virunga | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/WC/22012034935258 — Talab Nirman kharibala virunga | Completed | 2221008.51 | 1951387.66 | 2022-04-28 | 2025-07-25
MORENA / JOURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/WC/22012034935267 — Chek dem shanti dham ke bagal se virunga | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/WC/22012035012179 — Nbeen talab silarpur Chmranebali khoh | Closed | 0 | 0 | 2022-08-17
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/WC/22012035012182 — nabeen talab nirman khandi bali khoh silarpur | Closed | 0 | 0 | 2022-08-17
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1701005041/WC/22012035023581 — Amart sarovar talab khuai khoh silarpur | Completed | 1950059.12 | 1872000 | 2023-07-06 | 2024-10-28
MORENA / JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/WC/22012035061992 — amrit sarovar nirman karya chamrane bali kho silarpur | Completed | 1733002.87 | 1666844 | 2023-06-09 | 2024-10-28
MORENA / JOURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1701005041/WC/22012035061993 — amrit sarovar nirman karya khandi bali kho silarpur | Completed | 1946743.55 | 1866329.42 | 2023-06-16 | 2026-01-02
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119419 — rapata nirman karya band ke gujja kepas silarpur birnga | Closed | 0 | 0 | 2023-08-17
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119420 — rapata nirman karya band ke gujja kepas silarpur birnga | Closed | 0 | 0 | 2023-08-17
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119423 — rapata nirman karya band ke gujja kepas silarpur birnga | Completed | 1267131.82 | 1250278 | 2023-11-23 | 2025-07-25
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119442 — rapata nirman raysingh ke khet ke pass gram silarpur birunga | Completed | 1296782.62 | 1260280 | 2023-12-07 | 2025-07-25
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119450 — rapata nirman karya heerabhumiya mandir ke pass gram silarpur | Completed | 1285174.91 | 1279623 | 2023-12-14 | 2024-12-02
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119452 — rapata nirman karya heerabhumiya mandir ke pass gram silarpur | Closed | 0 | 0 | 2023-08-17
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119461 — rapata nirman karya jhore ki dangiya ke pass gram silarpur | Completed | 1290620.19 | 1227215.7 | 2023-12-21 | 2025-07-25
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119463 — rapata nirman karya lajja ke got ke pass gram silarpur birunga | Completed | 1285886.75 | 1274041 | 2023-12-21 | 2024-10-28
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119467 — rapata nirman ranveer ke khet ke pass gram silarpur birunga | Completed | 1248752.88 | 1238695.5 | 2023-10-25 | 2024-10-28
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119468 — rapata nirman karya heeraman madir ke pass gram silarpur birunga | Closed | 0 | 0 | 2023-08-17
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035119470 — rapata nirman karya heeraman madir ke pass gram silarpur birunga | Completed | 1278054.11 | 1254730 | 2023-11-19 | 2024-10-28
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012035152155 — Anicut nirman karya duda bale nare me | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012035152159 — Anicut nirman karya pamai bale me | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012035152161 — Anicut nirman karya kamaliya ke khar me | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012035152163 — Anicut nirman karya hardol ke khar me | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005041/WC/22012035152164 — Anicut nirman karya karu ke khar me | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1701005041/WC/22012035152171 — Rapta nirman kary Futi puliya ke pas | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/WC/22012035152172 — Rapta nirman kary banti ke Ghar ke pas | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/WC/22012035152173 — Rapta nirman kary banti ke Ghar ke pas | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1701005041/WC/22012035152174 — Rapta nirman kary lalla ke Ghar ke pas | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035152175 — Rapta nirman kary lambi gali bale raste pr | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701005041/WC/22012035152176 — Rapta nirman kary banteram ke pas raste par | Deleted | 0 | 0 | 2023-08-15
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229570 — Parkulesan tank raghuber ke kheta ke pass birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229574 — Prakukeshan tank nirmad karya nare ke pass briunga | Suspended | 0 | 0 | 2026-01-01
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229624 — Prakukeshan tank nirmad karya mandra ke pass birunga | Approved | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229654 — Praculationtanke nirmad karya chandaneya khoh shilarpuar | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229655 — Praculation tanke nirmad karya ram khoh | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229657 — Praculation tanke nirmad karya bar bali kho | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229752 — Percolation Talab nirman kary Gaiya kho Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229756 — Percolation Talab nirman kary sheetla kho Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229757 — Percolation Talab nirman kary sheetla kho me Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229758 — Percolation Talab nirman kary khirkai ke pass Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229760 — Percolation Tank nirman kary Birunga bali kho Gp Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229761 — Percolation Tank nirman kary Birunga bali kho Gp Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035229762 — Percolation talab nirman kary silarpur bali kho Gp Birunga | Deleted | 0 | 0 | 2024-10-02
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035249766 — Talab nirman kary chaviram ke khet ke paas Birunga | Physically Completed | 1493585.83 | 1438606.95 | 2025-03-20 | 2026-04-16
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035249768 — Talab nirman kary bhagvan singh ke khet ke paas Birunga | Physically Completed | 1498233.28 | 1441212.39 | 2025-03-20 | 2026-04-16
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035249770 — Amrat sarovar nirman kary gonje bali kho silarpur | Approved | 0 | 0 | 2025-01-27
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035249773 — talab nirman kary ramkho silarpur | Suspended | 0 | 0 | 2026-01-01
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035249775 — talab nirman kary shyam kho silarpur | Approved | 0 | 0 | 2025-01-27
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035249776 — talab nirman kary chandaniya kho silarpur | Approved | 0 | 0 | 2025-01-27
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035284076 — khet talab nirman kary yogendra /Ramnaresh gp birunga | Approved | 370607.74 | 0 | 2025-04-14
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035284085 — khet talab nirman kary Rajendra ke khet par gp birunga | Closed | 370607.74 | 0 | 2025-05-04
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701005041/WC/22012035302111 — Talab nirmad karya Toder par silalapura | Physically Completed | 1470270.92 | 1421342.15 | 2025-06-28 | 2026-04-16
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1701005041/WC/22012035302316 — Dug well Recharge bade kuaa ke pass gp birunga | Completed | 25899.46 | 12525.12 | 2025-05-18 | 2025-12-22
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1701005041/WC/22012035302333 — Dug well Recharge bholebaba ke mander ke pass silrpur | Completed | 25899.46 | 7045.92 | 2025-05-18 | 2025-12-22
MORENA / JOURA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005041/WH/198 — तालाव गहरीकरण सिलारपुरा | Completed | 0 | 78100 | 2010-04-21 | 2010-07-08
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005041/WH/22012034453154 — talab ripering hotamsingh ke pura ke pas | Closed | 0 | 0 | 2021-10-04
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005041/WH/22012034453203 — Talab renovation karya Silarpur | Completed | 749274.2 | 698022 | 2022-02-12 | 2022-05-09
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1701005041/WH/22012034909168 — तालाब जीर्णोंद्धार कार्य सिलापुर | Closed | 662869 | 0 | 2021-10-02
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1701005041/WH/22012034936333 — Nbeen talab silarpur Chmranebali khoh | Closed | 0 | 0 | 2022-08-17
MORENA / JOURA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701005/WC/195 — मद में सिलालपुर तालाव का जीर्णोध्‍दार कार्य | Completed | 0 | 15328 | 2008-08-25 | 2013-08-18