## Work List
Exported on: 2026-09-04 04:33:24
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KHANETA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005054/AV/22012034393158 — आंगनवाडी भवन निर्माण कार्य खनेता | Completed | 180000 | 129128 | 2019-02-01 | 2020-12-10
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701005054/AV/22012034462970 — आंगनवाडी भवन निर्माण कार्य प्रभूराम सिंह का पुरा | Completed | 180000 | 130960 | 2019-08-13 | 2021-03-19
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034568496 — सिग्रेगेशन कार्य निर्माण खनेता | Completed | 623292.23 | 514414.32 | 2021-10-11 | 2023-03-21
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034568497 — सिग्रेगेशन कार्य निर्माण खनेता | Closed | 0 | 0 | 2021-04-29
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034613035 — मा की बगिया प्रा वि प्रभु सिंह का पूरा खनेता | Completed | 8137.24 | 3860 | 2022-01-17 | 2022-10-21
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034613037 — कार्य का नाम मा की बगिया प्रा. वि.गड़ेराम का पूरा | Completed | 4068.62 | 1930 | 2022-01-17 | 2022-11-11
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034613038 — कार्य का नाम मा की बगिया प्रा वि दोहरे का पूरा खनेता | Completed | 4068.62 | 1930 | 2022-01-17 | 2022-11-11
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034613307 — कार्य का नाम ma ki बगिया प्रा वि खनेता | Completed | 4068.62 | 1930 | 2022-01-17 | 2022-11-11
MORENA / JOURA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1701005054/AV/22012034613308 — कार्य का नाम ma ki बगिया प्रा वि खनेता | Closed | 0 | 0 | 2021-11-24
MORENA / JOURA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005054/DP/180 — शांतीधाम निर्माण खनेता | Completed | 400800 | 236763.38 | 2011-12-24 | 2015-03-03
MORENA / JOURA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1701005054/DP/22012034229837 — शान्तिधाम निर्माण कार्य खनेता | Closed | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005054/FP/22012034203358 — पक्की नाली निर्माण कार्य सड़क से नदी की ओर | Completed | 1262000 | 1276436.79 | 2016-01-04 | 2021-08-22
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034204135 — पक्की नाली निर्माण कार्य गांडेराम का पूरा | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034362325 — पत्थर नाला निर्माण कार्य खनेता | Deleted | 0 | 0 | 2018-10-02
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034362326 — पत्थर नाला निर्माण कार्य कुम्हेरी | Suspended | 0 | 0 | 2020-12-22
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005054/FP/22012034365917 — नाला निर्माण कार्य शा0प्रा0वि0 कोक सिंह के पूरा से रामवीर एवं खनेता की ओर | Completed | 1397785.1 | 1304125 | 2020-06-18 | 2023-01-15
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005054/FP/22012034365918 — नाला निर्माण कार्य माता मंदिर से राधेश्याम कुशवाह के मकान तक खनेता | Completed | 1396879.94 | 1371948.5 | 2020-06-17 | 2021-06-21
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034367681 — पत्थर नाला निर्माण कार्य सिद्द्बबा से चिमनी की ओर गदेराम का पूरा खनेता | Deleted | 0 | 0 | 2020-01-26
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034367682 — पत्थर नाला निर्माण कार्य निहाल सिंह के माकन से राधान गुर्जर के माकन तक चक का पूरा खनेता | Deleted | 0 | 0 | 2020-01-26
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034369185 — रपटा कार्य प्रभु सिंह का पूरा खनेता | Completed | 1496538.69 | 1458316.6 | 2021-03-02 | 2021-08-02
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034369186 — नाला निर्माण कार्य नरेंद्र के मकान से तलाव तक खनेता | Deleted | 0 | 0 | 2020-11-23
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034625003 — पत्थर नाला निर्माण कार्य माता मंदिर से चिमनी की ओर गदेराम का पूरा खनेता | Completed | 1482058.64 | 1360415 | 2021-07-11 | 2022-08-27
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034625071 — नाला निर्माण कार्य प्रेम सिंह के घर से पोखर एवम् रामबीर के मकान की और | Completed | 1477121.77 | 1139743 | 2021-06-17 | 2025-02-17
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034625072 — नाला निर्माण कार्य निहाल सिंह कुशवाह के मकान से दिनेश कुशवाह के मकान की और चक का पूरा | Completed | 1477121.77 | 1393826.5 | 2021-06-17 | 2023-01-15
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034625819 — नाला निर्माण कार्य राजाराम के घर से रपटा की और खनेता | Completed | 1482058.64 | 1409922 | 2021-08-22 | 2022-04-27
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034625820 — रपटा कार्य निर्माण खनेता | Deleted | 0 | 0 | 2021-04-29
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034625821 — नाला निर्माण कार्य नेमी बरेठा के घर से शांति धाम तक खनेता | Completed | 1474392.44 | 1313100 | 2021-09-26 | 2023-01-15
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034626322 — नाला निर्माण कार्य हरिओम के माकन से कुमेर एवं महेश माहौर के गोंडा से नदी की और | Completed | 1471986.85 | 1342484 | 2022-03-14 | 2025-02-17
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034626323 — रपटा निर्माण कार्य रंचित्रा के गोत के पास एवं ाशो माता के मंदिर के पास | Deleted | 0 | 0 | 2021-04-29
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034626346 — रपटा निर्माण कार्य नरुआ पर गदेराम का पूरा खनेता | Deleted | 0 | 0 | 2021-04-15
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005054/FP/22012034626918 — नाला निर्माण कार्य कप्तान के घर से जबर सिंह के माकन की और चक का पूरा खनेता | Ongoing | 979571.49 | 662062.12 | 2022-01-31
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034628567 — पत्थर नाला निर्माण कार्य दर्शन कुशवाह के माकन से स्कूल की और | Deleted | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629027 — नाला निर्माण कार्य सुरेंद्र के माकन सेरामोतार के कहेत की ऒर गदेराम का पूरा खनेता | Completed | 1476411.62 | 1328132 | 2022-09-08 | 2023-12-14
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629028 — नाला निर्माण कार्य सियाराम के माकन से अमृत के माकन की ऒर प्रभु सिंह का पूरा खनेता | Completed | 1482813.81 | 1398356 | 2022-05-23 | 2025-10-10
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629029 — नाला निर्माण कार्य हरी सिंह के माकन से केशव के खेत की ऒर प्रभु सिंह का पूरा खनेता | Completed | 1489496.92 | 1415778 | 2023-08-09 | 2025-10-10
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629030 — नाला निर्माण कार्य हरी सिंह के माकन से केशव के खेत की ऒर प्रभु सिंह का पूरा खनेता | Deleted | 0 | 0 | 2022-04-14
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629031 — नाला निर्माण कार्य राधेश्याम कुशवाह के माकन से ईशाव खान की ऒर खनेता | Completed | 1491979.42 | 1392482 | 2022-06-07 | 2024-11-03
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629564 — पत्थर नाला निर्माण कार्य रामचित्र के मकान से रामौतार बरेठा के मकान तक | Completed | 1394052.18 | 1268558 | 2022-10-08 | 2025-02-17
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034629566 — रपटा निर्माण कार्य रामचित्र के मकान के सामने खनेता | Deleted | 0 | 0 | 2022-08-16
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1701005054/FP/22012034630764 — पत्थर नाला निर्माण कार्य मनोज राठौर के माकन से ब्रजेश जैन के माकन तक खनेता | Completed | 1477999.06 | 1377196 | 2023-06-19 | 2023-12-14
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005054/FP/22012034630765 — पत्थर नाला निर्माण कार्य कल्लू यादव के माकन से पोखर तक खनेता | Ongoing | 1480655.5 | 135425 | 2023-06-19
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701005054/FP/22012034630766 — पत्थर नाला निर्माण पंडित के माकन से रामवीर एवं पुलिया तक खनेता | Completed | 1483311.95 | 1348919 | 2023-05-01 | 2024-06-03
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1701005054/FP/22012034630802 — पत्थर नाला निर्माण कार्य पंचम गुर्जर के मकान से परशुराम के मकान की ओर खनेता | Completed | 1485968.39 | 1402290 | 2023-06-18 | 2024-06-03
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034630803 — पत्थर नाला निर्माण कार्य सुरेंद्र गुर्जर के मकान से नाला की ओर खनेता | Completed | 1488624.84 | 1377475 | 2023-06-26 | 2024-06-03
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034631532 — पत्थर नाला निर्माण कार्य प्रेम सिंह बघेल के मकान से पंकज जैन के मकान तक खनेता | Completed | 1450320.97 | 1375025 | 2023-06-19 | 2025-01-20
MORENA / JOURA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034631533 — पत्थर नाला निर्माण कार्य प्रेम सिंह बघेल के मकान से पंकज जैन के मकान तक खनेता | Deleted | 0 | 0 | 2022-10-02
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034631534 — पत्थर नाला निर्माण कार्य भगवान सिंह माहौर के मकान कल्याण मची के मकान तक खनेता | Ongoing | 1452913.44 | 1122491.84 | 2023-06-19
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034631535 — पत्थर नाला निर्माण कार्य ग्याशी राम कुशवाह के मकान सेवाराम कुशवाह के मकान तक तक खनेता | Completed | 1455505.89 | 1358448 | 2023-06-19 | 2025-02-17
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034634389 — पत्थर नाला निर्माण कार्य सुघर सिंह माहोर के मकान से कुमार सिंह बघेल के मकान की ओर खनेता | Completed | 1441129.38 | 1341739 | 2023-08-31 | 2025-02-17
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701005054/FP/22012034634390 — पत्थर नाला निर्माण कार्य जसमंत माहोर के मकान से केदार बघेल के मकान तक खनेता | Completed | 1440528.26 | 1359561 | 2023-08-31 | 2025-02-17
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005054/FP/9977521533 — पत्‍थर नाली निर्माण लाखन सिंह के घर से कोक सिंह के पुरा तक | Deleted | 0 | 0 | 2013-01-26
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701005054/FP/9977522504 — पत्थर नाली निर्माण कोकसिंह का पुरा से खनेता कि ओर | Completed | 174403 | 14287 | 2014-03-05 | 2016-12-18
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1701005054/IC/22012034885042 — शांतिधाम निर्माण कार्य ग्राम खनेता | New | 0 | 0 | 2024-06-10
MORENA / JOURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1701005054/IC/22012034885043 — शांतिधाम निर्माण कार्य प्रभु सिंह का पूरा खनेता | New | 0 | 0 | 2024-06-10
MORENA / JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of Canal, Distributary and Minor / Construction of distributary Canal for Community | Construction of Canal | 1701005054/IC/9993638067 — वाटर कोर्स फील्ड चैनल निर्माण कार्य -8 आर /एमबीसी(लम्बाई ३२४० मी. ) Santha 2036 Mahajpur | Completed | 2637000 | 2501568.36 | 2017-06-12 | 2018-03-31
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005054/IF/22012034355576 — सार्वजनिक वृक्ष रोपण कार्य शांतिधाम प्रभु सिंह का पुरा | Completed | 335000 | 6878 | 2017-07-01 | 2020-12-12
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701005054/IF/22012034368741 — सड़क किनारे वृक्ष रोपण कार्य गाढेराम पुरा से खनेता रोड पर | Completed | 335000 | 6878 | 2017-07-01 | 2020-12-12
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764805 — नाडेप घरेलू कार्य राकेश बरेठा /भरोशी प्रभु सिंह का पूरा | Closed | 18552.12 | 0 | 2025-10-13
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764819 — नाडेप घरेलू कार्य दिनेश बरेठा /भारोशी प्रभु सिंह का पूरा | Closed | 18552.12 | 0 | 2025-10-13
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764834 — नाडेप घरेलू कार्य नरेश बरेठा /भारोशी प्रभु सिंह का पूरा | Closed | 18552.12 | 0 | 2025-10-13
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764835 — नाडेप घरेलू कार्य नरेश बरेठा /भारोशी प्रभु सिंह का पूरा | Deleted | 0 | 0 | 2021-04-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764856 — नाडेप घरेलू कार्य रामौतार /हजारीलाल गड़ेराम का पूरा का पूरा | Completed | 18374.27 | 15615 | 2021-06-17 | 2024-06-03
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764867 — नाडेप घरेलू कार्य रामकेश /नबल गेडराम का पूरा | Completed | 18374.27 | 15615 | 2021-06-17 | 2024-06-03
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764876 — नाडेप घरेलू कार्य रघुनाथ यादव /स्यमलाल खनेता | Deleted | 0 | 0 | 2021-04-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034764886 — नाडेप घरेलू कार्य विद्याराम यादव /स्यामलाल खनेता | Deleted | 0 | 0 | 2021-04-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034812740 — घरेलु नाडेप कार्य संख्या 8 खनेता | Completed | 148417.37 | 143911 | 2021-09-05 | 2022-08-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034812745 — घरेलु नाडेप कार्य संख्या 7 खनेता | Completed | 129869.58 | 115890 | 2021-09-19 | 2022-08-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1701005054/IF/22012034812751 — सामुदायिक नाडेप कार्य संख्या04 खनेता | Deleted | 0 | 0 | 2021-04-29
MORENA / JOURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701005054/IF/22012035125886 — वृक्षरोपण कार्य पंचायत भवन एवं रोड किनारे खनेता | Deleted | 0 | 0 | 2023-04-14
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701005054/IF/22012035505413 — डगवेल रीचार्ज निर्माण कार्य प्रभु सिंह का पूरा खनेता | Deleted | 0 | 0 | 2025-04-14
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701005054/IF/22012035505483 — डगवेल रीचार्ज निर्माण कार्य खनेता | Deleted | 0 | 0 | 2025-04-14
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1701005054/IF/22012035505496 — डगवेल रीचार्ज निर्माण कार्य खनेता | Deleted | 0 | 0 | 2025-04-14
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005054/IF/9926713065 — पशु शैड निर्माण जोधा / चतुरी लाल | Completed | 80000 | 46775 | 2014-03-05 | 2016-01-19
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005054/IF/9926713089 — पशु शैड निर्माण सोनेराम / हुकमसिंह | Completed | 80000 | 28767 | 2014-03-05 | 2016-04-12
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005054/IF/9926713208 — पशु शैड निर्माण रामेस्वर सिंह / रामसिंह | Completed | 80000 | 42055 | 2014-03-05 | 2016-04-11
MORENA / JOURA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005054/IF/9926713214 — पशु शैड निर्माण नरवीर / सोवरन | Completed | 80000 | 43224 | 2014-03-05 | 2016-12-18
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005054/IF/9993725712 — पशु शैड निर्माण कार्य लज्जाराम पुत्र लोंडूराम | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701005054/IF/9993726968 — पशु शेड चेतराम पुत्र फेरन | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1120596 — Construction of IAY House -IAY REG. NO. MP1887240 | Completed | 15480 | 15492 | 2018-01-20 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1131098 — Construction of IAY House -IAY REG. NO. MP2412852 | Completed | 15480 | 22872 | 2017-08-28 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1132908 — Construction of IAY House -IAY REG. NO. MP2537509 | Completed | 15480 | 15480 | 2017-08-28 | 2018-04-12
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1133009 — Construction of IAY House -IAY REG. NO. MP2544924 | Completed | 15480 | 16608 | 2017-08-28 | 2018-07-19
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1137818 — Construction of IAY House -IAY REG. NO. MP2947002 | Completed | 15480 | 15480 | 2017-10-02 | 2018-04-12
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1138372 — Construction of IAY House -IAY REG. NO. MP2993699 | Completed | 15480 | 15492 | 2017-08-28 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1138619 — Construction of IAY House -IAY REG. NO. MP3018160 | Completed | 15480 | 15492 | 2018-01-20 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1142293 — Construction of IAY House -IAY REG. NO. MP3372121 | Completed | 15480 | 20832 | 2018-01-20 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1157762 — Construction of IAY House -IAY REG. NO. MP3414496 | Completed | 15480 | 20820 | 2018-01-20 | 2018-07-22
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1157872 — Construction of IAY House -IAY REG. NO. MP3422150 | Completed | 15480 | 15624 | 2018-01-20 | 2018-07-19
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/116624 — Construction of IAY House -IAY REG. NO. MP-01-005-054-001/31 | Completed | 14310 | 14200 | 2016-11-28 | 2018-06-17
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/116625 — Construction of IAY House -IAY REG. NO. MP-01-005-054-001/35 | Completed | 14310 | 13455 | 2016-11-28 | 2018-06-17
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1532138 — Construction of IAY House -IAY REG. NO. MP2359312 | Completed | 15480 | 18792 | 2018-07-26 | 2018-11-14
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1563409 — Construction of IAY House -IAY REG. NO. MP2135741 | Completed | 15480 | 14616 | 2018-07-26 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1576431 — Construction of IAY House -IAY REG. NO. MP2358960 | Completed | 15480 | 15764.4 | 2018-07-07 | 2019-03-22
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1755594 — Construction of IAY House -IAY REG. NO. MP2359393 | Completed | 15660 | 15660 | 2018-07-26 | 2018-10-19
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1755848 — Construction of IAY House -IAY REG. NO. MP2494140 | Completed | 15660 | 15660 | 2018-07-26 | 2018-08-15
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1755927 — Construction of IAY House -IAY REG. NO. MP2526414 | Completed | 15660 | 14964 | 2018-10-25 | 2019-02-27
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1755943 — Construction of IAY House -IAY REG. NO. MP2534902 | Completed | 15660 | 20880 | 2018-07-26 | 2018-08-31
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1755967 — Construction of IAY House -IAY REG. NO. MP2541246 | Completed | 15660 | 15816 | 2019-02-06 | 2019-05-16
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1756131 — Construction of IAY House -IAY REG. NO. MP2610890 | Completed | 15660 | 15720 | 2019-02-06 | 2019-05-16
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1757072 — Construction of IAY House -IAY REG. NO. MP2989626 | Completed | 15660 | 14616 | 2018-08-31 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1757083 — Construction of IAY House -IAY REG. NO. MP2994621 | Completed | 15660 | 14964 | 2019-01-17 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1765492 — Construction of IAY House -IAY REG. NO. MP3405920 | Completed | 15660 | 16704 | 2018-07-26 | 2018-08-31
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1765803 — Construction of IAY House -IAY REG. NO. MP3454758 | Completed | 15660 | 15672 | 2018-11-15 | 2019-05-20
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1765912 — Construction of IAY House -IAY REG. NO. MP3478433 | Completed | 15660 | 14616 | 2018-07-26 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1767535 — Construction of IAY House -IAY REG. NO. MP3444699 | Completed | 15660 | 15696 | 2018-10-01 | 2019-05-16
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1767546 — Construction of IAY House -IAY REG. NO. MP3454778 | Completed | 15660 | 16704 | 2018-07-26 | 2018-10-20
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1770237 — Construction of IAY House -IAY REG. NO. MP1007364 | Completed | 15660 | 15660 | 2019-01-02 | 2019-02-23
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1770238 — Construction of IAY House -IAY REG. NO. MP1008158 | Completed | 15660 | 14964 | 2019-01-28 | 2019-04-01
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1870205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3938769 | Completed | 15660 | 17748 | 2018-11-15 | 2019-01-04
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1870905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3963729 | Completed | 15660 | 17748 | 2018-10-11 | 2019-01-04
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1870919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3969092 | Completed | 15660 | 15660 | 2018-10-11 | 2019-04-21
MORENA / JOURA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1870923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3969229 | Completed | 15660 | 14784 | 2019-04-15 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1870927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3970221 | Completed | 15660 | 15696 | 2019-02-06 | 2019-04-25
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1882804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3016937 | Completed | 15660 | 15720 | 2018-12-02 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1883182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3970147 | Completed | 15660 | 15660 | 2018-08-23 | 2018-09-15
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1892293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4149478 | Completed | 15660 | 14616 | 2019-01-02 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1892310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4156185 | Completed | 15660 | 15660 | 2018-11-15 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1892517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4248266 | Completed | 15660 | 15684 | 2019-01-17 | 2019-04-25
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/1914835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4174848 | Completed | 15660 | 12528 | 2019-01-02 | 2019-05-20
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/205520 — Construction of IAY House -IAY REG. NO. MP-01-005-054-001/32 | Completed | 15030 | 14195 | 2016-11-28 | 2018-06-17
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/378569 — Construction of IAY House -IAY REG. NO. MP1668823 | Completed | 15030 | 14422 | 2017-01-30 | 2018-05-03
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/378920 — Construction of IAY House -IAY REG. NO. MP1710173 | Completed | 15030 | 15484 | 2017-01-30 | 2018-04-12
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/488928 — Construction of IAY House -IAY REG. NO. MP2119621 | Completed | 15030 | 14452 | 2017-01-30 | 2017-04-10
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/489302 — Construction of IAY House -IAY REG. NO. MP2123363 | Completed | 15030 | 15155 | 2017-01-30 | 2019-02-06
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/596206 — Construction of IAY House -IAY REG. NO. MP1693523 | Completed | 15030 | 14452 | 2017-02-06 | 2019-05-10
MORENA / JOURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/615291 — Construction of IAY House -IAY REG. NO. MP2119499 | Completed | 15030 | 14452 | 2017-02-13 | 2019-05-10
MORENA / JOURA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/691908 — Construction of IAY House -IAY REG. NO. MP1313507 | Completed | 15030 | 13200 | 2019-09-25 | 2019-10-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/719981 — Construction of IAY House -IAY REG. NO. MP1709629 | Completed | 15030 | 15480 | 2017-05-22 | 2018-04-12
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/720071 — Construction of IAY House -IAY REG. NO. MP1711921 | Completed | 15030 | 15660 | 2018-08-23 | 2019-02-17
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/720519 — Construction of IAY House -IAY REG. NO. MP1722618 | Completed | 15030 | 15768 | 2019-01-28 | 2019-05-16
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/720857 — Construction of IAY House -IAY REG. NO. MP1727044 | Completed | 15030 | 15660 | 2018-10-11 | 2019-01-19
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/721061 — Construction of IAY House -IAY REG. NO. MP1731663 | Completed | 15030 | 14792 | 2017-05-15 | 2017-11-17
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/735508 — Construction of IAY House -IAY REG. NO. MP2119047 | Completed | 15030 | 16732 | 2017-05-15 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/735509 — Construction of IAY House -IAY REG. NO. MP2119080 | Completed | 15030 | 14620 | 2017-05-15 | 2018-03-13
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/736007 — Construction of IAY House -IAY REG. NO. MP2130878 | Completed | 15030 | 19764 | 2018-01-20 | 2018-07-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/736020 — Construction of IAY House -IAY REG. NO. MP2131210 | Completed | 15030 | 16572 | 2017-05-22 | 2018-07-26
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/736327 — Construction of IAY House -IAY REG. NO. MP2136528 | Completed | 15030 | 15720 | 2018-01-20 | 2019-10-08
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/736388 — Construction of IAY House -IAY REG. NO. MP2138344 | Completed | 15030 | 14556 | 2017-05-22 | 2018-07-15
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/739336 — Construction of IAY House -IAY REG. NO. MP2212776 | Completed | 15030 | 18672 | 2018-01-20 | 2018-07-19
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/742262 — Construction of IAY House -IAY REG. NO. MP2293588 | Completed | 15030 | 16536 | 2017-05-22 | 2018-07-19
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/743574 — Construction of IAY House -IAY REG. NO. MP2333079 | Completed | 15030 | 14620 | 2017-05-15 | 2017-11-17
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/743607 — Construction of IAY House -IAY REG. NO. MP2333907 | Completed | 15030 | 15534 | 2018-07-07 | 2019-04-25
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/744038 — Construction of IAY House -IAY REG. NO. MP2346082 | Completed | 15030 | 14592 | 2017-05-22 | 2018-07-22
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/758913 — Construction of IAY House -IAY REG. NO. MP2907933 | Completed | 15030 | 15452 | 2019-01-28 | 2019-05-16
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/759798 — Construction of IAY House -IAY REG. NO. MP2947266 | Completed | 15030 | 15660 | 2018-11-04 | 2019-04-21
MORENA / JOURA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/759799 — Construction of IAY House -IAY REG. NO. MP2947298 | Completed | 15030 | 14784 | 2019-04-22 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/760253 — Construction of IAY House -IAY REG. NO. MP2968766 | Completed | 15030 | 14616 | 2019-01-28 | 2019-05-10
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/761535 — Construction of IAY House -IAY REG. NO. MP3033277 | Completed | 15030 | 15368 | 2019-02-06 | 2019-05-20
MORENA / JOURA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/765277 — Construction of IAY House -IAY REG. NO. MP3204180 | Completed | 15030 | 14784 | 2019-04-22 | 2019-05-10
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/765474 — Construction of IAY House -IAY REG. NO. MP3213608 | Completed | 15030 | 15480 | 2017-05-22 | 2018-04-12
MORENA / JOURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/765668 — Construction of IAY House -IAY REG. NO. MP3221811 | Completed | 15030 | 15780 | 2018-11-12 | 2019-05-16
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/817318 — Construction of IAY House -IAY REG. NO. MP1987954 | Completed | 15480 | 20640 | 2017-05-22 | 2018-04-12
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/818925 — Construction of IAY House -IAY REG. NO. MP2128275 | Completed | 15480 | 14620 | 2017-05-15 | 2018-03-13
MORENA / JOURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701005054/IF/IAY/818942 — Construction of IAY House -IAY REG. NO. MP2129541 | Completed | 15480 | 15462 | 2018-01-20 | 2018-04-25
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1701005054/LD/22012034956728 — पेरिफेरल स्टोन बॉन्ड शांति धाम खनेता | Deleted | 0 | 0 | 2025-04-14
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034956737 — periferal ston bund shanti dham khaneta | Ongoing | 1482421.93 | 1194053.78 | 2025-09-20
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034958635 — periferal ston bund | Deleted | 0 | 0 | 2025-08-18
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034958658 — periferal ston bund mata mandir bar ka pura | Ongoing | 1471041.85 | 1209733.18 | 2025-11-15
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034959753 — feripheral bund nirman kary shanti dham kabarsthan khaneta | Deleted | 0 | 0 | 2025-10-03
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034959754 — feripheral bund nirman kary shanti dham prabhu singh ka pura | Ongoing | 1457088.29 | 1348980.62 | 2026-02-03
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034959755 — feripheral bund nirman kary kabarsthan khaneta | Ongoing | 1475637.66 | 1356347.17 | 2026-02-03
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034960448 — periferal ston bund mata mandir bar ka pura | Deleted | 0 | 0 | 2025-10-02
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701005054/LD/22012034960573 — feripheral bund nirman kary mandir khaneta | Ongoing | 1487429.84 | 127655.1 | 2026-02-24
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1701005054/LD/3799387256 — khel maidan kheneta | Deleted | 0 | 0 | 2013-01-26
MORENA / JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005054/RC/13 — मिटटी मोरम रोड सुमावली रोड से शमशान घाट तक | Completed | 0 | 82304 | 2008-07-21 | 2015-07-01
MORENA / JOURA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005054/RC/151 — सी सी खरंजा शा. शाला भवन से लक्ष्‍मी के मकान तक | Completed | 0 | 78249 | 2009-08-24 | 2009-10-09
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034161348 — सी.सी. खरंजा भगरी के घर से फूल सिंह के घर तक | Deleted | 0 | 0 | 2013-01-26
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034164515 — पंच परमेश्‍वर सीसी खरंजा नाली निर्माण मुख्‍य मार्ग | Completed | 64228 | 56626 | 2013-06-03 | 2014-06-25
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034211505 — मिट्टी ग्रेवल रोड मैन रोड से प्रेम सिंह के घर के पास खादर कि ओर | Completed | 1251641 | 518908 | 2014-03-05 | 2017-01-21
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034211519 — सी.सी.रोड निर्माण भगवंत के घर से दर्शन लाल के घर क | Completed | 69010 | 37011 | 2014-03-05 | 2014-06-25
MORENA / JOURA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034229328 — सी. सी खरंजा नि. मेनरोड पन्नालाल के घर तक | Completed | 44743 | 25277 | 2014-09-15 | 2015-02-01
MORENA / JOURA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034229332 — सी.सी. खरंजा निर्माण व् नाली निर्माण गजेन्द्र के म | Completed | 21298 | 10519 | 2014-09-22 | 2015-02-01
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034288607 — पत्थर खरंजा (मैंन रोड से रमेश के घर तक ) | Completed | 562500 | 499443.82 | 2015-11-09 | 2017-04-02
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034295175 — सी सी खरंजा निर्माण श्यामवीर व विष्णु पंडित की गली खनेता | Completed | 54342 | 52947 | 2016-01-04 | 2016-08-08
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034307761 — पत्थर खरंजा निर्माण कोक सिंह के पूरा से राधे के मकान की ओर | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034307762 — पत्थर खरंजा निर्माण मिडिल स्कूल से शमशान घाट तक | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034307763 — पत्थर खरंजा निर्माण स्कूल से रमेश बरेठा के मकान तक रूप सिंह का पूरा | Deleted | 0 | 0 | 2016-01-26
MORENA / JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034344624 — सी सी खरंजा एवं नाली निर्माण रामेस्वर के घर से सुरेंद्र के माकन तक गडेराम का पूरा खनेता | Completed | 82503 | 80668 | 2017-07-24 | 2017-09-22
MORENA / JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034345365 — सी सी खरंज गसेरम क पुर | Deleted | 0 | 0 | 2017-05-30
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034382042 — सी सी खरंजा निर्माण हरी सिंह के माकन से स्कूल तक प्रभु सिंह का पूरा | Completed | 116058 | 113316 | 2018-12-29 | 2020-02-09
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034433176 — सी सी खरंजा ि‍निर्माण कार्य परसुराम के घर से वेताल गुर्जर के घर तक | Completed | 78822 | 77256 | 2018-12-29 | 2020-02-02
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034433487 — सी सी खरंजा निर्माण कार्य अमर सिंह गुर्जर के मकान से रामरूप व मेन रोड से स्‍कूल तक कोक सिंह का | Completed | 73872 | 64902 | 2019-01-25 | 2019-08-04
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034433489 — सी सी खरंजा निर्माण कार्य केदार के मकान से संजय के मकान तक प्रभू सिंह का पुरा | Completed | 25875 | 18792 | 2019-02-10 | 2019-09-09
MORENA / JOURA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034433490 — सी सी खरंजा निर्माण कार्य अमर सिंह के मकान से रामस्‍वरूप व ईस्‍वरिया के मकान त प्रभू सिंह का पुरा | Deleted | 126960 | 0 | 2019-02-05
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034463503 — सी सी खरंजा व नाली निर्माण कार्य नबल सिंह कुशवाह के मकान से जाहार सिंह कुश्‍वाह के मकान तक | Completed | 25009 | 24828 | 2020-03-09 | 2020-05-22
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034463522 — सी सी खरंजा निर्माण कार्य राजेन्‍द्र के घर से राधेश्‍याम का घर दोहरा का पुरा | Completed | 31294 | 31152 | 2019-08-06 | 2020-03-01
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034474251 — सी सी रोड़ निर्माण परसराम गुर्जर के देवताओं के चबूतरों से परिमाल गुर्जर एवं स्‍कूूूलकी ओर | Completed | 77872 | 75680 | 2019-09-30 | 2020-01-01
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1701005054/RC/22012034476023 — सी सी रोड निर्माण मरम्‍मत कार्य मनोज राठौर के मकान से प्रहलाद बरैठा एवं दर्शन वाली गली | Completed | 40365 | 40128 | 2019-11-01 | 2019-12-01
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1701005054/RC/22012034476025 — सी सी रोड निर्माण मरम्‍मत कार्य ओमी जैन से मातादीन एवं लक्ष्‍मण राठौर वाली गली | Completed | 24840 | 24816 | 2019-09-30 | 2020-02-02
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1701005054/RC/22012034476028 — सी सी खरंजा मरम्‍मत निर्माण कार्य बंटी जैन की दुकान से मुकेश माहाैैैरके घर तक | Physically Completed | 39330 | 73448 | 2019-09-30 | 2021-03-19
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034476030 — सी सी रोड निर्माण कार्य बदन सिंह बरेठा के मकान से माता मंदिर एवं आंगनवाडी से रणवीर गुर्जर के मका | Completed | 38250 | 38016 | 2019-11-27 | 2020-04-01
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034507378 — सी सी खरंजा निर्माण कार्य भूकन के मकान से स्‍वराज भवन तक | Completed | 64800 | 56672 | 2019-11-27 | 2020-03-20
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034507379 — सी सी रोड निर्माण कार्य मौजीराम के मकान से पूरन जैन हनुमान मंदिर एवं महेष सविता के मकान तक | Completed | 82080 | 32841.6 | 2019-11-27 | 2020-05-05
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034507390 — सी सी रोड निर्माण कार्य रमेश के मकान से मुरारी के मकान तक दोहरे का पुरा | Completed | 45360 | 46572 | 2019-11-27 | 2020-12-10
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034507391 — सी सी रोड निर्माण कार्य रतन ि‍सिंह के मकान से मोहन ि‍सिंह के मकान तक | Completed | 25920 | 17952 | 2019-11-27 | 2020-02-02
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034507392 — सी सी रोड निर्माण कार्य विद्याराम के मकान से महैन्‍द्र के मकान तक | Deleted | 21600 | 0 | 2019-08-15
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034507393 — सी सी रोड निर्माण कार्य अमर ि‍सिंह जाटव के घर से रामस्‍वरूप व ईस्‍वरिया भूरा के मकान तक | Completed | 126960 | 126368 | 2019-11-27 | 2020-01-15
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034525342 — एप्रोच रोड निर्माण कार्य प्रभु के पूरा से शान्तिधाम | Completed | 1228612.04 | 1215213.51 | 2020-06-29 | 2022-08-04
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034528081 — Sudur sadak nirman Puliya se Paidal ke Kyaa ki or khaneta | Deleted | 0 | 0 | 2020-04-14
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034529098 — सुदूर सडक पुलिया से ऐदल के कुआ की और खनेता | Completed | 2593395.17 | 2610004.83 | 2020-08-17 | 2023-01-25
MORENA / JOURA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034535785 — नवीन सुदूर सड़क खनेता गांव से करतार गुर्जर के माकन तक | Deleted | 0 | 0 | 2020-01-26
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542630 — सी सी रोड निर्माण कार्य घनश्याम के मकान से स्कूल एवं जुभान मंदिर तक | Deleted | 72675 | 0 | 2020-04-14
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542635 — सी सी रोड निर्माण कार्य जनक सिंह बघेल के मकान से बाबू खान के मकान तक | Deleted | 38250 | 0 | 2020-04-14
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542637 — सी सी खरंजा निर्माण कार्य उदयभान के मकान से केशव के मकान तक | Deleted | 26347 | 0 | 2020-04-14
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542641 — सी सी खरंजा निर्माण कार्य दर्शन के घर से रोड तक | Deleted | 19125 | 0 | 2020-04-14
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542743 — सी सी रोड निर्माण कार्य घनश्याम के मकान से स्कूल एवं जुभान मंदिर तक | Completed | 72675 | 96900 | 2020-12-23 | 2021-02-01
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542747 — सी सी रोड निर्माण कार्य जनक सिंह बघेल के मकान से बाबू खान के मकान तक | Completed | 38250 | 38760 | 2020-11-16 | 2020-12-12
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542748 — सी सी खरंजा निर्माण कार्य उदयभान के मकान से केशव के मकान तक | Completed | 26347 | 20520 | 2020-11-16 | 2020-12-12
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034542749 — सी सी खरंजा निर्माण कार्य दर्शन के घर से रोड तक | Completed | 19125 | 19380 | 2020-11-16 | 2020-12-12
MORENA / JOURA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034562495 — सी सी खरंजा निर्माण कार्य घनश्याम के मकान से स्कूल एवं हनुमान मंदिर तक | Completed | 72675 | 105342 | 2021-03-12 | 2021-06-21
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034568778 — सी सी रोड मेन रोड से सियाराम के मकान एवं उमा ग्‍लोबिन स्‍कूल तक | Completed | 71268 | 62532 | 2021-08-12 | 2021-10-26
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034578286 — सी सी खरंजा निर्माण कार्य शा० प्रा०वि० कोक सिंह के पुरा से राधेश्याम कुशवाह के मकान की ओर | Completed | 107482 | 98430 | 2021-08-22 | 2021-10-26
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034578288 — सी सी खरंजा निर्माण कार्य पुत्तू के माकन से गिर्राज शर्मा एवं अमर सिंह माहोर के मकान की ओर | Completed | 42457 | 39372 | 2021-08-22 | 2021-10-26
MORENA / JOURA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/22012034642693 — C C KHARANJA NIRMAN KARY DATARAM KE MAKN SE RAMVEER KUSHWAH KE MAKAN TAK | Completed | 108300 | 102102 | 2023-07-10 | 2024-06-03
MORENA / JOURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1701005054/RC/22012034850944 — feripheral bund nirman kary shanti dham kabarsthan khaneta | New | 0 | 0 | 2025-10-03
MORENA / JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005054/RC/30 — मिटटी मोरम रोड हनुमान मंदिर से मरघट तक | Completed | 0 | 114165 | 2008-12-08 | 2015-07-01
MORENA / JOURA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701005054/RC/4 — मिट्टी मोरम रोड | Completed | 0 | 0 | 2008-07-21 | 2007-10-17
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/603 — सी. सी. खरंजा रामेश्‍वर के घर से महादेव मंदिर | Completed | 41862 | 25755.96 | 2012-07-15 | 2012-08-16
MORENA / JOURA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701005054/RC/686 — सी.सी. खरंजा निर्माण लक्ष्‍मी नारायण मंदिर से | Completed | 134164 | 136209 | 2013-01-27 | 2013-03-17
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005054/RS/22012034585451 — Samudayik swachha parishar gram khaneta | Deleted | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701005054/RS/22012034599324 — सामुदायिक स्वच्छता परिषर ग्राम पंचायत खनेता | Completed | 43000 | 40530 | 2022-01-13 | 2023-12-14
MORENA / JOURA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1701005054/SK/939 — Bharat Nirman Rajeev Gandhi Sewa Kendra,KHANETA | Completed | 1425000 | 897 | 2013-09-23 | 2020-12-12
MORENA / JOURA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701005054/WC/22012034323615 — तालाब मरमम्‍त कार्य पंचायत भवन के पास | Deleted | 55359 | 0 | 2016-04-14
MORENA / JOURA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701005054/WC/22012034380631 — naveen talab nirman | Deleted | 0 | 0 | 2017-10-02
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619302 — मुन्ना लाल बरेठा के हैंडपंप के पास प्रभु सिंह का पूरा खनेता | Deleted | 0 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619305 — दिनेशं रजक हैंडपंप के पास प्रभु सिंह का पूरा खनेता | Deleted | 18200.42 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619308 — मोहन जाटव के हैंडपंप के पास प्रभु सिंह का पूरा खनेता | Deleted | 18200.42 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619309 — छतरी बाबा के हैंडपंप के पास प्रभु सिंह का पूरा खनेता | Deleted | 0 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619310 — छतरी बाबा के हैंडपंप के पास प्रभु सिंह का पूरा खनेता | Deleted | 0 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619311 — कोक सिंह का पूरा रोड किनारे खनेता | Deleted | 0 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034619313 — जगदीश सिंह के हैंडपंप के पास चक का पूरा का खनेता | Deleted | 0 | 0 | 2021-01-29
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034621267 — सोकफिट कार्य जगदीश कुशवाह चक का पूरा | Completed | 18200.42 | 17333 | 2021-03-12 | 2021-10-30
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034621269 — सोकफिट कार्य मुन्ना लाल बरेठा के हैंडपंप के पास प्रभु सिंह का प[ुरा खनेता | Completed | 18200.42 | 18461 | 2021-03-12 | 2021-10-31
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034621270 — सोकफिट कार्य दिनेश बरेठा के हैंडपंप के पास प्रभु सिंह का प[ुरा खनेता | Completed | 18200.42 | 19120 | 2021-03-12 | 2021-10-30
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034621271 — सोकफिट कार्य मोहन जाटव के हैंडपंप के पास प्रभु सिंह का प[ुरा खनेता | Completed | 18200.42 | 19330 | 2021-03-05 | 2021-10-26
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034621272 — सोकफिट कार्य रोड किनारे कोक सिंह का प[ुरा खनेता | Completed | 18200.42 | 17508 | 2021-03-05 | 2021-10-30
MORENA / JOURA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034621273 — सोक फिट कार्य छतरी बाले बाबा के हद पंप के पास खनेता | Completed | 18200.42 | 20998 | 2021-03-05 | 2021-10-30
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034696906 — सोकफिट कार्य फूल सिंह माहोर के हैंडपंप के पास खनेता | Deleted | 0 | 0 | 2021-04-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034696929 — सोकफिट कार्य शा.प्रा.चक का पूरा हैंडपंप के पास खनेता | Completed | 18398.36 | 16792.4 | 2021-06-24 | 2021-10-30
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034696937 — सोकफिट कार्य शा.प्रा.वि.प्रभु सिंह का पूरा हैंडपंप के पास खनेता | Closed | 0 | 0 | 2021-04-14
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034696942 — सोकफिट कार्य उपस्वास्थ्य केंद्र हैंडपंप के पास खनेता | Completed | 18398.36 | 18000 | 2021-06-10 | 2022-08-27
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034696947 — सोकफिट कार्य गुफा मंदिर के पास हैंडपंप के पास खनेता | Completed | 18398.36 | 18050 | 2021-06-10 | 2021-10-30
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034738879 — वाटर हार्वेसटिंग कार्य पंचायत भवन खनेता | Completed | 22173.14 | 21010 | 2021-06-17 | 2021-10-26
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034738891 — वाटर हार्वेस्टिंग कार्य शा.प्रा. वि.प्रभु सिंह का पूरा | Completed | 22173.14 | 21090 | 2021-06-17 | 2024-06-03
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034775011 — घरेलु सोकफिट कार्य 07 खनेता | Completed | 129101.13 | 128170 | 2021-09-12 | 2021-11-16
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034775012 — घरेलु सोकफिट कार्य 07 खनेता | Closed | 0 | 0 | 2021-04-29
MORENA / JOURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034775019 — सार्वजानिक सोकफिट कार्य 04 खनेता | Completed | 73774.78 | 70155 | 2021-09-12 | 2021-11-15
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034943942 — रूप हार्वेस्टिंग पी एस स्कूल दोहरे का पूरा खनेता | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034943947 — सोकफित निर्माण कार्य भूकन के हडपंप के पास खानेता | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034943973 — सोकफित निर्माण कार्य अमरतलाल के हेडपैंप हडपंप के पास खानेता | Closed | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034943982 — सोकफित निर्माण कार्य गौरेला कुशवाह के हेडपैंप हडपंप के पास खानेता | Deleted | 0 | 0 | 2022-04-01
MORENA / JOURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701005054/WC/22012034943986 — सोकफित निर्माण कार्य दर्शन बरेठा हडपंप के पास खानेता | Deleted | 0 | 0 | 2022-04-01
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1701005054/WC/22012035303444 — डगवेल रीचार्ज निर्माण कार्य खनेता | Approved | 25899.46 | 0 | 2025-04-14
MORENA / JOURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1701005054/WC/22012035303448 — डगवेल रीचार्ज निर्माण कार्य प्रभु सिंह का पूरा खनेता | Approved | 25899.46 | 0 | 2025-04-14
MORENA / JOURA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701005054/WH/19957973 — तालाब मरम्‍मत कार्य गाडेराम का पुरा | Completed | 79074 | 39051 | 2017-01-02 | 2017-08-06
MORENA / JOURA | 2017-2018 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1701005054/WH/19958743 — तालाब मरमम्‍त कार्य पंचायत भवन के पास | Completed | 55359 | 35604 | 2017-05-08 | 2017-08-06