## Work List
Exported on: 2026-10-26 13:50:27
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: RATANPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MORENA / SABALGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701007030/AV/22012034371242 — Shantidham Unnayan karya Ratanpur | Completed | 215000 | 213279 | 2019-03-02 | 2019-06-23
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701007030/AV/22012034581518 — सेग्रीगेशन शेड ककरारी | Deleted | 0 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1701007030/AV/22012034585041 — construction of kitchen shed dinning hall ps sahlla ratanpur | Closed | 18459.19 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1701007030/AV/22012034585042 — construction of kitchen shed dinning hall m.s. sahlla ratanpur | Closed | 18459.19 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1701007030/AV/22012034585043 — construction of kitchen shed dinning hall ps sahlla kakrari | Closed | 18459.19 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701007030/AV/22012034585045 — construction of kitchen shed dinning hall aganwadi bhavamn ratanpur | Deleted | 0 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1701007030/AV/22012034607060 — samudayik swachhta parisar kakarari | Deleted | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1701007030/AV/22012034657082 — Shantidham Unnayn Karya Kakarari | Deleted | 0 | 0 | 2024-06-09
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1701007030/AV/22012034657584 — Pakki nali nirman kary pokhar nali se ramkumar jadon ke ghar ki or | Approved | 1452381.98 | 0 | 2024-04-14
MORENA / SABALGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1701007030/DP/22012034602187 — Vashudha vandhan Amrit vatika takurbaba mandir ratanpur | Closed | 55847.4 | 0 | 2023-04-16
MORENA / SABALGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1701007030/DP/9926698280 — शांतीधाम निर्माण कार्य रतनपुर | Completed | 497000 | 312575.78 | 2013-09-20 | 2014-08-09
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701007030/FP/22012034202761 — नाली निर्माण मय पत्थर खरंजा निर्माण हरिजन बस्ती पोखर से पातीराम के बाडे की ओर रतनपुर | Completed | 1473500 | 1390079.67 | 2015-09-11 | 2016-01-28
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701007030/FP/22012034203463 — nally nirman murari kemakan se pokhar ke or and rod said | Completed | 1362000 | 1319868.9 | 2016-01-16 | 2016-12-05
MORENA / SABALGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701007030/FP/22012034203645 — nalli nerman murari ke kuoaa se ratanpur rod ke or | Completed | 1063000 | 1039133.43 | 2016-09-02 | 2017-01-26
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701007030/FP/22012034203646 — nalli nerman pokhar se beermpur ke or | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701007030/FP/22012034203647 — nali nirman rajendra sharma ke makan se pokhar ki or and shankar ke makan ki or | Completed | 1362000 | 1221146.6 | 2016-12-25 | 2017-07-26
MORENA / SABALGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1701007030/FP/22012034204356 — nalli nirman ramnaresh ke makhan se pansingh jadon or | Completed | 1063000 | 1045113.28 | 2016-09-02 | 2017-01-26
MORENA / SABALGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1701007030/FP/22012034362488 — नाली निर्माण कार्य बकील के मकान से शांतीधाम की ओर रतनपुर | Completed | 1314000 | 960598.31 | 2019-03-04 | 2020-09-20
MORENA / SABALGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034629081 — पक्की नाली एवं कच्चा नाला निर्माण कार्य भरोसी नाई एतत् से गिर्राज की नाली तक | Completed | 449427.66 | 143592 | 2022-05-30 | 2025-09-18
MORENA / SABALGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034629529 — पक्की नाली निर्माण कार्य रामदीन के घर से सुरेंद्र के घर तक | Closed | 0 | 0 | 2022-08-17
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034629530 — नाली निर्माण कार्य ककरारी बीरमपुर रोड की पुलिया से पोखर तक | Completed | 811619.41 | 410482 | 2023-05-06 | 2024-03-18
MORENA / SABALGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034629814 — नाली निर्माण कार्य राम जी के गेत से माता मंदिर तक | Deleted | 0 | 0 | 2022-08-16
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034629940 — पक्की नाली निर्माण कार्य राम जी के घर से माता मंदिर की ओर | Completed | 1481190.73 | 1458115 | 2023-04-22 | 2024-10-22
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034641255 — Nali Nirman karya ratanpur pokhar se ramkumar jadon ke ghar ki or ratanpur | Deleted | 0 | 0 | 2024-08-15
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1701007030/FP/22012034641256 — Nali Nirman karya ratanpur pokhar se rambeer jadon ke khet ki or ratanpur | Deleted | 0 | 0 | 2024-08-15
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/1000040813 — पशु शेड निर्माण कार्य रणवीर / लाखन | Completed | 80000 | 72518.83 | 2013-09-27 | 2014-03-15
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/1000040814 — पशु शैड निर्माण कार्य दयराम / इन्‍दर | Completed | 80000 | 73883.83 | 2013-09-27 | 2014-06-11
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/1000040815 — पशु शैड निर्माण कार्य रामराय / जालिम | Completed | 80000 | 77314.83 | 2013-09-27 | 2015-08-10
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/1000040816 — पशु शैड निर्माण कार्य सुनीता / रामवीर | Completed | 80000 | 72664.83 | 2013-09-27 | 2014-08-09
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701007030/IF/22012034347605 — Braksharopan Sarvjanik Sthal Madhymik Vidyalay Ratanpur | Completed | 335000 | 79011 | 2017-07-01 | 2020-04-01
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701007030/IF/22012034355703 — Biraksharopan Thakur Baba Ke Parisar Mai Ratanpur | Completed | 335000 | 71536 | 2017-07-01 | 2020-04-01
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701007030/IF/22012034355707 — Biraksharopan Dagi Baba Ke Pass Ratanpur | Completed | 335000 | 58762 | 2017-07-03 | 2019-08-20
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701007030/IF/22012034368365 — Biraksharopan Kabrsthan Ratanpur | Completed | 335000 | 8880 | 2017-07-25 | 2019-04-04
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034806599 — Nadep kary ranvir singh rawat ki khet par | Deleted | 20356.35 | 0 | 2021-04-10
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034806606 — Nadep kar rakesh rawat /lakhan singh ki khet par | Deleted | 0 | 0 | 2021-04-10
MORENA / SABALGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1701007030/IF/22012034811054 — नंदन फलोद्यान महेंद्र सिंह जादौन के खेत पर | Deleted | 0 | 0 | 2021-04-10
MORENA / SABALGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Medicinal Plantation in Individual land / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1701007030/IF/22012034811072 — नंदन फलोद्यान गंधर्व सिंह जादौन के खेत पर रतनपुरu | Deleted | 0 | 0 | 2021-04-10
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034829332 — nadep kary 1.rakesh rawat.2.haret rawat3.ramraj rawat 4banvari lal rawat5.ranvir rawat | Deleted | 0 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034829339 — nadep kary 1.bakil rawat2.ramveer rawat.3ramvilash rawat.uday singh .beerbal rawat | Completed | 100244.21 | 99691.55 | 2021-09-06 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034829540 — nadep kary 1.rakesh rawat.2.haret rawat3.ramraj rawat 4banvari lal rawat5.ramrayrawat | Completed | 100244.21 | 99691.55 | 2021-09-06 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034832904 — nadep kary 1,kedhar rawat,2,murari rawat 3,lokendra rawat 4,rup singh rawat 5,ashok sharma | Completed | 100699.07 | 98158 | 2021-10-07 | 2022-07-10
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost pit for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034832909 — nadep kar 1,ram singh 2,hotam rawat,3,amar singh rawat,4,narotam rawat 5,piryag singh | Ongoing | 100244.21 | 86254 | 2021-11-25
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034849121 — nadep kary 1,ramesh bansal 2,puran bansal 3,raghvar rawat 4,ramnivash 5,prdeep rawat | Completed | 81375.21 | 78653.5 | 2021-11-08 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034849124 — nadeep kary 1,santkumar jadon 2,ramvarn jadon 3ramotar jadon 4mahendra jadon 5ramnaresh jadon | Completed | 100699.07 | 99877 | 2021-10-08 | 2021-12-23
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034849138 — nadep kary 1,ray singh 2,bhopsingh 3,matadeen guor 4surendraguor 5,sandeep rawat | Completed | 100699.07 | 99509 | 2021-10-19 | 2022-07-30
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876624 — naddep kary 1.rajendra jadon 2.ramesur jadon 3.rakeshjadon 4.sher singh jadon 5 atendra singh jadon | Completed | 100699.07 | 99509 | 2021-11-15 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876628 — nadeep kary 1.shuda jadon 2.rajveer jadon 3.salim khan 4.ramuji rawat 5.punit jadon | Completed | 100699.07 | 99509 | 2021-11-15 | 2022-07-30
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876631 — nadeep kary 1.gorelal jatav2.mahendra jatav 3.mataden jatav 4.maniram jatav 5kaptan jatav | Completed | 100699.07 | 99509 | 2021-11-15 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876638 — nadeep kary 1banbari lal 2.mahesh jatav 3.narotam jatav .4ramsrup jatav 5.naresh jatav | Completed | 100699.07 | 99509 | 2021-11-15 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876642 — nadeep kary 1.jamal khan 2.basir khan 3.ishak khan 4.rahisha khan 5.kashiram jatav | Completed | 100699.07 | 99509 | 2021-11-15 | 2022-07-30
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876646 — nadeep kary 1.harishankar sharma 2.pirem sankar sharma 3.rajendra sharma 4.mishrilal 5.shirinibashra | Completed | 100699.07 | 99509 | 2021-11-15 | 2022-07-30
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034876649 — nadep kary 1.karimudeen kha2.tajudeen kha 3.gabrudeen kha 4.fakrudeen kha 5.sabo khaa | Completed | 100699.07 | 99509 | 2022-01-13 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034889257 — nadeep kary 1samnt jatav2 ramcharn jatav 3 shivcharn jatav 4 raghunath jatav 5.ramsingh jatav | Completed | 100699.07 | 99702 | 2021-12-02 | 2022-07-30
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034889258 — nadep kary 1.ramdeen jatav 2.munesh jatav 3.pirmod jatav 4.badsah jatav 5.satiybeer jatav | Completed | 100699.07 | 99509 | 2022-03-18 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034889260 — nadep kary 1.giyan singh 2.mahesh jatav 3.suresh jatav 4.shrinivash jatav 5.maniram jatav | Completed | 100699.07 | 99509 | 2022-03-18 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034889262 — nadep kary 1.murari jatav 2.basdev jatav 3.bedariya jatav 4.munna jatav | Completed | 100699.07 | 99509 | 2022-03-18 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034889263 — nadep kary 1.veer singh jatav 2.lakhan jatav 3.umeed rawat 4.narmda jatav 5.jagdish jatav | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034889264 — naddep kary 1.ramrup 2.gotelal 3.banbari 4.rajendra 5.beerendra sharma | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034894071 — Naddep kary 1.samkar rawat 2.rishikesh rawat3. Bhagbanlal rawat 4.emarti rawat 5.manish sharma | Deleted | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034896813 — nadep kary 1.ramdeen 2.gandarf 3.nekram jatav 4.pavan 5.bharoshi nai | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034896829 — nadeep kary 1.deevan singh 2.rambeer 3.patiram 4.manish rawat 5.ramesh nai | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034896838 — nadep kary 1.mukesh jatav2.ramesh jatav 3.surendra jadon 4.darsan jadon 5.ramkumar jadon | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034896856 — nadeep kary 1.vinod rawat 2.lalpati jatav 3.soneram rawat4.ramlkhan rawat 5.ramkumar rawat | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034896867 — nadep kary 1.manoj rawat 2.ramkesh rawat 3.bachan rawat 4.emarti rawat 5.naresh rawat | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1701007030/IF/22012034919053 — Naddep kary 1.sankar rawat 2.rishikesh rawat3. Bhagbanlal rawat 4.emarti rawat 5.manish sharma | Closed | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1701007030/IF/22012035230174 — Khet talab nirman kary sandip jadon Kotbar ke khet pr ratanpur | Deleted | 0 | 0 | 2024-04-14
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1701007030/IF/22012035230198 — Khet talab nirman kary Kireta jainam kha ke khet pr ratanpur | Deleted | 0 | 0 | 2024-04-14
MORENA / SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1701007030/IF/22012035501508 — khet talav nirman karya sandeep jadon ke khet par | New | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1701007030/IF/22012035501619 — khet talav nirman karya sandeep jadon ke khet par | New | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1701007030/IF/22012035501790 — khet talav nirman karya sandeep jadon ke khet par | New | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035502813 — khet talav nirman karya sandeep jadon ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035502858 — khet talab nirman kary jenam khan ke ket mai ratanpur | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035503011 — khet talav nirman karya tajudeen khan ke khet par | New | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035503160 — khet talav nirman karya tajudeen khan ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035503228 — khet talav nirman karya saboo khan ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1701007030/IF/22012035512770 — khet talav nirman karya Ramotar jadon ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1701007030/IF/22012035512778 — khet talav nirman karya meera rawat ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035517650 — khet talav nirman karya monu jadon ke khet par | Completed | 450885.64 | 351567 | 2025-05-17 | 2025-09-18
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035517665 — khet talav nirman karya bherolala sharma ke khet par | Completed | 450885.64 | 347913 | 2025-05-17 | 2025-09-18
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035517673 — khet talav nirman karya munna lal sharma ke khet par | Completed | 450885.64 | 347913 | 2025-05-17 | 2025-09-18
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035517687 — khet talav nirman karya jogesuri sharma ke khet par | Completed | 450885.64 | 351567 | 2025-05-17 | 2025-09-18
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1701007030/IF/22012035517943 — khet talav nirman karya Ramtar jadon ke khet par | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926710609 — पशु शैड् निर्माण कार्य नरोत्तम / रतनलाल ककरारी/रतन | Completed | 80000 | 76188.26 | 2014-02-28 | 2014-07-02
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711276 — पशु शैड निर्माण कार्य / रामानाथ/सुखलाल | Completed | 80000 | 75874.26 | 2014-02-28 | 2014-07-02
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711278 — पशु शैड निर्माण कार्य / शिवचण/विरखा | Completed | 80000 | 75875.34 | 2014-02-28 | 2014-07-02
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711280 — पशु शैड निर्माण कार्य / पुणिमा/तहसीलदार | Completed | 80000 | 75805.83 | 2014-02-28 | 2014-06-11
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711281 — पशु शैड निर्माण कार्य / उम्मेदसिंह/शिवचण | Completed | 80000 | 71571.32 | 2014-02-28 | 2015-05-10
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711282 — पशु शैड निर्माण कार्य / महेंद्र/दिलीपसिंह | Completed | 80000 | 75805.83 | 2014-02-28 | 2014-08-09
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711284 — पशु शैड निर्माण कार्य / भरतलाल/घनशयाम | Completed | 80000 | 78074.43 | 2014-02-28 | 2015-08-27
MORENA / SABALGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9926711286 — पशु शैड निर्माण कार्य / रामअवतार/वेदलसिह | Completed | 80000 | 76126.83 | 2014-02-28 | 2014-08-09
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993673858 — पशु आश्रय टीनशैड निर्माण रामरूप/मुरारीलाल रावत रतनपुर | Completed | 85000 | 78853.43 | 2015-09-11 | 2016-03-17
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993673859 — पशु आश्रय टीनशैड निर्माण अम्रतलाल/शिवलाल रावत रतनपुर | Completed | 85000 | 78853.43 | 2015-09-11 | 2015-11-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993673860 — पशु आश्रय टीनशैड निर्माण भगवनलाल/किशुनलाल रावत रतनपुर | Completed | 85000 | 78852 | 2015-09-11 | 2015-11-12
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993673861 — पशु आश्रय टीनशैड निर्माण बनवारीलाल/जीवनलाल रावत रतनपुर | Completed | 85000 | 78853.43 | 2015-09-11 | 2015-11-12
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993673862 — पशु आश्रय टीनशैड निर्माण रायसिंह/लालपति रावत रतनपुर | Completed | 85000 | 78853.43 | 2015-09-11 | 2015-11-12
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993692927 — pashu shed nirman -karimudeen /subrati | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993692955 — pashu shed nirman-vinod/patiram rawat | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993692964 — pasu shed nirman-choto/subrati | Deleted | 97000 | 0 | 2015-08-15
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693005 — pasu shed niraman-purn/ramgopal | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693021 — pasu shed nirman-gavrudeen/subrati | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693028 — pasushed niraman -munna/badri jatav | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693041 — pasu shed niraman-beeraba/duleeram | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693048 — pasu shed niraman -ramsing/kesori | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693052 — pasu shed niraman -ramdeen/shripal | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993693057 — pasu shed niraman-ramuji/parsha | Deleted | 97000 | 0 | 2015-12-11
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713567 — pasu sheid- banbari/bisu | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713568 — pasu sheid -ramsrup/bhagri | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713569 — pasu sehid-mehrvan/ramlal | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713570 — pasu sheid -kashiram/matre | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713571 — pasu sheid -baser/naneka | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713595 — pasu sheid -ismal/boduo | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713597 — pasu shied-ramrj/jeevanlal | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713600 — pasu sheid -munna/rambhajan | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713603 — pasu sheid -santkumar/janjel | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713605 — pasu sheid -haret/jeevanlal | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713801 — pasu sheid -mola/babhu | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713802 — pasu sheid -esak/alldeen kha | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713803 — pasu sheid-gandaf | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713805 — pasu sheid -surendra/ramkisun | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713808 — pasu sheid -ramskhi/ramhet | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713810 — pasu sheid -misrilal/manfool | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713811 — pasu sheid -rambilash/amirtlal | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713812 — pasu sheid -bake/ganjan | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713813 — pasu sheid -sankar/tosiram | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713814 — pasu sheid- beerendra/harebabu | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713815 — pasu sheid-darsan/toshiram | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713816 — pasu sheid -birbhosan/radela | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1701007030/IF/9993713817 — pasu sheid -samnt | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007030/IF/IAY/461315 — Construction of IAY House -IAY REG. NO. MP1710956 | Completed | 15030 | 15240 | 2017-02-07 | 2018-03-28
MORENA / SABALGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007030/IF/IAY/545227 — Construction of IAY House -IAY REG. NO. MP3219768 | Completed | 15030 | 15415 | 2017-02-07 | 2018-03-28
MORENA / SABALGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007030/IF/IAY/602913 — Construction of IAY House -IAY REG. NO. MP1693829 | Completed | 15030 | 15240 | 2017-02-07 | 2018-03-28
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007030/IF/IAY/765273 — Construction of IAY House -IAY REG. NO. MP3204004 | Completed | 15030 | 15318 | 2017-05-03 | 2018-04-25
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007030/IF/IAY/766666 — Construction of IAY House -IAY REG. NO. MP3267239 | Completed | 15030 | 15330 | 2017-05-03 | 2018-04-25
MORENA / SABALGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1701007030/IF/IAY/779172 — Construction of IAY House -IAY REG. NO. MP3947124 | Completed | 15030 | 15480 | 2017-05-03 | 2018-03-28
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701007030/LD/22012034256211 — santi dham -kakrari | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701007030/LD/22012034266723 — mitti bharv kakrari jatav basti road said | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1701007030/LD/22012034310477 — shantidham nrman kayrya kakararee | Completed | 245000 | 244880.6 | 2017-05-03 | 2017-06-20
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1701007030/LD/22012034576124 — ड्राई बौल्डर बाल प्राथमिक शाला के पास ककरारी | Deleted | 0 | 0 | 2022-01-26
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1701007030/LD/22012034576125 — ड्राई बौल्डर बाल ईसाक के मकान से तालाव तक रतनपुर | Completed | 578352.21 | 558132.8 | 2022-02-24 | 2022-09-28
MORENA / SABALGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1701007030/LD/22012034579914 — चबूतरा निर्माण एवं आंतरिक मार्ग कब्रिस्तान परिसर रतनपुर | Deleted | 0 | 0 | 2022-04-01
MORENA / SABALGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1701007030/LD/22012034579915 — चबूतरा निर्माण एवं आंतरिक मार्ग कब्रिस्तान परिसर रतनपुर | Deleted | 0 | 0 | 2022-04-01
MORENA / SABALGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1701007030/LD/22012034579916 — चबूतरा निर्माण एवं आंतरिक मार्ग कब्रिस्तान परिसर रतनपुर | Deleted | 0 | 0 | 2022-04-01
MORENA / SABALGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034579917 — ड्राई बॉर्डर वाल स्कूल से रिटेनिंग वॉल तक ककरारी | Deleted | 1496440.11 | 0 | 2022-04-01
MORENA / SABALGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034580256 — कब्रिस्तान उन्नयन कार्य रतनपुर | Completed | 498758.15 | 389848 | 2022-05-23 | 2024-11-07
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1701007030/LD/22012034590300 — Dry boulder ball nirman kary prathmik vidyalay ke pass kakrari | Completed | 1482712 | 1455706.5 | 2024-06-08 | 2024-11-27
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957339 — Perryferal ston bund nirman karya hanuman ji mandir ke pass kakrari | Physically Completed | 1454230.16 | 1415360.25 | 2025-11-07 | 2026-05-21
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957340 — Perryferal ston bund nirman karya dangi baba mandir ke pass kakrari | Ongoing | 1474085.9 | 1309995.32 | 2025-10-31
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957341 — Perryferal ston bund nirman karya pokhar ke pass kakrari | Physically Completed | 1471531.11 | 1334142.58 | 2025-11-07 | 2026-05-21
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957343 — Perryferal ston bund nirman karya ramcharan Rawat ke khet ke pass ratanpur | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957345 — Perryferal ston bund nirman karya mangi Rawat ke khet ke pass ratanpur | Approved | 0 | 0 | 2025-04-14
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957494 — perifaral ston bund nirman karya shanti dham kakrari | Ongoing | 1450192.02 | 1058285.97 | 2025-11-07
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034957495 — perifaral ston bund nirman karya swaraj bhawan midil school ke pass ratanpur | Ongoing | 1468684.07 | 1164526.97 | 2026-01-23
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1701007030/LD/22012034959497 — Periferal Stone Bund Nirman Karya Prahlad Rawat Ke Khet Se Netaram Ke Khet Ki Or Kakrari | Ongoing | 1497027.42 | 1147226.51 | 2025-12-19
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034959498 — Periferal Stone Bund Nirman Karya Munna Jatav Ke Khet Se Shanti dham Ki Or Kakrari | Ongoing | 1487559.81 | 1155690.14 | 2025-12-19
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034959499 — Periferl Stone Bund Lalpati Rawat Ke Khet Se Mata Mandir Ki Or ratanpur | Ongoing | 1490683.36 | 1029164.58 | 2025-12-19
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034959688 — fereeperal ston band nirman kary munna jadon ki khet se bherulal sharma ki khet ki or | Ongoing | 1483025.37 | 1204898.04 | 2025-12-19
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034960560 — Peripheral Ston Bund Nirman Karya Ramdeen K Khet Se Rishikesh Ke Khet Ki Or Ratanpur | Ongoing | 1497666.72 | 1273587.8 | 2026-01-23
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034960561 — Peripheral Ston Bund Nirman Karya Netaram Ke Khet Se Ballu Jadoun Ke Khet Ki Or Ratanpur | Ongoing | 1494970.75 | 1230020.2 | 2026-01-23
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034961230 — Peripheral Stone Bund Ratanpur Se Karari Raste Par Ratanpur | Ongoing | 1493360.78 | 1153386.51 | 2026-02-18
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034961231 — Peripheral Stone Bund Babu Rawat K Khet Se Ratanpur Ki Or | Ongoing | 1480215.76 | 1104194.76 | 2026-02-18
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034961232 — Peripheral Stone Bund Gyan Singh jatav k khet se mahesh ke khet ki or kakrari | Approved | 0 | 0 | 2025-10-02
MORENA / SABALGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/LD/22012034961233 — Peripheral Stone Bund Suresh jatav k khet se jaysingh k khet ki or kakrari | Approved | 0 | 0 | 2025-10-02
MORENA / SABALGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1701007030/LD/3799431984 — कब्रिस्तान निर्माण कार्य रतनपुर | Completed | 1271000 | 1098577.7 | 2014-02-28 | 2015-11-07
MORENA / SABALGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/1475 — मिट़टी ग्रेवल रोड रतनपुर से शाखातक | Completed | 0 | 469843.24 | 2010-06-23 | 2014-09-16
MORENA / SABALGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/1501 — मिट्र्टी ग्रेवल रोड निर्माण कार्य भि‍यानिया के मकान(खेम)से ककरारी | Completed | 0 | 308401.39 | 2011-03-25 | 2014-09-16
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/1522 — पत्‍थर खरजा निर्माण कार्य लाखन के दार से होली तक | Completed | 0 | 432904 | 2011-06-15 | 2014-09-12
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/1582 — पत्‍थर खरजा निमार्ण रतनपुर गुडडू के कमान से लालपति | Completed | 0 | 443635.89 | 2011-11-24 | 2014-09-16
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034161593 — C.C. Kharanja Nirman | Completed | 57572 | 37630 | 2013-05-09 | 2013-05-15
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034163051 — CC ROAD PS RATANPUR SE PANSING SABALGARH KE MAKAN KI AUR | Deleted | 0 | 0 | 2012-01-16
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034163055 — C.C.Road Ratanpur se pansing sabalgarh ke makan ki aur | Deleted | 0 | 0 | 2012-01-16
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034163057 — CC Road Ps ratanpur se pansing sabalgarh ke makan ki aur | Deleted | 0 | 0 | 2012-01-16
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034163059 — CC Road Ps ratanpur se pansing sabalgarh ke makan ki aur | Deleted | 0 | 0 | 2012-01-16
MORENA / SABALGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034163232 — CC Road Ps ratanpur se pansing sabalgarh ke makan ki aur | Deleted | 44496 | 0 | 2012-01-08
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034163235 — CC Road Ps ratanpur se pansing ke makan tak | Completed | 44496 | 40096 | 2013-04-24 | 2013-12-18
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034185254 — पत्‍थ्‍ार खरन्‍जा निर्माण कार्य हीरापुर से ठाकुर क | Completed | 499500 | 494025.95 | 2013-09-27 | 2014-04-30
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034185256 — पत्‍थ्‍ार खरन्‍जा निर्माण कार्य प्रा.वि.से नेकराम | Completed | 498000 | 486039.21 | 2013-09-27 | 2014-04-30
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034187501 — पत्‍थर खरन्‍जा निर्माण कार्य पानसिंह के मकान से सं | Completed | 498000 | 494209.64 | 2013-10-04 | 2014-03-26
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034187851 — मिटृटी ग्रेवल रोड ककरारी से कीरतपुर की ओर | Deleted | 500000 | 0 | 2013-10-04
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034210380 — पत्थर खरंजा निर्माण पातीराम के बाडे से मौला बक्स क | Completed | 499500 | 494399.2 | 2014-02-28 | 2015-08-27
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034210385 — पत्थर खरंजा निर्माण गाव के कुआअ से जीवनलाल एंव केद | Completed | 499500 | 474010.2 | 2014-02-28 | 2014-07-23
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034210393 — पत्थर खरंजा निर्माण कार्य मिश्री तथा मुंशी के बाडे | Completed | 499500 | 428261.19 | 2014-02-28 | 2015-01-29
MORENA / SABALGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034212483 — सी सी खरजा एव नाली निर्माण रतनपुर | Completed | 74191 | 69135 | 2014-02-28 | 2014-08-09
MORENA / SABALGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034220956 — सी.सी.खरन्‍जा निर्माणकार्य चिम्‍मन के मकान से मुरा | Completed | 103536 | 97142 | 2014-06-13 | 2014-08-09
MORENA / SABALGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034223085 — सी.सी.खरन्‍जा निर्माय कार्य रामदीन के मकान से उम्‍ | Completed | 74191 | 69135 | 2014-06-27 | 2014-07-02
MORENA / SABALGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034223088 — सी.सी.खरन्‍जा निर्माय कार्य ककरारी स्‍कूल से पटेल | Completed | 13193 | 13175 | 2014-06-26 | 2014-08-09
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034284216 — पत्थर खरंजा निर्माण उम्मेद के मकान से जयसिंह के कुआ की ओर | Completed | 947000 | 862815.98 | 2015-09-11 | 2016-03-03
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034293253 — पत्थर खरंजा रामराय के पशु शैड से भरोषी नाई के मकान की ओर रतनपुर | Completed | 1019000 | 655115.7 | 2015-12-16 | 2016-05-30
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034299545 — mite girbal rood kakrari se beermpur ke or | Deleted | 0 | 0 | 2015-10-02
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034299548 — pathar karnja lalpate ke makan se ukar ke bade ke or ratanpur | Deleted | 0 | 0 | 2015-10-02
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034299565 — pathar karnja sahdiv ke makan se badire ke kuoaa ke or | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034299567 — meti rood lalpati ke makan se sanjaynagar ke or | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034299569 — pathar karnja nirman rambeer jadon ke makan se rajbeer ke makan ke or | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034308542 — meeti girebal road-lakhan ke kuaa se ramrup ke khet tak | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034327665 — CC Kharanja and nali nirman ratanlal jatav ke makan se ramroop ke makan tak | Completed | 99563 | 48683 | 2017-03-27 | 2017-08-25
MORENA / SABALGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034331944 — CC kharanja and nali beerbal ke makan se ramraj ke makan tak | Completed | 45000 | 54528 | 2017-03-27 | 2017-08-25
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034336635 — MITTI ROAD RATANPUR SE RAMUJI KE KUAA KI OR | Completed | 1372000 | 1324825.06 | 2017-05-03 | 2017-10-23
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034338600 — Mitti gravel road kakarari se veerampur ki or | Completed | 1372000 | 1300531.63 | 2017-05-24 | 2018-01-28
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034341523 — Mitti Gravel road Ramuji ke kuaa se sanjay nagar ki or ratanpur | Completed | 1147000 | 1106505.05 | 2017-06-12 | 2017-11-11
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034353098 — CC Kharanja and nali alladir k makan se hari sharma k makan tak | Completed | 48600 | 47472 | 2017-09-15 | 2017-09-22
MORENA / SABALGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1701007030/RC/22012034353104 — cc kharanja and nali pansingh k makan se sudha jadon k makan ki or | Deleted | 39825 | 0 | 2017-01-26
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034370052 — Sudhor sampark sadhak kakrarai se bhadureyapura rood ke or | Deleted | 0 | 0 | 2017-10-02
MORENA / SABALGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034370054 — Sudhor sampark sadhak ratanpur se ramrup ke kuaa take | Deleted | 0 | 0 | 2017-10-02
MORENA / SABALGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034443819 — chik dem etava babu ke khet pass | Deleted | 0 | 0 | 2018-10-02
MORENA / SABALGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034463724 — रपटा निर्माण कार्य कब्रिस्तान के पास रतनपुर | Completed | 906000 | 866829.36 | 2019-03-10 | 2020-11-28
MORENA / SABALGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034476425 — Rapata nirman karya musalaman basti nale par ratanpur | Completed | 1380958.29 | 1370173 | 2019-10-20 | 2020-05-06
MORENA / SABALGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034476426 — Rapata nirman karya harijan basti pokhar ke pass kakarari bale road par Ratanpur | Completed | 1379647.83 | 1371613 | 2019-10-20 | 2020-04-01
MORENA / SABALGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034522598 — Rapta nirman karya ramesh rawat ki makhn ki pass kakrari rode par | Completed | 1312443.99 | 1227868.68 | 2020-05-23 | 2021-03-31
MORENA / SABALGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034522599 — Rapta nirman kary lalpati ki makhn ki pass ratanpur | Completed | 975908.96 | 913022.78 | 2020-05-23 | 2021-03-31
MORENA / SABALGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034538015 — rapata avam aproch road nirman kary santhi dham se pass ratanpur | Completed | 1485537.75 | 1203409.87 | 2020-09-19 | 2021-03-31
MORENA / SABALGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034538018 — rapata nirman kary avam aproch road santi dham raste par kakrari | Completed | 733281.82 | 720139.4 | 2020-09-25 | 2024-10-22
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034567281 — rapata avam aproch road nirman kary lakhan singh makhan se ladhpura nale tak | Completed | 898797.69 | 748868.18 | 2021-05-23 | 2022-08-04
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034606833 — Pulya Ev Aproch Road Munna Jatav Ke Ghar Se Kaakator Ki Or | Completed | 303258.11 | 266690.52 | 2022-02-24 | 2023-07-10
MORENA / SABALGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034616489 — मिट्टी ग्रेवल रोड एप्रोच पहलाद के मकान से लक्ष्मण के कुआं तक ककरारी | Deleted | 0 | 0 | 2022-08-17
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1701007030/RC/22012034639164 — Rapat evm approch road Nirman karya Lakshman Ramchandra khet ki or kakarari | Ongoing | 906837.47 | 875406.6 | 2024-04-15
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034678989 — rapta evm aprochh nirman kary sankar ki khet se kotvar ki khet ki or ratanpur | Closed | 1488563.06 | 0 | 2024-01-24
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034679297 — rapta evm aprochh giraj ki khet ki pass ratnpur | Closed | 1488563.06 | 0 | 2024-01-24
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034679298 — rapta evm aprooch nirman kary sandip jadon ki khet par | Deleted | 0 | 0 | 2024-01-24
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034679299 — Rapta evm aprocch nirman kary meghnath rawat ki khet par ratnpur | Closed | 1488563.06 | 0 | 2024-01-24
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034679300 — Rapta evm aprooch nirman kary ramcharn ki khaleyan ki pass ratanpur | Closed | 1474902.23 | 0 | 2024-01-24
MORENA / SABALGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1701007030/RC/22012034679301 — Rapta evm aprochh nirman kary Ramnath ki khet par | Closed | 1465971.81 | 0 | 2024-01-24
MORENA / SABALGARH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/371 — मिटटी ग्रेवल रोड रतन पुर से ककरारी की ओर | Completed | 0 | 276484 | 2009-06-17 | 2010-12-29
MORENA / SABALGARH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1701007030/RC/rm-001 — मिटटी गिरेबल रोड ककरारी से कीर्तिपुरा की ओर रतनपुर | Completed | 433194 | 485960 | 2008-05-25 | 2011-03-26
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1701007030/RS/22012034526347 — Braksharopan kar lakhan singh ki makan se Ladpura nale tak aprochh rode par | Deleted | 0 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1701007030/RS/22012034532087 — नाडेप कार्य संदीप रावत/ रामराज रावत रतनपुर | Deleted | 0 | 0 | 2021-04-10
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701007030/RS/22012034599595 — सामुदायिक कंपोस्ट पिट ग्राम ककरारी | Deleted | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1701007030/RS/22012034599597 — सामुदायिक कंपोस्ट पिट ग्राम ककरारी | Deleted | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1701007030/RS/22012034638512 — Samudayik Swachhata parisar kakrari ratanpur | Completed | 43000 | 41688 | 2022-02-03 | 2022-07-30
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1701007030/RS/22012035127795 — nali nirman karya pokhar nali se ramkumar jadon ke ghar ki or ratanpur | Deleted | 0 | 0 | 2024-06-09
MORENA / SABALGARH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1701007030/WC/22012034380221 — Chik deem kavrestan ke pass ratanpur | Deleted | 1400000 | 0 | 2017-10-02
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1701007030/WC/22012034702528 — khet talab nirman kary mahendra jadon ke | Completed | 955945.37 | 601967 | 2021-06-06 | 2022-04-15
MORENA / SABALGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of gabion Spur for Comm / Repair and Maintenance of Wire crate (gabion) Spur for Community | Repair & maint of Water Harvesting Structures | 1701007030/WC/22012034702542 — khet talab nirman kar gandarf jadon ke khet par | Completed | 953839.97 | 638058 | 2021-07-04 | 2022-04-15
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1701007030/WC/22012034716729 — rin watar harviting m.s .school ratanpur | Completed | 22173.14 | 21310.44 | 2021-06-06 | 2022-07-17
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701007030/WC/22012034716736 — rin watar harviting shamudayak bhavan ratanpur | Completed | 22173.14 | 21310.44 | 2021-06-06 | 2022-07-17
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701007030/WC/22012034727446 — roof top water harwesting p.s.shcool ratanpur | Deleted | 0 | 0 | 2021-04-14
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701007030/WC/22012034727450 — roof top water harwesting p.s.shcool ratanpur | Completed | 22207.9 | 21187.24 | 2021-06-06 | 2022-07-17
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701007030/WC/22012034833229 — तालाब क्षमता वर्धन एव पिचिंग एव सोक पिट एवं शिडी निर्माण कार्य ककरारी | Deleted | 0 | 0 | 2021-09-15
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1701007030/WC/22012034841409 — किचन गार्डन माध्यमिक शाला रतनपुर | Completed | 15277.83 | 4439 | 2022-01-20 | 2022-07-30
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007030/WC/22012034877503 — Pokhar jirnodhar work Ratanpur | Deleted | 0 | 0 | 2021-08-15
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1701007030/WC/22012034918628 — Talab kshamata bardhan karya kakarari | Completed | 487411 | 298392 | 2022-03-04 | 2022-07-20
MORENA / SABALGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1701007030/WC/22012034918632 — Pokhar jeernoddhar samudayik bhawan k pass Ratanpur | Completed | 122294 | 60216 | 2022-03-04 | 2022-07-20
MORENA / SABALGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701007030/WC/22012035085456 — khet talab nirman kary sandeep jadon ki khet par | Deleted | 0 | 0 | 2023-04-14
MORENA / SABALGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1701007030/WC/22012035186726 — Khet talab nirman kary sandip jadon kotvar ki khet par ratanpur | Deleted | 0 | 0 | 2023-04-14
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035219390 — Khet Talab nirman karya sandeep Jadon ke khet par ratanpur | Approved | 420123.57 | 0 | 2024-08-15
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035219391 — Khet Talab nirman karya kreta jenamkhan ke khet par ratanpur | Approved | 420123.57 | 0 | 2024-08-15
MORENA / SABALGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1701007030/WC/22012035219394 — Nali Nirman karya ratanpur pokhar se ramkumar jadon ke ghar ki or ratanpur | Deleted | 0 | 0 | 2024-08-15
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035231043 — Khet Talab nirman karya sandeep jadon ke khet par | Ongoing | 926092.44 | 7290 | 2024-12-09
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035231045 — Khet Talab nirman karya jenam khan ke khet par ratanpur | Ongoing | 942278.87 | 6561 | 2024-12-09
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035235042 — Khet Talab nirman karya tajuddin ke khet par Ratanpur | Ongoing | 843929.76 | 7290 | 2025-01-16
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035235045 — Khet Talab nirman karya sabbo khan ke khet par Ratanpur | Ongoing | 895540.68 | 7290 | 2025-01-16
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1701007030/WC/22012035235047 — Khet Talab nirman karya ranveer jadon ke khet par Ratanpur | Deleted | 0 | 0 | 2024-10-02
MORENA / SABALGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1701007030/WC/22012035239557 — Khet Talab nirman karya meera rawat ke khet par ratanpur | Ongoing | 464056.74 | 7280.1 | 2025-01-16
MORENA / SABALGARH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701007030/WC/9993630289 — nirmal neer work | Deleted | 0 | 0 | 2013-01-26
MORENA / SABALGARH | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1701007030/WC/9993630290 — nirmal neer work | Deleted | 0 | 0 | 2013-01-26
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check wall / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701007030/WC/9993662642 — रिटेनिंग वाल निर्माण हरिजन बस्ती पोखर की साइड ककरारी | Completed | 1300000 | 1274067 | 2015-12-18 | 2017-02-25
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check wall / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1701007030/WC/9993665090 — retaining wall nirman harejan basti pokhar se narotam ke bade ke or | Completed | 1300000 | 1259405 | 2016-01-16 | 2017-03-30
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/WC/9993665094 — retaining wall nirman harejan bati or muslmanbati pokhar ke said ratanpur | Completed | 1300000 | 1273639.5 | 2016-01-16 | 2017-03-28
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/WC/9993667144 — retarning wal pokhar me rawat basti rod said | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1701007030/WC/9993667145 — retaring wal pokhar me kakrari rod said | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1701007030/WC/9993667416 — pokhar gahrikarn-kakrari | Deleted | 0 | 0 | 2016-01-26
MORENA / SABALGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Model Talab / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1701007030/WH/19955268 — tallav gahrikarn ratanpur harejan basti | Deleted | 0 | 0 | 2016-01-26